## Log
Week Ending | Date | Cost Code | Description | Hours
44815 | 44809 | 99-7200 | HOLIDAY PAY | 240
44815 | 44810 | 02-1900 | SGN LOAD CARDELLA (2 LOADS) CONCRETE AND METAL | 9.5
44815 | 44810 | 31-2200 | SGN LOAD (1 LOAD) HNS BACKFILL TO OG EAST | 3
44815 | 44810 | 31-2200 | SGN BACKFILL ELECTRICAL TRENCH AND BEHIND RETAINING WALL | 1.5
44815 | 44810 | 32-6610 | SGN EXCAVATE AND GRADE FO SUB-GRADE FOR WALKWAY | 9
44815 | 44810 | 02-2100 | SGN DEMO EXISTING CURB | 1.5
44815 | 44810 | 33-2600 | OG4 WEST UNLOAD TRUCK WITH MH DELIVERY | 8
44815 | 44810 | 33-2600 | PREPARE FOR DRAINAGE TO TRANSFER MATERIAL FROM OG4 EAST TO OG4 WEST | 13
44815 | 44810 | 31-2200 | BACKFILL ELECTRIC PIPE, STEAM PIPE AND CLEANING FOR DRAINAGE INSTALL (BACKFILL UTILITIES) | 20.5
44815 | 44810 | 03-1000 | FORM COLUMNS AT TOP OF SHAFT (FORM WORK NB) | 25
44815 | 44810 | 32-6520 | REMOVE FENCE AT SG TO SG3 TO BRING VAC TRUCK ON SITE | 3
44815 | 44810 | 33-3100 | SG2-SG3 EXPOSE STEAM LINE W/VAC TRUCK | 18
44815 | 44810 | 32-6520 | PLACE FENCE BACK AFTER FINISHING WITH VAC TRUCK | 3.5
44815 | 44810 | 33-2600 | FLAGGING FOR DOMINGOS AT OG EAST | 8
44815 | 44810 | 02-3000 | OG4 CUT PENETRATIONS FOR FSE ON 1ST FLOOR (SAW CUT/CORE) | 7
44815 | 44810 | 03-2300 | OG3 PATCH AND SET SHELVES (TRUST BLOCK) | 7
44815 | 44810 | 02-6010 | SG2 SET UP PUMP AND REMOVE SUMP PUMP MATERIALS (PUMP REMOVAL/DEMO) | 5
44815 | 44810 | 99-4560 | OG3 CLEAN BASEMENT (BASEMENT MAINT.) | 9
44815 | 44810 | 99-4560 | OG2 CLEAN BASEMENT AND SECOND FLOOE | 9
44815 | 44810 | 03-2120 | OG6 TAKE MORE PALETS FOR BASEMENT (SHOCKCRETE SUPPORT) | 4.5
44815 | 44810 | 99-4560 | SG6 CLEAN AROUND SITE AND TAKE IT TO SITE8 (BOOM TRUCK) | 8.5
44815 | 44810 | 99-4560 | OG3 BLOCK PARKING FOR SWITCH GEAR DELIVERY (SITE MAINT) | 4.5
44815 | 44810 | 07-6220 | SG6 CLOSE OUT CONDUIT PENETRATION AT 2ND FLOOR | 8.5
44815 | 44810 | 03-1400 | SG2 DRILL AND DOWEL WINDOWS | 8.5
44815 | 44810 | 31-1400 | OG9 BACKFILL | 17.5
44815 | 44810 | 04-6120 | SG6 LULL NEEDED FOR FAXA | 8.5
44815 | 44810 | 31-2200 | SG2 SG3 BACKHOE NEEDED FOR BACKFILL | 1
44815 | 44811 | 99-4560 | SGN MOVE MATERIAL | 12
44815 | 44811 | 02-1900 | SGN LOAD CARDELLA (2 LOADS OF CONCRETE) | 6
44815 | 44811 | 31-1400 | SGN LOAD HNS WITH BACKFILL (3 LOADS) FOR OG EAST | 6
44815 | 44811 | 33-1000 | OG EAST REPAIR BROKEN WATER LINE | 4.5
44815 | 44811 | 31-1400 | OG9 BACKFILL | 3
44815 | 44811 | 33-2500 | INSTALL AT OG4 WEST - AD14-AD13 - INSTALL 24' LF 8" DTP BET AD14-AD13 DIP19 AND 1-45-8" | 43
44815 | 44811 | 33-1000 | OG4 REPAIR 8" WATER MAIN | 16
44815 | 44811 | 31-2200 | BACKFILL STEAMLINE AND ELECTRIC PIPE | 5
44815 | 44811 | 02-6130 | SG5 ERECT STAIR TOWER FOR APARTMENT | 6
44815 | 44811 | 03-1100 | SG4 FINISH UPPER CHEEK WALL | 32.5
44815 | 44811 | 03-1100 | OG5 FORM CHEEK WALL AT FRONT ENTRANCE | 16
44815 | 44811 | 03-1500 | STRIP WINDOW ON RAMP | 1.5
44815 | 44811 | 33-1000 | PICK UP VAC TRUCK TRAILER | 4
44815 | 44811 | 32-6220 | FLAG FOR STONE DELIVERY | 12
44815 | 44811 | 33-3100 | ADJUST STEAM LINE PITCH AT SG3 TO SG2 | 16.5
44815 | 44811 | 07-6220 | OG8 PREP FOR ROOFING | 8
44815 | 44811 | 03-1400 | SG1 DRILL AND DOWEL | 17
44815 | 44811 | 03-1400 | SG3 DRILL AND DOWEL FOR MASONRY SHELF | 17.5
44815 | 44811 | 99-4560 | SG5 LOAD OUT MATERIALS FROM AREA | 17.5
44815 | 44811 | 04-6120 | OG8 LULL NEEDED FOR FAXA | 6.5
44815 | 44811 | 99-4560 | SG5 LULL NEEDED TO CLEAN AROUND AREA | 5.5
44815 | 44811 | 99-4560 | SG5 FLAGGING FOR BOOM TRUCK ON SIDE WALK | 16
44815 | 44811 | 02-2300 | SG2 CLEAN BASEMENT | 17.5
44815 | 44812 | 31-2200 | OG9 BACKFILL | 10
44815 | 44812 | 99-4560 | SGN MOVE MATERIAL | 18.5
44815 | 44812 | 32-6610 | SGN GRADE OUT AREA IN PREP FOR ASPEN | 10
44815 | 44812 | 31-2200 | SG2 SG3 BACKFILL | 3
44815 | 44812 | 33-2500 | INSTALL 8" DTP. DIP 18 31' LF BET AD13 + AD7 - INSTALL 60' LF DTP - DIP16 BET AD8 - AD9 | 40.5
44815 | 44812 | 31-2200 | BACKFILL ELECTRIC PIPE AND WATER PIPE | 1
44815 | 44812 | 03-1100 | OG5 FORM CHEEK WALL (FLOODWALL FORM WORK) | 14
44815 | 44812 | 03-1000 | SG7 FORM AT TOP OF SHAFT (NB FORM WORK) | 20
44815 | 44812 | 03-2500 | SG1 STAYFORM FOR MASONRY SHELF | 12
44815 | 44812 | 03-1000 | SG7 BUILD SCAFFOLD INSIDE OF SHAFT (NB FORM WORK) | 10.5
44815 | 44812 | 33-3100 | SG3 ADJUST PITCH FOR STEAM PIPE (WELKIN B/C) | 6
44815 | 44812 | 33-3100 | REMOVE SAND BAGS TO ADJUST PITCH (WELKIN B/C | 3
44815 | 44812 | 33-3100 | ADD BAGS TO ADJUST PITCH (WELKIN B/C | 3
44815 | 44812 | 31-2200 | BACKFILL STEAM PIPE WITH SAND | 6
44815 | 44812 | 31-2200 | BACKFILL WALKWAY AND PLACE PLATE BACK FOR NEIGHBORS TO HAVE ACCESS | 3
44815 | 44812 | 32-6520 | PLACE FENCE BACK TO GIVE SAFE ACCESS TO NEIGHBORS - FENCE INSTALL | 3.5
44815 | 44812 | 03-1400 | SG1 DRILL AND DOWEL WINDOWS | 17.5
44815 | 44812 | 02-3000 | SG1 CLOSE UP PIPE PENETRATION | 9.5
44815 | 44812 | 99-4560 | SG5 LOAD OUT MATERIALS NO LONGER NEEDED WITH BOOM TRUCK | 17.5
44815 | 44812 | 07-6220 | OG8 CONTINUE PREP FOR ROOFING | 26.5
44815 | 44812 | 99-4560 | SG6 CLEAN UP 1ST FLOOR FOR FSE, WELKIN, VOTAL AND CUSTOM CARP | 8
44815 | 44812 | 99-4560 | OG3 CLEAN UP 2ND FLOOR (FSE GARBAGE) | 13.5
44815 | 44812 | 99-4560 | OG4 CLEAN UP 2ND FLOOR (FSE GARBAGE) | 12
44815 | 44812 | 04-6120 | SG5 LULL NEEDED FOR FAXA | 4
44815 | 44812 | 99-4560 | OG9 LULL NEEDED FOR VITAL | 2
44815 | 44812 | 26-6030 | OG9 LULL NEEDED FOR FSE SWITCH GEAR | 2
44815 | 44812 | 31-2200 | OG5 BACKHOE NEEDED BACKFILL BY OG5 (FOR POUR) | 1
44815 | 44812 | 04-6120 | OG1 CLOSE WATER FOR FAXA (HOSEBTB) | 1
44815 | 44813 | 33-2600 | SG5 INSTALL AD CASTINGS | 8.5
44815 | 44813 | 32-6610 | SG5 CUT/FILL GRADE FOR SIDEWALK (GRADING) | 18
44815 | 44813 | 32-6610 | SGN CUT/FILL GRADE FOR LANDSCAPING (GRADING) | 4
44815 | 44813 | 32-6610 | SGN RECEIVE 3 LOADS OF CLEAN FILL FROM HNS (GRADING) | 6
44815 | 44813 | 32-6610 | SGN RECEIVE LOADS OF BACKFILL FROM OG WEST (GRADING) | 12
44815 | 44813 | 33-2600 | INSTALL AD15 AND AD9 - INSTALL 45'8" LF DTP - DIP 20 BET AD15 & AD9 - INSTALL 20'8" DTP - DIP 16 BET AD8 AND A9 | 40.5
44815 | 44813 | 33-2600 | FLAGGING | 8
44815 | 44813 | 02-1900 | SG4 LOADED 20 YD CONCRETE CONTAINER AND LOADED 4 TRUCKS | 1
44815 | 44813 | 03-1000 | SG7 FORM TOP OF SHAFT (NB FORM WORK) | 27.5
44815 | 44813 | 03-1100 | SG2 FORM WINDOW (EXIST BLD FORM WORK) | 18
44815 | 44813 | 03-1000 | OG8 FORM OUT ROOF PENETRATION (NB FORM WORK) | 19
44815 | 44813 | 03-2100 | SG4 POUR CHEEKWALLS | 13
44815 | 44813 | 03-2100 | SG5 POUR CHEEKWALLS | 13.5
44815 | 44813 | 32-6520 | OG5 POUR CHEEKWALL AND TEMP WALKWAY | 13.5
44815 | 44813 | 99-4560 | SG3 CLEAN BASEMENT (CLEAN ISOLATION BOXES) | 4
44815 | 44813 | 32-6220 | SG6 FLAGGING FOR GMC | 4
44815 | 44813 | 99-4560 | SG6 CLEAN 1ST FLOOR (VITAL, FSE AND WELKIN) | 4
44815 | 44813 | 99-4560 | SG4 SG5 SG6 CLEAN AROUND | 15
44815 | 44813 | 03-1400 | SG3 DRILL FOR DOWELS | 24
44815 | 44813 | 03-2100 | OG3 OG5 SG5 SG4 FLAGGING FOR POUR CEMENT TRUCK | 11
44815 | 44813 | 03-2300 | OG3 POUR | 7
44815 | 44813 | 05-6020 | SG7 PREP TO GROUT COLUMNS | 4
44815 | 44813 | 04-6120 | LULL NEEDED FOR FAXA | 5
44815 | 44813 | 26-6030 | LULL NEEDED FOR FSE SWUTCH GEAR | 3
44815 | 44813 | 99-4560 | SG2 SG1 PICK UP GARBAGE | 1
44815 | 44813 | 31-2200 | PICK UP VACUUM TRAILER | 8.5
44815 | 44813 | 00-0025 | SG6 CLEAN UP OIL SPILL FROM BACKHOE | 0.5
44808 | 44802 | 03-1100 | OG5 STRIP PADS ON 2ND FLOOR | 5.5
44808 | 44802 | 03-1100 | OG5 STRIP PADS ON 1ST FLOOR | 3
44808 | 44802 | 03-1100 | SG1 STRIP BASEMENT FOUNDATION WALL | 3
44808 | 44802 | 03-1000 | SG7 FORM LAST COLUMNS | 16
44808 | 44802 | 03-1100 | SG6 BOX OUT PIPES AND JUNCTION BOX | 15
44808 | 44802 | 99-4560 | OG10 SAFETY HANDRAILS | 6
44808 | 44802 | 33-2510 | SG6 FENCE REMOVAL | 2
44808 | 44802 | 31-2200 | SG3 BACKFILL WATER SERVICE TO BUILDING | 15
44808 | 44802 | 33-2600 | INSTALL DRAINAGE AD22 | 3
44808 | 44802 | 33-2510 | SG6 INSTALL FENCE | 2
44808 | 44802 | 00-0025 | PLACE PLATES BACK INTO STREET AND PUT COLD PATCH AROUND PLATES (WATER LINE C/O) | 3.5
44808 | 44802 | 99-4560 | OG8 SG6 REMOVE TRASH | 2.5
44808 | 44802 | 33-2510 | SG6 EXPOSE SEWER FOR DEP INSPECTION | 5
44808 | 44802 | 31-2200 | SG6 BACKFILL WATER LINE | 22.5
44808 | 44802 | 33-2600 | SGN EXCAVATE AND BACKFILL FOR ELECTRICIANS (SITE LIGHTING) | 9
44808 | 44802 | 33-2600 | SGN INSTALL LIGHT PILE BASES | 7
44808 | 44802 | 02-2100 | SGN DEMO PART OF EXISTING RETAINING WALL | 6
44808 | 44802 | 33-2900 | WORK EXCAVATION TO REMOVE EXISTING MH AT AD7 - | 20.5
44808 | 44802 | 03-1400 | SG1 DRILL AND DOWEL | 25.5
44808 | 44802 | 03-1400 | SG2 DRILL AND DOWEL WINDOWS | 17.5
44808 | 44802 | 03-2100 | OG5 CLEAN UP SECOND FLOOR APARTMENT FROM POUR (POUR CONC EXISTING BUILDING) | 5.5
44808 | 44802 | 05-6020 | SITE8 PREP FOR GROUT COLUMNS (GROUT COLUMN) | 5.5
44808 | 44802 | 02-2300 | SG4 CLEAN BASEMENT | 9
44808 | 44802 | 33-3100 | OG2 HAND DIG FOR WELKIN (NORTH SIDE) | 4
44808 | 44802 | 02-2300 | SG1 SG2 SG5 CHECK PUMP (BASEMENT MAINT) | 3
44808 | 44802 | 99-4560 | OG9 CLEAN UP AROUND SITE | 7
44808 | 44802 | 04-6120 | OG8 LULL NEEDED FOR FAXA | 3
44808 | 44802 | 04-6120 | OG9 LULL NEEDED FOR FAXA TO UNLOAD BLOCK TRAILER (FAXA CODE) | 3
44808 | 44802 | 99-4560 | SG4 LULL NEEDED (1 TON BAGS FROM FAXA) SITE MAINT | 3
44808 | 44802 | 99-4560 | SG7 CLEAN BY SITE (SITE MAINT) | 4
44808 | 44802 | 99-4560 | SG6 CLEAN ROOF AND 2ND FLOOR (SITE MAINT) | 4
44808 | 44802 | 99-4560 | OG8 CLEAN AROUND 2ND FLOOR | 3
44808 | 44802 | 33-2600 | INSTALL AD7 - DIP 20 | 30
44808 | 44803 | 05-6020 | SITE8 FORM COLUMN BASES FOR GROUT | 6
44808 | 44803 | 03-1000 | SG6 BOX OUT AND CLOSE WINDOWS | 6
44808 | 44803 | 03-1000 | SG7 FORM COLUMNS | 30.5
44808 | 44803 | 99-4560 | OG6 HANDRAIL AROUND AT OPEN AREAS | 2
44808 | 44803 | 03-2120 | OG6 COMPLETE SCAFFOLDING | 4
44808 | 44803 | 31-2200 | OG5 OG6 BACKFILL STEAM PIPE | 8
44808 | 44803 | 31-1000 | OG6 AND SG3 HAND DIG CONCRETE SHELF | 16
44808 | 44803 | 03-1800 | SITE8 MOVE REBAR TO START DIGGING FOR ELECTRIC PIPES | 8.5
44808 | 44803 | 99-4560 | SITE8 COVER WELDING MACHINE FOR GUYTEC | 1
44808 | 44803 | 33-2510 | SG6 EXPOSE SEWER LINE AND COMPLETE FORMWORK | 16.5
44808 | 44803 | 33-2510 | SG6 POUR CONCRETE AROUND SEWER BY HAND | 6
44808 | 44803 | 31-2200 | SGN EXCAVATE AND BACKFILL FOR ELECTRICIANS | 12
44808 | 44803 | 33-2600 | SGN MOVE MANHOLES FROM SITE8 TO SGN (CATCH BASIN CONNECTION) | 5
44808 | 44803 | 33-2500 | SG6 DIG FOR DRAINAGE PIPE BY HAND (DIP) | 1
44808 | 44803 | 31-2200 | SGN BEGIN TO DIG FOR SUB-GRADE FOR WALK-WAY AND DEMO WALKWAY | 5
44808 | 44803 | 33-2500 | INSTALL AD12 - AD14 - AD13 - INSTALL 36' LF 12" DTP BETWEEN AD12 AND AD14 | 51.5
44808 | 44803 | 05-6020 | SITE8 GROUT COLUMNS (BASES) | 1
44808 | 44803 | 33-2510 | SG6 FORM/POUR BLOCK AROUND SEWER | 26
44808 | 44803 | 03-1400 | SG1 DRILL AND DOWEL WINDOWS | 9
44808 | 44803 | 03-1400 | SG2 DRILL AND DOWEL WINDOWS | 9
44808 | 44803 | 99-4560 | SG4 CLEAN BASEMENT (VITAL GARBAGE) | 9
44808 | 44803 | 99-4560 | SG6 CLEAN 2ND FLOOR (FSE AND CUSTOM CARP) | 9
44808 | 44803 | 33-2510 | SG6 FLAGGING | 9
44808 | 44803 | 33-6010 | OG8 MACHINE NEEDED AT 2ND FLOOR (WELKIN) | 3.5
44808 | 44803 | 03-1800 | SG7 MACHINE NEEDED AT 2ND FLOOR (TONAGE) | 3
44808 | 44803 | 31-1100 | SG4 BACKFILL WITH STONE | 2
44808 | 44803 | 99-4560 | OG9 PICK UP GARBAGE | 1.5
44808 | 44803 | 99-4560 | SG4 PICK UP GARBAGE | 1.5
44808 | 44804 | 03-2300 | OG9 FORM THRUST BLOCK | 15
44808 | 44804 | 03-2300 | OG5 FORM THRUST BLOCK | 15
44808 | 44804 | 03-2120 | OG6 BUIILD RAMP IN BASEMENT (PREP FOR SHOTCRETE) | 8
44808 | 44804 | 03-1100 | OG6 CLOSE UP AT WINDOW (EXISTING BUILDING FORMWORK) | 11
44808 | 44804 | 22-6060 | OG10 INSTALL BRIDGE BRACKERS AND SCAFFOLDING PLANK | 6
44808 | 44804 | 03-1000 | SSG7 START FORM FOR PLUMBING SHAFT | 5.5
44808 | 44804 | 33-2900 | DEMO CATCH BASIN + LIGHT POLE | 4
44808 | 44804 | 05-6110 | OG8 MOCE CONCRETE BLOCKS TO PREP FOR ENY TO INSTALL STAIRS | 4
44808 | 44804 | 05-6110 | OG8 OFFLOAD DIRT TO PREP FOR ENY | 6.5
44808 | 44804 | 31-1000 | OG6 HAND DIG FOR CONCRETE SHELF | 8
44808 | 44804 | 02-6025 | SG3 CHOP VENT FOR CONCRETE SHELF | 8
44808 | 44804 | 31-1000 | OG2 TAMPER TRENCH (FLOODWALL INSTALL) | 2
44808 | 44804 | 00-0025 | SITE8 LOAD 5-12' PIPES (WATER) 2-10' (WATER) FOR DOMINGOS TO SGN | 9
44808 | 44804 | 31-2200 | SG6 BACKFILL WATER MAIN | 3
44808 | 44804 | 04-6120 | WORK WITH FAXA ON LULL | 4
44808 | 44804 | 33-2510 | SG6 EXPOSE SEWER LINE/ASIST PLUMBERS WITH CORE DRILL/FLAG (SEWER WORK) | 13
44808 | 44804 | 33-2510 | SG6 HAND DIG TO EXPOSE TRENCH FOR SEWER LINE | 6
44808 | 44804 | 33-2600 | SG4 EXCAVATE AND DEMO CATCH BASIN AND LIGHT POLE | 20
44808 | 44804 | 03-1400 | SG2 DRILL AND DOWEL WINDOWS | 18
44808 | 44804 | 03-1400 | SG1 DRILL AND DOWEL WINDOWS | 18
44808 | 44804 | 03-1900 | OG8 CLOSE OUT PENETRATION AT 2ND FLOOR | 10
44808 | 44804 | 33-2510 | SG6 FLAGGING (SEWER INSTALL) | 9.5
44808 | 44804 | 99-4560 | SG3 CLEAN AROUND (SITE MAINT) | 5.5
44808 | 44804 | 99-4560 | SG7 CLEAN AROUND (SITE MAINT) | 4
44808 | 44804 | 03-1100 | OG6 EXISTING BUILDING FORMWORK | 5
44808 | 44804 | 03-2120 | OG6 SHOTCRETE PREP | 5
44808 | 44804 | 33-2500 | INSTALL ADA5 - INSTALL 6" DTP 8'LF DIP 8. INSTALL 52' LF 12" DTP - BET AD14 - AD15 | 51.5
44808 | 44804 | 33-2500 | INSTALL 20' LF DTP BET AD7 AND AD26 DIP 28 AND MAKE NEW HOLLS | 1
44808 | 44805 | 03-1600 | FORM UPPER CHEEK WALL | 32
44808 | 44805 | 03-1000 | CLOSE OUT CONDUIT PENETRATION AT 2ND FLOOR (NB FORM WORK) | 10.5
44808 | 44805 | 03-2300 | FORM THRUST BLOCK | 6
44808 | 44805 | 33-2600 | INSTALL AD-28 AND LIGHT POLE BASE | 32
44808 | 44805 | 33-3100 | SITE8 DIG FOR ELECTRIC RUN AND SET 2 SHORING BOXES | 20.5
44808 | 44805 | 02-6015 | SG3 DEMO VENT WITH HELLDOG | 3
44808 | 44805 | 31-1400 | OG9 BACKFILL BEHIND BUILDNF AFTER NEW STEAM LINE | 12
44808 | 44805 | 31-2200 | OG6 BACKFILL NEW STEAM LINE | 10
44808 | 44805 | 00-0038 | SG3 PREPARE FOR POUR WITH SERGIO (TEMP DUCT BANK C/O) | 2
44808 | 44805 | 00-0038 | SG7 PREPARE FOR POUR WITH SERGIO (TEMP DUCT BANK C/O) | 2
44808 | 44805 | 02-3000 | OG9 CUT OUT PENETRATIONS FOR THEMIS | 3
44808 | 44805 | 31-1000 | SG5 HAND DIG | 6.5
44808 | 44805 | 03-1500 | SG5 POUR WINDOW (RAMP) | 4.5
44808 | 44805 | 03-1800 | SG7 LULL NEEDED FOR TONAGE (REBAR TO ROOF) | 15.5
44808 | 44805 | 99-4560 | SG7 CLEAN AROUND | 8.5
44808 | 44805 | 03-1400 | SG2 DRILL AND DOWEL WINDOWS | 4.5
44808 | 44805 | 03-1400 | SG1 DRILL AND DOWEL WINDOWS | 8.5
44808 | 44805 | 03-1400 | SG3 DRILL AND DOWEL FOR MASONRY SHELF | 22.5
44808 | 44805 | 03-2120 | OG6 PREP FOR SHOTCRETE | 2.5
44808 | 44805 | 33-2500 | SG4 SG5 HELP DOMINGOS AND CHRIS ON DRAINAGE INSTALL | 15
44808 | 44805 | 03-1900 | SG6 PREP FOR POUR (CEMENT BAGS) POUR CONC NB | 5.5
44808 | 44805 | 99-4560 | SG4 PICK UP GARBAGE FROM BASEMENT | 4
44808 | 44805 | 03-2300 | SITE8 PREP FOR POUR (MANHOLE) POUR DUCT BANK | 4.5
44808 | 44805 | 99-4560 | OG3 CLEAN 2ST FLOOR GARBAGE | 10.5
44808 | 44805 | 04-6120 | OG8 OG10 LULL NEEDED FOR FAXA (FAXA CODE) | 4
44808 | 44805 | 33-2500 | INSTALL AB25 - AD26 INSTALL 54' LF 12" DTP - BET AD7 AND AD26 | 50
44808 | 44805 | 03-1900 | LOAD CONTAINER WITH CONCRETE | 3.5
44808 | 44806 | 03-1600 | SG4 FORM UPPER CHEEK WALLS | 19.5
44808 | 44806 | 03-1600 | SG5 FORM UPPER CHEEK WALLS | 39
44808 | 44806 | 03-1000 | SG6 CLOSE OUT CONDUIR PENETRATION (FW NEW BUILD) | 6
44808 | 44806 | 33-2600 | SG5 EXCAVATE AND INSTALL CONDUIT FOR LIGHT POLE FOR ELECTRICIANS | 15.5
44808 | 44806 | 02-1900 | SGN MOVE MATERIALS IN PREP CARDELLA (DEMO WALKWAYS) | 6
44808 | 44806 | 33-2600 | SGN BACKFILL AND GRADE AREA (LIGHT POLE INSTALL) | 3
44808 | 44806 | 04-6120 | FAXA | 1
44808 | 44806 | 03-1400 | SG3 DRILL AND DOWEL MASONRY SHELF | 32
44808 | 44806 | 31-2600 | SITE FURNITURE DELIVERY | 9
44808 | 44806 | 31-1000 | HAND DIG FOR RETAINING WALL (MASONRY SHELF) | 2.5
44808 | 44806 | 07-6220 | SG6 TRIANGLE G.C WITH LULL | 3
44808 | 44806 | 99-4560 | OG9 SG7 OG4 PICK UP GARBAGE WITH BACKHOE | 4
44808 | 44806 | 02-6060 | SG5 REMOVE CABINETS, STOVE AND FRIDGE FROM 2ND FL APARTMENT (DEMO 2ND FLOOR) | 9.5
44808 | 44806 | 03-1100 | OG5 CLEAN BASEMENT | 6
44808 | 44806 | 03-1900 | SG6 PREP FOR POUR, BRING CEMENT BAGS TO 2ND FLOOR (POUR CONC NB) | 7.5
44808 | 44806 | 99-4560 | SG6 PICK UP GARBAGE FROM TRIANGLE G.C (SITE MAINT.) | 2
44808 | 44806 | 03-1100 | OG3 PICK UP GARBAGE FROM 2ND FLOOR APRT FROM PADS POUR (FROM EXIST BUILD) | 6
44808 | 44806 | 33-1100 | SG4 PICK UP GARBAGE FROM BASEMENT (UTILITY DEMO) | 6
44808 | 44806 | 99-4560 | OG2 CLEAN 1ST FLOOR FSE GARBAGE (SITE MAINT.) | 8
44808 | 44806 | 99-4560 | OG8 CLEAN AROUND | 8
44808 | 44806 | 07-6220 | SG6 LULL NEEDED FOR TRIANGLE (TRIANGLE B/C) | 4
44808 | 44806 | 04-6120 | OG8 OG9 OG10 LULL NEEDED FOR FAXA (FAXA CODE) | 4
44808 | 44806 | 03-2300 | SITE8 MACHINE NEEDED FOR SITE POUR (POUR DUCT BANK) | 1
44808 | 44806 | 03-2300 | SG7 MACHINE NEEDED FOR SITE POUR (POUR TEMP DUCT BANK) | 1
44808 | 44806 | 03-2300 | OG9 MACHINE NEEDED FOR SITE POUR (POUR THRUST BLOCK) | 1
44808 | 44806 | 03-2300 | OG4 MACHINE NEEDED FOR SITE POUR (POUR THRUST BLOCK) | 1
44808 | 44806 | 03-1400 | SG3 DRILL AND DOWEL | 12
44808 | 44806 | 03-1400 | SG1 DRILL AND DOWEL | 21.5
44808 | 44806 | 03-2300 | SITE8 SF7 OG9 OG4 POUR SITE (POUR THRUST BLOCK AND DUCT BANK 22YD) | 0.5
44808 | 44806 | 33-1100 | LOAD CONTAINER WITH STEEL (DEMO UTILITIES) | 7.5
44808 | 44806 | 33-2510 | INSTALL 3YDS CONCRETEAT WALKWAY (TEMP FENCE INSTALL) | 5
44808 | 44806 | 33-2600 | INSTALL ELECTRIC POLLS AND PICK UP AT SG5 - TAKE TO SG4 | 30
44808 | 44806 | 99-4560 | BOOM TRUCK - ENY TOOK DOWN STAIRS | 1
44801 | 44795 | 03-2100 | SG5 PATCH HOLES AT FLOODWALL | 5.5
44801 | 44795 | 03-2100 | SG4 PATCH HOLES AT FLOODWALL | 5.5
44801 | 44795 | 03-2100 | OG1 PATCH HOLES AT FLOODWALL | 5.5
44801 | 44795 | 03-2100 | OG2 PATCH HOLES AT FLOODWALL | 5.5
44801 | 44795 | 00-0039 | OG4 INSTALL AC BRACKETS AND CUT OUT SLEEVES | 9.5
44801 | 44795 | 02-3000 | OG4 CLEAN BASEMENT DEBRIS (CONCRETE CHOPPING) | 11
44801 | 44795 | 32-6520 | OG8 HOUSE KEEPING ALONG THE FENCE | 2
44801 | 44795 | 99-4560 | OG9 REMOVE GARBAGE FROM 2ND FLOOR LANDING | 4.5
44801 | 44795 | 99-4560 | OG6 HOUSE KEEPING NEEDED, LUMBER | 2
44801 | 44795 | 02-3000 | OG1 CUT PENETRATION AT 2ND FL AND BASEMENT | 8
44801 | 44795 | 03-1400 | OG6 DRILL AND INSTALL DOWELS WALL/WINDOWS | 8
44801 | 44795 | 99-4560 | OG5 CLEAN AROUND 1 TON BAGS | 3
44801 | 44795 | 99-4560 | OG2 CLEAN AROUND 1 TON BAGS | 3.5
44801 | 44795 | 03-1400 | SG3 DRILL DOWELS AT WINDOWS FOR CONCRETE SHELF | 16
44801 | 44795 | 02-6025 | SG3 DIG FOR MASONRY SHELF | 32.5
44801 | 44795 | 33-3100 | SG6 COVER TRENCH WITH PLATES AND OPEN ROAD | 3.5
44801 | 44795 | 07-6110 | SG6 FINISH PATCHING ROOF | 1
44801 | 44795 | 03-1600 | SG6 STRIP FORM WORK AND CLEAN | 21
44801 | 44795 | 07-6110 | SG6 TAKE DOWN PLYWOOD | 2.5
44801 | 44795 | 03-1000 | OG8 STRIP PADS | 4.5
44801 | 44795 | 03-1000 | SG7 FORM AROUND PIPES | 4
44801 | 44795 | 03-1600 | WORK WITH CARPENTERS STRIPPING CONCRETE WALL | 5
44801 | 44795 | 33-2510 | WORK AT EXCAVATION FOR SEWER AND INSTALL THECH BOX - 1 VACUUM TRUCK | 63
44801 | 44795 | 33-2400 | Dewater sewer excavation | 8
44801 | 44795 | 99-7210 | PTO | 8
44801 | 44796 | 03-2300 | SG7 POUR TEMP DUCT BANK AND COLUMN BASES | 9
44801 | 44796 | 03-1400 | OG6 DRIL DOWELS AND INSTALL | 28
44801 | 44796 | 02-3000 | OG1 CUT PENETRATIONS (SAWCUT) | 22
44801 | 44796 | 03-1800 | OG1 UNLOAD TRAILER REBAR - FLAGGING | 25
44801 | 44796 | 03-1800 | SITE8 UNLOAD TRAILER REBAR - FLAGGING | 5
44801 | 44796 | 04-6120 | OG10 LULL NEEDED FOR FAXA | 2
44801 | 44796 | 26-6030 | SG6 LULL NEEDED FOR FSE | 3
44801 | 44796 | 05-6040 | OG10 MOVING MATERIAL FOR PREP FOR CRANE | 3
44801 | 44796 | 31-2200 | SG6 LULL NEEDED BACKFILL | 2.5
44801 | 44796 | 26-6030 | OG9 PREP FOR CRANE | 1
44801 | 44796 | 03-1400 | SG1 DRILL DOWELS FOR CONCRETE SHELF | 14
44801 | 44796 | 31-1000 | SG3 DIG CONCRETE SHELF | 10
44801 | 44796 | 31-1000 | OG6 HAND DIG TO EXPOSE UTILITIES FOR CONCRETE SHELF | 10.5
44801 | 44796 | 26-6030 | MOVE MATERIAL (CUSTOM CARPENTRY) TO PREP FOR CRANE | 6
44801 | 44796 | 04-6120 | MOVE MATERIAL (FAXA) TO PREP FOR CRANE (FAXA CODE) | 2
44801 | 44796 | 03-1800 | OG1 OFFLOAD REBAR TRAILER (REBAR OFFLOAD) | 4
44801 | 44796 | 99-4560 | OG9 OG10 CLEAN DEBRI FOR CRANE (SITE MAINT) | 2
44801 | 44796 | 03-1100 | SG4 FORM UPPER CHEEK WALL | 15
44801 | 44796 | 03-1100 | SG5 FORM UPPER CHEEK WALL | 15.5
44801 | 44796 | 03-1100 | OG5 FORM EQUIPMENT PADS | 10
44801 | 44796 | 33-2600 | EXCAVATION AND INSTALL AD5 AND EXCAVATION FOR INSTALL PIPE | 11
44801 | 44796 | 33-2510 | WORK AT EXCAVATION FOR SEWER | 47.5
44801 | 44797 | 02-2300 | SG1 CLEAN BASEMENT | 2.5
44801 | 44797 | 02-2300 | SG2 CLEAN BASEMENT | 3.5
44801 | 44797 | 02-2300 | SG5 CLEAN BASEMENT | 3.5
44801 | 44797 | 02-2300 | SG4 CLEAN BASEMENT DEBRI FROM FSE | 8.5
44801 | 44797 | 99-4560 | SG6 CLEAN SHAFT WATER | 4
44801 | 44797 | 99-4560 | OG5 PICK UP GARBAGE | 5
44801 | 44797 | 99-4560 | SG3 PICK UP GARBAGE | 5
44801 | 44797 | 99-4560 | SG2 PICK UP GARBAGE | 6
44801 | 44797 | 99-4560 | SG6 PICK UP GARBAGE | 2.5
44801 | 44797 | 00-0005 | OG9 INSTALL REBAR AND POUR PAD IN SHAFT | 5.5
44801 | 44797 | 02-1000 | SG1 COVER DIRT (EROSION CONTROL) | 7.5
44801 | 44797 | 02-6015 | OG9 CHOP WINDOW | 5
44801 | 44797 | 03-1400 | OG6 DRILL AND INSTALL DOWELS WINDOWS | 19.5
44801 | 44797 | 00-0025 | SG6 FLAGGING FOR DOMINGOS (BULLETIN 1) | 4
44801 | 44797 | 99-4560 | SG7 PICK UP GARBAGE | 0.5
44801 | 44797 | 26-6030 | OG9 PREP FOR CRANE WITH STONE | 8
44801 | 44797 | 26-6030 | PREP FOR CRANE WITH STONE , MOVE MATERIALS TO SET CRANE | 8
44801 | 44797 | 99-4000 | SITE8 & SGN REMOVE MAFIA BLOCKS | 2
44801 | 44797 | 26-6030 | OG10 PUT MAFIA BLOCKS | 4
44801 | 44797 | 31-1000 | OG6 DIG FOR CONCRETE SHELF | 12
44801 | 44797 | 03-1100 | FLAG FOR LUMBER DELIVERY | 0.5
44801 | 44797 | 03-1100 | SG5 FORM EQUIPMENT PADS | 15
44801 | 44797 | 02-6060 | OG5 REPAIR WINDOW AND DOOR IN APARTMENT | 3
44801 | 44797 | 03-2120 | OG6 ERECT SCAFFOLDING IN BOILER ROOM | 20.5
44801 | 44797 | 03-2500 | SG2 STAY FORM FOR MASONRY SHELF | 9
44801 | 44797 | 99-4560 | REPAIR OVERHEAD POST FOR TEMP ELEC. LINE | 9.5
44801 | 44797 | 33-2510 | EXCAVATION FOR SEWER CONNECTION | 46.5
44801 | 44797 | 33-2500 | EXCAVATION 2' MORE WIDE NEXT TO WATER MAIN - 50' LONG | 15
44801 | 44797 | 31-2200 | BACKFILL AROUND CONCRETE WALL | 4
44801 | 44797 | 33-2400 | COVER PUMP | 1
44801 | 44798 | 03-1400 | SG1 DRILL AND DOWEL WINDOWS | 20.5
44801 | 44798 | 03-1400 | OG6 DRILL AND INSTALL DOWEL WINDOWS | 20
44801 | 44798 | 99-4560 | SG4 CLEAN AROUND | 8.5
44801 | 44798 | 99-4560 | SG6 CLEAN AROUND | 8
44801 | 44798 | 26-6030 | OG9 FLAGGING FOR CRANE IN MORNING (FSE B/C NO CERTIFIED FLAGGER) | 8
44801 | 44798 | 31-1100 | SG2 BACKFILL FOR MASONRY SHELF | 19
44801 | 44798 | 04-6120 | LULL NEEDED FOR FAXA (FAXA CODE) | 4
44801 | 44798 | 33-6010 | OG8 LULL NEEDED FOR WELKIN | 3
44801 | 44798 | 26-6030 | OG9 OG10 LULL NEEDED FOR CRANE (FSE B/C, NO MEANS TO OFFLOAD PLATES, LULL WAS FOR PREVIOUSLY) | 3
44801 | 44798 | 31-1000 | SG3 DIG FOR MASONRY SHELF | 11.5
44801 | 44798 | 99-4000 | OG10 MOVE MATERIAL TO GET CRANE | 3.5
44801 | 44798 | 31-1000 | SG3 HAND DIG FOR MASONRY SHELF | 16
44801 | 44798 | 03-2500 | SG3 MACHINE NEEDED FOR SERGIO TO PREP CONCRETE SHELF FOR CONCRETE | 6
44801 | 44798 | 03-2500 | SG2 STAY FORM MASONRY SHELF | 15
44801 | 44798 | 03-1000 | SG7 MAKEUP COLUMNS (SG7 COLUMN FORMWORK) | 27.5
44801 | 44798 | 03-2120 | OG6 ERECT SCAFFOLD (WALL REINFORCEMENT/PATRIOT EXCLUSION) | 6
44801 | 44798 | 33-2500 | INSTALL DRAINAGE AD6 INSTALL 19' LF - 10" DIP-18-35'LF 10'DTP - DIP19 | 24.5
44801 | 44798 | 33-2400 | COVER ELECTRIC PUMP (SEWER INSTALL IN STREET) | 1
44801 | 44798 | 33-2510 | SG6 EXPOSE SEWER LINE AND FORM FOR TIE IN | 41.5
44801 | 44798 | 00-0038 | SGN EXCAVATE FOR ELECTRICIANS FOR TIE IN (SITE LIGHTING EXCAVATION) | 8
44801 | 44799 | 03-1400 | SG1 DRILL DOWELS | 16
44801 | 44799 | 99-4560 | SITE8 CLEAN UP | 8
44801 | 44799 | 99-4560 | OG10 CLEAN AROUND SITE | 9
44801 | 44799 | 03-2100 | SG1 SG2 G5 FLAGGING FOR POUR | 16
44801 | 44799 | 03-2500 | SG2 POUR MASONRY SHELF | 30
44801 | 44799 | 03-2100 | SG1 POUR BASEMENT WALL | 12
44801 | 44799 | 00-0005 | OG5 POUR PADS ON 2ND FLOOR APARTMENT | 13
44801 | 44799 | 03-2100 | CLEAN UP CEMENT BUCKET AFTER POUR | 2.5
44801 | 44799 | 04-6120 | OG8 LULL NEEDED FOR FAXA | 4
44801 | 44799 | 26-6030 | SG7 LULL NEEDED FOR FSE | 3
44801 | 44799 | 32-6220 | OG8 LULL NEEDED FOR GMC | 1
44801 | 44799 | 33-6010 | OG8 LULL NEEDED FOR WELKIN | 1
44801 | 44799 | 33-2500 | WORK EXCAVATION FOR DRAINAGE - INSTALL AD-19 AND AD-18 - 23'LF DTP - DIP 22 | 20.5
44801 | 44799 | 33-2600 | MOVE MH FROM SG5 TO SG4 | 12
44801 | 44799 | 33-2400 | COVER COMPRESSOR | 1
44801 | 44799 | 03-1000 | SG7 FORM COLUMNS | 39
44801 | 44799 | 03-1100 | OG6 MAKE BOX5 TO BOX OUT PIPES | 1.5
44801 | 44799 | 03-1000 | OG7 MOVE COLUMNS TO MATERIAL | 16
44801 | 44799 | 33-2510 | SG6 EXPOSE SEWER LINE FOR INSPECTION AND FORM WORK | 28.5
44801 | 44799 | 31-2200 | SG NORTH EXCAVATE AND BACKFILL FOR ELECTRICIANS | 12
44801 | 44799 | 03-2500 | SG SOUTH POUR CONCRETE | 3
44801 | 44799 | 03-2500 | OG6 HAND DIG FOR CONCRETE SHELF | 9
44801 | 44799 | 03-2500 | SG3 HAND DIG FOR CONCRETE SHELF | 8.5
44801 | 44799 | 03-2100 | SG2 CONCRETE POUR | 4
44801 | 44799 | 03-2100 | SG1 POUR BASEMENT WALL | 2
44801 | 44799 | 03-2100 | SG5 POUR PADS AT 2ND FLOOR APARTMENTS | 2
44794 | 44788 | 99-4560 | SG6 CLEAN 1ST FLOOR (SITE MAINT) | 4.5
44794 | 44788 | 99-4560 | OG8 CLEAN 1ST FLOOR (SITE MAINT) | 4
44794 | 44788 | 99-4560 | SG7 CLEAN 1ST FLOOR (SITE MAINT) | 4
44794 | 44788 | 02-2300 | SG1 CLEAN BASEMENT (BASEMENT MAINT) | 10
44794 | 44788 | 02-6075 | SG1 CLEAN PIT (PLUMBING DEMO) | 8.5
44794 | 44788 | 03-1900 | OG8 PATCH SHAFT (OUTSIDE) (POUR CONC NB, 2YD) | 4.5
44794 | 44788 | 03-1900 | OG10 PATCH SHAFT (OUTSIDE) (POUR CONCRETE NB, 2YD) | 4.5
44794 | 44788 | 03-1900 | SG1 PATCH PIT (PLUMBING DEMO) (POUR CONCRETE NB, 2YD) | 14.5
44794 | 44788 | 02-3000 | OG5 CHOP WALL FROM FSE PENETRATION | 8.5
44794 | 44788 | 99-4560 | OG8 SITE8 OG9 SG6 PICK UP GARBAGE (SITE MAINT) | 12.5
44794 | 44788 | 03-1400 | OG6 DRILL DOWELS | 0.5
44794 | 44788 | 02-6060 | OG3 PATCH SHEETROCK 2ND FLOOR APPARTMENT (2ND FLOOR DEMO) | 9
44794 | 44788 | 02-6060 | OG4 PATCH SHEETROCK 2ND FLOOR APPARTMENT (2ND FLOOR DEMO) | 9
44794 | 44788 | 02-2300 | SG4 CLEAN BASEMENT | 4.5
44794 | 44788 | 04-6120 | LOAD NEEDED FOR FAXA (FAXA CODE) | 4
44794 | 44788 | 04-6120 | LOAD NEEDED FOR FSE/VITAL OG8 (FAXA CODE) | 3
44794 | 44788 | 03-1100 | OG2 STRIP 2ND FLOOR EQUIPMENT PADS | 4.5
44794 | 44788 | 03-1100 | OG2 STRIP 1ST FLOOR EQUIPMENT PADS | 3.5
44794 | 44788 | 03-1100 | OG6 EQUIPMENT PADS IN BASEMENT | 5
44794 | 44788 | 03-1100 | OG5 STRIP EQUIPMENT PADS IN BASEMENT | 12
44794 | 44788 | 03-1600 | SG5 FORM RETAINING WALL | 8.5
44794 | 44788 | 03-1100 | MOVING HARDWARE TO SG5 FROM AROUND JOBSITE | 6
44794 | 44788 | 32-6520 | OG9 SAFELY REPAIR WORK | 1
44794 | 44788 | 03-1400 | SG5 DRILL AND DOWEL AT MASONRY SHELF | 20.5
44794 | 44788 | 33-3100 | SG7 HAND DIG FOR FSE TO FIND ELECTRIC PIPES | 8
44794 | 44788 | 33-1000 | SG3 HAND DIG TO EXPOSE UTILITIES FOR MASONRY SHELF | 12
44794 | 44788 | 02-1900 | REMOVE CONCRETE AND LOAD ONE 20 YARD CONTAINER | 6.5
44794 | 44788 | 31-2100 | REMOVE DEBRI FROM RETAINING WALL TO INSTALL REBAR (RET WALL EXC) | 6
44794 | 44788 | 33-2900 | REMOVE MANHOLE FROM SG4 TO SG5 | 6
44794 | 44788 | 33-2500 | CLEANING AT SG4 TO INSTALL DRAINAGE | 10.5
44794 | 44788 | 00-0025 | SG6 SAWCUT ROADWAY TO INSTALL SEWER PIPE AND WATER MAIN (PAVEMENT DEMO) | 12
44794 | 44789 | 03-1400 | OG6 DRILL AND INSTALL DOWELS | 19
44794 | 44789 | 99-4560 | OG8 OG9 OG10 CLEAN ONE TON BAGS (SM) | 7.5
44794 | 44789 | 32-6520 | SG3 PREP FENCE (FENCE) | 6
44794 | 44789 | 02-2300 | SG6 CLEAN SHAFT (BASEMENT MAINT) | 10
44794 | 44789 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR (SITE MAINT) | 4
44794 | 44789 | 99-4560 | OG10 CLEAN | 5
44794 | 44789 | 02-6010 | SG3 CLEAN BASEMENT (PUMP DEMO) | 7
44794 | 44789 | 02-2300 | SG4 SG5 CLEAN WATER FROM BASEMENT (BASEMENT MAINT) | 5
44794 | 44789 | 02-6060 | OG5 PATCH EXISTING SHEET ROCK (DEMO 2ND FLOOR APT) | 19
44794 | 44789 | 04-6120 | OG8 LOAD NEEDED FOR FAXA (FAXA B/C) | 4
44794 | 44789 | 99-4560 | SG4 SG5 SG6 PICK UP GARBAGE (SITE MAINT) | 5
44794 | 44789 | 03-1600 | FORMING RETAINING WALL | 38
44794 | 44789 | 32-6520 | SAFETY, REPAIRING HANDRAILS | 1.5
44794 | 44789 | 05-6010 | REMOVE BRIDGE BRACKETS | 1
44794 | 44789 | 31-2100 | HAND DIG STAIRS FOR JMC | 16
44794 | 44789 | 03-1400 | DRILL AND DOWEL FOR MASONRY SHELF | 16
44794 | 44789 | 33-2500 | LOAD PLATES AND LOAD PIPES FOR SGN FOR DOMINGO (DRAINAGE) | 24.5
44794 | 44789 | 31-2100 | SG4 LOAD 30 YRD CONTAINER | 12
44794 | 44789 | 33-2510 | SG6 SAW CUT ROADWAY FOR INSTALL SEWER & WATER MAIN | 8
44794 | 44789 | 33-2510 | REMOVE SPHALT AND CONCRETE FOR INSTALL SEWER AND EXCAVATION | 30
44794 | 44790 | 31-2200 | OG10 BACKFILL 3 TRUCK LOADS OF CLEAN FILL FOR FAXA | 2
44794 | 44790 | 32-6520 | SG3 REMOVAL OF FENCE TO DEMO PAVEMENT | 6
44794 | 44790 | 31-1000 | SG3 EXCAVATE FOR MASONRY SHELF AND FLOODWALLS | 12
44794 | 44790 | 32-6520 | SG3 INSTALL FENCE ON TEMP WALKWAY | 11.5
44794 | 44790 | 03-1400 | SG2 INSTALL DOWELS FOR MASONRY SHELF | 16
44794 | 44790 | 33-3100 | SG3 REMOVE TRENCH BOX FOR STEAM PIPE | 5
44794 | 44790 | 02-1900 | SG3 DEMO PAVEMENT | 9
44794 | 44790 | 03-1600 | SG5 FORM RETAINING WALL | 30.5
44794 | 44790 | 03-1100 | OG3 STAYFORM WALKWAY | 2
44794 | 44790 | 03-1400 | OG6 DRILL AND INSTALL WALL/WINDOWS | 21.5
44794 | 44790 | 05-6020 | SG7 GROUT COLUMNS | 9.5
44794 | 44790 | 32-6520 | SG3 INSTALL TEMP WALKWAY | 4
44794 | 44790 | 02-6025 | OG5 DEMO TO EXTEND FAI | 2.5
44794 | 44790 | 99-4560 | SG7 REMOVE SMALL PILE OF DEBRI | 10
44794 | 44790 | 33-3100 | OG3 TRENCH MAINTENANCE/CLEAN UP | 4
44794 | 44790 | 99-4560 | OG9 CLEAN WATER ON 1ST FLOOR AND SHAFT | 6.5
44794 | 44790 | 32-6520 | SITE8 MAINTAIN FENCE LINE | 8
44794 | 44790 | 02-6045 | OG5 CUT OUT AC SHELVES | 9.5
44794 | 44790 | 00-0039 | OG2 INSTALL A/C BRACKETS | 9.5
44794 | 44790 | 04-6120 | OG8 FAXA NEEDED LULL | 5.5
44794 | 44790 | 33-2510 | SG6 LULL NEEDED (DOMINGOS) | 1
44794 | 44790 | 32-6220 | WORK WITH JMC - INSTALL CONCRETE | 7
44794 | 44790 | 00-0025 | EXCAVATION TO INSTALL 6" WATER PIPE "CO44" | 13
44794 | 44790 | 33-2510 | WORK ON SEWER TO INSTALL WOOD SHEETING AND PREPARE SHEETING | 30
44794 | 44791 | 33-2500 | MOVE MH FROM SG5 TO SG4 (DRAINAGE INSTALL) | 4
44794 | 44791 | 00-0025 | EXCAVATION FOR WATER MAIN AND INSTALL WOOD SHEETING FOR WET TAP (CO 44) | 51.5
44794 | 44791 | 00-0025 | PREPARE WOOD SHEETING TO INSTALL AT SEWER (CO 44 BULLETIN 1) | 10.5
44794 | 44791 | 03-1000 | OG8 REMOVE SCAFFOLDING FROM SHAFT | 13
44794 | 44791 | 03-1000 | OG8 FORM ROOF PENETRATION (FW NEW BUILDING) | 13.5
44794 | 44791 | 03-1000 | OG10 REMOVE HARDWARE (FW NEW BUILDING) | 1
44794 | 44791 | 32-6520 | SG6 OG10 REPAIR HANDRAIL (FENCE INSTALL) | 2
44794 | 44791 | 03-1600 | SG5 WATCH OVER CONCRETE POUR (FORMWORK FOR RETAINING WALL) | 3
44794 | 44791 | 33-2900 | LIVE LOAD OF DEBRIS @ SITE8 (AREAWAY DEMO 40 YD) | 4.5
44794 | 44791 | 33-3100 | HAND DIG GROUND RODS FOR FSE (UTILITY EXCAVATION) | 16
44794 | 44791 | 31-1000 | DIG MASONRY SHELF FOR FAXA | 19
44794 | 44791 | 00-0043 | HAND DIG FOR UTILITIES AT MASONRY SHELF (SHELF EXCAVATION) | 2
44794 | 44791 | 07-6210 | COVER BOOM TRUCK TO LOAD FROM TRAILER TO THE ROOF FOR ROOFERS (TRIANGLE B/C) | 1
44794 | 44791 | 03-2400 | SG5 POUR RETAINING WALL | 22.5
44794 | 44791 | 32-6520 | SG3 INSTALL TEMP WALKWAY (FENCE INSTALL) | 7
44794 | 44791 | 33-1100 | CLEAN BY WELKIN YARD (STEAM DEMO/UTILITY DEMO) | 9
44794 | 44791 | 03-1400 | OG6 DRILL DOWELS | 7
44794 | 44791 | 03-1400 | SG2 INSTALL DOWELS | 9
44794 | 44791 | 00-0039 | OG2 INSTALL A.C IN WINDOW OF APT 1F | 16
44794 | 44791 | 02-3000 | OG4 CLEAN BASEMENT (COREDRILL/SAWCUT CLEAN UP) | 9
44794 | 44791 | 99-4560 | SG1 CLEAN AROUND BASEMENT | 9
44794 | 44791 | 04-6120 | NEED LULL FOR FAXA | 4
44794 | 44791 | 02-6010 | SG7 CLEAN UP (SUMP PUMP BASEMENT DEMO) | 4
44794 | 44791 | 26-6030 | SG6 LOAD NEEDED FOR FSE | 2
44794 | 44792 | 33-2510 | WORK AT EXCAVATION AND VACUUM FOR INSTALL SEWER AND INSTALL WOOD SHEETING | 62
44794 | 44792 | 03-1600 | STRIP RETAINING WALL | 28
44794 | 44792 | 03-2300 | DUCT BANK | 8.5
44794 | 44792 | 03-1000 | SG6 ROOF, CLOSE PENETRATIONS - NB FORMWORK 10SF | 4
44794 | 44792 | 32-6520 | SG3 REMOVAL OF FENCE TO EXCAVATE FOR MASONRY SHELF | 5
44794 | 44792 | 31-1000 | SG3 DIG FOR MASONRY SHELF | 24.5
44794 | 44792 | 32-6520 | SG3 REPLACE FENCE | 5.5
44794 | 44792 | 03-1400 | DRILL AND DOWEL WINDOWS AND MASONRY SHELF | 14
44794 | 44792 | 02-1900 | SAW CUT CONCRETE AND SIDEWALK | 3
44794 | 44792 | 02-3000 | OG1 PATCH FOR CMU PENETRATIONS IN BASEMENT (SAWCUT/CORE) | 17.5
44794 | 44792 | 02-6060 | OG6 REMOVE CEILING IN 1ST FLOOR OFFICE | 9
44794 | 44792 | 03-1900 | OG8 POUR PADS ON ROOF AND 2ND FLOOR (CONC. NEW BUILDING) | 13.5
44794 | 44792 | 00-0039 | OG3 INSTALL AC BRACKETS | 9.5
44794 | 44792 | 00-0039 | OG4 INSTALL AC BRACKETS | 9
44794 | 44792 | 04-6120 | SG6 FLAG FOR DOMINGOS | 5
44794 | 44792 | 02-3000 | OG4 CLEAN BASEMENT (SAWCUT/CORE DRILL) | 9
44794 | 44792 | 99-4560 | SG6 CLEAN AROUND (SITE MAINTENANCE) | 8
44794 | 44792 | 04-6120 | OG8 LULL NEEDED FOR FAXA | 2
44794 | 44792 | 04-6120 | OG8 LULL NEEDED FOR FSE | 2
44794 | 44792 | 00-0025 | SG6 "BACHUE" NEEDED FOR DOMINGOS (CO44) | 5
44794 | 44792 | 32-6210 | POUR CONCRETE FOR JMC | 6
44794 | 44792 | 99-4560 | SITE CLEAN UP | 2
44787 | 44781 | 33-3100 | TRENCH FOR ELECTRICAL SITE LIGHTING | 6
44787 | 44781 | 03-1800 | TONAGE SUPPORT REBAR TRANSPORT | 3
44787 | 44781 | 33-2600 | INSTALL AD-23 | 7.5
44787 | 44781 | 33-2500 | INSTALL DIP 15 TRENCHING AND MOVING PIPE ONLY | 5.5
44787 | 44781 | 04-6120 | GROUT PUMP | 1
44787 | 44781 | 02-6025 | SG4 PLATE WELDING FOR FAXA - DEMO BRICKS | 24
44787 | 44781 | 22-6070 | SG7 REMOVAL OF BRIDGE BRACKETS | 5
44787 | 44781 | 22-6070 | OG9 INSTALLMENT OF BRIDGE BRACKETS | 4
44787 | 44781 | 03-1000 | SG7 REPAIR SCAFFOLDING | 1
44787 | 44781 | 04-6130 | OG9 INSTALLMENT OF ANGLE FOR BRICK SHELF | 3.5
44787 | 44781 | 03-1000 | SG8 FORM COLUMN | 6.5
44787 | 44781 | 03-1100 | SG1 SG2 COMPLETE FORM WALL IN BASEMENT | 8
44787 | 44781 | 03-1100 | SG1 FORM AND COMPLETE WALL IN BASEMENT | 4.5
44787 | 44781 | 03-1000 | SG7 CLEAN SHAFT FORMWORK | 12
44787 | 44781 | 99-4560 | OG9 CLEAN AROUND BUILDING | 10
44787 | 44781 | 00-0039 | OG2 INSTALL AC BRACKET | 12
44787 | 44781 | 02-6005 | SITE8 PAINT REMOVAL | 10
44787 | 44781 | 04-6120 | LOAD MATERIALS FOR FAXA | 6
44787 | 44781 | 03-1900 | OG10 POUR CEMENT (2ND FLOOR SLAB) | 14
44787 | 44781 | 32-6520 | MOVE FENCE FROM SG2 AND MOUNT IT AT SG3 | 19
44787 | 44781 | 33-3100 | OG2 EXCAVATE FOR TEMP STEAM | 16
44787 | 44781 | 31-2200 | OG3 OG4 BACKFILL STEAM TRENCH | 17.5
44787 | 44781 | 03-1900 | SG7 CLEAN SHAFT CONCRETE | 11.5
44787 | 44781 | 33-2900 | REMOVE EXISTING AREA DRAIN | 3
44787 | 44781 | 99-7210 | PTO | 8
44787 | 44782 | 03-2400 | SG5 POUR FOOTING - RETAINING WALL/SITE WORK | 20.5
44787 | 44782 | 32-6520 | SG3 POUR TEMP SIDEWALK | 6
44787 | 44782 | 03-1900 | OG8 POUR PITS ON 1ST FLOOR (SLAB POUR, CONCRETE NEW BUILDING) | 7
44787 | 44782 | 32-6220 | LOAD STONE FOR JMC (BACKCHARGE JMC) | 4
44787 | 44782 | 32-6520 | SG3 MOUNT FENCE | 21
44787 | 44782 | 99-4560 | SG3 CLEAN TRENCH | 9
44787 | 44782 | 99-4560 | SG2 CLEAN PATH | 4
44787 | 44782 | 99-4560 | SG6 CLEAN 1ST FLOOR AND 2ND FLOOR | 4
44787 | 44782 | 07-6220 | OG9 CUT EXTENSIONS AT METAL POSTS - GUYTEC CHARGE | 8
44787 | 44782 | 07-6220 | OG10 CUT EXTENSIONS AT METAL POSTS - GUYTEC CHARGE | 4.5
44787 | 44782 | 03-1000 | OG10 STRIP FORM WORK FROM SLAB | 10.5
44787 | 44782 | 22-6070 | OG10 REMOVAL OF BRIDGE BRACKETS | 2
44787 | 44782 | 03-2400 | OG2 LOAD OUT FORMS AND MOVE TO SG5 (SITE WORK - RETAINING WALL) | 4
44787 | 44782 | 03-1000 | OG8 COMPLETE FORMING COLUMN | 4.5
44787 | 44782 | 03-1000 | OG8 FORM EQUIPMENT PADS ON 2ND FLOOR | 10
44787 | 44782 | 99-4560 | OG8 CLEAN DEBRIS FROM ROOM TO INSTALL EQUIPMENT PADS | 1.5
44787 | 44782 | 33-2500 | IMSTALL 40' DIP | 24
44787 | 44782 | 33-2600 | CHOP RISER FROM AD24, AD23 CONNECTIONS FOR AD | 2
44787 | 44782 | 04-6130 | SG4 BRICK REMOVAL AND WELDOONG FOR FAXA | 24
44787 | 44782 | 02-6025 | SG1 + SG2 DEMO VENTS AND REMOVE CELLAR WINDOWS (DEMO AREAWAYS) | 16
44787 | 44782 | 31-1000 | OG2 EXCAVATE REMAINING FLOODWALL FOOTING | 12
44787 | 44782 | 02-6025 | USE OF COMPRESSOR (DEMO AREAWAYS) | 2
44787 | 44782 | 31-2200 | OG3 OG4 BACKFILL (BACKFILL FOR STEAM PIEPES) | 4.5
44787 | 44782 | 99-7210 | PTO | 8
44787 | 44783 | 00-0036 | SG5 PUNCHLIST ITEMS FOR 2ND FLOOR APT | 9
44787 | 44783 | 00-0039 | OG1 AC BRACKETS INSTALL | 9
44787 | 44783 | 07-6210 | OG8 SELF LEVEL ROOF | 9
44787 | 44783 | 07-6220 | OG8 CUT OUT STANSIONS AT ROOF (PREP ROOF) | 9
44787 | 44783 | 03-2300 | SITE8 POUR CEMENT DUCTBANK | 9
44787 | 44783 | 31-1000 | SG3 HAND DIG FOR EXPOSE UNTILITIES (MASONRY SHELF) | 21
44787 | 44783 | 99-4560 | OG5 OG6 CLEAN TRENCH FOR WELKIN | 9
44787 | 44783 | 99-4560 | OG5 OG6 DIG TRENCH FOR WELKIN | 5
44787 | 44783 | 03-2100 | SITE8 PREPARE FOR CONCRETE | 2.5
44787 | 44783 | 04-6120 | OG8 LOAD FOR FAXA | 5
44787 | 44783 | 99-4560 | OG10 CLEAN GARBAGE | 2
44787 | 44783 | 99-4560 | SG6 CLEAN SECOND FLOOR | 4
44787 | 44783 | 99-4560 | OG10 CLEAN | 4
44787 | 44783 | 03-2300 | SITE8 EASTSIDE FORM BULKHEAD AND STAYFORM | 8
44787 | 44783 | 03-1000 | OG8 FORM 2ND FLOOR SLAB OPENING | 8.5
44787 | 44783 | 03-1600 | SG5 START FORMING WALL (SITEWORK - RETAINING WALL) | 16
44787 | 44783 | 33-2500 | INSTALL 80LF 6" DLP AND BACKFILL AT DIP4 - PATCH MH | 26.5
44787 | 44783 | 33-2600 | SAW CUT AD 23 | 4
44787 | 44783 | 33-2600 | CLEARANCE TO INSTALL AD21 | 2
44787 | 44783 | 03-2300 | OG3 OG4 INSTALL CONCRETE WITH SERGIO - THRUST BLOCK STEAM PIPE | 2
44787 | 44783 | 33-3100 | OG1 REMOVE TRENCH BOXES FROM OG1 TO SITE8 (ELECTRIC TRENCH) | 10
44787 | 44783 | 31-2200 | OG1 BACKFILL AND COMPACT PIPES FROM FSE | 8.5
44787 | 44783 | 31-1000 | SG1 DIG AND HAND DIG FOR MASONRY FOUNDTION | 8
44787 | 44783 | 33-3100 | OG2 DIG FOR STEAM PIPE (TEMP STEAM PIPE EXCAVATION | 8
44787 | 44783 | 03-2300 | POUR THRUST BLOCK | 1
44787 | 44783 | 04-6130 | AG4 DEMO BRICK AND WELD PLSTE | 14
44787 | 44783 | 99-7210 | PTO | 8
44787 | 44784 | 03-2100 | OG5 POUR AT BASEMENT PADS | 9.5
44787 | 44784 | 03-2100 | OG2 POUR 2ND FLOOR PADS | 6
44787 | 44784 | 03-2100 | OG3 POUR 2ND FLOOR PADS | 5
44787 | 44784 | 03-1900 | OG8 POUR COLUMN (CONCRETE NEW BUILDING) | 7
44787 | 44784 | 32-6520 | SG1 SG2 FINISH WALKWAY FENCE | 8
44787 | 44784 | 05-6030 | SG7 POUR GROUT COLUMNS | 11
44787 | 44784 | 33-3100 | SG3 HAND DIG (TEMP ELECTRICAL TRENCH) | 19.5
44787 | 44784 | 99-4560 | CLEAN AOUND AREA AT WEST 33RD STREET | 15
44787 | 44784 | 99-4560 | OG9 CLEANING | 10
44787 | 44784 | 99-4560 | SG4 CLEAN AROUND BUILDING | 2.5
44787 | 44784 | 02-2300 | OG4 PUMP WATER FROM BASEMENT | 3
44787 | 44784 | 07-6220 | OG10 DRY ROOF AND CUT EXTENSIONS (ROOF PREP) | 6
44787 | 44784 | 03-2100 | OG2 OG3 OG5 OG8 NEEDED MACHINE FOR POURS | 6
44787 | 44784 | 31-1400 | OG8 BACKFILL FOR FAXA (NEW BUILDING) | 2
44787 | 44784 | 02-1900 | OG1 EXCAVATE FOR GMC FLOORING (SIDEWALK) | 2
44787 | 44784 | 03-2100 | OG2 FORM EQUIPMENT PADS (CONCRETE EXISTING BUILDINGS) | 4
44787 | 44784 | 07-6110 | SG6 SHIMMING CURTAIN WALL FOR PANELS (NAVILLUS SUPPORT) | 5
44787 | 44784 | 03-1600 | SG5 FORM RETAINING WALL (SITE WORK) | 23.5
44787 | 44784 | 33-2600 | EXCAVATION TO INSTALL AD21 | 12.5
44787 | 44784 | 33-2900 | REMOVE CONCRETE AND REMOVE EXISTING MANHOLE AND PIPES | 9
44787 | 44784 | 33-2500 | INSTALL 40' LF 6" DIP BETWEEN AD3 - AD21. DIP 24 (INSTALL DIP) | 10
44787 | 44784 | 33-2500 | CUT AD3 AND AD21 TO INSTALL PIPE (DIP IINSTALL) | 2
44787 | 44784 | 31-1000 | OG1 EXCAVATE/HAND DIG FOR STAIRS AND FOOTING (SITE WORK) | 16
44787 | 44784 | 31-1400 | OG8 BACKFILL AND FLAG FOR 322 ON SIDEWALK (BACKFILL NEW BUILDING) | 16.5
44787 | 44784 | 04-6120 | FAXA BACKCHARGE | 5
44787 | 44784 | 99-7210 | PTO | 8
44787 | 44785 | 04-6120 | SG5 RELOCATE METAL BOX (FAXA SUPPORT) | 4.5
44787 | 44785 | 07-6220 | OG8 FINISH CUTTING EXTENTIONS IN 2ND FLOOR (PREP ROOF) | 7
44787 | 44785 | 07-6220 | OG10 FINISH CUTTING EXTENTIONS IN 2ND FLOOR (PREP ROOF) | 7
44787 | 44785 | 02-2300 | OG4 CLEAN BASEMENT | 11
44787 | 44785 | 33-3100 | OG9 DIG FOR WELKIN (TRENCH) | 5
44787 | 44785 | 02-2300 | SG5 CLEAN BASEMENT WATER (BASEMENT MAINT) | 3
44787 | 44785 | 03-1900 | OG8 REPAIR COLUMN (CONCRETE NEW BUILDING) | 7
44787 | 44785 | 03-1900 | OG9 PATCH HOLE IN 2ND FLOOR | 15
44787 | 44785 | 32-6520 | SG3 INSTALL TEMP FENCE | 8.5
44787 | 44785 | 32-6220 | SG5 LOAD NEEDED FOR JMC (BACKCHARGE JMC) | 5.5
44787 | 44785 | 02-6060 | SG5 FIX LOCK IN APARTMENT | 6
44787 | 44785 | 02-6060 | OG1 WORK IN APARTMENT (AE BRACKETS) | 10
44787 | 44785 | 33-3100 | SG3 HAND DIG FOR FSE AND CUT ABANDONED CONDUITS (TEMP ELECTRIC) | 16
44787 | 44785 | 03-1000 | OG8 STRIP COLUMN | 1
44787 | 44785 | 07-6110 | OG9 SHIM FOR PANELS | 3
44787 | 44785 | 03-1100 | OG3 STRIP 2ND FLOOR EQUIPMENT PAD | 3
44787 | 44785 | 03-1100 | OG3 STRIP 1ST FLOOR PAD | 4.5
44787 | 44785 | 03-1600 | SG5 FORM RETAINING WALL (SITE WORK) | 22.5
44787 | 44785 | 03-1000 | OG8 FORM EQUIPMENT HOLES | 6.5
44787 | 44785 | 33-2500 | PICK UP 6"PIPE FROM SITE8 | 4
44787 | 44785 | 02-1900 | LOAD (2) 20 YARD CONCRETE MATERIAL AND REMOVE CONCRETE | 4
44787 | 44785 | 33-2600 | INSTALL AD1 AND AD2 | 9
44787 | 44785 | 33-2500 | EXCAVATION AND INSTALL 6" DIP, FROM AD1 TO AD2 - DIP 11 = 55' | 16.5
44787 | 44785 | 33-2500 | LOAD 8" AND 6" PIPE FOR SGN AT SITE8 (DRAINAGE) | 8.5
44787 | 44785 | 02-6025 | DEMO ARER -CHOP AND REMOVE VENT | 19
44787 | 44785 | 99-4560 | SITE8 LOAD AND REMOVE CARDELLA | 2
44787 | 44785 | 03-2300 | SITE BACKFILL FOR ELECTRICAL PIPES (DUCTBANK) | 3
44787 | 44785 | 02-6025 | USE OF COMPRESSOR (DEMO AREAWAY) | 1
44787 | 44785 | 99-7210 | PTO | 8
44780 | 44774 | 02-6025 | SG4 DEMO BRICK TO PREP FOR WELDING | 28.5
44780 | 44774 | 33-3100 | SGN HAND DIG TO EXPOSE STEAM LINE AND UTILITIES | 7.5
44780 | 44774 | 02-2100 | SGN DEMO RETAINING WALL TO PREP FOR NEW RETAINING WALL | 6
44780 | 44774 | 02-1900 | SGN DEMO WALK WAYS | 4
44780 | 44774 | 31-2200 | SGN BACKFILL AFTER DEMO | 3
44780 | 44774 | 04-6120 | FAXA SUPPORT - COVER GROUT POT | 1
44780 | 44774 | 00-0038 | SG1 EXCAVATE FOR TEMP ELECTRIC FOR 5 STAR (C/O) | 26
44780 | 44774 | 02-6045 | OG1 OG5 OG6 OG2 OG3 REMOVE METAL FRAMING AND WINDOW GUARDS AT AC UNITS | 16
44780 | 44774 | 33-2600 | SITE8 PREP AREA FOR DIGGING (MH EXCAVATION) | 6.5
44780 | 44774 | 03-1100 | OG2 FINISHED INSTALLMENT OF EQUIPMENT PADS ON THE 2ND FLOOR (EXISTING BUILDING) | 6
44780 | 44774 | 03-1100 | OG2 FORM THE BOTTOM OF EQUIPMENT PADS | 12.5
44780 | 44774 | 31-1400 | OG8 FORM FOR FLOW FILL (BACK FILL NB CODE) | 6
44780 | 44774 | 99-4560 | SG4 REMOVE PILED DEBRIS NEAR FRONT ENTRANCE | 4
44780 | 44774 | 99-4560 | SG4 CLEAN GARBAGE AROUND BLD | 4
44780 | 44774 | 99-4560 | SG6 REMOVE PILED DEBRIS 1ST AND 2ND FORMS | 4
44780 | 44774 | 99-4560 | OG8 REMOVE PILED DEBRIS 1ST AND 2ND FORMS | 4
44780 | 44774 | 00-0019 | OG2 TEMP WALKWAY FNCE RELOCATION (O'DWEYER FENCE C/O) | 13.5
44780 | 44774 | 03-1400 | OG6 DRILL AND DOWEL FOR FOUNDATION WALL AND REMOVE INSULATION | 20
44780 | 44774 | 99-4560 | OG9 REMOVE PILED DEBRIS AROUND BLD | 6
44780 | 44774 | 99-4560 | OG10 REMOVE PILED DEBRIS AROUND BLD | 5
44780 | 44774 | 04-6120 | FAXA LULL | 4
44780 | 44775 | 04-6130 | SG4 WELD PLATES FOR FAXA | 33.5
44780 | 44775 | 02-6025 | SG4 DEMO BRICK AND PREP FOR WELDING | 9
44780 | 44775 | 33-3100 | SGN DIG TRENCH FOR RETAINING WALL | 8.5
44780 | 44775 | 02-2100 | SGN DEMO CURB | 4
44780 | 44775 | 02-2100 | SGN CARDELLA - PICK ONE UP/SWAP ONE OUT/LIVE LOAD X 2 CONCRETE (DEMO PUMT CUB REMOVAL) | 6
44780 | 44775 | 33-2600 | SGN MOVE MATERIAL AND ORGANIZE YARD (LIGHT POLE INSTALL) | 4
44780 | 44775 | 04-6120 | FAXA SUPPORT (COVER GROUT) | 1
44780 | 44775 | 00-0038 | SG1 EXCAVATE FOR TEMP ELECTRIC (CHANGE ORDER) | 4.5
44780 | 44775 | 03-1000 | OG10 DIG BACKSIDE OF FORMS, STRIP FORMS (STRIPPING) | 4
44780 | 44775 | 31-1000 | SG1 EXCAVATE FOR MASONRY SHELF | 24
44780 | 44775 | 31-1000 | SG1, SG2 HAND DIG TO EXPOSE ALL UTILITIES AROUND BUILDING FOR MASONRY SELF | 6
44780 | 44775 | 02-6015 | SG1 REMOVE WINDOWS | 2
44780 | 44775 | 03-1100 | OG2 FORM EQUIPMENT PADS AT FIRST FLOOR | 3
44780 | 44775 | 31-1400 | OG8 FORM WALL FOR FLOW FILL | 6.5
44780 | 44775 | 03-1100 | OG5 FORM EQUIPMENT PAD IN BASEMENT | 5.5
44780 | 44775 | 03-2300 | OG1 FORM BULK HEAD | 6
44780 | 44775 | 03-1000 | OG8 OG5 OG2 OG1 MOVE MATERIAL FOR CARPENTER | 8
44780 | 44775 | 31-2200 | JUMP/PUMPS | 2
44780 | 44775 | 03-1400 | OG6 DRILL AND DOWEL FOUNDATION WALL | 8.5
44780 | 44775 | 03-1400 | OG10 DRILL AND DOWEL AT SHAFT WALL | 5.5
44780 | 44775 | 00-0005 | OG2 OG3 OG5 INSTALL ANCHOR BOLTS IN PADS | 16.5
44780 | 44775 | 03-2120 | SG3 CLEAN AFTER SPRAYING (SHOTCRETE SUPPORT) | 18
44780 | 44775 | 00-0019 | SG2 BACKFILL FOR TEMP WALKWAY (OG FENCE C/O) | 9
44780 | 44775 | 31-1400 | OG8 POUR FLOW FILL AT LEAVE OUTS (BACKFILL) | 3
44780 | 44775 | 04-6120 | FAXA LULL | 4
44780 | 44775 | 31-1400 | OG8 CLEAN AREA AT BLD EXTERIOR ALPNG 33RD ST FOR POUR FLOWFILL | 1.5
44780 | 44775 | 99-4560 | OG1 MAINTENANCE CLEAN | 2
44780 | 44775 | 99-4560 | SG3 MAINTENANCE CLEAN | 0.5
44780 | 44775 | 99-4560 | SG3 MAINTENANCE CLEAN | 8
44780 | 44775 | 02-2100 | CURB/PAVEMENT REMOVAL | 4
44780 | 44776 | 03-2300 | OG1 INSTALL FOAM AGAINST TRENCH BOX (DUCT BANK POUR) | 3.5
44780 | 44776 | 03-1100 | OG3 FORM EQUIPMENT PADON 2ND FLOOR | 15
44780 | 44776 | 03-1100 | OG3 FORM EQUIPMENT PAD 1ST FLOOR | 6
44780 | 44776 | 03-1100 | CLEAN AND MOVE MATERIAL FROM OG1 OG3 (FORM WORK EXISTING BUILDING) | 8
44780 | 44776 | 04-6130 | SG5 WELD PLATES FOR FAXA | 16
44780 | 44776 | 02-6025 | SG5 DEMO BRICKS AND PREP FOR WELDING | 16.5
44780 | 44776 | 33-2600 | SGN OFFLOAD 1 TRUCK OF CASTING AND LIGHT POLE BASES (MH INSTALL) | 8.5
44780 | 44776 | 02-1900 | SGN LOAD OUT 1 CARDELLA OF CONCRETE + DROP OFF STEEL CONTAINER | 6
44780 | 44776 | 33-2600 | SGN INSTALL AD-8 | 6
44780 | 44776 | 99-4560 | SGN MOVE MATERIAL AND ORGANIZE YARD | 2
44780 | 44776 | 33-1000 | DEMO EXIST UTILITY | 4
44780 | 44776 | 99-4560 | SG3 SITE MAINT | 6
44780 | 44776 | 04-6120 | FAXA SUPPORT - COVER GROUT POT | 1
44780 | 44776 | 31-1000 | SG1 EXCAVATE FOR MASONRY SHELF | 32.5
44780 | 44776 | 02-6025 | CHOP CONCRETE VENTS | 17
44780 | 44776 | 33-2400 | USE 32Z JUMP TO MINI | 1
44780 | 44776 | 00-0019 | SG2 PREP AND POUR TEMP. WALKWAY (OG FENCE C/O) | 8
44780 | 44776 | 03-2300 | OG1 POUR DUCTBANK | 6
44780 | 44776 | 03-2120 | SG3 REMOVE 1 TON BAGS FROM BASEMENT | 21.5
44780 | 44776 | 03-1400 | OG6 DRILL AND DOWEL FOR FOUNDATION WALL | 4.5
44780 | 44776 | 03-1800 | MOVE REBAR FROM OG10 TO SGN | 2
44780 | 44776 | 04-6120 | FAXA - LULL | 3
44780 | 44776 | 99-4560 | SG6 HOUSE KEEPING BY ALL TRADES (SITE MAINT) | 4
44780 | 44776 | 99-4560 | SG3 MAINTAIN AREA BY STEAM TRENCH (SITE MAINT) | 4
44780 | 44776 | 31-1400 | OG8 PREP TO POUR LEAVE OUTS - DRILL AND DOWEL - STRIP LUMBER (NB BACKFILL) | 19.5
44780 | 44776 | 33-2400 | JUMP | 2
44780 | 44777 | 31-2100 | SG6 ADJUSTED OITSIDE CURTAIN WALL | 20.5
44780 | 44777 | 03-2300 | SG2 STRIP DUCTBANK BULKHEAD | 6
44780 | 44777 | 03-2300 | SG3 STRIP DUCTBANK BULKHEAD | 6
44780 | 44777 | 04-6130 | SG5 WELD PLATES FOR FAXA | 16
44780 | 44777 | 02-6025 | SG5 DEMO BRICK AND PREP FOR WELDING | 12.5
44780 | 44777 | 02-6025 | SG5 CLEAN FOR FAXA (BRICK) | 4.5
44780 | 44777 | 31-2100 | SGN DIG TRENCH FOR RETAINING WALL (LOAD OUT HNS X 6 LOADS) | 18.5
44780 | 44777 | 33-2600 | SGN INSTALL AD-27 - LOAD OUT HNS 1 LOAD | 16
44780 | 44777 | 31-2200 | SGN BACKFILL TRENCH WITH STONE | 5
44780 | 44777 | 04-6120 | FAXA SUPPORT - COVER GROUT POT) | 1
44780 | 44777 | 31-2200 | JUMP | 2
44780 | 44777 | 03-2120 | SG3 REMOVE 1 TON BAGS OF DEBRIS FOM SHOTCRETE (SHOTCRETE SUPT) | 28
44780 | 44777 | 03-1900 | OG10 PREP TO POUR SLAB EDGE (POUR CONC NB) | 1.5
44780 | 44777 | 03-1400 | OG8 PREP TO POUR LEAVE OUTS - INSTALL DOWEL | 5
44780 | 44777 | 03-1000 | OG8 INSTALL MESH AT COLUM (FORMWORK NB) | 3.5
44780 | 44777 | 00-0005 | OG3 INSTALL ANCHOR BOLTS AT 2ND FLOOR PADS - CONC EXIST BLD | 11
44780 | 44777 | 02-6005 | SITE8 PAINT REMOVAL FOR FOUNDATION WALL | 7.5
44780 | 44777 | 03-1800 | MOVE REBAR FROM OG10 TO SGN (EXCAVATE FOR RETAINING WALL) | 4
44780 | 44777 | 04-6120 | FAXA - LULL | 4
44780 | 44777 | 99-4560 | OG10 CLEAN UP 1ST AND 2ND FLOOR (SITE MAINT) | 8
44780 | 44777 | 31-1000 | SG2 EXCAVATE FOR MASONRY SHELF | 25.5
44780 | 44777 | 02-6025 | SG1 SAWCUT, CHOP AND REMOVE CONCRETE FOR VENTS | 16
44780 | 44778 | 04-6130 | SG5 WELD PLATES FOR FAXA | 24.5
44780 | 44778 | 02-6025 | SG5 DEMO BRICKS FOR FAXA AND PREP FOR WELDING | 6
44780 | 44778 | 31-2100 | SGN DIG TRENCH FOR REATAINING WALL | 14.5
44780 | 44778 | 33-2500 | SGN INSTALL PIPES IN AD-27 (DRAINAGE) | 10
44780 | 44778 | 33-2500 | SGN PATCH PIPES IN AD-27 (DRAINAGE) | 6
44780 | 44778 | 99-4560 | ENTIRE SITE/ENSURE ALL GATES ARE LOCKED (SITE MAINT) | 0.5
44780 | 44778 | 03-1900 | SITE8 CLEAN 1ST FLOOR (CHOPPING CONCRETE > POUR CONCRETE) | 2
44780 | 44778 | 02-2300 | SG4 REPLACE PUMP IN BASEMENT (BASEMENT MAINT) | 1
44780 | 44778 | 04-6120 | FAXA - LULL | 4
44780 | 44778 | 02-6045 | OG1 AND OG4 INSTALL AC BRACKETS | 9
44780 | 44778 | 02-6005 | SITE8 PAINT REMOVAL FOR FOUNDATION WALL | 10
44780 | 44778 | 02-2300 | OG1 CLEAN AND REMOVE CHOPPED CONCRETE FROM BARS - INSTALL PUMP IN BASEMENT | 15
44780 | 44778 | 99-4560 | OG1 OG4 OG10 OG2 REMOVE 1 TON BAGS (SITE MAINT) | 8
44780 | 44778 | 32-6520 | SG2 INSTALL FENCE ON TEMP WALKWAY | 9
44780 | 44778 | 03-1900 | OG10 BOLT DOWN HSS POSTS (CONCRETE NB) | 14
44780 | 44778 | 04-6120 | GROUT PUMP JUMP | 2
44780 | 44778 | 26-6030 | SET MILL FOR FSE | 12
44780 | 44778 | 33-3100 | BACKFILL MANHOLE AND EXCAVATE TRENCH TO NEW BUILDING | 6.5
44780 | 44778 | 02-6025 | SG1 SG2 CUT, CHOP CONCRETE EVENTS (DEMO AREA WAYS) | 22
44780 | 44778 | 02-6025 | SG1 SG2 USE OF COMPRESSOR | 1
44780 | 44778 | 03-1100 | OG3 FORM EQUIPMENT PAD 1ST FLOOR | 16
44780 | 44778 | 04-6130 | OG9 INSTALL ANGLE FOR BRICK SHELF | 6
44780 | 44778 | 03-1100 | SG1 FORM OFF WALL IN BASEMENT | 6.5
44780 | 44778 | 02-2300 | SG1 CLEAN UP BASEMENT | 2
44780 | 44778 | 03-1100 | MOVE FORM FROM SG1 TO SG2 | 2
44773 | 44767 | 00-0036 | SG5 PUNCH LIST ITEMS IN APARTMENT 2E (CHANGE ORDER) | 18.5
44773 | 44767 | 32-6000 | OG1 SAW CUT POE FOR 5 STAR (SAW CUT) | 20
44773 | 44767 | 99-4560 | SG6 SITE MAINTENANCE | 16
44773 | 44767 | 02-6010 | SG2 REMOVE SUMP PUMP AND CLEAN PIT FOR TAL (SUMP PUMP DEMO) | 10
44773 | 44767 | 99-4560 | OG6 OG8 ORGANIZE AND CLEAN AREA (SITE MAINT REMOVE PILED DEBRIS) | 8
44773 | 44767 | 03-1000 | SITE8 REMOVE AND PICKUP ALL FORMS FROM JOB SITE AND STACK, BAND FORMS (FORMWORK LOADOUT) | 16
44773 | 44767 | 33-2600 | OG3 OFFLOAD AD CASTINGS AND LIGHT POLE BASES (1 TRUCK) | 12.5
44773 | 44767 | 33-2600 | SGN OFFLOAD CASTINGS AND MH'S (1 TRUCK) | 3.5
44773 | 44767 | 04-6130 | SGN WELD PLATES FOR FAXA (FAXA SUPPORT) | 16
44773 | 44767 | 33-2500 | SGN PATCH HOLES FOR INSTALLED DRAINAGE PIPE (PIPE INSTALL) | 7
44773 | 44767 | 33-2500 | SGN DIG FOR AD-24 (DRAINAGE INSTALL) | 6
44773 | 44767 | 33-2500 | SGN MODIFY AD-24 TO FIT EXISTING PIPE (PIPE INSTALL0 | 3
44773 | 44767 | 32-6000 | OG1 COMPRESSOR - SAW CUT POE | 1
44773 | 44767 | 03-1400 | OG6 DRILL AND DOWEL FOR FOUNDATION WALL | 10
44773 | 44767 | 99-4560 | OG10 REMOVE MONOCOAT FROM LEAVEOUT AREAS (CLEANED OUT FOR SIG, B/C) | 10
44773 | 44767 | 05-6050 | SITE8 CHIPAT ANCHOR BOLTS AND CLEAN UP FOR STEEL - CLEAN ALL SLABS | 10
44773 | 44767 | 33-6010 | MOVE EQUIPMENT FOR WELKIN - FROM WELKIIN YARD TO OG8 WITH PICK UP TRUCK (WELKIN SUPPORT) | 0.5
44773 | 44767 | 04-6120 | FAXA NEEDED LULL (FAXA SUPPORT) | 4
44773 | 44767 | 03-1900 | SG7 REMOVAL OF SCAFFOLD PLANKS AND BRIDGE BRACKETS (POUR CONCRETE) | 13
44773 | 44767 | 03-1000 | SG10 INSTALLMENT OF BRIDGE BRACKETS AND SCAFFOLD PLANKS (FORM WORK) | 14
44773 | 44767 | 32-6520 | OG8 REMOVAL OF SAFETY NETS (FENCE INSTALL) | 12
44773 | 44767 | 99-4560 | OG8 ADJUSTMENT OF SAFETY CABLE, REINSTALL SAFETY NETS | 3
44773 | 44767 | 03-1100 | OG2 FORM FLOODWALLS | 9
44773 | 44767 | 03-1100 | OG3 FORM FLOODWALL | 7
44773 | 44767 | 03-1100 | SG4 FORM FLOODWALLS | 6.5
44773 | 44768 | 01-6300 | SITE8 INSTALLMENT OF OVERHEAD PROTECTION AT DOORWAY | 14
44773 | 44768 | 32-6520 | OG6 MAINTAIN AND ADJUST SAFETY NETS AND CABLE (FENCE INST) | 4
44773 | 44768 | 99-4560 | SG6 SAFETY COVER OPENING (SITE MAINT) | 1.5
44773 | 44768 | 03-1100 | SG4 FORM FLOODWALL | 19
44773 | 44768 | 03-1000 | INSTALL TOE BOARD ON BRIDE BRACKET (FORM WORK) | 26
44773 | 44768 | 03-1000 | OG10 FORM SHAFT LEDGE | 8
44773 | 44768 | 31-2200 | OG3 TO OG4 BACKFILL STEAM LINE TRENCH | 17.5
44773 | 44768 | 31-2200 | OG1 BEGIN BACKFILL OF TRENCH (ELECTRIC DUCTBANK) | 7
44773 | 44768 | 04-6130 | SG5 WELD PLATES FOR FAXA (FAXA SUPPORT) | 16.5
44773 | 44768 | 31-2200 | PUMPS | 2
44773 | 44768 | 99-4560 | SG1 CLEAN/REMOVE CENTER PILED DEBRIS FROM 1ST FL PRAMBULAR ROOM (SITE MAINT) | 6
44773 | 44768 | 32-6000 | SG3 SAWCUT 2ND FLOOR SLAB OPENINGS | 16.5
44773 | 44768 | 99-4560 | SGN REMOVE ALL ONE TON BAGS AND COLLECT GARBAGE AND PUT IN DUMPSTER (SITE MAINT) | 38
44773 | 44768 | 04-6120 | RUN LULL 4HRS FOR FAXA | 4
44773 | 44768 | 03-1400 | OG6 DRILL AND DOWELL FOR FOUNDATION WALL | 13
44773 | 44768 | 03-1000 | SITE8 LOAD OUT FORMS (FORM WORK) | 18
44773 | 44768 | 05-6040 | SG7 TO SITE8 MOVE PLATES FOR CRANE | 6
44773 | 44768 | 03-1900 | SITE8 CHIP AT ANCHOR BOLTS (PREP COLUMN FOR STEEL) | 4
44773 | 44768 | 03-1000 | SITE8 CLEAN FORMWORK (FORM LOAD OUT) | 14.5
44773 | 44768 | 99-4560 | SITE8 CLEAN REBAR (DEBRIS REMOVAL) | 5
44773 | 44768 | 99-4560 | SG5 REMOVE CENTER PILED GARBAGE | 4
44773 | 44769 | 31-2200 | OG1 BACKFILL ELECTRICAL CONDUIT FOR PIPE INSTALL | 6
44773 | 44769 | 33-2500 | OG1 INSTALL DRAINAGE PIPE | 9.5
44773 | 44769 | 99-4560 | OG1 CLEAN UP GARBAGE | 4
44773 | 44769 | 04-6130 | SG5 WELD PLATES FOR FAXA | 16.5
44773 | 44769 | 00-0037 | FIVESTAR YARD - GRADE AREA FOR JACOBS TRAILER REMOVAL (CHANGE ORDER) | 10
44773 | 44769 | 33-2600 | SGN MODIFY AD-24 TO ACCOMMODATE EXISTING PIPE | 8
44773 | 44769 | 05-6040 | SITE8 MOVE CONCRETE BLOCKS FROM SG7 FOR CRANE (PREP FOR CRANE) | 4
44773 | 44769 | 02-6005 | SG2 PAINT REMOVAL AND DRILL/DOWEL IN BASEMENT FOUNDATION WALL | 5
44773 | 44769 | 03-1400 | SG1 & SG2 & OG6 DRILL AND DOWEL FOR FOUNDATION WALL | 21
44773 | 44769 | 00-0037 | OG6 PREP FOR JACOBS TRAILER MOVE (CHANGE ORDER) | 16
44773 | 44769 | 32-6000 | SG3 SAWCUT 2ND FLOOR SLAB OPENINGS | 20
44773 | 44769 | 02-6005 | SG1 PAINT REMOVAL | 5.5
44773 | 44769 | 03-1400 | OG6 DRILL AND DOWEL FOR FOUNDATION WALL | 7
44773 | 44769 | 00-0019 | OG2 SG4 PREP FOR TEMP. WALKWAY (O'DWEYER FENCE C/O) | 14.5
44773 | 44769 | 32-6000 | OG8 COMPLETE SAW CUTTINGS AT TANK ROOM | 6
44773 | 44769 | 99-4560 | OG10 CLEAN UP AREA OUTSIDE BLD AND INSIDE (SITE MAINT) | 17
44773 | 44769 | 99-4560 | SG6 REMOVE 1 TON BAG OF DEBRIS FROM ROOF | 4
44773 | 44769 | 31-2200 | JACOBSTRAILER REMOVAL THUR AM - BACKFILL AREA (BACKFILL TRENCH) | 2
44773 | 44769 | 99-4560 | OG8 VITAL NEEDS LULL FOR LOADING 2ND FLOOR WITH PIPE | 1
44773 | 44769 | 26-6030 | OG10 FSE NEEDS LULL (SWITCH GEAR DELIVERY) | 2
44773 | 44769 | 04-6130 | OG9 INSTALLMENT OF ANGLE IRON | 10
44773 | 44769 | 03-1000 | OG10 FORMING FOR SHAFT LEDGE (NB FORM WORK) | 14
44773 | 44769 | 03-1100 | SG4 COMPLETE FORM FOR FLOODWALL | 13.5
44773 | 44769 | 03-1100 | SG5 SOUTHSIDE COMPLETE FORM FOR FLOODWALL | 15
44773 | 44769 | 99-4560 | COVER OPEN AT SG8 (SITE MAINT) | 3
44773 | 44769 | 03-1100 | SG4 CLEAN UP FLOODWALL - FORMWORK | 3.5
44773 | 44769 | 03-1000 | MOVE FORM TO SG4 SG5 OG10 FLOODWALL - FORMWORK | 11.5
44773 | 44769 | 04-6120 | JUMP (GROUT PUMPS) | 1
44773 | 44769 | 33-2600 | JUMP (BACKHOE) | 1
44773 | 44770 | 33-2600 | SGN MODIFY MANHOLE TO ACCOMMODATE EXISTING PIPES | 10.5
44773 | 44770 | 33-2500 | SGN TRENCH FOR PIPE INSTALLATION | 7
44773 | 44770 | 33-2600 | SGN INSTALL DRAINAGE PIPE AD4 AD24 + AD24 AD3 | 12
44773 | 44770 | 04-6130 | SG5 WELD PLATES FOR FAXA | 16
44773 | 44770 | 03-1800 | SG7 OFFLOAD REBAR FOR TONAGE "TONAGE OFFLOAD" | 4
44773 | 44770 | 04-6120 | FAXA LULL CODE TO COVER GROUT PUMP | 1
44773 | 44770 | 33-2600 | JUMPS | 1
44773 | 44770 | 03-1100 | SG4 COMPLETE FLOODWALLS INSTALL SCAFFOLD (FORMWORK) | 5
44773 | 44770 | 03-1100 | SG5 SOUTH SIDE COMPLETE FLOODWALLS INSTALL SCAFFOLD (FORMWORK) | 5
44773 | 44770 | 03-1100 | SG5 NORTH SIDE COMPLETE FLOODWALLS INSTALL SCAFFOLD (FORMWORK) | 31
44773 | 44770 | 03-1100 | OG2 INSTALL OF ELECTRICAL EQUIPMENT PADS | 18
44773 | 44770 | 32-6520 | SG5 SOUTH SIDE SIDEWALK PROTECTION (FENCE INSTALL) | 5.5
44773 | 44770 | 32-6000 | SG3 SAW CUT 2ND FLOOR SLAB OPENINGS | 20
44773 | 44770 | 00-0011 | OG6 REMOVE CEILING TILES IN FIRST FLOOR IN MANAGEMENT BREAK ROOM (C/O) | 18.5
44773 | 44770 | 02-6015 | OG5 OG1 OG2 REMOVE WINDOW SILL FOR FAXA | 18
44773 | 44770 | 03-1400 | SG2 DRILL DOWEL IN BASEMENT FOUNDATION WALL | 11.5
44773 | 44770 | 99-4560 | SG3 MAINTAIN GROUNDS AROUND BLD. | 8.5
44773 | 44770 | 03-1800 | SG7 REBAR DELIVERY | 4.5
44773 | 44770 | 99-4560 | SG7 MAINTAIN AREA - PILE DEBRI TO REMOVE LATE WITH MACHINE | 5.5
44773 | 44770 | 03-1900 | SITE8 CHOP AT SHAFT (POUR CONCRETE RE-WORK) | 4
44773 | 44770 | 03-1900 | OG10 FILL/PATCH OPENINGS AT ROOF DECK (POUR CONCRETE NB) | 7
44773 | 44770 | 03-2100 | OG1 OG2 SG4 SG5 POUR FLOODWALLS AND TEMPORARY WALKWAY | 28
44773 | 44770 | 33-6010 | OG8 WELKIN NEED LULL | 1
44773 | 44770 | 04-6120 | FAXA NEED LULL (FAXA SUPT/BC) | 3
44773 | 44771 | 03-1100 | OG1 STRIP FLOODWALL | 4.5
44773 | 44771 | 03-1100 | OG1 CLEAN FORM AND AREA | 0.5
44773 | 44771 | 03-1100 | OG1 STRIP FLOODWALL | 4
44773 | 44771 | 03-1100 | OG2 CLEAN FORM AND AREA | 0.5
44773 | 44771 | 03-1100 | SG4 STRIP FLOODWALL | 7.5
44773 | 44771 | 03-1100 | SG4 CLEAN FORM AND AREA | 0.5
44773 | 44771 | 03-1100 | SG5 STRIP FLOODWALL | 7.5
44773 | 44771 | 03-1100 | SG5 NORTH SIDE STRIP FLOODWALL | 7.5
44773 | 44771 | 32-6000 | SG3 SAW CUT 2ND FLOOR SLAB | 16
44773 | 44771 | 02-6015 | OG1 OG2 OG3 OG4 REMOVE WINDOW SILLS | 16
44773 | 44771 | 02-3000 | CORE DRILL HOLES IN SG3 | 6.5
44773 | 44771 | 03-6000 | OG6 FRP | 10
44773 | 44771 | 99-4560 | OG10 REMOVE MONOCOAT FROM LEAVE OUT AREAS | 9
44773 | 44771 | 33-3100 | OG3 HAND DIG/EXPOSE EXISTING STEAM LINE ABATEMENT | 16
44773 | 44771 | 02-6015 | SG4 CLEAN FLOODWALL AREA/CLEAN 1ST FLOOR WINDOWS (BRICK DEMO) | 3.5
44773 | 44771 | 99-4560 | OG5 REMOVE CENTER PILED (SITE MAINT) | 1.5
44773 | 44771 | 99-4560 | OG9 REMOVE (4) 1 TON BAGS FROM 2ND FLOOR | 27.5
44773 | 44771 | 99-4560 | OG10 REMOVE CENTER PILED FROM 1ST FLOOR | 7
44773 | 44771 | 04-6120 | FAXA - LULL | 4
44773 | 44771 | 04-6130 | SG5 WELD PLATES FOR FAXA | 8
44773 | 44771 | 04-6130 | SG4 WELD PLATES FOR FAXA | 12.5
44773 | 44771 | 33-2600 | SGN INSTALL DRAINAGE PIPE AD-4 AD24 + AD24 - AD3 | 6.5
44773 | 44771 | 31-2200 | SGN BACKFILL INSTALLED PIPES | 5
44773 | 44771 | 33-2600 | SG4 INSTALL LIGHT POLE BASE | 5
44773 | 44771 | 33-2600 | SGN PATCH HOLES IN MANHOLES | 8
44773 | 44771 | 04-6120 | COVER GROUT PUMP - FAXA SUPPORT | 1
44773 | 44771 | 33-3100 | HANG DIG/EXPOSE PIPE FOR ABATEMENT | 4
44773 | 44771 | 04-6120 | JUMP | 1
44766 | 44760 | 03-6000 | SG3 INSTALL FRP AT 1ST FLOOR | 17.5
44766 | 44760 | 02-6010 | SG3 VITAL INSTALL SUMP PUMP - CLEAN PIT | 8
44766 | 44760 | 02-2300 | OG1 PUMP OUT AND CLEAN BASEMENT | 8
44766 | 44760 | 02-3000 | OG1 SAWCUT OUTSIDE RAMP (ELECTRIC P.O.E) | 12.5
44766 | 44760 | 02-3000 | OG5 DEMO FOR DUCTWORK PENETRATIONS | 10.5
44766 | 44760 | 02-6015 | OG6 REMOVE EXISTING LOUVERS BASEMENT WINDOWS/CLEAN DEBRIS FROM BASEMENT "LOUVERS" | 17
44766 | 44760 | 03-2100 | OG6 DRILL AND INSTALL ANCHORS FOR EQUIPMENT PAD AND FORM | 4.5
44766 | 44760 | 32-6000 | SITE8 SAWCUT CONTROL JOINTS IN SLAB | 7
44766 | 44760 | 07-6110 | OG9 CLEAN AREA FOR NAVILLUS - STORAGE PANELS | 8.5
44766 | 44760 | 31-1100 | OG5 BACKFILL/COMPACT BEHIND FLOODWALL | 5.5
44766 | 44760 | 99-4560 | SG6 SG7 LOAD OUT CONCRETE DEBRIS - 1 LIVE LOAD CARDELLA | 3.5
44766 | 44760 | 07-6220 | OG10 CLEAN AND PREP ROOF | 9.5
44766 | 44760 | 99-4560 | OG8 CLEAN 1ST FLOOR AND 2ND FLOOR | 11.5
44766 | 44760 | 33-6010 | OG8 WELKIN - LULL NEEDED TO LIFT PIPES TO 2ND FLOOR | 2
44766 | 44760 | 04-6120 | OG8 OG10 SG6 FAXA NEED LULL | 3
44766 | 44760 | 33-2400 | JUMP BACKHOE | 1
44766 | 44760 | 02-6050 | CHOP AND REMOVE RAMP AT SG1 ENTRANCE (PAVEMENT DEMO SG1) | 4
44766 | 44760 | 02-6050 | CUT AND REMOVE RAILINGS AT SG1 (PAVEMENT DEMO SG1) | 10
44766 | 44760 | 02-6050 | LOAD OUT CONCRETE INTO CARDELLA CONTAINER AT SG1 (PAVEMENT DEMO SG1) | 11.5
44766 | 44760 | 31-1000 | SG1 HAND DIG TO EXPOSE GAS LINES (TEST PIT FOR GAS PIPE) | 16
44766 | 44760 | 99-4560 | CLOSE ALL GATES | 0.5
44766 | 44760 | 03-1000 | SITE8 FORM SHAFT AND STRIP WALLS | 56
44766 | 44760 | 99-4560 | OG9 OG10 OG8 HANDRAILS | 16
44766 | 44760 | 99-7210 | PTO | 16
44766 | 44761 | 02-1000 | SG7 SETUP DUSTBOSS NEAR SG3 | 2
44766 | 44761 | 03-1400 | OG6 DRILL/DOWEL FOR FOUNDATION WALL IN BASEMENT | 10.5
44766 | 44761 | 02-6070 | OG6 REMOVE OLD ELECTRIC CONDUIT IN BASEMENT (DEMO FOR ELECTRICAL) | 18.5
44766 | 44761 | 02-6010 | SG2 PATCH SUMP PIT IN BASEMENT (DEMO SUMP PUMP) | 3
44766 | 44761 | 99-4560 | OG8 CLEAN 1ST FLOOR | 3.5
44766 | 44761 | 99-4560 | OG9 CLEAN 2ND FLOOR | 3.5
44766 | 44761 | 99-4560 | SG3 CLEAN UP AREA BY WELKIN YARD (SITE MAINT + WINDOW DEBRIS) | 13
44766 | 44761 | 99-4560 | SG6 CLEAN ROOF | 3.5
44766 | 44761 | 04-6120 | FAXA NEED LULL (FAXA CODE) | 7
44766 | 44761 | 07-6110 | NAVILLUS NEED OPERATOR FOR LULL (NAV CODE) | 8
44766 | 44761 | 03-1400 | SG3 DRILL/DOWEL FOR FOUNDATION WALL | 8
44766 | 44761 | 33-2400 | PUMPS | 1
44766 | 44761 | 33-2600 | SGN MOVE MATERIAL AND ORGANIZE AREA | 8.5
44766 | 44761 | 33-3100 | OG5 HAND DIG FOR WELKIN FOR STEAM LINE | 4
44766 | 44761 | 04-6130 | SG5 WELD PLATES FOR WELKIN (ANGLE FOR FAXA) | 14
44766 | 44761 | 33-2600 | SGN DIG AND INSTALL TWO LIGHT POLE BASES | 12
44766 | 44761 | 33-1000 | OG5 MOVE BRACES AND RE-BRACE WATER LINES FOR WELKIN | 2
44766 | 44761 | 33-2400 | JUMPS | 1
44766 | 44761 | 31-1000 | SG1 HAND DIG AND EXPOSE UTILITIES AT FRONT ENTRANCE (TEST PIT | 12.5
44766 | 44761 | 02-6010 | SG2 CLEAN 2 SUMP PITS FOR VITAL (DEMO SUMP PUMPS) | 18
44766 | 44761 | 32-6000 | OG1 SAWCUT OUTSIDE RAMP WALL (SAWCUT) | 5
44766 | 44761 | 03-6000 | SG3 INSTALL FRP AT 1ST FLOOR | 16
44766 | 44761 | 33-1100 | SG1 TERMINATE AND DEMOLISH UTILITIES | 5
44766 | 44761 | 99-4560 | CLOSE ALL GATES | 0.5
44766 | 44761 | 03-1000 | SITE8 STRIP SLAB (FORM WORK) | 10
44766 | 44761 | 03-1000 | SITE8 CLOSE WALL (FORM WORK) | 42
44766 | 44761 | 03-1900 | BUILD SCAFFOLD TO REPAIR COLUMNS | 4
44766 | 44761 | 03-1000 | SITE8 CLEAN SITE (FORM WORK) | 11
44766 | 44761 | 03-1300 | COVER OPENINGS (ANCHOR BOLTS BRACKETS - ANCHOR BOLT CODE) | 5.5
44766 | 44761 | 99-7210 | PTO | 8
44766 | 44762 | 03-1000 | OG8 CHOP COLUMN (POUR CONC 1/2, FORMWORK 1/2) | 5
44766 | 44762 | 32-6510 | SG1 INSTALL WHITE MESH ON FENCE | 17
44766 | 44762 | 03-1400 | SG3 DRILL AND DOWEL FOUNDATION WALL | 24
44766 | 44762 | 02-6070 | OG6 CLEAN ELECTRIC CONDUIT PIPE FROM BASEMENT (UTILITY REMOVAL/DEMO) | 10
44766 | 44762 | 07-6110 | NAVILLUS - OPERATOR FOR LULL (NAV B/C) | 8
44766 | 44762 | 04-6120 | SG6 OG8 OG10 FAXA - LULL NEEDED | 4
44766 | 44762 | 32-6000 | OG1 REMOVE CONCRETE BLOCK AFTER SAWCUT | 1.5
44766 | 44762 | 99-4560 | OG10 CLEAN GARBAGE FROM ROOF AND 1ST FLOOR - 1 TON BAG | 2
44766 | 44762 | 03-2100 | PICK UP REPAIR TOOL/DROP ANOTHER ONE TO FIX - CONCRETE VIBRATORS (POUR CONC) | 1
44766 | 44762 | 03-6000 | SG3 INSTALL FRP AT BASEMENT | 1
44766 | 44762 | 33-2400 | PUMPS | 2
44766 | 44762 | 04-6130 | SG5 WELD PLATES FOR FAXA (FAXA SUPPORT) | 16
44766 | 44762 | 33-2600 | SGN INSTALL 3 LIGHT POLE BASES (LIGHT POLE INSTALL) | 11.5
44766 | 44762 | 33-2600 | SGN DUMP 3 LOADS OF FILL (1 SAND & 2 CLEAN FILL) WITH HNS (LIGHT POLE INSTALL) | 3
44766 | 44762 | 33-2600 | OG6 LOAD 10 LIGHT POLE BASES AND OFFLOAD AT SGN WITH HNS (LIGHT POLE INSTALL) | 6
44766 | 44762 | 02-2100 | SG5 DIG AND EXPLORE TO FIND STEAM LINES | 3
44766 | 44762 | 03-1900 | COVER COMPRESSOR - OG8 CHOP AT COLUMN | 1
44766 | 44762 | 03-6000 | SG3 INSTALL FRP 1ST FLOOR AT SG3 | 16
44766 | 44762 | 02-6010 | SG2 FINISH CLEANING AND REMOVING MUCK OUT OF PUMP PIT FOR VITAL (SUMP PUMP REMOVAL) | 6.5
44766 | 44762 | 02-2100 | SG5 HAND DIG TO EXPOSE EXISTING STEAM PIPE (RETAINING WALL DEMO) | 14
44766 | 44762 | 32-6000 | OG1 SAWCUT BELOW THE RAMP FOR POE | 12
44766 | 44762 | 99-4560 | OG10 CLEAN ROOF AND REMOVE GARBAGE FROM ROOF AND CLEAN AROUND BUILDING | 8
44766 | 44762 | 99-4560 | CLOSE ALL GATES | 0.5
44766 | 44762 | 03-1000 | SITE8 FORM SHAFT (FORM WORK) | 42.5
44766 | 44762 | 03-1900 | CLEAN OUT ALL ANCHOR BOLTS (POUR CONCRETE) | 2
44766 | 44762 | 03-1000 | SITE8 CLEAN (WOOD & DEBRIS) FORM WORK | 4
44766 | 44762 | 03-1900 | SITE8 CHIP KEYWAY ON SOUTH SIDE (POUR CONCRETE) | 2
44766 | 44762 | 03-2300 | OG1 BULKHEAD ON DUCT BANK (DUCT BANK CODE) | 8
44766 | 44762 | 03-1900 | START INSTALLING BRIDGE BRACKET AT SG7N + WEST SIDE (POUR CONCRETE) | 8
44766 | 44762 | 03-1900 | SITE8 BUILD POUR DECK (POUR CONCRETE) | 6
44766 | 44763 | 03-1900 | SG7 CHOP SHAFT WALLS | 23
44766 | 44763 | 99-4560 | SG4 CLEAN 2ND FLOOR APARTMENT | 7.5
44766 | 44763 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR | 6.5
44766 | 44763 | 99-4560 | OG9 CLEAN 1ST AND 2ND FLOOR | 5.5
44766 | 44763 | 03-1900 | SITE8 POUR SHAFT | 23
44766 | 44763 | 04-6120 | OG10 FAXA - LULL NEEDED | 3
44766 | 44763 | 02-1900 | SG5 DEMO WALKWAY | 5
44766 | 44763 | 33-6010 | WELKIN - LULL NEEDED | 2
44766 | 44763 | 33-6010 | OG5 SET STEAM PIPE FOR WELKIN (WM SUPT) | 4.5
44766 | 44763 | 04-6130 | SG5 WELD PLATES FOR FAXA | 2
44766 | 44763 | 04-6130 | SG5 PREP ENTIRE BUILDING FOR WELDING | 14
44766 | 44763 | 33-2600 | SG5 INSTALL AD.20 AND LIGHT POLE BASE | 8
44766 | 44763 | 31-2000 | SG5 HAND DIG AND EXPLORE TO FIND GAS LINE | 20.5
44766 | 44763 | 32-6520 | SG5 REMOVE FENCE | 4.5
44766 | 44763 | 02-2100 | SG5 DEMO CURB | 12
44766 | 44763 | 33-3100 | OG1 HAND DIG BELOW THE RAMP FOR POE (EXCAVATION OF OG1 DUCT BANK) | 16
44766 | 44763 | 03-6000 | OG6 INSTALL FRP AT 2ND FLOOR | 16
44766 | 44763 | 33-2400 | JUMP | 1
44766 | 44763 | 99-4560 | LOCK GATES | 0.5
44766 | 44763 | 03-1000 | SITE8 FINISH SHAFT WALL | 21.5
44766 | 44763 | 03-1900 | SG7 INSTALLMENT OF BRIDGE BRACKETS | 35
44766 | 44764 | 03-2300 | OG1 POUR DUCT BANK - REMOVE AND INSTALL FENCE FOR BACKUP CONCRETE TRUCKS | 12
44766 | 44764 | 03-1400 | OG6 DRILL AND DOWEL FOUNDATION WALL | 10
44766 | 44764 | 03-1000 | OG8 CHIP COLUMN (5HR TO FORMWORK/5 HR TO POUR CONC) | 10
44766 | 44764 | 31-1000 | SG5 GRADE AREA FOR ENTRANCE SLAB (FLOOD GATE EXCAVATION) | 4
44766 | 44764 | 03-6000 | OG6 INSTALL FRP 2ND FLOOR | 4.5
44766 | 44764 | 07-6110 | NAVILLUS NEED OPERATOR (B/C) | 8
44766 | 44764 | 04-6130 | SG4 WELD PLATES FOR FAXA (FAXA SUPPORT) | 8
44766 | 44764 | 04-6130 | SG5 CLEAN AND PREP AREAS FOR WELDING (FAXA SUPPORT) | 8
44766 | 44764 | 33-2600 | SGN INSTALL AD-3 AND ADJUST LIGHT POLE BASES | 11.5
44766 | 44764 | 33-2500 | SGN DIG AND TRENCH FOR DRAINAGE PIPE (PIPE INSTALL CODE, DRAINAGE) | 8
44766 | 44764 | 33-2500 | SGN PREP EXISTING MANHOLE FOR PIPE INSTALLATION (PIPE INSTALL CODE, DRAINAGE) | 8
44766 | 44764 | 33-2500 | SGN INSTALL DRAINAGE PIPE (AD-20 TO EXISTING + AD-4 AD-9) | 4.5
44766 | 44764 | 33-2400 | JUMP | 1
44766 | 44764 | 02-3000 | OG1 SAW CUT/CHOP POE | 1
44766 | 44764 | 33-2400 | COMPRESSOR | 1
44766 | 44764 | 03-6000 | OG6 INSTALL FRP ON 2ND FLOOR | 16
44766 | 44764 | 02-3000 | OG5 CHOP AND CLEAN 3 HOLES FOR THEMIS | 4
44766 | 44764 | 02-6025 | OG3 OG1 DEMO BRICK FOR VITAL TO EXTEND PIPE OUT | 4
44766 | 44764 | 02-2100 | SG5 GRADE AREAFOR ENTRANCE SLAB AND CHOP/REMOVE CURB FOR JMC | 16.5
44766 | 44764 | 03-1000 | SITE8 STACK PANELS, CLEAN AREA FOR CRANE (FORM LOAD OUT) | 8
44766 | 44764 | 02-2100 | SG5 LIVE LOAD CORDELLA TO REMOVE CONCRETE AND EXTRA DIRT (CURB REMOVAL) | 16
44766 | 44764 | 04-6120 | OPERATE LULL FOR FAXA (FAXA B/C) | 4
44766 | 44764 | 03-1900 | COVER CONCRETE PUMP (POUR CONCRETE) | 1
44766 | 44764 | 99-4560 | SG6 CLEAN (SITE MAINT) | 8
44766 | 44764 | 03-1000 | SITE STRIP SHAFT | 52
44766 | 44764 | 32-6520 | OG8 ADJUST AND MAINTAIN CABLES ON 2ND FLOOR (FENCE INSTALL) | 8.5
44766 | 44764 | 00-0036 | ADJUSTMENTOF DOORS AND WINDOWS IN APARTMENT 2E (APT RENO) | 3
44766 | 44764 | 03-1000 | OG10 FORM AND PATCH CONDUIT PENETRATIONS ON 2ND FLOOR | 9
44766 | 44764 | 99-4560 | LOCK GATES | 0.5
44759 | 44753 | 02-6060 | SG3 INSTALL FRP AT 2ND FL | 25
44759 | 44753 | 05-6110 | NAVILLUS - LULL NEEDED | 8.5
44759 | 44753 | 03-1900 | OG8 POUR STAIRS | 7
44759 | 44753 | 99-4560 | HOUSEKEEPING ALL AREAS | 25
44759 | 44753 | 99-4560 | VITAL - LULL NEEDED | 2.5
44759 | 44753 | 04-6120 | FAXA - LULL NEEDED | 6.5
44759 | 44753 | 03-1400 | OG6 DRILL/INSTALL DOWELS FOR WALL REINFORECEMENT | 9
44759 | 44753 | 99-4000 | SG1 BLOCK PARKING SPOTS (FOR CRANE) | 4
44759 | 44753 | 99-4560 | SITE8/SGN SWAPOUT 30 YARD CONTAINER "CARDELLA" | 3
44759 | 44753 | 03-1000 | SG7 LOAD OUT FORMS (FORMWORK) | 6
44759 | 44753 | 33-2400 | PUMPS | 1
44759 | 44753 | 31-1000 | SG1 HAND DIG TO EXPOSE UTILITIES (MASONRY SHELF EXCVATION) | 24.5
44759 | 44753 | 99-4560 | ENTIRE SITE - ENSURE ALL GATES AND LOCKED | 1
44759 | 44753 | 03-1000 | SG7 BAND FORMS (FORMWORK) | 30
44759 | 44753 | 03-1000 | SG7 LOAD OUT TRUCK (FORMWORK) | 12.5
44759 | 44753 | 03-1000 | OG8 CONCRETE STAIRS (FORMWORK) | 18
44759 | 44753 | 03-1000 | OG8 MOVE FORMS TO SITE8 (FORMWORK) | 26
44759 | 44753 | 03-1500 | OG8 STRIP WINDOWS | 21
44759 | 44753 | 03-1400 | OG6 BUILD PLATFORM IN BASEMENT FOR SCISSOR LIFT | 27
44759 | 44753 | 32-6510 | SG6 SAFETY (NETTING) | 3
44759 | 44753 | 99-4560 | SG7 SAFETY (REBAR CAPS) | 2
44759 | 44753 | 99-4560 | OG8 SAFETY (REBAR CAPS) | 3
44759 | 44753 | 32-6510 | OG8 SAFETY (NETTING) | 2.5
44759 | 44753 | 99-7210 | PTO | 8
44759 | 44754 | 31-2200 | SG7 BACKFILL AROUND BLD AND ELECTRICAL TRENCH/PREP AREA FOR CRANE/BLOCK PARKING SPOTS | 18.5
44759 | 44754 | 03-1400 | OG6 DRILL/INSTALL DOWELS FOR WALL REINFORCEMENT | 11.5
44759 | 44754 | 03-1400 | OG6 DRILL/INSTALL DOWELS FOR WINDOWS IN BASEMENT | 7
44759 | 44754 | 03-1800 | OG8 CLEAN AREA - REMOVE SCRAP STEEL AND DEBRIS (SITE MAINTENANCE) | 20
44759 | 44754 | 99-4560 | SG7 CLEAN DEBRIS | 2.5
44759 | 44754 | 04-6120 | FAXA LULL NEEDED | 6.5
44759 | 44754 | 33-6010 | WELKIN - LULL NEEDED | 2.5
44759 | 44754 | 33-2400 | PUMPS | 1
44759 | 44754 | 31-1820 | SG7 BURN SHEETING WALL FOR WELKIN | 9.5
44759 | 44754 | 33-3100 | SG2 HAND DIG TO EXPOSE UTILITIES FOR MASONRY SHELF | 15
44759 | 44754 | 99-4560 | ENTIRE SITE - ENSURE ALL GATES ARE LOCKED | 0.5
44759 | 44754 | 03-1000 | SG7 PREP FOR CLEANER (FORMWORK) | 38
44759 | 44754 | 03-2100 | OG6 PADS IN BASEMENT (FOR WELKIN EQUIPMEMT) | 18
44759 | 44754 | 33-6010 | SG6 REMOVE SCAFFOLD (VITAL AND WELKIN SUPPORT) | 8
44759 | 44754 | 33-6010 | OG9 SET UP SCAFFOLD (VITAL AND WELKIN SUPPORT) | 8.5
44759 | 44754 | 02-6010 | SG1 PREP AND PATCH AREA FOR THE TEST PITS IN BASEMENT FOR VITAL (CLEAN PITS FOR VITAL) | 12
44759 | 44754 | 02-6065 | SG3 DEMO FOR THEMIS DUCTWORK IN CELLAR AND PUMP WATER OUT OF TANK ROOM | 18.5
44759 | 44754 | 02-3000 | SAWCUT HOLES IN OIL TANK ROOM FOR THEMIS | 16
44759 | 44754 | 03-1900 | OG8 PATCH TIE HOLES AROUND THE SHAFT AT OG8 - POUR CONCRETE NEW BUILDINGS | 10
44759 | 44754 | 99-4560 | OG10 CLEAN AND REMOVE DEBRI | 24
44759 | 44754 | 03-6000 | SG3 INSTALL FRP AT 1ST FLOOR | 16
44759 | 44754 | 99-7210 | PTO | 8
44759 | 44755 | 02-6060 | SG3 INSTALL FRP ON 1ST FLOOR | 16
44759 | 44755 | 02-6060 | SG6 PATCH AROUND SLAB PENETRATIONS AT 2ND FL AND ROOF (CONCRETE NEW BUILDING) | 16
44759 | 44755 | 02-6010 | OG5 CLEAN PIT AFTER PUMP REMOVAL SG3 CLEAN PIT IN TANK ROOM OG3 PUMP WATER IN BASEMENT | 20
44759 | 44755 | 32-6000 | SAWCUT HOLES IN OIL TANK ROOM (PUMP REMOVAL FOR VITAL) | 18.5
44759 | 44755 | 99-4560 | SG6 CEAN AND REMOVE DEBRI (PUMP REMOVAL FOR VITAL) | 16
44759 | 44755 | 02-6010 | OG4 CLEAN PIT AND PUMP OUT WATER IN BASEMENT (PUMP REMOVAL FOR VITAL) | 10
44759 | 44755 | 33-6010 | WELKIN - MACHINE NEEDED TO MOVE PIPE IN TRENCH OG5 TO OG6 | 2.5
44759 | 44755 | 07-1100 | SITE - FIX VAPOR BARRIER ON SLAB | 1
44759 | 44755 | 03-1900 | SG7 PATCH TIE HOLES AROUND THE SHAFT (CONCRETE NEW BUILDING) | 1
44759 | 44755 | 03-1800 | TONAGE MOVE REBAR FROM SG7 TO SITE8 | 7
44759 | 44755 | 03-1900 | OG9 PATCH TIE HOLES AROUND SHAFT - BUSH HAMMER AND PATCH AREA FOR BRICKWORK (CONCRETE NEW BUILDING) | 25
44759 | 44755 | 05-6030 | MOVE CRANEMATS FROM OG8 TO SG7 | 4
44759 | 44755 | 31-1300 | DURANTE PICK UP 1140 TRACK MACHINE FROM SG7 (EXCAVATION) | 3
44759 | 44755 | 07-6220 | SG6 LULL NEEDED FOR ROOFER - PUT MATERIAL ON ROOF | 1
44759 | 44755 | 04-6120 | FAXA - LULL NEEDED | 4
44759 | 44755 | 03-1900 | SITE8 BACKFILL AND PREP AREA FOR SLAB POUR (SLAB POUR) | 8
44759 | 44755 | 99-4560 | SG7 SG6 CLEAN DEBRIS - HOUSEKEEPING | 8
44759 | 44755 | 03-1300 | SG7 PREP ANCHOR BOLTS FOR STEEL INSTALLATION | 14
44759 | 44755 | 33-2400 | PUMPS | 2
44759 | 44755 | 03-1000 | SITE8 FORM AND BRACE INSIDE PLUMBING SHAFT | 26
44759 | 44755 | 03-1300 | SG7 PREP FOR IRONWORKS | 28
44759 | 44755 | 03-1900 | SG6 ROOF PENETRATIONS | 10
44759 | 44755 | 03-1900 | OG9 SCAFFOLD ON OUTSIDE PLUMBINGS SHAFT | 5
44759 | 44755 | 02-3000 | OG10 CONDUIT PENETRATIONS | 5.5
44759 | 44755 | 33-6010 | OG6 MOVE PIPE FOR WELKIN | 6.5
44759 | 44755 | 31-1000 | OG6 HARD DIG FOR MASONRY SHELF | 9
44759 | 44755 | 33-3100 | OG6 HAND DIG TO EXPOSE UNTILITIES | 6
44759 | 44755 | 02-6015 | OG6 DEMO LOUVERS | 3
44759 | 44755 | 99-7210 | PTO | 8
44759 | 44756 | 02-6060 | SG3 INSTALL FRP | 18
44759 | 44756 | 07-6220 | SG6 PREP AREA FOR ROOFING | 5
44759 | 44756 | 03-1900 | OG8 PATCH LEAVE OUT ON 2ND FLOOR/PATCH TIE HOLES ON TANK ROOM AND SHAFT (NEW BUILDING CONCRETE | 31
44759 | 44756 | 03-1900 | OG9 PATCH TIE HOLES AROUND THE SHAFT/BUSH HAMMER AND PATCH SHAFT FOR BRICKWORK | 4.5
44759 | 44756 | 99-4560 | OG10 MAINTAIN HOUSEKEEPING - LOAD OUT DEBRI BAGS - 2ND FLOOR | 20
44759 | 44756 | 04-6120 | FAXA - LULL NEEDED | 3.5
44759 | 44756 | 03-1800 | SITE8 OG6 SGN OGWEST REBAR DELIVERY | 43.5
44759 | 44756 | 05-6030 | SG7 CRANE BACKUP | 2
44759 | 44756 | 03-1900 | PICK UP SCREED MACHINE FOR SITE8 POUR | 1
44759 | 44756 | 33-2400 | PUMPS | 1
44759 | 44756 | 33-3100 | OG1 TRENCH FOR ELECTRICAL CONDUIT | 28
44759 | 44756 | 31-2200 | SG7 BACKFILL AND SETUP CRANE (BACKFILL TRENCH) | 8
44759 | 44756 | 31-2200 | OG3 DUMP THREE LOADS OF DIRT FROM OG1 | 4
44759 | 44756 | 99-4560 | ENTIRE SITE - ENSURE ALL GATES ARE LOCKED | 1
44759 | 44756 | 33-2400 | PUMPS | 1
44759 | 44756 | 03-1000 | SITE8 SLAB EDGE + BRACING | 52.5
44759 | 44756 | 03-1000 | OG10 CONDUIT PENETRATION | 20
44759 | 44756 | 99-7210 | PTO | 16
44759 | 44757 | 03-6000 | SG3 INSTALL FRP AT 1ST FLOOR | 25
44759 | 44757 | 00-0016 | SG4 SG5 DEMO BRICK FOR FAXA FOR LINTEL INSTALLATION | 16
44759 | 44757 | 31-1100 | OG5 BACKFILL FLOODWALL AND COMPACT FOR INSPECTION | 9.5
44759 | 44757 | 03-1900 | SITE8 BACKFILL FORMS - PREP FOR POUR | 5
44759 | 44757 | 03-1900 | SITE8 POUR SLAB | 43
44759 | 44757 | 03-1300 | SG7 GUYTEC - NEEDED LABOR FOR STEEL ERECTION | 6
44759 | 44757 | 03-2100 | OG6 DRILL AND INSTALL ANCHORS FOR EQUIPMENT PADS - POUR CONCRETE | 9.5
44759 | 44757 | 32-6520 | SITE8 INSTALL FENCE AND WET SLAB AFTER POUR | 3
44759 | 44757 | 33-6010 | WELKIN - LULL NEEDED TO MOVE SANDBAGS FROM YARD TO TRENCH | 1.5
44759 | 44757 | 04-6120 | FAXA - LULL NEEDED SG6 OG8 OG9 OG10 | 7.5
44759 | 44757 | 99-4560 | OG1 CLEAN UP AROUND BLD. | 4
44759 | 44757 | 99-4560 | SG6 OG8 OG9 CLEAN UP | 16
44759 | 44757 | 03-1900 | RETURN SCREED MACHINE <POUR SLAB SITE8> | 1
44759 | 44757 | 03-1900 | TAKE CONCRETE VIBRATOR MOTION FOR FIX <POUR SLAB SITE8> | 0.5
44759 | 44757 | 03-1900 | SITE8 PREP FOR SLAB POUR | 6.5
44759 | 44757 | 02-3000 | OG10 CONDUIT PENETRATIONS | 19
44759 | 44757 | 02-3000 | OG9 CONDUIT PENETRATIONS | 31
44759 | 44757 | 33-3100 | OG1 FINISH DIGGING ELECTRICAL CONDUIT TRENCH <EXCAVATION ELECTRIC> | 20.5
44759 | 44757 | 33-3100 | OG1 ASSEMBLE TRENCH BOXES <EXCAVATION ELECTRIC> | 6
44759 | 44757 | 33-3100 | OG1 INSTALL TRENCH BOXES <EXCAVATION ELECTRIC> | 8
44759 | 44757 | 33-3100 | SITE8 LOAD CONDUIT PIPE ON TO RACK TRUCK FOR FSE <EXCAVATION ELECTRIC> | 1.5
44759 | 44757 | 99-4560 | ENTIRE SITE - ENSURE ALL GATES ARE LOCKED - SITE MAINTENANCE | 1
44759 | 44757 | 31-1100 | OG5 DUMP TWO LOADS OF DIRT FOR BACKFILL (HNS TRUCK) BACKFILL FLOODWALL | 6
44759 | 44757 | 99-7210 | PTO | 16
44752 | 44746 | 99-7200 | HOLIDAY PAY | 64
44752 | 44747 | 31-2200 | SITE8 BACKFILL & COMPACT AM INSPECTION | 28.5
44752 | 44747 | 31-1500 | INSTALL STONE AND COMPACT PM INSPECTION | 12
44752 | 44747 | 32-6520 | SITE8 REMOVE BRIDGE - FLAGGER AT THE DOOR | 8
44752 | 44747 | 32-6520 | SITE8 REMOVE FENCE AND REINSTALL AFTER REMOVE BRIDGE | 4
44752 | 44747 | 04-6120 | OG9 OG10 FAXA NEEDS LULL | 6
44752 | 44747 | 07-6110 | NAVILLUS NEEDS LULL | 2
44752 | 44747 | 33-3100 | OG1 VACUUM EXCAVATE FOR CONDUIT RUN | 9.5
44752 | 44747 | 33-3100 | EXCAVATION TRAINING | 4
44752 | 44747 | 03-2100 | SG1 PATCH AROUND LOUVERS | 10
44752 | 44747 | 07-6220 | SG6 CLEAN ROOF FOR ROOFERS | 10
44752 | 44747 | 99-4560 | SG6 CLEAN 1ST AND WEST SIDE OF BUILDING | 16
44752 | 44747 | 99-4560 | OG9 CLEAN DEBRI 1ST AND 2ND FLOOR | 8
44752 | 44747 | 03-6000 | SG3 FRP INSTALL | 16.5
44752 | 44747 | 02-2300 | OG5 FINISHING CLEANING AT BASEMENT | 14
44752 | 44747 | 02-3000 | OG4 CUT PENETRATIONS | 14
44752 | 44747 | 03-1900 | OG9 PATCH HOLES AT ROOF | 16
44752 | 44747 | 03-1000 | SG7 FORM PLUMBING SHAFT | 64
44752 | 44747 | 03-1300 | SG7 SET ANCHOR BOLTS | 7
44752 | 44747 | 03-1000 | SITE8 FORM OUTSIDE OF PLUMBING PITS | 25
44752 | 44747 | 32-6520 | SITE8 REMOVE WALKWAY BRIDGE | 8
44752 | 44747 | 32-6520 | SITE8 BUILD TEMP WALKWAY | 1
44752 | 44747 | 99-4560 | SG6 TAKEOUT + REDO WORKINF PLATFORM | 14
44752 | 44747 | 03-1000 | OG8 FINISH SCAFFOLDING PLUMBING | 6
44752 | 44747 | 03-1900 | OG9 PATCH HOLE IN ROOF | 6.5
44752 | 44747 | 99-4560 | OG5 COVER PENETRATIONS ON 1ST & 2ND FLOOR (SITE MAINT) | 5
44752 | 44747 | 99-4560 | LOCK GATES | 0.5
44752 | 44747 | 31-2000 | OG1 VAC TRUCK - VAC OUT CONDUIT TRENCH AND EXPOSE GAS LINE TEST PIT | 17.5
44752 | 44747 | 33-3100 | OG1 BEGIN TO TRANSPORT TRENCH BOXES FROM OG6 OG1 EXCAVATION | 4
44752 | 44747 | 33-2600 | OG6 OFFLOAD 1 TRAILER OF PRECAST MANHOLE AND STREET LIGHT BASES | 4
44752 | 44747 | 33-3100 | OFFICE - EXCAVATION TRAINING | 2
44752 | 44747 | 26-6030 | SITE8 MOVE MATERIAL TO ACCESS ELECTRICIANS BOXES | 5
44752 | 44748 | 03-1900 | SG7 POUR SHAFT WALLS/CLEAN AREA AFTER POUR (40 YRDS) | 38
44752 | 44748 | 07-1100 | SITE8 INSTALL FOAM AND VAPOR BARRIER | 27
44752 | 44748 | 99-4560 | SG4 CLEAN AREA FOR CONCRETE POUR ON FRIDAY FOR JMC | 4
44752 | 44748 | 33-2500 | SITE8 PIPE DELIVERY | 4.5
44752 | 44748 | 07-6110 | NAVILLUS NEED LULL | 7.5
44752 | 44748 | 99-7200 | HOLIDAY PAY | 3
44752 | 44748 | 33-3100 | COVER COMPRESSION, OG1 EXPOSE UTILITIES | 4
44752 | 44748 | 99-4560 | OG8 AND SITE8 CLEANING - SG4 SG5 RAMP | 20.5
44752 | 44748 | 03-6000 | SG3 FRP INSTALL OG4 FRP | 16
44752 | 44748 | 02-6065 | SG3 DEMO 1ST FLOOR DUCTS | 20
44752 | 44748 | 32-6000 | OG4 SAWCUT FOR FSE COMPACTOR ROOM (2 HOLES) | 20
44752 | 44748 | 02-3000 | OG5 CORE 2ND FLOOR PENETRATIONS FOR FSE | 4
44752 | 44748 | 03-1000 | SITE8 FORM PLUMBING SHAFT | 30
44752 | 44748 | 03-1000 | SG7 FINISH FORMING SHAFT | 38
44752 | 44748 | 03-1300 | SG7 SET ANCHOR BOLTS | 8
44752 | 44748 | 03-1000 | OG8 FORM STAIRS | 16
44752 | 44748 | 03-2300 | SG7 DUCT BANK | 37
44752 | 44748 | 99-4560 | OG10 HANDRAIL AT TOP OF STAIRS | 7
44752 | 44748 | 99-4560 | OG9 CABLE + NETTING | 5
44752 | 44748 | 99-4560 | OG8 TIE BOARDS | 4
44752 | 44748 | 33-6010 | WELKIN YARD - MOVE SANDBAGS TO OG5 | 2
44752 | 44748 | 33-2500 | SITE8 OGGLOAD TWO TRAILERS OF STEEL DRAINAGE PIPE | 14.5
44752 | 44748 | 33-6010 | SG7 MOVE AND SET STEAM PIPE FOR WELKIN | 7
44752 | 44748 | 99-4560 | SITE8 CLEAN GARBAGE | 1
44752 | 44748 | 33-3100 | OG1 VAC TRUCK FOR ELECTRICAL CONDUIT | 20.5
44752 | 44748 | 99-4560 | OG1 CLEAN UP AND REMOVE GARBAGE | 12
44752 | 44749 | 03-1400 | SG4 SG5 DRILL AND DOWEL FOR REBAR INSTALL | 19
44752 | 44749 | 31-2200 | SG2 BACKFILL BEHIND STAYFORM/PREP FOR POUR DUCTBANK | 5
44752 | 44749 | 03-1800 | MOVE REBAR FOR TONAGE FROM OG8 OG9 OG10 TO SG7 AND SITE8 | 33
44752 | 44749 | 03-1000 | SG7 STRIP SHAFT - SUPPORTED BY 322 | 6.5
44752 | 44749 | 04-6120 | OG8 OG9 OG10 AND SG5 FAXA NEEDS LULL | 7.5
44752 | 44749 | 99-4560 | OG10 VITAL NEEDS LULL | 1.5
44752 | 44749 | 33-2400 | PUMPS | 2
44752 | 44749 | 03-6000 | SG3 FRP INSTALL AT 2ND FLOOR | 24
44752 | 44749 | 33-6010 | SG3 FINISHING PATCH LOUVERS | 20
44752 | 44749 | 03-1400 | OG6 DRILL DOWELS IN BASEMENT | 18
44752 | 44749 | 99-4560 | CLEAN AROUND OG8 - 1ST AND 2ND FLOOR | 17
44752 | 44749 | 02-6060 | SG3 DEMO/PATCH 2ND FLOOR EXTERIOR WALL | 9.5
44752 | 44749 | 32-6000 | OG8 SAW CUT WALL AND CORE | 19
44752 | 44749 | 02-6015 | SG5 REMOVE WINDOWS FRAMES | 5
44752 | 44749 | 02-2300 | SG3 CLEAN BASEMENT | 9.5
44752 | 44749 | 31-2000 | OG1 DIG TRENCH BY HAND | 16
44752 | 44749 | 03-1000 | SG7 STRIP PLUMBING SHAFT | 83.5
44752 | 44749 | 03-2300 | SG7 DUCTBANK | 9
44752 | 44749 | 07-1100 | SITE8 STYROFOAM WALL | 25
44752 | 44749 | 03-1000 | OG8 STAIRS | 19
44752 | 44749 | 99-4560 | SITE MAINT | 16
44752 | 44750 | 03-1000 | SG7 STRIP PLUMBING SHAFT | 68
44752 | 44750 | 03-2300 | SG7 DUCTBANK | 8
44752 | 44750 | 07-1100 | SITE8 STYROFOAM WALL | 8
44752 | 44750 | 03-1000 | OG8 STAIRS | 4.5
44752 | 44750 | 99-4560 | SITE MAINT | 16
44752 | 44750 | 03-1000 | SG7 BAND FORMS FOR LOADOUT | 16
44752 | 44750 | 03-1000 | SITE8 FINISH DECK WORK | 24
44752 | 44750 | 03-2300 | SG2 POUR DUCTBANK | 6
44752 | 44750 | 03-1400 | OG6 DRILL/INSTALL DOWELS FOR WALL REINFORECEMENT | 16
44752 | 44750 | 99-4560 | OG2 CLEAN GARBAGE AFTER FSE DELIVERY | 3
44752 | 44750 | 99-4560 | SITE8 SG7 CLEAN AREA | 14
44752 | 44750 | 32-6220 | SG5 JMC NEED MACHINE FOR POUR | 3
44752 | 44750 | 03-1000 | SG7 STRIP SHAFT NEED MACHINE | 6.5
44752 | 44750 | 04-6120 | FAXA NEEDS LULL | 4
44752 | 44750 | 26-6030 | FSE NEEDS LULL | 4
44752 | 44750 | 33-2400 | PUMPS | 2
44752 | 44750 | 03-6000 | SG3 FRP INSTALL AT 2ND FLOOR | 20.5
44752 | 44750 | 02-3000 | OG8 FINISHING SAWCUT | 20
44752 | 44750 | 99-4560 | CLEAN GARBAGE AROUND ALL BUILDING | 20
44752 | 44750 | 03-1400 | OG6 DRILL/INSTALL DOWELS FOR BASEMENT | 28
44752 | 44750 | 31-2000 | OG1 VAC TRUCK TO EXPOSE UTILITIES FOR ELECTRICAL CONDUIT | 35
44752 | 44750 | 02-3000 | OG8 CORE DRILLING FOR THEMIS | 2
44752 | 44750 | 02-3000 | OG8 SAW CUT FOR THEMIS | 12
44752 | 44750 | 99-4560 | ENTIRE SITE - ENSURE GATES ARE LOCKED | 1
44745 | 44739 | 03-6000 | OG4 FRP INSTALL | 1
44745 | 44739 | 03-6000 | OG5 FRP IN BASEMENT | 17
44745 | 44739 | 03-1400 | SG3 DRILL FOR ALL REINFORCEMENT | 11
44745 | 44739 | 32-6000 | OG5 CUT SLABS ON 2ND FLOOR | 7
44745 | 44739 | 03-1000 | SG6 CLEAN AND PATCH HOLES ON ROOF | 15
44745 | 44739 | 04-6130 | SG6 ANGLE AT FAÇADE | 11
44745 | 44739 | 02-3000 | SG2 CUT THE TEST OF POE EXTERIOR | 5
44745 | 44739 | 02-6010 | SG3 MLJ TO CLEAN PITS AND BASEMENT | 17
44745 | 44739 | 99-4560 | OG8 CLEAN 2ND FLOOR | 0.5
44745 | 44739 | 99-4560 | SG7 CLEAN GARBAGE | 4
44745 | 44739 | 99-4560 | OG9 CLEAN GARBAGE | 4
44745 | 44739 | 02-2300 | OG5 CLEAN BASEMENT AND 2ND FLOOR | 4
44745 | 44739 | 99-4560 | OG8 SG6 SG7 SG3 OG9 SG5 OG5 CLEAN ALL LOCATIONS WITH BACKHOE | 13
44745 | 44739 | 02-2300 | SG2 SAWCUT FOR CONDUIT (POE @ SG2) | 10
44745 | 44739 | 99-4560 | OG6 MOVE MATERIAL AND PREP AREA | 2
44745 | 44739 | 33-6010 | OG6 OFFLOAD 1 TRUCK OF PIPE MATERIAL (FITTINGS) | 4.5
44745 | 44739 | 03-1000 | SG7 STRIP SLAB EDGE + BRICKSHELF | 16
44745 | 44739 | 03-1000 | SG7 STRIP COLUMN BOX OUTS | 14
44745 | 44739 | 03-1000 | SG7 STRIP COLUMNS | 41
44745 | 44739 | 03-1900 | OG9 PATCH HOLES IN ROOF | 17.5
44745 | 44739 | 99-4560 | OG8 PATCH HOLES IN ROOF | 3
44745 | 44739 | 31-1000 | SG5 FIX HANDRAIL AT SHAFT | 5
44745 | 44739 | 99-4560 | LOCK GATES | 0.5
44745 | 44739 | 03-2300 | SITE8 POUR DUCTBANK AND FOUNDATION WALL (44 YDS) | 11
44745 | 44739 | 32-6000 | SG7 SAWCUT JOINTS ON SLAB/CLEAN AREA/PREP FOR REBAR DELIVERY FOR SG1 SG2 SG3 | 20.5
44745 | 44739 | 31-2200 | OG5 BACKFILL STAYFORM FOR MASONRY SHELF/PREP FOR POUR | 4
44745 | 44739 | 03-2500 | OG5 BACKFILL STAYFORM FOR MASONRY SHELF/PREP FOR POUR | 4
44745 | 44739 | 04-6120 | FAXA CODE | 4
44745 | 44739 | 32-6520 | SITE8 CLEAN AREA AND TEMPORARY WALKWAY | 10.5
44745 | 44739 | 03-6000 | OG4 FRP INSTALL ON 1ST FLOOR/BASEMENT | 17
44745 | 44739 | 32-6510 | INSTALL AND REPAIR WHITE NETTING | 9
44745 | 44739 | 33-6010 | OG9 OG9 OG10 LULL NEEDED FOR FSE WELKIN | 4
44745 | 44739 | 33-6010 | SG3 WELKIN LAYING PIPE IN TRENCH - MACHINE NEEDED | 8.5
44745 | 44739 | 02-3000 | SG2 CUT POE | 1
44745 | 44740 | 99-4560 | OG8 TOE BOARDS + NETTING | 7
44745 | 44740 | 99-4560 | OG9 CABLE REPAIR | 13.5
44745 | 44740 | 99-4560 | OG10 TOE BOARDS + NETTING | 7
44745 | 44740 | 03-1000 | SG7 FORM PLUMBING SHAFT | 42
44745 | 44740 | 03-2300 | SITE8 STRIP DUCT BANK | 27
44745 | 44740 | 03-1000 | SITE8 FORM PLUMBING | 7
44745 | 44740 | 03-1500 | OG5 FORM WINDOWS | 33
44745 | 44740 | 99-4560 | LOCK GATES | 0.5
44745 | 44740 | 03-1000 | SG7 SET PANELS FOR PLUMBING SHAFT (FORM WORK) | 3.5
44745 | 44740 | 02-3000 | SG2 COMPLETE SAW CUT/CHOPPING FOR CONDUIT | 3
44745 | 44740 | 99-4560 | SITE8 CLEAN AND GATHER GARBAGE FOR CARDELLA | 12
44745 | 44740 | 33-6010 | SITE8 PREP AREA FOR PIPE DELIVERY | 6
44745 | 44740 | 32-6000 | SG2 FINISHING SAWCUT EXTERIOR FOR FSE | 9
44745 | 44740 | 32-6000 | OG4 SAWCUT WALL PENETRATIONS FSE | 9
44745 | 44740 | 32-6000 | OG5 SAWCUT PENETRATIONS ON 2ND FLOOR | 25.5
44745 | 44740 | 02-2300 | SG3 SG4 SG5 CHECK PUMPS AND CLEAN WATER FROM BASEMENTS | 17.5
44745 | 44740 | 03-6000 | OG5 FRP INSTALL | 17.5
44745 | 44740 | 02-3000 | SG6 COMPLETE HOLES EIA | 17.5
44745 | 44740 | 99-4560 | SG3 SG6 SG7 SITE8 CLEAN ALL LOCATIONS WITH BACKHOE + LULL | 30.5
44745 | 44740 | 03-1800 | SG7 REBAR DELIVERY (TONAGE SUPPORT) | 26
44745 | 44740 | 31-1100 | OG5 BACKFILL MASONRY SHELF/USE BACKHOE TO MOVE MATERIAL FOR BACKFILL | 18.5
44745 | 44740 | 03-6000 | OG4 FRP INSTALL ON BASEMENT | 10
44745 | 44740 | 99-4560 | SG7/OG10 CLEAN AREA | 13
44745 | 44740 | 04-6120 | OG5 OG6 OG10 OG8 FAXA SGN | 5
44745 | 44740 | 02-3000 | SG2 SAWCUT POE | 1
44745 | 44740 | 33-6010 | WELKIN MACHINE SUPPORT | 1.5
44745 | 44740 | 07-6220 | SG6 ROOF DEBRIS REMOVAL | 1.5
44745 | 44741 | 03-6000 | SG3 FRP INSTALL | 17
44745 | 44741 | 03-2100 | SG4 PATCH EXTERIOR WALL | 11
44745 | 44741 | 03-2100 | SG5 PATCH PIT AND CLEAN IT | 9
44745 | 44741 | 07-6220 | PREP ROOF AT G6 AND CLEAN | 18
44745 | 44741 | 32-6000 | OG5 CUT PENETRATIONS SAWCUT | 18
44745 | 44741 | 31-1500 | SG5 GRACE STONE COMPLETE HOLES | 17
44745 | 44741 | 02-2300 | PUMP BASEMENT | 11
44745 | 44741 | 02-2300 | SG3 CLEAN BASEMENT | 11.5
44745 | 44741 | 03-2300 | SG7 DUCT BANK | 25
44745 | 44741 | 03-1000 | SG7 FORM PLUMBING SHAFT | 83
44745 | 44741 | 03-1000 | SG6 SCAFFOLD ON SHAFT | 24
44745 | 44741 | 03-1000 | SG6 CURBS AROUND OPENING | 4.5
44745 | 44741 | 99-4560 | LOCK GATES | 0.5
44745 | 44741 | 33-3100 | SG2 ATTEMPT TO FIX STEAM PIPE PITCH | 16.5
44745 | 44741 | 03-1400 | SG3 DRILL AND DOWEL FOR WALL REINFORCEMENT | 18
44745 | 44741 | 99-4560 | SITE8 SET UP CONTAINER "CARDELLA"/CLEAN UP PIPE OF DEBRIS | 2.5
44745 | 44741 | 99-4560 | OG10 CLEAN BACK OF BLD FOR FSE INSTALL TRAILER AND BOX CONTAINER | 7
44745 | 44741 | 31-2200 | SG7 BACKFILL DUCTBANK AND BACK OG BLD/HNS TRUCK ON SITE MOVING MATERIAL | 26.5
44745 | 44741 | 31-1400 | MOVING MATERIAL FROM OG3/OG4 FILES OF SAND TO SG7-BACKFILL/LOAD HNS TRUCK | 13
44745 | 44741 | 99-4560 | OG8 OG10 CLEAN AREAS | 17
44745 | 44741 | 04-6120 | LULL NEEDED FOR FAXA | 4.5
44745 | 44741 | 33-2400 | PUMPS | 1
44745 | 44742 | 03-6000 | SG3 FRP INSTALL AT 2ND FLOOR | 17
44745 | 44742 | 31-1500 | SG4/SG5 GRADE STONE CAP REBAR | 27
44745 | 44742 | 02-2300 | OG2 CLEAN BASEMENT | 19
44745 | 44742 | 32-6000 | SG6 CUT WALL | 11
44745 | 44742 | 32-6000 | OG6 CUT PAD AT BASEMENT | 12
44745 | 44742 | 32-6000 | OG5 CUT SLABS AT 2ND FLOOR | 18.5
44745 | 44742 | 03-1000 | SG7 FORM PLUMBING SHAFT | 101.5
44745 | 44742 | 03-1000 | SITE8 FORM GRADE BEAM | 1
44745 | 44742 | 03-1000 | SG6 FINISH SCAFFOLD IN SHAFT | 6
44745 | 44742 | 03-1000 | OG9 PATCH PENETRATIONS IN ROOF | 22
44745 | 44742 | 99-4560 | LOCK GATES | 0.5
44745 | 44742 | 31-1820 | SG7 FIREWATCH | 6
44745 | 44742 | 99-4560 | SGN 2 EA LIVE LOADS CONCRETE "CARDELLA" | 3.5
44745 | 44742 | 31-1400 | SG6 BACKFILL BEHIND BLD/CLEAN SIDE OF BLD - CONCRETE DEBRIS AND STEEL/GRADE AREA - GARBAGE | 21
44745 | 44742 | 03-2500 | OG5 POUR MASONRY SHELF AND BASEMENT WINDOWS | 4
44745 | 44742 | 03-1500 | OG5 POUR MASONRY SHELF AND BASEMENT WINDOWS | 4
44745 | 44742 | 03-2300 | SG7 POUR DUCTBANK | 14.5
44745 | 44742 | 03-1900 | SITE8 POUR PITS INSIDE BLD | 10
44745 | 44742 | 04-6120 | SG6 OG8 OG10 LULL NEEDED FOR FAXA | 4.5
44745 | 44742 | 26-6030 | SG6 OG8 LULL NEEDED FOR FSE | 4.5
44745 | 44742 | 31-2000 | OG3 OG4 VAC TRUCK UNCOVER STEAM RUN | 19.5
44745 | 44742 | 31-1810 | SUT SCRAP STEEL FOR LOADOUT, LAGGING, SOE MATERIAL | 7
44745 | 44742 | 33-6010 | MOVE PIPE - WELKIN | 6
44745 | 44743 | 03-1400 | SG3 DOWEL FOR WALL REINFORCEMENT | 17.5
44745 | 44743 | 07-6220 | OG9 CLEAN AND PREP ROOF FOR ROOFER | 14.5
44745 | 44743 | 99-4560 | OG2 REMOVE 1 ON BAGS OF DEBRIS/CLEAN AREA "GARBAGE USE BACKHOE | 10.5
44745 | 44743 | 03-6110 | SG4 MOVE REBAR FOR TANAGE | 3
44745 | 44743 | 31-1400 | SITE8 BACKFILL AND COMPACT | 16.5
44745 | 44743 | 33-6010 | OG8 WELKIN NEEDS LULL | 2.5
44745 | 44743 | 33-5000 | OG3 ADJUST STEAM PIPE TO OG4 | 19.5
44745 | 44743 | 31-1810 | SG7 LOAD CONTAINER WITH SCRAP STEEL (SOE MATERIAL) | 3
44745 | 44743 | 33-6010 | SG7 MOVE AND INSTALL PIPE FOR WELKIN | 6
44745 | 44743 | 33-6010 | OG10 MOVE PIPE (WELKIN SUPPORT) | 4
44745 | 44743 | 03-1000 | SG7 FORM PLUMBING SHAFT | 74
44745 | 44743 | 03-1000 | SITE8 STRIP PIT BOXES | 21
44745 | 44743 | 03-1000 | SITE8 FORM PIT WALLS | 22
44745 | 44743 | 03-1000 | OG10 SETUP SCAFFOLDING IN PLUMBING SHAFT | 7
44745 | 44743 | 03-1000 | OG9 SPRAY FOAM OPENING IN ROOF | 5
44745 | 44743 | 03-1000 | OG8 SET UP SCAFFOLDING IN SHAFT FOR DSTAR | 7.5
44745 | 44743 | 99-4560 | LOCK GATES | 0.5
44745 | 44743 | 33-2400 | PUMPS | 2
44745 | 44743 | 03-6000 | SG3 INSTALL FRP AT 2ND FLOOR | 17.5
44745 | 44743 | 32-6000 | OG5 SAWCUT SLABS PEN | 17.5
44745 | 44743 | 31-1500 | SG4 GRADE STONE | 25.5
44745 | 44743 | 07-6220 | SG6 PREP ROOF | 18
44745 | 44743 | 99-4560 | OG9 CLEAN 1ST AND 2ND FLOOR | 18
44738 | 44732 | 03-6000 | OG5 INSTALL FRP | 16.5
44738 | 44732 | 02-6005 | SG3 PAINT REMOVAL | 16.5
44738 | 44732 | 02-3000 | OG4 CORE FOR FSE | 7.5
44738 | 44732 | 02-6025 | SG5 DEMO BRICK FOR BOND BEAM | 11
44738 | 44732 | 99-4560 | OG9 CLEAN 1ST AND 2ND FLOOR | 13
44738 | 44732 | 99-4560 | SG6 CLEAN ROOF | 13
44738 | 44732 | 07-6220 | SG6 PREP ROOF FOR ROOFING (WHITE MESH INSTALL) | 18
44738 | 44732 | 32-6510 | SG1 OG5 OG6 SG2 PUT UP MESH (WHITE MESH INSTALL) | 8.5
44738 | 44732 | 04-6130 | SG6 INSTALL ANGLE AT FAÇADE | 16.5
44738 | 44732 | 31-2000 | OG6 TEST PIT AND EXPLORE FOR GAS LINES | 4
44738 | 44732 | 33-2600 | OG6 DIG AND ATTEMPT INSTALL OF AD-18 (ELECTRIC CONDUIT IN THE WAY | 6
44738 | 44732 | 32-6000 | OG6 MODIFY MH-3 TO ACCOMMODATE EXISTING PIPE (SAWCUT) | 8
44738 | 44732 | 33-1000 | PROTECTION AND MAINTENANCE OF EXISTING UTILITIES | 12
44738 | 44732 | 03-1000 | SITE8 STRIP FORMS AROUND CONDUIT | 17
44738 | 44732 | 03-1000 | SITE8 FORM AROUND CONDUIT | 31
44738 | 44732 | 03-1000 | OG8 STRIP STAIR FOOTING | 7
44738 | 44732 | 03-1000 | OG10 FIX STOP AT STAIR PLATFORM | 4
44738 | 44732 | 02-6060 | OG4 PLYWOOD OVER PENETRATIONS ON 2ND FL APT | 2
44738 | 44732 | 03-1100 | OG5 CLOSE-UP FLOOD WALL | 22
44738 | 44732 | 03-2300 | SG7 POUR DUCKBANK | 8
44738 | 44732 | 03-2300 | SG4 SG5 POUR THRUST BLOCK | 4
44738 | 44732 | 03-1900 | OG10 POUR 1ST FL SLAB/POUR LANDINGS W. LULL/BUCKET | 21.5
44738 | 44732 | 33-3100 | SG3 EXCAVATE FOR FSE RUN CONDUIT TO POE | 5
44738 | 44732 | 03-1800 | SG7 TONAGE SHAPE OUT AND INSTALL REBAR/MACHINE NEEDED | 5
44738 | 44732 | 31-1100 | OG5 BACKFILL BELOW REBAR AND INSTALL STAYFOAM ON MASONRY SHELF | 9
44738 | 44732 | 32-6510 | FIX AND INSTALL WHITE NETTING | 9
44738 | 44732 | 31-2200 | SG5 BACKFILL STEAMPIPE/HNS ON SITE MOVING MATERIAL | 14
44738 | 44732 | 99-4560 | UNLOAD HEATERS FOR VITAL | 3
44738 | 44732 | 04-6120 | OG2 OG9 SG5 FAXA NEED LULL | 6
44738 | 44732 | 33-2400 | PUMPS | 2
44738 | 44733 | 03-2500 | OG4 POUR MASONRY SHELF AND WINDOWS | 16
44738 | 44733 | 03-1500 | OG3 POUR | 9
44738 | 44733 | 03-2100 | SG4 POUR FLOOR DRAIN IN BASEMENT | 5
44738 | 44733 | 31-2200 | SG5 BACKFILL STEAM PIPE/HNS TRUCK ON SITE MOVING MATERIAL | 11
44738 | 44733 | 31-1500 | SG7 INSTALL STONE AND FOAM | 7.5
44738 | 44733 | 32-6220 | JMC PLACE STONE - BACKHOE NEEDED | 8
44738 | 44733 | 99-4560 | OG8 MOVE SCAFFOLD FROM 2ND FLOOR/LULL NEEDED | 1.5
44738 | 44733 | 04-6120 | OG8 LULL FOR FAXA OG5 TRUCKLOAD OF BRICK | 6
44738 | 44733 | 33-6010 | OG5 WELKIN NEEDS MACHINE/MOVE PIPE TO OG5/OG6 RUAU | 12.5
44738 | 44733 | 33-2600 | OG6 INSTALL MANHOLE/DRAINAGE | 2
44738 | 44733 | 32-6510 | REPAIR AND INSTALL WHITE NETTING | 2.5
44738 | 44733 | 33-3100 | CHOP UTILITY OBSTRUCTION AT OG3-9 | 2
44738 | 44733 | 33-2400 | PUMPS | 3
44738 | 44733 | 03-1000 | SITE8 FINISH BRACING WALL | 19
44738 | 44733 | 03-1000 | SITE8 FRAME FOR 2 PLUMBING PITS | 21
44738 | 44733 | 03-1000 | SITE8 START CUTTING FOR SLAB EDGE | 7
44738 | 44733 | 99-4560 | SITE8 MAINTENANCE | 5
44738 | 44733 | 03-1000 | SG6 FORM PAD | 5
44738 | 44733 | 03-1100 | OG4 FORM FLOOD WALL | 16
44738 | 44733 | 03-1100 | OG3 FORM FLOOD WALLS | 28
44738 | 44733 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44738 | 44733 | 99-4560 | OG8 SAFETY (SITE MAINT) | 3.5
44738 | 44733 | 33-1000 | OG6 SAWCUT MH-3 TO ACCOMMODATE EXISTING PIPE - PROTECT AND MAINTAIN EXISTING UTILITY | 8.5
44738 | 44733 | 99-4560 | OG6 PREP AREA FOR PIPE DELIVERY - SITE MAINTENANCE | 2
44738 | 44733 | 33-2600 | OG6 INSTALL AD23 AND MH3 FOR DRAINAGE | 4
44738 | 44733 | 33-2600 | OG6 BEGIN TO MAKE RISERS FOR AD23 AND MH3 | 2
44738 | 44733 | 02-2300 | SG5 CLEAN GARBAGE FROM PUMPS BASEMENT | 16.5
44738 | 44733 | 02-2300 | SG4 CLEAN GARBAGE FROM PUMPS BASEMENT | 16.5
44738 | 44733 | 02-6005 | SG3 PAINT REMOVAL/BUSG HAMMER WALL BASEMENT | 16.5
44738 | 44733 | 03-6000 | OG5 INSTALL FRP | 16.5
44738 | 44733 | 02-6025 | SG5 DEMO BRICK FOR BOND BEAM | 17.5
44738 | 44733 | 99-4560 | SG6 CLEAN GARBAGE ON ROOF | 6.5
44738 | 44733 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR | 6.5
44738 | 44733 | 02-6025 | OG3 TO OG9 DEMO FOR WELKIN (HOP OBSTRUCTION) | 17.5
44738 | 44733 | 03-1900 | OG8 FINISH PATCHING SHAFT AND CLEAN | 11.5
44738 | 44733 | 32-6520 | SG1 MOUNT FENCE | 11
44738 | 44734 | 03-1000 | OG8 FORM UNDERSIDE DECK, ELECTRICAL PENETRATION | 18
44738 | 44734 | 03-1000 | SG7 STRIP BULKHEAD | 2
44738 | 44734 | 03-1000 | SITE8 COLUMN BASE BLOCK OUTS | 30
44738 | 44734 | 03-1500 | OG4 STRIP WINDOWS | 34
44738 | 44734 | 03-1500 | OG3 STRIP WINDOWS | 10
44738 | 44734 | 02-6060 | OG4 COVER DOOR WITH PLYWOOD | 5
44738 | 44734 | 02-6060 | OG3 COVER DOOR WITH PLYWOOD | 5.5
44738 | 44734 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44738 | 44734 | 03-1400 | OG1 OG2 SG4 SG5 DRILL AND DOWEL AT FLOODWALL | 18
44738 | 44734 | 31-2200 | SG5 BACKFILL STEAM PIPE | 18
44738 | 44734 | 07-1100 | SG6 PREP FOR INFILL/INSTALL FOAM | 3
44738 | 44734 | 31-1100 | OG3 OG5 OG4 PREP FOR CONCRETE POUR/BACKFILL FOR TRUCK ACCESS/BACKFILL THRUST BLOCKS FOR POUR | 17
44738 | 44734 | 99-4560 | SG6 TAKE MATERIAL FROM ROOF/LULL NEEDED | 2
44738 | 44734 | 99-4560 | SG4 MOVE CONEX BOX AND OTHER MATERIAL/CLEAN AREA FOR ACCESS | 7
44738 | 44734 | 32-6220 | JMC PLACE STONE/BACKHOE NEEDED | 9
44738 | 44734 | 33-6010 | VITAL AND WELKI NEEDS LULL AT OG8 & OG10 | 4
44738 | 44734 | 04-6120 | FAXA B/C | 5
44738 | 44734 | 02-6005 | SG3 BUSH HAMMER FOUNDATION WALL (FOR WALL REINFORCEMENT) | 34
44738 | 44734 | 03-6000 | OG5 FRP INSTALL | 26
44738 | 44734 | 02-2300 | SG3 CLEAN WATERIN BASEMENT (BASEMENT MAINT) | 9
44738 | 44734 | 02-6060 | OG3 DEMO 2ND FLOOR EXTERIOR | 11.5
44738 | 44734 | 02-6060 | OG4 DEMO 2ND FLOOR EXTERIOR | 9
44738 | 44734 | 03-1900 | SG6 POUR PAD AND HOLE ON ROOF (POUR CONC NB) | 11
44738 | 44734 | 02-2300 | SG4 CLEAN WATER IN BASEMENT | 3
44738 | 44734 | 07-6220 | SG6 PREP ROOF FOR ROOFING | 17
44738 | 44734 | 33-2500 | OG6 OFFLOAD DRAINAGE PIPE (1 TRUCK LOAD) | 12.5
44738 | 44734 | 31-1100 | OG6 BACKFILL | 13
44738 | 44734 | 33-2600 | OG6 BEIN PATCHWORK FOR MH3 | 7
44738 | 44735 | 03-2100 | OG3 OG4 OG5 POUR FLOODWALLS | 12
44738 | 44735 | 03-1900 | SG7 PREP FOR SLAB POUR/BACKFILL BEHIND SLAB FORMS | 17
44738 | 44735 | 03-2300 | SG3 BACKFILL STAYFORM FOR POUR FSE CONDUIT | 5
44738 | 44735 | 31-2200 | SG5 BACKFILL STEAM PIPE | 9
44738 | 44735 | 03-1400 | SG6 DRILL AND DOWEL - PREP FOR INFILL | 5
44738 | 44735 | 33-6010 | OG8 OG9 OG10 SG4 SG5 LULL NEEDED FOR VITAL, WELKIN & FAXA | 4.5
44738 | 44735 | 99-4560 | SAFETY MEETING | 1.5
44738 | 44735 | 02-2100 | SGN DEMO RETAINNG WALL | 9
44738 | 44735 | 04-6120 | OG8 OG9 OG10 SG4 SG5 LULL NEEDED FAXA | 4
44738 | 44735 | 33-2400 | PUMPS | 2
44738 | 44735 | 33-2500 | OG3 OFFLOAD DRAINAGE PIPE (1 LOAD) | 15.5
44738 | 44735 | 33-2900 | OG6 DEMO EXISTING MH AND CATCH BASIN | 8
44738 | 44735 | 33-2600 | OG6 DIG AND GRADE FOR MH-2 AND AD18 | 10
44738 | 44735 | 33-2600 | OG6 PATCH WORK AROUND MANHOLES | 4
44738 | 44735 | 32-6000 | OG6 SAWCUT MATERIALS | 3
44738 | 44735 | 99-4560 | OFFICE SAFETY TRAINING | 1.5
44738 | 44735 | 32-6520 | SG1 FENCE INSTALL FOR FLOODGATE | 44
44738 | 44735 | 99-4560 | SG3 MLJ TO CLEAN | 11.5
44738 | 44735 | 02-6060 | OG5 DEMO EXTERIOR WALL AT 2ND FLOOR | 10
44738 | 44735 | 99-4560 | SG4 SG5 SG6 CLEAN GARBAGE AT ALL BUILDINGS | 19
44738 | 44735 | 03-6000 | OG5 FRP INSTALL | 18.5
44738 | 44735 | 03-1400 | SG3 DRILL DOWELS | 9.5
44738 | 44735 | 32-6000 | PICK UP SAW MACHINE (SAW CUT CODE) | 1
44738 | 44735 | 02-6005 | BUSH HAMMER/PAINT REMOVAL FOR WALL REINFORCEMENT | 8
44738 | 44735 | 03-2300 | SG7 DUCT BANK IN TRENCH + BASEMENR | 22
44738 | 44735 | 02-6060 | OG5 PLYWOOD DOOR | 6
44738 | 44735 | 03-1000 | SITE8 SLAB EDGE | 26
44738 | 44735 | 03-1000 | SG6 FORM 2 PENETRATIONS TO ROOF | 10
44738 | 44735 | 03-1100 | SG4 STRIP KEY ON TOP OF WALL | 7
44738 | 44735 | 03-1100 | SG5 STRIP KEY ON TOP OF WALL | 7
44738 | 44735 | 32-6510 | SAFETY - NETTING, CABLE | 2
44738 | 44735 | 03-1500 | OG4 STRIP WINDOWS | 24.5
44738 | 44735 | 99-4560 | SAFETY MEETING | 1.5
44738 | 44735 | 99-4560 | SITE MAINTENANCE | 0.5
44738 | 44736 | 03-1900 | SG7 POUR SLAB | 52
44738 | 44736 | 03-2300 | SG3 POUR CONDUIT ENCASEMENT | 11
44738 | 44736 | 03-1900 | SG6 POUR INFILL | 6
44738 | 44736 | 03-2300 | SITE8 POUR CONDUIT ENCASEMENT - 4 YRDS LEFT FROM SG7 POUR | 3
44738 | 44736 | 33-3100 | OG1 START EXCAVATION FOR FSE CONDUIT RUN TO MH/REMOVE CONCRETE RAMP AND CURBS/HNS ON SITE MOVING MATERIAL TO SG6/OG5 | 17.5
44738 | 44736 | 02-2100 | SG5 DEMO RETAINING WALL AND SIDEWALK/LOAD OUT | 17
44738 | 44736 | 04-6120 | LULL NEEDED FOR WELKIN - FAXA AND FSE/OG2 OG3/MORTAR - OG8 AND 9/MOVE PIPE | 5.5
44738 | 44736 | 33-6010 | LULL NEEDED FOR WELKIN - FAXA AND FSE/OG2 OG3/MORTAR - OG8 AND 9/MOVE PIPE | 4
44738 | 44736 | 02-6025 | DEMO RAMP | 8.5
44738 | 44736 | 03-1000 | SITE8 DUMMY DECK IN PLUMBING SHAFT, BRICKSHELF AROUND PERIMETER (NB FORM WK) | 54.5
44738 | 44736 | 03-1100 | OG3 STRIP FLOODWALLS | 12
44738 | 44736 | 03-1100 | OG4 STRIP FLOODWALLS | 12
44738 | 44736 | 03-1100 | OG5 STRIP FLOODWALLS | 12
44738 | 44736 | 03-2500 | OG5 STAYFORM BRICKSHELF | 12
44738 | 44736 | 03-1000 | SG6 STRIP ATS PAD | 1
44738 | 44736 | 03-2500 | SG5 SUPPORT BRICK FAÇADE | 9
44738 | 44736 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44738 | 44736 | 33-6010 | OG6 MOVE PIPE FOR WELKIN | 20.5
44738 | 44736 | 33-3100 | OG6 MOVE MATERIAL | 4
44738 | 44736 | 33-3100 | OG6 BEGIN TRENCHING FOR PIPE INSTALLATION | 8
44738 | 44736 | 03-6000 | OG5 FRP INSTALL | 18
44738 | 44736 | 26-6030 | SG3 REMOVE CABINET FOR FSE | 10
44738 | 44736 | 02-6060 | SG3 CLEAN 2ND FLOOR APPT | 14
44738 | 44736 | 02-2300 | OG2 PUMP OUT BASEMENT (MAINT) | 6
44738 | 44736 | 02-2300 | OG4 PUMP OUT BASEMENT (MAINT) | 6
44738 | 44736 | 99-4560 | SG6 CLEAN ROOF | 9.5
44738 | 44736 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR | 9
44738 | 44736 | 03-1400 | SG3 DRILL WALL (DOWEY) | 35
44738 | 44736 | 03-2100 | DROP AND PICK UP SCRED MACHINE (NWK) (POUR CONC) | 2
44731 | 44725 | 02-3000 | SG6 CUT PENETRATIONS FOR THEMIS | 6
44731 | 44725 | 32-6000 | OG1 CUT SLABS PENETRATIONS AT 1ST FLOOR | 22
44731 | 44725 | 02-2300 | OG10 CLEAN SHAFT (BASE MAINT) | 6
44731 | 44725 | 03-6000 | OG5 FRP | 18
44731 | 44725 | 03-1900 | OG10 POUR SHAFT | 6
44731 | 44725 | 03-1900 | OG8 PREPARE SHAFT FOR POUR PAD | 6
44731 | 44725 | 99-4560 | SITE8 CLEAN | 10
44731 | 44725 | 31-1820 | SITE8 FIRE WATCH (BURN OUT PILES) | 5.5
44731 | 44725 | 04-6120 | OG8 OG10 LOAD NEEDED (FAXA) | 4
44731 | 44725 | 31-1100 | SG5 BACKFILL | 4
44731 | 44725 | 99-4560 | SG7 CLEAN GARBAGE | 2
44731 | 44725 | 31-1400 | SG7 COMPACT FOOTPRINT/INSTALL STONE AFTER INSPECTION/EXCAVATE FSE CONDUIT TO SG3 | 15
44731 | 44725 | 03-1400 | OG5 INSTALL DOWELS AT MASONRY SHELF | 17
44731 | 44725 | 07-1100 | OG10 REPLACE FOAM | 5
44731 | 44725 | 31-2200 | SITE8 BACKFILL STAYFORM AT DUCTBANK - CONDUIT | 9
44731 | 44725 | 31-1100 | SG5 BACKFILL INSIDE OF FLOODWALL | 9.5
44731 | 44725 | 32-6510 | SG2 INSTALL WHITENING ON FENCE | 9
44731 | 44725 | 31-1820 | SITE8 CUT PILES | 6.5
44731 | 44725 | 31-1400 | SITE 8 BACKFILL | 5
44731 | 44725 | 33-3100 | SITE8 DIG TRENCH FOR PLUMBING AND CONDUIT | 6
44731 | 44725 | 33-2400 | PUMPS | 2
44731 | 44725 | 03-1000 | SITE8 FORM BULK HEAD FOR DUCT BANK | 7.5
44731 | 44725 | 03-1000 | OG8 FORM FOOTING FOR STAIRCASE | 21
44731 | 44725 | 03-1500 | OG3 STRIP WINDOWS IN BASEMENT | 9
44731 | 44725 | 03-1100 | OG4 FORM WINDOWS | 24
44731 | 44725 | 03-1000 | SG7 FORM SLAB SIDE + MAKEUP BRICKSHELF | 23
44731 | 44725 | 03-2500 | SG7 FORM SLAB SIDE + MAKEUP BRICKSHELF | 20
44731 | 44725 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44731 | 44726 | 31-1100 | SG4 SG5 BACKFILL BEHIND FLOODWALL AND COMPACT | 26.5
44731 | 44726 | 33-3100 | SG7 EXCAVATE ELECTRIC TRENCH TO SG3 | 17
44731 | 44726 | 33-3100 | OG5 VACUUM EXCAVATE STEAM PIPE | 18
44731 | 44726 | 03-1400 | OG5 INTALL DOWELS AT BASEMENT WINDOWS | 9
44731 | 44726 | 04-6120 | OG8 OG9 LULL NEEDED FOR FAXA (FAXA CODE) | 4
44731 | 44726 | 99-4560 | OG5 SG7 SITE8 CLEAN AREAS | 13
44731 | 44726 | 03-2300 | SITE8 POUR DUCTBANK | 2
44731 | 44726 | 33-2500 | OG6 SHAKE OUT MATERIAL AND PREP AREA (DRAINAGE) | 9
44731 | 44726 | 33-3100 | SITE8 DIG TRENCH FOR CONDUIT AND PLUMBING | 6
44731 | 44726 | 33-2500 | OG6 INSTALL MANHOLE FOR DRAINAGE | 9.5
44731 | 44726 | 33-2400 | PUMPS | 3
44731 | 44726 | 03-6000 | OG4 FRP INSTALL | 18
44731 | 44726 | 07-6020 | OG8 PREP WATERPROOFING | 18
44731 | 44726 | 02-6010 | SG4 MLJ CLEAN | 10
44731 | 44726 | 99-4560 | SG3 CLEAN GARBAGE AROUND BUILDING | 6
44731 | 44726 | 99-4560 | OG8 CLEAN GARBAGE AROUND BUILDING | 6
44731 | 44726 | 32-6000 | OG1 CUT SLAB PENETRATIONS AT 1ST FLOOR | 18
44731 | 44726 | 99-4560 | SG6 CLEAN ROOF 1ST AND 2ND FLOOR | 6
44731 | 44726 | 99-4560 | OG8 CLEAN 2ND FLOOR | 6.5
44731 | 44726 | 03-1000 | SG6 FORM ROOF PENETRATIONS (ELECTRICAL CONDUIT) | 21
44731 | 44726 | 03-1000 | OG10 STRIP PAD IN SHAFT | 3
44731 | 44726 | 03-1000 | OG10 STRIP OUT KEYWAY | 2
44731 | 44726 | 99-4560 | OG8 PUT HANDRAIL AT TOP OF STAIRS AT ROOF, COVER HOLE BETWEEN COLUMN AND BLOCKWALL (SITE MAINT) | 5
44731 | 44726 | 03-1500 | OG4 FINISH FRAMING WINDOWS | 20
44731 | 44726 | 03-1100 | OG3 PUT SHOE DOWN FOR FLOODWALL | 5
44731 | 44726 | 03-1100 | OG4 PUT SHOE DOWN FOR FLOODWALL | 4
44731 | 44726 | 03-1100 | OG5 PUT SHOE DOWN FOR FLOODWALL | 3
44731 | 44726 | 03-1000 | SG7 SLAB SIDE, FORMWORK | 33.5
44731 | 44726 | 99-4560 | LOCK GATES - SITE MAINT | 0.5
44731 | 44727 | 31-2200 | SG2 BACKFILL PLUMBING RUN/HNS ON SITE MOVING MATERIAL | 12.5
44731 | 44727 | 33-3100 | SG7 LOAD OUTSTOCKPILE FROM ELEC EXCAVATION/HNS ON SITE | 3
44731 | 44727 | 31-1100 | SG4 BACKFILL/COMPACT BEHIND FLOODWALL | 7
44731 | 44727 | 07-1100 | OG10 REMOVE REBAR AND FOAM/REPLACE FOAM/PREP FOR CONCRETE POUR | 12
44731 | 44727 | 31-2200 | SITE8 BACKFILL DUCTBANK/PREP FOR CONCRETE POUR | 11
44731 | 44727 | 03-1900 | OG8 PREP FOR CONCETE POUR | 3
44731 | 44727 | 33-3100 | SG5 EXCAVATE FOR ELEC | 10
44731 | 44727 | 33-2400 | PUMPS | 1
44731 | 44727 | 99-4560 | OG1 COVER HOLES ON 1ST FLOOR | 5
44731 | 44727 | 33-1000 | OG1 REMOVE WALKWAYS FOR FSP (MAINT/PROT EXIST PUT UTILITIES) | 3
44731 | 44727 | 03-1100 | OG5 FORM FLOOWALL | 17
44731 | 44727 | 03-1100 | OG4 FORM FLOODWALL | 17
44731 | 44727 | 99-4560 | OG10 FIX HANDRAIL ON ROOF AT STAIR PLATFORM | 5
44731 | 44727 | 03-1000 | OG10 FORM LANDING AT TOP OF STAIRS AT ROOF | 5
44731 | 44727 | 03-1000 | SG7 SLAB EDGE + BRICK SHELF | 16
44731 | 44727 | 03-2500 | SG7 SLAB EDGE + BRICK SHELF | 9
44731 | 44727 | 03-2300 | SITE8 FORM ELECTRICAL CONDUIT | 9
44731 | 44727 | 99-4560 | LOCK GATES (SITE MAINT) | 2.5
44731 | 44727 | 31-1400 | SLAB BACKFILL | 3
44731 | 44727 | 03-1000 | GRADE BEAM FORM WORK | 5
44731 | 44727 | 33-1000 | OG6 TEST PT AROUND MANHOLE | 11.5
44731 | 44727 | 33-2500 | OG6 INSTALL DRAINAGE | 9
44731 | 44727 | 33-1100 | DEMO EXISTING - CATCH BASIN | 4
44731 | 44727 | 32-6520 | SG1 INSTALL TEMP FENCE | 30
44731 | 44727 | 02-2300 | SG4 BASEMENT CLEAN UP | 12
44731 | 44727 | 99-4560 | SG6 PREP ROOF FOR ROOFING | 10
44731 | 44727 | 03-1000 | OG5 INSTALL FRP | 18
44731 | 44727 | 02-1900 | OG1 DEMO FOR FAI | 4
44731 | 44727 | 32-6000 | OG4 CUT SLAB PENETRATIONS | 18
44731 | 44727 | 07-6020 | OG8 PREP SHAFT FOR WATER PROOFING | 18
44731 | 44727 | 33-6010 | SITE8 LOAD NEEDED (WELKIN) | 3
44731 | 44727 | 04-6120 | OG8 LOAD NEEDED (FAXA) | 5
44731 | 44727 | 99-4560 | OG8 PICK UP GARBAGE | 3.5
44731 | 44727 | 99-4560 | OG0 CLEAN BY BUILDING | 4
44731 | 44728 | 03-6000 | OG5 FRP | 18
44731 | 44728 | 32-6000 | OG4 CUT SLABS ON 1ST FLOOR | 18
44731 | 44728 | 03-1900 | OG6 CLEAN/PREP TO POUR LANDINGS | 15
44731 | 44728 | 07-6020 | OG8 PREP SHAFT TO WATERPROOFING | 19
44731 | 44728 | 99-4560 | OG9 HOUSE KEEPING AROUND FENCE | 14
44731 | 44728 | 99-4560 | SG4 MLJ CLEAN | 10
44731 | 44728 | 99-4560 | SG1 CLEAN 1ST FLOOR ROOM FOR THEMIS | 7.5
44731 | 44728 | 99-4560 | SG6 CLEAN AROUND BUILDING | 9
44731 | 44728 | 99-4560 | SG6 PREP FOR FOOTING | 10
44731 | 44728 | 00-0016 | SG6 INSTALL ANGLE AT FAÇADE | 12
44731 | 44728 | 03-1900 | SG6 POOR ROOFING | 4
44731 | 44728 | 33-6010 | OG8 LOAD NEEDED (WELKIN) | 3
44731 | 44728 | 04-6120 | OG9 OG10 LOAD NEEDED (FAXA) | 6
44731 | 44728 | 03-1000 | SITE8 FINISH BRACING FOR CONCRETE | 6
44731 | 44728 | 03-2500 | SG7 FINISH SLAB EDGE + BRICK SHELF | 26
44731 | 44728 | 03-1000 | SG7 BOX OUTS FOR COLUMNS | 11
44731 | 44728 | 99-5100 | BUILD (1) SHELF + (1) CABINET IN OFFICE | 3
44731 | 44728 | 99-4560 | OG8 FIX HANDRAIL 2ND FLOOR @ PLUMBING SHAFT | 5
44731 | 44728 | 99-4560 | OG9 FIX CABLE + NETTING | 7
44731 | 44728 | 03-2500 | OG4 STAYFORM BACKSHELF | 25
44731 | 44728 | 03-1100 | FORM FLOOD WALL | 21.5
44731 | 44728 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44731 | 44728 | 33-2600 | OG6 TEST PIT/EXPLORE CATCH BASIN | 9.5
44731 | 44728 | 33-2600 | OG6 INSTALL DRAINAGE AD-25 | 6
44731 | 44728 | 03-2600 | OG6 PREP AREA FOR DRAINAGE AND RETAINING WALL/MOVE MATERIALS | 6
44731 | 44728 | 33-3100 | OG6 BREAK DOWN TRENCH BOXES | 3
44731 | 44728 | 31-1100 | SG4 BACKFILL/COMPACT BEHIND FLOODWALL | 7
44731 | 44728 | 03-1900 | OG8 CLEAN AND PREP FOR POUR - STAIR FOUNDATION | 4.5
44731 | 44728 | 03-1900 | SITE8 POUR WALL/CONDUIT ENCASEMENT/GRADE BEAM AND PAD | 7
44731 | 44728 | 03-1900 | OG10 FINISH REBAR (POUR CONCRETE) | 3
44731 | 44728 | 03-1900 | SG7 POUR PIT BASES | 3
44731 | 44728 | 03-1900 | OG8 POUR STAIN FOUNDATION | 4
44731 | 44728 | 31-1100 | SG5 STOCKPILE SAND FOR PIPE BACKFILL | 3
44731 | 44728 | 31-1400 | SG7 BACKFILL - COMPACT DINT FOR INSPECTION | 5.5
44731 | 44728 | 31-2200 | SG2 BACKFILL PLUMBING PIPES | 4.5
44731 | 44728 | 33-1100 | SG2 REMOVE EXISTING GAS LNE AND STEAM PIPE (UTILITY DEMO) | 9
44731 | 44728 | 33-2400 | PUMPS | 1
44731 | 44729 | 03-6000 | OG5 INSTALL FRP | 24
44731 | 44729 | 02-6025 | OG5 DEMO BRICK FOR BOND BEAM | 13
44731 | 44729 | 02-6060 | OG4 DEMO WALL AT 1ST FLOOR ROOM | 5
44731 | 44729 | 99-4560 | OG9 HOUSEKEEPING | 5
44731 | 44729 | 99-4560 | SG6 HOUSEKEEPING | 5
44731 | 44729 | 00-0016 | SG6 INSTALL ANGLE AT FAÇADE | 17
44731 | 44729 | 02-6060 | OG6 DEMO AT OFFICES | 5
44731 | 44729 | 02-6025 | SG5 DEMO AROUND BUILDING BRICK OUTSIDE | 7
44731 | 44729 | 31-1100 | SG6 BACKFILLHOLE 1ST FLOOR FIRE PIPE | 11
44731 | 44729 | 33-2400 | SG6 PUMP WATER FROM SHAFT | 6
44731 | 44729 | 07-6020 | OG8 PREP SHAFT | 12.5
44731 | 44729 | 04-6120 | SG4 OG10 LOAD NEEDED FOR FAXA | 6
44731 | 44729 | 99-4560 | SG4 SG5 SG6 PICK UP GARBAGE | 3
44731 | 44729 | 32-6000 | PICK UP MACHINE FROM NEWARK | 1
44731 | 44729 | 33-3100 | OG6 BREAKDOWN AND STACK TRENCH BOXES | 3.5
44731 | 44729 | 33-3100 | OG6 TEST PIT AND EXPLORE AROUND CATCH BASINS IN SEARCH OF PIPE | 12
44731 | 44729 | 33-2600 | OG6 MODIFY MANHOLES TO ACCOMMODATE EXISTING PIPE | 9
44731 | 44729 | 03-2500 | SG7 FINISH BRICKSHELF + COLUMN BOX OUT | 28
44731 | 44729 | 03-1000 | SG7 FORM INSIDE PIT WALLS | 10
44731 | 44729 | 99-4560 | SITE8 REBAR CAPS | 4
44731 | 44729 | 99-4560 | SG5 REBAR CAPS | 4
44731 | 44729 | 99-4560 | SG4 REBAR CAPS | 3
44731 | 44729 | 03-2300 | SG4 THRUST BLOCK | 10
44731 | 44729 | 03-2300 | SG5 THRUST BLOCK | 14
44731 | 44729 | 32-6520 | SG5 FIX WALKWAY | 10.5
44731 | 44729 | 03-1900 | OG10 PREP STAIR LANDING FOR CONCRETE | 5
44731 | 44729 | 99-4560 | LOCK ALL GATES | 0.5
44731 | 44729 | 31-1500 | SG7 COMPACT DINT/INSTALL STONE | 13.5
44731 | 44729 | 31-1100 | SG5 BACKFILL FLOODWALL BY BLD ENTRANCE/COMPACT FOR INSPECTION | 16
44731 | 44729 | 99-4560 | OG10 REBAR INSPECTION/INSTALL AND FIX REBAR/TESR RUN CONCRETE BUCKET FOR LANDING POUR | 5
44731 | 44729 | 31-1100 | OG4 BACKFILL MASONRY SHELF - PREP FOR CONCRETE POUR | 9
44731 | 44729 | 99-4560 | TAKE COMPANY VEHICLE FOR MAINTENANCE | 1
44731 | 44729 | 32-6510 | FIX AND INSTALL WHITE NETTING | 17
44731 | 44729 | 07-1100 | SG7 FOAM + V BARRIER | 5
44731 | 44729 | 33-2400 | PUMPS | 2
44724 | 44718 | 31-2200 | SG7 BACKFILL ELECTRIC CONDUIT | 21
44724 | 44718 | 33-3100 | OG2 STEAM EXCAVATION WITH TRUCK | 8
44724 | 44718 | 33-3100 | OG6 COMPLETE ELECTRIC TRENCH BACKFILL/REMOVE TRENCH BOXES/REOPEN WALKWAY | 29
44724 | 44718 | 33-3100 | SITE8 COMPLETE ELECTRIC TRENCH ON PARKING LOT SIDE/BACK FILL INSIDE BUILDING | 8
44724 | 44718 | 33-6010 | SG5 WELKIN INSTALL UG PIPE SG4 TO SG5 - MACHINE NEEDED | 2.5
44724 | 44718 | 31-1820 | SG7 BURN OUT SHEETING | 1
44724 | 44718 | 31-1820 | SITE8 BURN PILE | 0.5
44724 | 44718 | 99-4560 | SG7 ENY STRINGER DELIVERY | 2
44724 | 44718 | 31-2200 | OG6 LOAD HNS TRUCK TO SG7 BACKFILL | 3
44724 | 44718 | 33-6010 | OG8 LULL NEEDED - WELKIN | 5
44724 | 44718 | 03-1800 | SG5 UNLOAD FLOOD BARRIER | 1
44724 | 44718 | 32-6000 | SG3 SAWCUT | 1
44724 | 44718 | 02-2300 | OG4 CLEAN BASEMENT OF WATER (TANK ROOM) | 3.5
44724 | 44718 | 02-2300 | OG2 CLEAN BASEMENT | 3.5
44724 | 44718 | 32-6000 | SG6 CUT (2) PENETRATIONS | 2
44724 | 44718 | 02-3000 | SG3 POE | 6
44724 | 44718 | 03-6000 | OG4 FRP | 10
44724 | 44718 | 03-6000 | OG1 FRP | 18
44724 | 44718 | 32-6000 | OG1 CUT SLABS | 8
44724 | 44718 | 07-6020 | OG8 SCARIFY SHAFT | 18
44724 | 44718 | 99-4560 | SG6 CLEAN 1ST AND 2ND FLOOR ROOF | 8
44724 | 44718 | 03-1400 | OG4 DRILL FOR MASONRY WALL | 8.5
44724 | 44718 | 02-2300 | SG1 CLEAN BASEMENT | 3
44724 | 44718 | 03-1000 | SITE8 CLOSE UP FORMS | 41
44724 | 44718 | 03-1000 | SG6 RAISE BAKER SCAFFOLD IN PLUMBING SHAFT | 3
44724 | 44718 | 03-2300 | SG1 BUILD BULKHEAD IN BASEMENTFOR ELECTRIC CONDUIT | 18
44724 | 44718 | 03-2300 | SG7 FINISH DUCTBANK | 18.5
44724 | 44718 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44724 | 44719 | 03-2300 | SG7 POUR DUCTBANK 1 EA THRUST BANK | 25
44724 | 44719 | 03-2100 | SG1 POUR TEMPORARY RAMP - FRONT BLD ENTRANCE | 12
44724 | 44719 | 31-1400 | SITE8 BACKFILL INSIDE BLD | 9.5
44724 | 44719 | 99-4560 | SG7 CLEAN SITE | 3
44724 | 44719 | 31-2200 | OG2 STEAM EXCAVATION W/VAC TRUCK AND MACHINE | 24
44724 | 44719 | 04-6120 | OG8 OG9 LULL NEEDED FOR FAXA (FAXA CODE) | 5.5
44724 | 44719 | 26-6030 | OG10 LULL NEEDED FOR FSE | 3
44724 | 44719 | 33-1000 | OG2 SUPPORT EXISTING UTILITY STEAMPIPE | 1.5
44724 | 44719 | 33-6010 | WELKIN SUPPORT | 8
44724 | 44719 | 33-2400 | PUMPS | 11
44724 | 44719 | 03-6000 | OG4 FRP | 9
44724 | 44719 | 03-6000 | OG1 FRP | 17
44724 | 44719 | 02-3000 | SG3 CUT ELECTRIC POE | 17
44724 | 44719 | 03-1400 | OG4 DRILL FOR MASONRY SHELF AND FINISH OG3 | 17
44724 | 44719 | 02-2300 | OG8 WASH DOWN SHAFTAND PUMP WATER FROM BOTTOM OF SHAFT | 17
44724 | 44719 | 02-2300 | SG4 CLEAN PUMP PIT (BASE MAINT) | 5
44724 | 44719 | 99-4560 | OG8 CLEAN ON 2ND FLOOR | 9
44724 | 44719 | 99-4560 | SG6 CLEAN 1ST FLOOR | 5.5
44724 | 44719 | 03-1300 | SITE8 FINISH CLOSING UP WALL + PIERS | 16
44724 | 44719 | 03-1300 | SITE8 SET BOLT PATTERNS | 32
44724 | 44719 | 02-6060 | SG4 BUILD TEMP WALL ON 2ND FLOOR | 15.5
44724 | 44719 | 03-1500 | OG3 BRICK SHELF + CLOSE UP WINDOWS | 19
44724 | 44719 | 03-2500 | OG3 BRICK SHELF + CLOSE UP WINDOWS | 22
44724 | 44719 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44724 | 44720 | 03-1000 | SITE 8 FINISH FORMS FOR POUR | 5
44724 | 44720 | 03-1000 | SITE8 STRIP FORMS IN SHAFT FOR PLUMBING PIPE | 9
44724 | 44720 | 03-1500 | OG3 WINDOWS | 55
44724 | 44720 | 02-6060 | SG4 PUT DOOR ON TEMP WALL (2ND FL DEMO) | 5
44724 | 44720 | 03-1000 | OG10 PAD IN SHAFT | 13
44724 | 44720 | 03-1000 | OG8 STRIP DUMMY DECK | 26
44724 | 44720 | 02-6060 | SG4 DEMO CMU WALL | 12
44724 | 44720 | 02-3000 | SG6 CORE 8" HOLE ON TANK ROOM | 4
44724 | 44720 | 99-4560 | OG8 CLEAN AROUND BUILDING | 16
44724 | 44720 | 02-3000 | SG3 CUT ELECTRIC POE | 16
44724 | 44720 | 02-2300 | SG3 CLEAN BASEMENT WATER | 6
44724 | 44720 | 02-2300 | SG4 CLEAN BASEMENT WATER | 2
44724 | 44720 | 02-6060 | SG3 DEMO WALL ON 2ND FLOOR | 6
44724 | 44720 | 99-4560 | OG9 CLEAN BY BUILDING | 2
44724 | 44720 | 03-6000 | OG4 FRP | 24
44724 | 44720 | 03-1900 | OG8 PATCH HOLES REMOVE SCAFFOLDING (CONCRETE NEW BUIDINGS) | 8
44724 | 44720 | 04-6120 | SG6 OG8 LOAD NEEDED | 5
44724 | 44720 | 99-4560 | OG8 CLEAN GARBAGEBY BUILDING | 5
44724 | 44720 | 02-2100 | SG4 LOAD CONTAINER BOX (UNLOAD NAVILLUS CONTAINER) | 7.5
44724 | 44720 | 31-1400 | SG7 BACKFILL FOOT PRINT OF BLD | 22
44724 | 44720 | 03-1800 | OG6 UNLOAD REBAR DELIVERY | 9
44724 | 44720 | 31-1100 | OG3 BACKFILL MASONRY SHELF | 7
44724 | 44720 | 31-1000 | OG3 PREP FOR SUBGRADE INSPECTION | 3.5
44724 | 44720 | 33-6010 | OG9 PLACE PIPE IN TRENCH FOR WELKIN/NEED MACHINE ALL DAY | 8.5
44724 | 44720 | 03-1900 | SITE8 POUR WALLS AND PIERS | 6
44724 | 44720 | 31-2200 | OG6 LOAD OUT MATERIAL TO OG3 & OG7/HNS TRUCK ON SITE | 20
44724 | 44720 | 99-4560 | SG7 CLEAN SITE | 6.5
44724 | 44720 | 07-6110 | SG5 UNLOAD MATERIAL FOR NAVILLUS | 2
44724 | 44720 | 03-1400 | SITE8 DRILLING DOWELS FOR GRADE BEAM | 2.5
44724 | 44720 | 31-1830 | SITE8 GATHER MATERIAL AND PRECUT LUMBER FOR LAGGING | 4
44724 | 44720 | 33-2400 | PUMPS | 1
44724 | 44721 | 31-2200 | SG6 BACKFILL SOUTHSIDE OF BLD/HNS ON SITE MOVING MATERIAL | 4.5
44724 | 44721 | 31-1400 | SG7 BACKFILL FOOTPRINT OF BLD//HNS ON SITE MOVING MATERIAL | 4.5
44724 | 44721 | 31-1500 | OG10 PREP FOR SLAB INFILL/INSTALL FOAM/STEGO WRAP | 5
44724 | 44721 | 31-2200 | OG4 BACKFILL TRENCH FOR CHAS INSTALL | 5
44724 | 44721 | 31-1100 | OG3 BACKFILL STAYFORM FOR FLOODWALL FOOTING/PREP FOR POUR | 3.5
44724 | 44721 | 31-1100 | OG5 BACKFILL STAYFORM FOR FLOODWALL FOOTING/PREP FOR POUR | 3.5
44724 | 44721 | 33-6010 | OG9 WELKIN NEED MACHINE FOR PIPE INSTALL ON TRENCH | 4
44724 | 44721 | 31-1830 | SITE8 DIG OUT AND LAG SIDEWALK FOR PLUMBING PIPE | 15
44724 | 44721 | 31-1400 | SITE8 BACKFILL INSIDE BLD FOR FSE CONDUIT INSTALL | 5
44724 | 44721 | 03-1400 | OG4 DOWEL FOR MASONRY SHELF | 11.5
44724 | 44721 | 32-6510 | OG4 OG5 OG6 REPAIR AND INSTALL WHITE NETTING | 17
44724 | 44721 | 99-4560 | SG6 OG8 PICK UP GARBAGE | 2
44724 | 44721 | 33-6010 | WELKIN NEED LULL ON ITS YARD | 1
44724 | 44721 | 99-4560 | OG9 VITAL NEED LULL | 2
44724 | 44721 | 99-4560 | OG9 STEEL DELIVERY LULL NEEDED | 2
44724 | 44721 | 32-6520 | SG2 INSTALL TEMP FENCE | 33
44724 | 44721 | 32-6000 | OG1 CUT SLAB PENETRATION | 17
44724 | 44721 | 03-6000 | OG5 FRP | 17
44724 | 44721 | 99-4560 | OG8 CLEAN | 9
44724 | 44721 | 02-6060 | OG6 LOAD OUT DEBRI FROM 2ND FLOOR APT (2ND FLOOR DEMO) | 5
44724 | 44721 | 02-2300 | SG5 CLEAN BASEMENT WATER | 5
44724 | 44721 | 99-4560 | OG3 CLEAN GARBAGE | 5
44724 | 44721 | 99-4560 | OG8 CLEAN GARBAGE | 5.5
44724 | 44721 | 99-4560 | OG8 PICK UP GARBAGE | 2.5
44724 | 44721 | 99-4560 | SG6 PICK UP GARBAGE | 2.5
44724 | 44721 | 99-4560 | SG7 PICK UP GARBAGE | 2
44724 | 44721 | 99-4560 | OG3 PICK UP GARBAGE | 2
44724 | 44721 | 99-4560 | OG6 PICK UP GARBAGE | 1
44724 | 44721 | 03-1000 | SITE8 STRIP WALLS, PIERS + PLUMBING SHAFT | 34
44724 | 44721 | 03-1100 | OG3 STAY FORM FOR FLOODWALL FOOTING | 20
44724 | 44721 | 03-1500 | OG3 FINISH WINDOWS FOR POUR | 10
44724 | 44721 | 32-6520 | OG10 HELP SERGIO WITH FENCE | 2
44724 | 44722 | 31-1400 | SG7 BACKFIL/COMPACT FOOTPRINT OF BLD | 17
44724 | 44722 | 03-2100 | OG3 OG4 OG5 POUR FLOODWALL FOOTINGS | 16
44724 | 44722 | 03-2500 | OG3 POUR CONCRETE AT MASONRY SHELF | 12.5
44724 | 44722 | 31-2200 | OG2 BACKFILL BY FSP | 2
44724 | 44722 | 03-1400 | OG4 DOWEL FOR MASONRY SHELF | 13.5
44724 | 44722 | 99-4560 | OG1 CLEAN AFTER FSE SWITCH GEAR DELIVERY | 4.5
44724 | 44722 | 32-6510 | FIX AND INSTALL WHITE NETTING (WHITE MESH INSTALL) | 17
44724 | 44722 | 04-6120 | LULL NEEDED OG2/OG8 FOR FAXA (FAXA CODE) | 4
44724 | 44722 | 26-6030 | LULL NEEDED OG1 FOR FSE. SWITCH GEAR DELIVERY | 4
44724 | 44722 | 99-7200 | HOLIDAY PAY | 8
44724 | 44722 | 32-6520 | SG1 INSTALL TEMP FENCE | 33
44724 | 44722 | 02-3000 | OG1 CUT SLABS PENETRATIONS | 17
44724 | 44722 | 03-6000 | OG5 FRP | 18
44724 | 44722 | 99-4560 | DROP FIRE EXTINGUISHER ON EVERY 2ND FLOOR BUILDING | 5
44724 | 44722 | 02-2300 | OG9 PUMP DOWN SHAFT | 5
44724 | 44722 | 02-2300 | SITE8 PUMP DOWN SHAFT | 5
44724 | 44722 | 99-4560 | SG7 CLEAN GARBAGE | 5
44724 | 44722 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOORS | 17.5
44724 | 44722 | 04-6120 | OG2 AND OG8 LOAD NEEDED (FAXA) | 5
44724 | 44722 | 99-4560 | OG6 OG8 OG9 SG7 CLEAN GARBAGE | 5
44724 | 44722 | 03-2300 | SITE8 DUCT BANK | 23
44724 | 44722 | 03-1000 | SITE8 FINISH STRIPPING | 6
44724 | 44722 | 03-1000 | SITE8 FORM PADIN PLUMBING SHAFT | 10
44724 | 44722 | 99-4560 | SITE8 SITE MAINTENANCE (GUARDRAIL) | 7
44724 | 44722 | 03-1500 | OG4 FORM WINDOWS | 29
44724 | 44722 | 03-1000 | SG7 FORM 2 PLUMBING PITS SLABS | 11
44724 | 44722 | 99-4560 | OG8 SAFETY (HANDRAIL) | 7
44724 | 44722 | 03-1000 | SG7 SLAB SLIDES | 11.5
44717 | 44711 | 99-7200 | HOLIDAY PAY | 68
44717 | 44711 | 04-6120 | FAXA BACKCHARGE | 4
44717 | 44712 | 03-6000 | OG4 FRP INSTALL | 17
44717 | 44712 | 03-6000 | OG1 FRP INSTALL | 32.5
44717 | 44712 | 02-3000 | SG1 CUT PENETRATIONS | 7
44717 | 44712 | 02-3000 | OG2 CUT SLAB PENETRATIONS | 11
44717 | 44712 | 04-6120 | OG8 LOAD | 4
44717 | 44712 | 04-6120 | OG9 OG8 SG6 LOAD (FAXA CODE) | 4
44717 | 44712 | 99-4560 | OG8 CLEAN GARBAGE | 1
44717 | 44712 | 99-4560 | OG8 CLEAN OUTSIDE BUILDING | 8.5
44717 | 44712 | 33-3100 | SG4 SG5 CLEAN TRENCH AND FLOODWALL | 8.5
44717 | 44712 | 33-1000 | SG5 PUMP DOWN BASEMENT AND SANITIZE (BASEMENT MAINT) | 8.5
44717 | 44712 | 03-1400 | OG5 DRILL AND DOWEL FOR MASONRYSHELF | 5
44717 | 44712 | 03-1400 | OG3 FINISHING DOWELS ON OG3 | 5
44717 | 44712 | 00-0025 | GOING AROUND MAKING HOLES FOR INSPECTOR | 1.5
44717 | 44712 | 99-4560 | PICK UP TOOLSA ALREADY FIX NEWARK | 1
44717 | 44712 | 03-1400 | OG5 DRILL FOR MASONRY SHEF | 17.5
44717 | 44712 | 31-1000 | OG4 COMPACT AL FLOODWALL FOOTING/SUBGRADE IN PECTION | 2
44717 | 44712 | 02-1900 | SG5 REMOVE ASPHALT AND CONCRETE CURB WALL/3 - CONTAINERS LOAD OUT | 35
44717 | 44712 | 31-2200 | OG5 BACKFILL ELECTRIC TRENCH | 3
44717 | 44712 | 99-4560 | OG8 CLEAN AND LEVEL AREA | 3
44717 | 44712 | 32-6620 | OG5 TREE REMOVAL AND LOADOUT (1 CONTAINER) | 12
44717 | 44712 | 32-6620 | OG2 TREE REMOVAL AND LOADOUT (1 CONTAINER) | 12
44717 | 44712 | 33-2500 | SG5 SHAKE OUT DRAINAGE MATERIAL | 3
44717 | 44712 | 33-3100 | SG3 REMOVE TRENCH BOX | 2.5
44717 | 44712 | 32-6000 | COVER COMPRESSION, CHOP @ POE SG1 (SAW CUT) | 1
44717 | 44712 | 33-2400 | COVER PUMPS | 1
44717 | 44712 | 03-1000 | SITE8 STAYFORM FOOTINGS | 44
44717 | 44712 | 03-1000 | SG7 STAY FORM DUCT BANK | 36.5
44717 | 44712 | 99-4560 | LOCKGATES (SITE MAINT) | 0.5
44717 | 44713 | 02-1900 | SG5 LOAD OUT ASPHALT/3 CONTAINERS | 9
44717 | 44713 | 33-3100 | OG5 EXCAVATE STEAM TRENCH TO OG6/INSTALL TRENCH BOXES/HNS TRUCK ON SITE MOVING MATERIAL | 42
44717 | 44713 | 07-6020 | OG8 SCARIFY SHAFT FOR WATERPROOFING | 1.5
44717 | 44713 | 33-2500 | SG5 INSTALL DRAINAGE | 3.5
44717 | 44713 | 33-3100 | SG3 BREAKDOWN AND MOVE TRENCH BOXES TO OG5 | 10
44717 | 44713 | 33-2400 | COVER PUMPS | 1
44717 | 44713 | 33-2400 | SG2 SAW CUT POE - COVER COMPRESSOR | 1
44717 | 44713 | 02-3000 | SG2 CUT POE | 17
44717 | 44713 | 02-3000 | OG1 CUT SLABS ON 2ND FLOOR | 17
44717 | 44713 | 03-6000 | OG4 INSTALL FRP | 16.5
44717 | 44713 | 07-6020 | OG8 SCARIFY SHAFT FOR WATERPROOFING | 16.5
44717 | 44713 | 03-6000 | OG1 INSTALL FRP | 17
44717 | 44713 | 99-4560 | SG6 GARBAGE REMOVAL 1ST AND 2ND FLOOR | 16.5
44717 | 44713 | 99-4560 | OG8 CLEAN AROUND BUILDING | 16.5
44717 | 44713 | 04-6120 | OG8 LOAD NEEDED (FAXA) | 1.5
44717 | 44713 | 04-6120 | SG6 LOAD NEEDED (FAXA) | 3
44717 | 44713 | 04-6120 | OG9 LOAD NEEDED (FAXA) | 3
44717 | 44713 | 33-3100 | SG6 BACKFILL BEHIND (UTILITY TRENCH) | 3
44717 | 44713 | 33-6010 | OG8 LOAD 2ND FLOOR (WELKIN SUPPORT) | 2
44717 | 44713 | 03-1000 | SITE 8 STRIP FORMS | 44
44717 | 44713 | 03-1000 | SITE8 FINISH FOOTINGS | 8
44717 | 44713 | 03-1100 | OG4 FORM FLOOD WALL FOOTING | 4.5
44717 | 44713 | 03-2300 | SG7 FINISH DUCT BANK | 24
44717 | 44713 | 99-4560 | LOCK GATES - SITE MAINT | 0.5
44717 | 44714 | 03-6000 | OG1 FRP | 17
44717 | 44714 | 02-3000 | OG1 CUT SLAB PENETRATION AT 2ND FLOOR | 17
44717 | 44714 | 02-2300 | OG2 CLEAN BASEMENT | 10
44717 | 44714 | 03-6000 | OG4 FRP | 17
44717 | 44714 | 99-4560 | SG6 CLEAN AROUND OG8 CLEAN OUTSIDE | 9
44717 | 44714 | 99-4560 | OG4 OG5 GO AROUND WITH INSPECTOR (BRICK WALLS - SITE MAINT) | 3
44717 | 44714 | 00-0019 | OG3 MODIFY FENCE (FENCE CO) | 11
44717 | 44714 | 02-2300 | OG3 CLEAN BASEMENT WATER | 12.5
44717 | 44714 | 33-6010 | SG6 OG8 OG9 LOAD NEEDED (4HR FAXA/4HR WELKIN) | 4
44717 | 44714 | 04-6120 | SG6 OG8 OG9 LOAD NEEDED (4HR FAXA/4HR WELKIN) | 4
44717 | 44714 | 31-2200 | OG5 EXCAVATE STEAM TO OG6 - HNS TRUCK ON SITE MOVING MATERIAL | 34
44717 | 44714 | 31-1400 | OG10 PREP FOR FLOW FILL POUR (BACKFILL 2 YDS) | 5
44717 | 44714 | 31-2200 | OG4 START BACKFILL STEAM TRENCH TO OG3 | 3
44717 | 44714 | 03-1900 | SITE8 POUR FOOTINGS (62 YARDS) | 20
44717 | 44714 | 07-6110 | SITE8 INSTALL FOAM ON PLUMBING SHAFT/PREP FOR FLOWFILL | 7
44717 | 44714 | 99-4560 | SITE 8 CLEAN AREA | 4
44717 | 44714 | 33-3100 | SG3 BREAKDOWN AND MOVE TRENCH BOX TO OG5 | 2
44717 | 44714 | 33-3100 | OG5 INSTALL TRENCHB BOX/LAGGING/HANDRAIL | 6.5
44717 | 44714 | 33-2500 | SG5 INSTALL DRAINAGE | 4
44717 | 44714 | 33-1000 | OG5 SUPPORT EXISTING WATER LINES | 4
44717 | 44714 | 33-2400 | COVER PUMPS | 2
44717 | 44714 | 33-2400 | COVER COMPRESSOR - SAW CUT AT SG2 | 1
44717 | 44714 | 03-1000 | SITE8 BRACE FOOTING | 16
44717 | 44714 | 03-1000 | SITE8 STRIP FORMS | 32
44717 | 44714 | 07-6110 | SITE8 STYROFOAM + DRAINAGE BOARD | 8
44717 | 44714 | 03-1100 | OG4 FORM FLOOD WALL FOOTING | 17.5
44717 | 44714 | 03-2300 | SG7 OG6 OG4 FORM 3 THRUST BLOCKS | 12
44717 | 44714 | 99-4560 | OG1 OG2 REBAR CAPS (SAFETY) | 11
44717 | 44714 | 99-4560 | LOCK GATES | 0.5
44717 | 44715 | 03-6000 | OG1 FRP | 17.5
44717 | 44715 | 02-3000 | OG1 CUT SLABS | 17
44717 | 44715 | 02-3000 | SG2 CUT POE | 17
44717 | 44715 | 02-2300 | SG6 PUMP DOWN SHAFT (BASEMENT MAINT) | 9
44717 | 44715 | 33-2400 | SG4 PUMP DOWN BEHIND FLOODWALL | 8.5
44717 | 44715 | 02-2300 | SG5 PUMP DOWN BASEMENT | 10.5
44717 | 44715 | 07-6020 | OG8 SCARITY SHAFT FOR WATERPROOFING | 14
44717 | 44715 | 04-6120 | SG6 LOAD NEEDED FOR FAXA (FAXA CODE) | 5
44717 | 44715 | 26-6030 | OG8 LOAD NEEDED FOR FSE | 2
44717 | 44715 | 33-6010 | OG8 LOAD NEEDED FOR WELKIN | 2
44717 | 44715 | 03-1000 | SITE8 STRIP FOOTINGS | 7
44717 | 44715 | 03-1000 | SITE8 LAYOUT SHOES FOR PIERS + WALL | 16
44717 | 44715 | 03-1000 | SITE8 START FORMING | 16
44717 | 44715 | 03-2300 | SG7 FINISH THRUST BLOCK | 5
44717 | 44715 | 03-1100 | OG4 FINISH FOOTING FOR FLOOD WALL | 6
44717 | 44715 | 03-1000 | OG8 STRIP COLUMN | 4
44717 | 44715 | 03-1000 | OG8 STAIR FOOTING (DIGGING) | 10
44717 | 44715 | 02-6060 | OG4 + OG5 INSTALL LARRY LOCKS | 4
44717 | 44715 | 02-6060 | OG4 + OG5 PUT ON LOCKS | 1.5
44717 | 44715 | 99-4560 | OG6 SAFETY CABLE | 3
44717 | 44715 | 99-4560 | OG10 HANDRAIL ON STAIRS | 4
44717 | 44715 | 99-4560 | OG1 COVER HOLES ON FLOOR (2ND FLOOR APARTMENT) | 4
44717 | 44715 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44717 | 44715 | 31-2200 | OG5 EXCAVATE STEAM TRENCHTO OG6/HNS TRUCK ON SITE MOVING MATERIAL TO OG3 | 21.5
44717 | 44715 | 31-1000 | OG3 EXCAVATE FOR FLOODWALL/ 1 - CARDELLA LOADOUT - CONCRETE | 13.5
44717 | 44715 | 31-2200 | OG3 BACKFILL STEAM TRENH - BOTTOM PIPE ONLY | 13.5
44717 | 44715 | 31-1400 | SITE8 POUR FLOWFILL - 154 YARDS | 14
44717 | 44715 | 33-3100 | SITE8 EXCAVATE ELECTRIC TRENCH/CLEAN AREA BEFORE DIG | 8
44710 | 44704 | 03-1400 | OG1 COMPLETE DOWELS FOR MASONRY SHELF | 5
44710 | 44704 | 03-1400 | OG3 DRILL AND DOWELS FOR MASONRY SHELF | 13
44710 | 44704 | 02-2100 | OG5 DEMO CURB AND PAVEMENT AT FRONT + BLD/ 2 EA LIVE LOADS CONCRETE DEBRIS | 7
44710 | 44704 | 31-1000 | OG5 EXCAVATE FOR MASONRY SHELF AND FLOODWALL/HNS TRUCK ON SITE MOVING MATERIAL | 19
44710 | 44704 | 31-1000 | OG4 CLEAN AREA /MOVE MATERIAL BEFORE DIGGING | 4
44710 | 44704 | 31-1000 | OG4 EXCAVATE FOR MASONRY SHELF/HNS ON SITE MOVING MATERIAL | 8
44710 | 44704 | 31-2200 | OG6 BACKFILL DUCTBANK | 12
44710 | 44704 | 04-6120 | SG6 OG8 FAXA NEED LULL | 1.5
44710 | 44704 | 99-4560 | VITAL PUMP DELIVERY | 2
44710 | 44704 | 33-2400 | COVER PUMPS | 1
44710 | 44704 | 02-6015 | DEMO VENTS/WINDOWS | 1
44710 | 44704 | 99-4560 | TAMP SITE 8 FOR INSPECTION/CLEAN AREA | 7
44710 | 44704 | 31-1820 | SG7 CUT SHEET PILE/GRADE AREA | 6
44710 | 44704 | 33-1000 | OG8 DIG FOR ABATEMENT/BUILD PLATFORM FOR FIRE DEPARTMENT | 5.5
44710 | 44704 | 03-1000 | SITE 8 SET FORMS FOR CARPENTERS/MOVE BOXES FOR ELECTRICIANS | 7
44710 | 44704 | 03-1000 | SITE 8 FORM WALLS | 50.5
44710 | 44704 | 03-2300 | SG3 STAY FORM THRUST BLOCK | 8
44710 | 44704 | 03-2300 | SG8 STAY FORM THRUST BLOCK | 7
44710 | 44704 | 99-4560 | OG9 SAFETY (ADD HANDRAIL/TOP RAIL) | 4
44710 | 44704 | 99-4560 | OG8 SAFETY (PLYWOOD OVER HOLES, 2ND FL) | 3
44710 | 44704 | 03-1500 | OG1 WINDOWS | 8
44710 | 44704 | 02-3000 | OG2 CUT SLABS | 18
44710 | 44704 | 99-4560 | CLEAN/SITE MAINT | 18
44710 | 44704 | 03-6000 | FRP INSTALL | 29.5
44710 | 44704 | 33-6010 | CLEAN/EXPOSE JOINTS @ PLUMBING PIPE FOR INSULATION INST (WELKIN) | 3
44710 | 44704 | 02-2300 | BASEMENT MAINT | 3
44710 | 44704 | 32-6510 | INST WHITE MESH ON FENCE | 1
44710 | 44705 | 03-1800 | SG7 REBAR DELIVERY | 3.5
44710 | 44705 | 31-1000 | OG5 EXCAVATE FOR MASONRY SHELF AND COMPACT | 12
44710 | 44705 | 33-3100 | OG2 EXCAVATE STEAM RUN TO OG3/ 2 LIVE LOADS CONTAINERS - CONCRETE/HNS TRUCK ON SITE MOVING MATERIAL | 21
44710 | 44705 | 02-2000 | OG4 EXCAVATE FOR MASONRY SHELF/HNS TRUCK ON SITE MOVING MATERIAL | 27
44710 | 44705 | 02-2000 | OG8 (1) LIVE LOAD CONTAINER - GARBAGE/CLEAN AREA | 4
44710 | 44705 | 02-1700 | SG7 SITE8 (1) LIVE LOAD CONTAINER - STEEL DEBRIS | 3
44710 | 44705 | 03-1000 | OG8 SUPPORT FORMWORK | 5
44710 | 44705 | 03-1400 | OG3 DRILL AND DOWEL FOR MASONRY SHELF | 33
44710 | 44705 | 33-1000 | MAINT PROT EXIST PUT UTILIRY | 4.5
44710 | 44705 | 33-2400 | COVER FIREPROOFER PUMP (SIG) | 1
44710 | 44705 | 03-1800 | DROP IN REBAR | 2
44710 | 44705 | 33-2400 | COVER PUMPS | 1
44710 | 44705 | 03-1000 | SITE8 FORM WALLS | 53
44710 | 44705 | 03-1500 | OG1 CLOSE WINDOWS | 9.5
44710 | 44705 | 03-2300 | SG3 TRUST BLOCK | 9
44710 | 44705 | 03-2300 | SG7 THRUST BLOCK | 9
44710 | 44705 | 99-4560 | SAFETY - OG9/OG9 SG6 TOE BOARDS + NETTING | 8
44710 | 44705 | 03-6000 | OG1 FRP INSTALL | 15.5
44710 | 44705 | 99-4560 | OG10 CLEAN 1ST FLOOR AND 2ND FLOOR | 17
44710 | 44705 | 02-3000 | SITE8 CORE FOR CHAS (2) | 7
44710 | 44705 | 03-1500 | OG2 PATCH WINDOWS | 7
44710 | 44705 | 03-2100 | OG6 POUR FLOOR DRAINS | 5
44710 | 44705 | 02-3000 | OG2 CUT SLABS CLEAN UP | 17
44710 | 44705 | 00-0025 | SG7 MAKE HOLES WITH INSEPCTOR | 7
44710 | 44705 | 32-6520 | SG6 FIX FENCE | 3.5
44710 | 44705 | 04-6120 | LOAD OG8 AND OG9 (FAXA) | 2
44710 | 44705 | 02-2300 | OG2 CLEAN UP DEBRIS | 1
44710 | 44705 | 02-2300 | OG3 CLEAN UP DEBRIS | 1
44710 | 44705 | 26-6030 | OG5 LOAD SWITCH GEAR FOR FSE | 5
44710 | 44706 | 04-6120 | OG8 OG10 LOAD BLOCK FOR FAXA (FAXA CODE) | 3
44710 | 44706 | 04-6120 | OG9 CLEAN DEBRI (FAXA CODE) | 1
44710 | 44706 | 99-4560 | OG8 CLEAN GARBAGE | 2.5
44710 | 44706 | 99-4560 | SG6 LOAD TRUCK | 2.5
44710 | 44706 | 03-6000 | OG1 INSTALL FRP | 17
44710 | 44706 | 02-3000 | OG4 CUT PEN FOR THEMIS | 9
44710 | 44706 | 02-3000 | SG1 CUTE ELECTRIC POE | 9
44710 | 44706 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR | 15
44710 | 44706 | 99-4560 | SG5 CLEAN BY FLOODWALL | 5
44710 | 44706 | 99-4560 | SG6 MOVE HARDWARE FROM SG6 TO OFFICES SG6 | 3
44710 | 44706 | 02-2300 | OG2 PUMP DOWN PIT AREA IN BASEMENT/FIX LEAK PIPE (BASEMENT MAINT) | 8.5
44710 | 44706 | 03-2100 | OG6 POUR DRAIN PIT | 11.5
44710 | 44706 | 02-6000 | OG6 DEMO IN OFFICE | 16.5
44710 | 44706 | 99-4560 | PICK UP 6' PIPE (DRIVING) NATIONAL GRID GAS PIPE/COLD ROLLED BEND) | 2
44710 | 44706 | 31-2200 | SG3 BACKFILL CHAS FROM OG5/HNS ON SITE MOVING MATERIAL | 14
44710 | 44706 | 33-3100 | SG6 EXCAVATE FOR GAS PIPE (NATIONAL GRID RUN) | 3
44710 | 44706 | 31-2200 | OG10 BACKFILL/PREP FOR FLOW FILL/HNS ON SITE MOVING MATERIAL | 2
44710 | 44706 | 31-1400 | OG10 FLOW FILL POUR | 2
44710 | 44706 | 33-3100 | OG2 EXCAVATE/EXPOSE STEAM RUN TO OG3/HNS ON SITE MOVING MATERIAL | 28
44710 | 44706 | 31-1000 | OG4 EXCAVATE FOR MASONRY SHELF | 11.5
44710 | 44706 | 02-2000 | OG4 1 EA LIVE LOAD CONCRETE CONTAINER (CODE FOR DEMO) | 4
44710 | 44706 | 03-1000 | SITE8 SUPPORT FORMWORK | 13
44710 | 44706 | 03-2500 | OG1 INSTALL STAYFORM FOR MASONRY SHELF | 14
44710 | 44706 | 03-1800 | REBAR SUPPORT | 3
44710 | 44706 | 33-2400 | COVER PUMP FOR FIREPROOFER | 1
44710 | 44706 | 33-2400 | COVER PUMPS | 1
44710 | 44706 | 33-1000 | MAINT/PROT EXIST PUT UTILITY (SUPPORT EXISTING STEAM LINE + MISC UTILITIES) | 5.5
44710 | 44706 | 02-6015 | DEMO VENTS | 6
44710 | 44706 | 03-1000 | SITE8 FORMS (PLUMBING SHAFT + WALL) | 101
44710 | 44706 | 03-1000 | SITE8 SCAFFOLDING (POUR CONCRETE) | 11
44710 | 44706 | 03-1000 | SITE 8 TEMPLATES FOR LATHER | 2.5
44710 | 44707 | 02-6015 | SG5 DEMO VENT WINDOW | 10.5
44710 | 44707 | 99-4560 | SG6 CLEAN OUTSIDE & AROUND 1ST AND 2ND FLOOR | 25
44710 | 44707 | 03-6000 | OG2 COMPLETE FRP | 10.5
44710 | 44707 | 03-6000 | OG4 FRP ON 1ST FLOOR | 16.5
44710 | 44707 | 02-3000 | SG1 CUTE ELECTRIC POE | 16.5
44710 | 44707 | 02-3000 | OG4 CURE 5" HOLES | 3.5
44710 | 44707 | 03-6000 | OG1 INSTALL FRP | 10.5
44710 | 44707 | 02-6060 | OG8 CLEAN 2ND FLOOR | 8.5
44710 | 44707 | 31-1300 | SITE 8 LOAD TRUCK WITH STONE (SITE 8 EXCAVATION, 2YDS) | 1.5
44710 | 44707 | 04-6120 | SG6 FAXA INSTALL CMU ON 2ND FL (FAXA CODE) | 4.5
44710 | 44707 | 99-4560 | SG6 PICK UP GARBAGE | 1.5
44710 | 44707 | 33-6010 | OG8 LOAD LEED FOR WELKIN (WELKIN MACHINE SUPPORT) | 2
44710 | 44707 | 33-6010 | OG8 LOAD LEED FOR FSE | 2
44710 | 44707 | 99-4560 | CHECK GATE (MON, TUES, WED) SITE MAINT | 2
44710 | 44707 | 99-4560 | PICK UP CUT MACHINE IN NEWARK | 1
44710 | 44707 | 31-1100 | OG1 BACKFILL STAYFORM/PREP FOR CONCRETE TRUCK ACCESS | 17
44710 | 44707 | 33-3100 | OG2 EXCAVATE/EXPOSE STEAM RUN TO OG3 | 17
44710 | 44707 | 31-1000 | OG4 EXCAVATE FOR FLOODWALL FOOTING | 13
44710 | 44707 | 33-2600 | AREA DRAIN DELIVERY TO OGE | 8.5
44710 | 44707 | 03-2300 | SG3 POUR TRUST BLOCKS | 3
44710 | 44707 | 03-1900 | SITE8 POUR FOUNDATION WALLS/66 YDS | 12
44710 | 44707 | 32-6620 | OG2START REMOVAL OF TREE | 7
44710 | 44707 | 03-2500 | OG1 FINISH STAYFORM FOR MASONRY SHELF | 6
44710 | 44707 | 33-1000 | OG2 SUPPORT EXISTING STEAM PIPE (MAINT/PROT EXIST PUT UTILITY) | 3.5
44710 | 44707 | 02-3000 | COVER COMPRESSOR/CUTE ELECTRIC POE @ SG1 | 1
44710 | 44707 | 03-1900 | PUMP FOR CONCRETE POUR | 15.5
44710 | 44707 | 03-1900 | SITE 8 SCAFFOLDING (POUR CONCRETE) | 15.5
44710 | 44707 | 03-1000 | SITE8 FINISH CLOSING UP (FORMWORK NEW BLD) | 32
44710 | 44707 | 03-1300 | SITE8 BOLT PATTERNS (SET ANCHOR BOLTS) | 20
44710 | 44707 | 03-1500 | OG1 BRICKSHELF + WINDOWS | 20
44710 | 44707 | 03-2500 | OG1 BRICKSHELF + WINDOWS | 18
44710 | 44707 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44710 | 44708 | 02-3000 | SG2 CORE 5" HOLES FOR CHAS | 9
44710 | 44708 | 02-3000 | OG3 CORE 5" HOLES FOR CHAS | 9
44710 | 44708 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOORS | 17
44710 | 44708 | 02-3000 | SG1 CUT FOR POE | 33
44710 | 44708 | 04-6120 | OG9 OG8 LOAD NEEDED FOR FAXA (FAXA CODE) | 5
44710 | 44708 | 99-4560 | OG8 LOAD NEED (SITE MAINT) | 4.5
44710 | 44708 | 03-6000 | OG4 INSTALL FRP | 16
44710 | 44708 | 03-6000 | OG1 INSTALL FRP | 17
44710 | 44708 | 99-4560 | PICK UP MACHINE IN NEWARK (SITE MAINT) | 1
44710 | 44708 | 99-4560 | SG6 SITE8 SG7 CLEAN YODOCKS AND SWEEP | 9
44710 | 44708 | 03-1500 | OG1 FINISH WINDOWS | 24
44710 | 44708 | 03-1500 | OG2 STRIP WINDOWS INSIDE | 26
44710 | 44708 | 03-1100 | OG5 FORM FLOOD WALL FOOTING | 24
44710 | 44708 | 04-6120 | SAFETY ITEMS - NETTING, CABLE + TOE BOARDS (MAINLY OG8 - FAXA WITH DELIVERIES) | 22.5
44710 | 44708 | 03-1500 | OG1 POUR WINDOWS AND MASONRY SHELF | 23.5
44710 | 44708 | 03-2500 | OG1 POUR WINDOWS AND MASONRY SHELF | 28.5
44710 | 44708 | 32-6620 | OG2 TREE REMOVAL | 20
44710 | 44708 | 33-2400 | COVER PUMPS | 1
44710 | 44708 | 33-6010 | OFFLOAD MATERIAL - WELKIN MOBILIZE @ OG8 | 3
44710 | 44708 | 31-1000 | EXCAVATE FOR FLOODWALL FOOTING | 4
44710 | 44708 | 31-2200 | OG10 BACKFILL CHAS | 2
44710 | 44708 | 33-2400 | PUMPS | 1
44703 | 44697 | 31-1830 | SITE8 LAGGING | 8
44703 | 44697 | 99-4560 | SITE 8 HANDRAIL | 4
44703 | 44697 | 03-1100 | SG5 STRIP FLOODWALL | 8
44703 | 44697 | 03-2500 | OG2 BRICKSHELF | 52.5
44703 | 44697 | 99-4560 | LOCKGATES (SITE MAINT) | 0.5
44703 | 44697 | 33-2210 | SG7 EXCAVATE FOR UTILITIES COMING OUT OF BLD | 12
44703 | 44697 | 33-2210 | SG7 COMPLETE EXCAVATION FOR ELECTRIC POE BY SG3 | 4
44703 | 44697 | 03-1400 | OG1 DRILL AND DOWEL FOR MASONRY FOUNDATION | 17.5
44703 | 44697 | 31-2200 | OG5 CONTINUE BACKFILLING STEAM TRENCH/HNS TRUCK ON SITE MOVING MATERIAL | 13
44703 | 44697 | 31-1830 | SITE8 DIG AND LAG. INSTALL STONE/HNS TRUCK ON SITE MOVING MATERIAL | 31
44703 | 44697 | 02-1600 | SGN STOCK PILE MATERIAL FROM SITE8/HNS TRUCK ON SITE MOVING MATERIAL | 9.5
44703 | 44697 | 33-2400 | COVER FIREPROOFERS PUMP | 2
44703 | 44697 | 33-2400 | COVER DEWATERING PUMP | 6
44703 | 44697 | 99-4560 | OG2 PICK UP GARBAGE FROM 2ND FLOOR | 2
44703 | 44697 | 07-6310 | OG8 UNLOAD DELIVERY FOR MATERIALS FOR SIG | 2.5
44703 | 44697 | 04-6120 | OG10 FAXA (FAXA CODE) | 2
44703 | 44697 | 99-4560 | OG6 SG6 OG8 PICK UP GARBAGE FROM BASEMENT | 2.5
44703 | 44697 | 31-1500 | SITE8 BACKFILL WITH BACKING STONE ON SITE8 | 2.5
44703 | 44697 | 99-4560 | SG6 SET PUMP ON SG6 PIT AND CLEAN GARBAGE | 2.5
44703 | 44697 | 02-2300 | SG1 CLEAN GARBAGE FROM BASEMENT AND SET PUMP FOR WELKIN | 2.5
44703 | 44697 | 05-6020 | OG5 COMPLETE GROUT BEAMS | 9
44703 | 44697 | 02-2300 | OG5 BASEMENT DRAINS | 9
44703 | 44697 | 31-2200 | OG5 & OG6 LOAD CEMENT PALETS TO BASEMENT | 5
44703 | 44697 | 32-6000 | SG1 COMPLETE CUTTING SLABS AND MOVE DEBRI | 7
44703 | 44697 | 32-6000 | OG2 CUT SLABS ON 2ND FLOOR | 11
44703 | 44697 | 03-6000 | OG2 FRP IN BASEMENT | 24
44703 | 44698 | 03-6000 | OG2 FINISHING FRP IN BASEMENT | 11.5
44703 | 44698 | 03-6000 | OG1 PREPARE FOR FRP | 7.5
44703 | 44698 | 03-2100 | OG5 POUR FLOOR DRAIN IN COMPACTOR ROOM | 11
44703 | 44698 | 03-2100 | OG6 PREPARE TO POUR DRAINS | 7
44703 | 44698 | 32-6000 | OG2 CUT SLABS PENETRATIONS ON 2ND FLOOR | 17
44703 | 44698 | 31-1700 | SG5 CLEAN AND PUMP OUT BEHIND FLOODWALL | 13
44703 | 44698 | 31-1700 | SG4 CLEAN AND PUMP OUT BEHIND FLOODWALL | 13.5
44703 | 44698 | 99-4560 | SG6 SAFETY (DOB INSPECTION) | 10
44703 | 44698 | 99-4560 | OG10 SAFETY (DOB INSPECTION) | 4.5
44703 | 44698 | 03-1500 | OG2 WINDOWS | 14
44703 | 44698 | 31-1900 | TREE PROTECTION | 8
44703 | 44698 | 31-1830 | LAGGINGS | 8
44703 | 44698 | 99-4560 | OG8 REMOVE HANDRAIL | 13
44703 | 44698 | 03-1000 | SITE8 ASSIST LATHER W/ TEMPLATES | 35
44703 | 44698 | 31-1100 | OG1 COMPACT BEHIND FLOODWALL | 4
44703 | 44698 | 31-1100 | OG2 BACKFILL/COMPACT BEHIND FLOODWALL | 10.5
44703 | 44698 | 31-2200 | OG5 CONTINUE BACKFILLING TO STEAM TRENCH/HNS TRUCK ON SITE MOVING MATERIAL | 8.5
44703 | 44698 | 31-2200 | OG8 BACKFILL DUCTBANKS/HNS TRUCK ON SITE MOVING MATERIAL | 4
44703 | 44698 | 31-1830 | SITE8 DIG AND LAG. INSTALL STONE AND COMPACT/SET REBAR CAGES/SET REBAR TEMPLATES | 34
44703 | 44698 | 03-1400 | OG1 DRILL AND DOWEL FOR MASONRY FOUNDATION | 9
44703 | 44698 | 31-1100 | OG2 BACKFILL FOR MASONRY FOUNDATION | 4.5
44703 | 44698 | 04-6120 | OG10 LULL NEEDED FOR FAXA (FAXA CODE) | 2.5
44703 | 44698 | 31-2200 | SGN LOAD HNS TRUCK FOR BACKFILL - OG2 OG5 OG8 | 12.5
44703 | 44698 | 99-4560 | OGW LIGHT POLE BASE DELIVERY | 6
44703 | 44698 | 33-2400 | PUMPS/DEWATER | 1
44703 | 44698 | 07-6310 | COVER FIREPROOFER PUMP/SPRAYER | 2
44703 | 44698 | 33-2400 | SITE8 DRAINAGE/DEWATERING INSTALL | 13
44703 | 44699 | 03-1900 | SITE8 SET KEYWAY + FIX HANDRAIL (POUR CONCRETE NB) | 6
44703 | 44699 | 03-1100 | SG4 STRIP FLOODWALL | 14
44703 | 44699 | 03-1100 | SG5 STRIP FLOODWALL | 48
44703 | 44699 | 03-1900 | OG10 FIX ELECTRICAL PADS | 6
44703 | 44699 | 03-1900 | SITE8 FIX STAYFORM FOR BACKFILL | 6.5
44703 | 44699 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44703 | 44699 | 03-1400 | OG1 DRILL AND DOWEL FOR MASONRY FOUNDATION | 4.5
44703 | 44699 | 31-2200 | OG10 BACKFILL CHAS | 4
44703 | 44699 | 31-2200 | OG8 BACKFILL DUCTBANK | 8
44703 | 44699 | 03-1900 | OG5 POUR TEMP. WALKWAY/STONE AREA AT FRONT OF BLD | 8
44703 | 44699 | 03-1900 | SITE8 POUR FOOTINGS/CLEAN AREA FOR POUR | 45
44703 | 44699 | 33-2400 | COVER FIRE PROOFER PUMP | 5
44703 | 44699 | 32-6520 | SG4 DEMO FOR FSE AND REMOVE TEMP RAMP | 3
44703 | 44699 | 31-2000 | SG5 SG6 DOG HOLES FOR INSPECTOR | 7
44703 | 44699 | 03-2100 | SG5 POUR FLOODWALL | 3.5
44703 | 44699 | 03-2100 | OG6 POUR FLOOR DRAINS | 14.5
44703 | 44699 | 99-4560 | SG4 CLEAN FLOODWALL AND PUMP | 6.5
44703 | 44699 | 99-4560 | SG6 CLEAN AROUND BUILDING | 3.5
44703 | 44699 | 31-1100 | OG2 BACKFILL FLOOR WALL MASONRY | 5.5
44703 | 44699 | 02-1900 | DEMO AND STONE AREA PREP WALKWAY | 9.5
44703 | 44699 | 99-4560 | OG5 FLAGGING | 16.5
44703 | 44699 | 99-4560 | FLAGGING BY SG5 AND SG4 | 8
44703 | 44699 | 99-4560 | OG8 FLAGGING | 8
44703 | 44699 | 31-2200 | OG8 SG6 LOAD TRUCK | 6.5
44703 | 44699 | 03-2100 | OG6 CONCRETE DELIVERY | 1.5
44703 | 44699 | 04-6120 | FAXA USED LOAD BY SG5 AND OG10 | 5
44703 | 44700 | 02-6015 | OG1 DEMO VENT | 17
44703 | 44700 | 31-2200 | OG5 BACKFILL CHAS | 4.5
44703 | 44700 | 31-2200 | OG8 BACKFILL AT DUCTBANKS/HNS TRUCK ON SITE MOVING MATERIAL FROM SGN TO OG8 | 17
44703 | 44700 | 04-6120 | SG5 OG10 LULL NEEDED FOR FAXA (FAXA CODE) | 2.5
44703 | 44700 | 04-6120 | OG8 LULL NEEDED FOR FAXA - 2 SCISSOR LIFT TO 2ND FLOOR (FAXA CODE) | 1.5
44703 | 44700 | 02-1700 | OG2 REMOVE TEMP. FENCE (FENCO CO.) | 1
44703 | 44700 | 03-1900 | OG2 POUR MASONRY SHELF AND BASEMENT WINDOWS | 25.5
44703 | 44700 | 03-1900 | OG9 OG10 POUR ELECT. PADS ON 2ND FLOOR | 11.5
44703 | 44700 | 31-2100 | SITE8 DIG/LAG MAKE GRADE FOR FOOTING | 26
44703 | 44700 | 07-6310 | COVER FOREPROOFER PUMP/SPRAYER/SIG SUPPORT | 1
44703 | 44700 | 33-2400 | PUMPS/DEWATERING | 1
44703 | 44700 | 03-1900 | SITE8 PACK OUT WALL W/ STAYFOAM (POUR CONCRETE) | 16
44703 | 44700 | 03-1600 | SITE8 SET SHOE FOR WALL (FORM WORK) | 28
44703 | 44700 | 03-1500 | OG1 WINDOWS | 22
44703 | 44700 | 99-4560 | OG2 CLOSE HOLES IN FLOOR | 5.5
44703 | 44700 | 31-2200 | OG10SLAB LEAVE OUT ( BACKFILL) | 17
44703 | 44700 | 99-4560 | LOCK GATES | 0.5
44703 | 44700 | 03-6000 | OG1 INSTALL FRP | 17.5
44703 | 44700 | 32-6000 | OG2 CUT SLABS ON 2ND FLOOR | 17.5
44703 | 44700 | 99-4560 | SG4 CLEAN DEBRI FROM 1ST AND 2ND FLOOR | 6.5
44703 | 44700 | 99-4560 | OG5 CLEAN DEBRI ON 2ND FLOOR | 6
44703 | 44700 | 99-4560 | OG8 CLEAN AROUND BUILDING | 7
44703 | 44700 | 00-0019 | OG4 INSTALL FENCE AND TEMPORARY WALKWAY (FENCE C/O) | 13
44703 | 44700 | 02-1700 | OG2 REMOVE TEMP FENCE/CLOSE TEMP WALKAY (FENCE C/O) | 13
44703 | 44701 | 31-1100 | SG4 BACKFILL BEHIND FLOODWALL AND COMPACT | 12.5
44703 | 44701 | 31-1100 | SG5 BACKFILL BEHIND FLOODWALL AND COMPACT | 12.5
44703 | 44701 | 02-6015 | OG1 DEMO VENT - REMOVE WINDOW | 17.5
44703 | 44701 | 31-2200 | OG1 BACKFILL TEST PITS (CHANGE ORDER?) | 2.5
44703 | 44701 | 31-2000 | OG5 WALKWAY CROSSING FOR CHAS/ROLL OUT BACKFILL AREA | 16.5
44703 | 44701 | 31-2200 | SITE8 DIG-LAG MAKE GRADE FOR REMAINING FOOTINGS/COMPACT SUBGRADE/HANS TRUCK ON SITE | 29.5
44703 | 44701 | 02-2000 | SITE 8 2 EA CARDELLA LOAD OUT - CONCRETE (DEMO) | 2.5
44703 | 44701 | 03-1000 | SITE8 ASSIST CARPENTERS/INSTALL FORMS FOR PLUMBING SHAFT - FOUNDATION WALLS | 4
44703 | 44701 | 33-2400 | COVER FIRE PROOFERS PUMPS | 1
44703 | 44701 | 33-2400 | DEWATERING PUMPS | 1
44703 | 44701 | 03-1000 | SITE8 FORM WALLS + PLUMBING SHAFT | 51
44703 | 44701 | 03-1500 | OG1 WINDOWS | 8
44703 | 44701 | 02-6015 | OG2 STRIP HARDWARE OF WINDOWS | 4
44703 | 44701 | 03-1000 | OG10 STRIP ELECTRICAL PADS | 5
44703 | 44701 | 03-1000 | OG9 STRIP ELECTRICAL PADS | 5
44703 | 44701 | 03-1000 | OG10 FORM WALL FOR SLAB | 14
44703 | 44701 | 99-4560 | SG6 PROTECTION | 1.5
44703 | 44701 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44703 | 44701 | 00-0019 | OG5 INSTALL FENCE ON TEMP WALKWAY (FENCE C/O) | 17.5
44703 | 44701 | 03-6000 | OG1 INSTALL FRP | 17.5
44703 | 44701 | 32-6000 | OG2 CUTE SLAB PENETRAIONS ON 1ST FLOOR | 17.5
44703 | 44701 | 99-4560 | CLEAN AROUND OG5 FOR MACHINE CLEARANCE BY OG8 | 11.5
44703 | 44701 | 31-2000 | OG1 DIP HOLES WITH VACCUM | 5.5
44703 | 44701 | 99-4560 | SG6 CLEAN WATER ON 1ST FLOOR AND CLEAN AROUND OG8 | 11
44703 | 44701 | 99-4560 | SG6 2HR?? | 2
44703 | 44701 | 99-4560 | OG CLEAN?? | 3
44696 | 44690 | 03-1000 | SG7 STRIP GRADE BEAM | 34
44696 | 44690 | 99-4560 | SG7 ORGANIZE SITE | 9
44696 | 44690 | 03-1100 | SG4 CLOSE UP FLOODWALL FORMS | 15
44696 | 44690 | 03-1100 | SG5 FORM BACKSIDE OF FLOODWALL | 21
44696 | 44690 | 03-1900 | OG8 CLOSE P STAIR LANDING FOR CONCRETE + ROOF (POUR CONCRETE) | 14
44696 | 44690 | 03-2300 | OG8 DUCT BANK | 3.5
44696 | 44690 | 99-4560 | LOCK ALL GATES (SITE MAINT) | 0.5
44696 | 44690 | 31-2200 | OG5 BACKFILL TRANCH/HNS ONSITE MOVING MATERIAL | 17
44696 | 44690 | 03-1900 | OG8 POUR ROOF/STAIR LANDINGS AND 2ND FLOOR SLABS (109 YDS) | 87.5
44696 | 44690 | 31-1300 | SITE8 EXCAVATE TO TOP OF WATER TABLE AND LAGGING | 16
44696 | 44690 | 04-6120 | SG6 FAXA NEEDS LULL FOR DELIVERY (FAXA CODE) | 1
44696 | 44690 | 04-6120 | OG10 FAXA NEEDS LULL FOR DELIVERY (FAXA CODE) | 2
44696 | 44690 | 33-2400 | COVER PUMPS | 3
44696 | 44690 | 03-6000 | SG1 FRP INSTALL IN 1ST FLOOR | 17
44696 | 44690 | 02-2300 | SG6 CLEAN SHAFT PIT (BASEMENT MAINT) | 8.5
44696 | 44690 | 99-4560 | SG6 CLEAN 1ST/2ND FLOOR | 5.5
44696 | 44690 | 02-6060 | SG4 CLEAN 2ND FLOOR APARTMENT FOR FSE | 3.5
44696 | 44690 | 31-1830 | SITE8 LAGGING | 2.5
44696 | 44690 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 16.5
44696 | 44690 | 03-6000 | OG3 CUT SLAB AT FRP LOCATIONS | 18
44696 | 44690 | 03-1900 | OG8 CONCRETE | 2
44696 | 44691 | 03-2300 | OG8 DUCT BANK | 36
44696 | 44691 | 99-4560 | OG8 SAFETY (NETTING, CABLE, TOE BOARDS) | 7
44696 | 44691 | 99-4560 | OG9 SAFETY (NETTING, CABLE, TOE BOARDS) | 9.5
44696 | 44691 | 99-4560 | OG10 SAFETY (NETTING, CABLE, TOE BOARDS) | 4
44696 | 44691 | 03-1100 | SG4 FLOODWALL | 20
44696 | 44691 | 03-1100 | SG5 FLOODWALL | 20
44696 | 44691 | 99-4560 | LOCK GATES (SITE MAINT) | 0.5
44696 | 44691 | 99-4560 | SG6 CLEAN ROOF CONCRETE BAGS | 4.5
44696 | 44691 | 31-1300 | SITE8 EXCAVATION | 1
44696 | 44691 | 02-6060 | OG9 CLEAN 2ND FLOOR | 3.5
44696 | 44691 | 03-6000 | OG3 CUT SLAB AT FRP LOCATIONS | 18
44696 | 44691 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 18
44696 | 44691 | 03-6000 | SG1 INSTALL FRP ON 1ST FLOOR | 17
44696 | 44691 | 99-4560 | OG9 CLEAN AROUND BUILDING | 5
44696 | 44691 | 99-4560 | SG6 CLEAN AROUND BUILDING AND ROOF | 9.5
44696 | 44691 | 99-4560 | OG8 CLEAN AROUND BUILDING | 5
44696 | 44691 | 04-6120 | MOVE EQUIPMENT FROM SG6 TO SG5 (FAXA CODE) | 8
44696 | 44691 | 33-2400 | COVER PUMP FOR SIG (COE's EXCLUDED IN CONTRACT) | 1
44696 | 44691 | 31-1000 | MAINT PRT EXIST PRT UNTILITY - MOVE MAFIA BLOCK FROM "BRIDGE" | 1
44696 | 44691 | 02-6015 | OG2 REMOVE BASEMENT WINDOW INSTALL DOWELS | 5
44696 | 44691 | 03-1400 | OG2 COMPLETE DOWELS FOR MASONRY FOUNDATION | 5
44696 | 44691 | 03-1400 | OG1 DRILL AND DOWEL FOR MASONRY FOUNDATION | 9
44696 | 44691 | 33-3100 | SG7 EXCAVATE TRENCH TO SG2 | 34.5
44696 | 44691 | 02-3000 | OG4 & OG5 CORE 5" HOLES FOR CHASS | 17
44696 | 44691 | 99-4560 | SG6 & OG8 CLEAN UP DEBRI | 1
44696 | 44691 | 99-4000 | OG5 MOVE MAFIA CONCRETE BLOCKS FROM STEAM TRENCH WALKWAY | 1
44696 | 44691 | 33-2400 | PUMPS | 1
44696 | 44692 | 33-3100 | SG7 EXCAVATE TRENCH TO SG2/HNS TRUCK ON SITE MOVING MATERIAL TO OG1/OG2/SG6 | 23
44696 | 44692 | 33-3100 | SG7 EXCAVATE FOR UNTILITIES COMING OUT OF BLD | 7
44696 | 44692 | 31-2200 | SG7 BACKFILL STEAM AND WATER TRENCH BY SG1 | 4.5
44696 | 44692 | 03-2100 | SG4 OG8 PREP FOR CONCRETE POUR (FLOODWALL) | 2
44696 | 44692 | 03-1400 | OG1 DRILL AND DOWEL FOR MASONRY FOUNDATION | 17
44696 | 44692 | 33-2500 | SGN DELIVERY LIGHT POLE BASES + DRAINAGE (CODE FOR DRAINAGE EXCAVATION) | 6
44696 | 44692 | 33-2500 | OG6 DELIVERY CONCRETE BAGS FOR DRAINS | 11
44696 | 44692 | 04-6120 | SG5 SG6 FAXA NEED LULL (FAXA CODE) | 4
44696 | 44692 | 07-6310 | COVER FIRE PROOFER PUMP FOR SIG | 1
44696 | 44692 | 33-1000 | SG5 REMOVE PLYWOOD AND FENCE BY FIREPIPE FOR FAXA (MAINT PROT EXIT UTL) | 5
44696 | 44692 | 02-3000 | OG2 CHOP WALL PENETRATIONS FOR FSE | 14
44696 | 44692 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 16
44696 | 44692 | 03-6000 | SG1 FINISHING FRP INSTALL ON 1ST FLOOR | 10.5
44696 | 44692 | 03-6000 | OG2 FRP INSTALL IN BASEMENT | 6.5
44696 | 44692 | 99-4560 | SG5 CLEAN GARBAGE AROUND FLOODWALL | 5
44696 | 44692 | 99-4560 | OG4 CLEAN 1ST AND 2ND FLOOR | 4
44696 | 44692 | 02-6060 | OG1 CLEAN 2ND FLOOR APARTMENT | 4
44696 | 44692 | 03-1000 | OG8 LOAD OUT FORMS FROM 2ND FLOOR | 3
44696 | 44692 | 31-1100 | SG5 BACKFILL BY FLOODWALL BY FORE PIPE | 3
44696 | 44692 | 99-4560 | OG4 LOAD GARBAGE FROM 2ND FLOOR WINDOW | 1
44696 | 44692 | 31-1100 | OG1 BACKFILL BEHIND FLOODWALL | 1
44696 | 44692 | 99-4560 | SG6 LOAD NEEDED FOR VITAL | 2
44696 | 44692 | 03-6000 | OG3 CUT SLAB @ FRP | 18
44696 | 44692 | 03-1100 | SG5 FORM FLOOD WALL | 60
44696 | 44692 | 99-4560 | OG8 OG10 SG6 SAFETY ITEMS (NETTING, CABLE, WHOLES ETC) | 6
44696 | 44692 | 03-2300 | OG8 DUCT BANK | 20
44696 | 44692 | 03-1000 | SG6 CONDUIT PENETRATION FORMED, ELECTRICAL PADS | 18.5
44696 | 44692 | 99-4560 | LOCK GATES | 1
44696 | 44693 | 03-2100 | SG4 SG5 POUR FLOODWALL AT FRONT/SIDE OF ENTRANCE | 12
44696 | 44693 | 31-2200 | OG5 CONTINUE BACKFILL STEAM TRANCH/HNS ON SITE MOVING MATERIAL FROM SGN AND SITE 8 | 10
44696 | 44693 | 03-2300 | OG8 POUR DUCTBANK | 11
44696 | 44693 | 31-2200 | SG7 BACKFILL PLUMBLING TRENCH/HNS ON SITE MOVING MATERIAL FROM SGN AND SITE 8 | 13
44696 | 44693 | 31-1300 | SITE8 DIG AND LAG/LAY STONE/INSTALL PUMPS | 27
44696 | 44693 | 31-2200 | LOAD HNS TRUCKS FROM SGN TO SG7 AND OG5 - BACKFILL | 6.5
44696 | 44693 | 31-1100 | OG1 FINISH BACKFILL BEHIND FLOODWALL | 1.5
44696 | 44693 | 31-1100 | OG2 BACKFILL BEHIND FLOODWALL | 1
44696 | 44693 | 99-4560 | SG6 VITAL NEED LULL | 1
44696 | 44693 | 99-4560 | SG6 OG2 OG3 OG1 CLEAN DEBRIS | 2.5
44696 | 44693 | 99-4560 | SG4 CLEAN AREA FOR PANELS DELIVERY | 5
44696 | 44693 | 07-6310 | COVER FIRE PROOFERS PUMP FOR SIG | 3
44696 | 44693 | 03-1500 | OG1 CLOSE WINDOWS ON INSIDE | 36
44696 | 44693 | 03-1500 | OG2 CLOSE WINDOWS ON INSIDE | 39
44696 | 44693 | 03-1100 | OG8 WATCH CONCRETE/MAINTAIN FORMS (FORM WORK @ FLOODWALL) | 1
44696 | 44693 | 99-4560 | OG8 PUT UP HANDRAIL | 4
44696 | 44693 | 03-1000 | OG10 STRIP COLUMNS | 3.5
44696 | 44693 | 03-2100 | SG4 SG5 SET KEYS IN CONCRETE (POUR CONCRETE) | 4
44696 | 44693 | 31-1830 | SITE 8 LAGGING | 9
44696 | 44693 | 99-4560 | LOCK GATES | 0.5
44696 | 44693 | 03-2100 | OG3 FINISHING CLEANING SLABS DEBRI | 6
44696 | 44693 | 02-3000 | SG3 CHOP PENETRATION IN BASEMENT THEMIS | 11.5
44696 | 44693 | 02-3000 | OG6 CORE (4) 5" HOLES FOR FSE | 6
44696 | 44693 | 02-3000 | OG1 CORE (2) 5" HOLES FOR FSE | 4.5
44696 | 44693 | 02-6060 | OG1 CLEAN GARBAGE FROM 2ND FLOOR | 5
44696 | 44693 | 02-3000 | OG2 CLEAN GARBAGE FROM BASEMENT PENETRATIONS | 4.5
44696 | 44693 | 02-2300 | OG3 CLEAN BASEMENT DEBRI | 5.5
44696 | 44693 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 9
44696 | 44693 | 03-6000 | OG2 FRP INSTALL IN BASEMENT | 24
44696 | 44693 | 99-4560 | SG6 CLEAN 2ND FLOOR AND 1ST FLOOR FOR LIGHT DELIVERY | 3.5
44696 | 44693 | 31-1100 | OG1 BACKFILL BEHIND FLOODWALL | 0.5
44696 | 44693 | 31-1100 | SG4 SG5 LOAD TRUCKS WITH BACKHOLE?? (BACKFILL) | 0.5
44696 | 44694 | 02-1900 | SG2 CLEAN TRENCH AT LOOP/CHOP CONCRETE OBSTRUCTION | 12
44696 | 44694 | 31-2200 | SG7 BACKFILL PLUMBING TRENCH | 11.5
44696 | 44694 | 33-3100 | SG7 EXCAVATE ELECTRIC POE AT SG3 | 10
44696 | 44694 | 33-3100 | OG10 RAKE DOWN FOR CHAS INSTALL | 1.5
44696 | 44694 | 31-1830 | SITE8 DIG AND LAG/HNS TRUCK ONSITE MOVING MATERIAL | 43
44696 | 44694 | 31-1100 | OG5 STAGE MATERIALN FOR BACKFILL | 4
44696 | 44694 | 05-6110 | NAVILLUS DELIVERY (BACK CHARGE) | 28
44696 | 44694 | 33-2400 | COVER FIREPROOFERS PUMP | 1
44696 | 44694 | 33-2400 | COVER PUMPS | 2
44696 | 44694 | 03-1900 | SG6 POUR PAD ON ROOF | 4.5
44696 | 44694 | 02-3000 | SG3 CORE 5" HOLES FOR CHASS (4) | 13.5
44696 | 44694 | 03-6000 | SG1 CUT SLAB AT FRP LOCATIONS | 17.5
44696 | 44694 | 02-3000 | SG3 CLEAN PANELS FROM SLAB CUTS IN BASEMENT (CUTTING CODE) | 4.5
44696 | 44694 | 99-4560 | SG3 & SG7 CLEAN AROUND | 5.5
44696 | 44694 | 99-4560 | CLEAN TRENCH AROUND SG5 | 5.5
44696 | 44694 | 99-4560 | CLEAN AROUND OG8 | 3.5
44696 | 44694 | 03-6000 | OG2 FRP INSTALL IN BASEMENT | 32.5
44696 | 44694 | 04-6120 | SG5 LOAD FOR FAXA (FAXA CODE) | 1.5
44696 | 44694 | 04-6120 | OG10 LOAD FOR FAXA ON 2ND FLOOR (FAXA CODE) | 2.5
44696 | 44694 | 33-6010 | SG5 HELP WELKIN WITH LIFTING PIPE | 2.5
44696 | 44694 | 33-6010 | TAKE SAND BAGS PALETS FOR WELKIN YARD SG5 | 1.5
44696 | 44694 | 99-4560 | CLEAN AROUND OG9 | 2.5
44696 | 44694 | 03-1500 | OG1 WINDOWS CLOSE UP | 29
44696 | 44694 | 03-2500 | OG2 WINDOW CLOSE UP + STAYFORM FOR BRICK SHELF | 25
44696 | 44694 | 03-1500 | OG2 WINDOW CLOSE UP + STAYFORM FOR BRICK SHELF | 24
44696 | 44694 | 31-1830 | SITE8 LAGGING | 9
44696 | 44694 | 99-4560 | SITE8 HANDRAIL | 11
44696 | 44694 | 99-4560 | SAFETY ITEMS | 6.5
44696 | 44694 | 99-4560 | LOCK GATES (SITE MAIN) | 0.5
44689 | 44683 | 05-6020 | OG3 GROUT STEEL BEAMS (1ST FL DONE) | 10.5
44689 | 44683 | 05-6020 | SG5 GROUT STEEL BEAMS (1ST FL DONE) | 10
44689 | 44683 | 03-6000 | OG3 FRP INSTALL IN BASEMENT | 18
44689 | 44683 | 99-4560 | SG3 CLEAN AROUND TRENCH ON WELKIN YARD | 10
44689 | 44683 | 99-4560 | SG6 SG5 SG4 CLEAN GARBAGE | 12
44689 | 44683 | 99-4560 | SITE8 CLEAN AROUND BUILDING | 6
44689 | 44683 | 32-6510 | SG6 FIX WHITE MESH | 6
44689 | 44683 | 99-4560 | OG8 CLEAN AROUND BUILDING | 5
44689 | 44683 | 99-4560 | OG10 CLEAN AROUND BUILDING | 4
44689 | 44683 | 03-1400 | OG2 DRILL FOR DOWEL INSTALL | 17.5
44689 | 44683 | 33-6010 | SG5 WELKIN INSTALL UG PIPE - MACHINE NEEDED | 7
44689 | 44683 | 31-1000 | SG5 GRADE/CLEAN ARA - 1 LIVE LOAD CONCRETE SCHEDULED/LOAD OUT MATERIAL - HNS ONSITE (CODE FOR FLOODGATE SHELF) | 17.5
44689 | 44683 | 03-2300 | OG10 OG5 POUR DUCT BANK/POUR TRUST BLOCK | 12.5
44689 | 44683 | 31-2200 | SG6 BACKFILL BACKSIDE OF BLD | 7
44689 | 44683 | 31-2200 | OG9 BACKFILL BACKSIDE OF BLD | 7
44689 | 44683 | 31-2200 | OG8 BACKFILL UG PIPE/CLEAN AROUND MANHOLE | 8
44689 | 44683 | 31-2200 | OG5 BACKFILL UG PIPE | 5
44689 | 44683 | 33-2400 | COVER PUMPS | 1
44689 | 44683 | 33-2400 | COVER FIREPROOFING PUMP | 1
44689 | 44683 | 03-1100 | OG1 STRIP FLOODWALL | 16.5
44689 | 44683 | 03-1100 | OG2 STRIP FLOODWALL | 13.5
44689 | 44683 | 03-2300 | OG8 FORM TRUST BLOCK | 17
44689 | 44683 | 02-6060 | SG6 BUILD 2 TEMP DOORS | 10.5
44689 | 44683 | 03-1000 | SG7 STRIP FOOTINGS | 17
44689 | 44683 | 03-1100 | SG4 FORN FLOOD WALL | 30
44689 | 44683 | 32-6520 | MAINTAIN FENCES | 0.5
44689 | 44684 | 31-2200 | SG4 LEVEL AREA FOR PANEL DELIVERY/LOAD OUT MATERIAL FOR BACKFILL ON SG5 0 HNS TRUCKS ON SITE | 9.5
44689 | 44684 | 31-1100 | SG5 GRADE/CLEAN AREA - LOAD OUT STOCKPILE - HNS TRUCK ON SITE | 11.5
44689 | 44684 | 33-6010 | OG4 WELKIN INSTALL UG PIPE TO OG3 - MACHINE NEEDED | 4.5
44689 | 44684 | 31-2200 | OG5 BACKFILL DUCTBANK | 9
44689 | 44684 | 33-3100 | OG8 CLEAN OUT & AROUND MANHOLE (TRENCH MAINT) | 8
44689 | 44684 | 31-2200 | OG10 BACKFILL DUCTBANK | 5.5
44689 | 44684 | 31-2200 | OG9 BACKFILL BACKSIDE OF BLD | 5.5
44689 | 44684 | 03-6000 | OG3 FRP INSTALL | 9
44689 | 44684 | 03-1400 | OG2 DRILL AND DOWEL FOR MASONRY SHELF | 8.5
44689 | 44684 | 31-1000 | OG1 DIG BY HAND FOR MASONRY SHELF | 2.5
44689 | 44684 | 02-3000 | OG6 CUT (2 EA) HOLES IN CMU FOR THEMIS | 2.5
44689 | 44684 | 32-6620 | SITE8 TREES REMOVAL - 1 LIVE LOAD 30 YDS | 4.5
44689 | 44684 | 33-2400 | PUMPS | 2
44689 | 44684 | 07-6020 | OG8 PREP SHAFT FOR WATERPROOF | 16.5
44689 | 44684 | 02-1900 | SITE8 CONCRETE REMOVAL AND LOAD OUT | 8.5
44689 | 44684 | 03-6000 | OG3 FRP INSTALL IN BASEMENT | 8.5
44689 | 44684 | 03-1400 | OG2 INSTALL REBAR AROUND BUILDING | 8.5
44689 | 44684 | 03-1400 | OG2 DRILL HOLES FOR MASONRY SHELF | 2.5
44689 | 44684 | 32-6620 | SITE8 CUT TREES BY BUILDING | 9.5
44689 | 44684 | 02-3000 | OG6 CUT TWO PENETARTIONS | 4.5
44689 | 44684 | 99-4560 | OG1 CLEAN AROUND BUILDING | 4.5
44689 | 44684 | 99-4560 | OG8 CLEAN 1ST AND 2ND FLOOR | 4.5
44689 | 44684 | 99-4560 | OG9 CLEAN BY BUILDING | 5.5
44689 | 44684 | 04-6120 | SG6 LOAD MATERIALS FOR FAXA | 2.5
44689 | 44684 | 99-4560 | SG6 CLEAN GARBAGE | 2.5
44689 | 44684 | 99-4560 | OG9 CLEAN DEBRI | 2.5
44689 | 44684 | 33-6010 | OG3 LOAD PIPE FOR WELKIN | 2
44689 | 44684 | 03-1500 | OG2 START CLOSING UP WINDOWS | 21
44689 | 44684 | 03-2300 | OG8 FORM THRUST BLOCK | 18
44689 | 44684 | 03-1100 | SG4 FORM FLOOD WALLS | 15
44689 | 44684 | 99-4560 | SG4 & G5 SAFETY (REBAR CAOS + 2X4'S) | 6.5
44689 | 44684 | 03-1000 | SG7 FORM GRADE BEAMS | 44
44689 | 44685 | 02-2300 | SG4 PUMP BASEMENT WATER | 9
44689 | 44685 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 18
44689 | 44685 | 03-6000 | OG3 FRP INSTALL ON 1ST FLOOR | 18
44689 | 44685 | 99-4560 | SG5 CLEAN AROUND | 5.5
44689 | 44685 | 99-4560 | SG6 CLEAN 1ST & 2ND FLOOR | 7.5
44689 | 44685 | 99-4560 | OG9 CLEAN 1ST FLOOR | 4
44689 | 44685 | 99-4560 | SG4 CLEAN AROUND BUILDING | 4
44689 | 44685 | 32-6510 | OG8 FIX WHITE MESH | 2.5
44689 | 44685 | 32-6510 | SG5 REPLAVE WHITE MESH | 2
44689 | 44685 | 31-1700 | OG9 CLEAN WATER FROM SHAFT | 4
44689 | 44685 | 31-1700 | OG10 CLEAN WATER FROM SHAFT | 4
44689 | 44685 | 31-1000 | SG5 LEVEL GROUND BUILDING | 2
44689 | 44685 | 02-1900 | SITE8 CONCRETE REMOVAL | 3
44689 | 44685 | 31-2200 | LOST TIME MACHINE WAS DOWN, REPAIRED BY SUNBELT | 6
44689 | 44685 | 33-1100 | OG8 REMOVE EXISTIG UTILITY ELECTRIC PIPES | 6
44689 | 44685 | 03-2100 | SG5 POUR FOOTING | 4
44689 | 44685 | 03-2300 | OG8 POUR THRUST BLOCKS | 3
44689 | 44685 | 31-2200 | OG10 BACKFILL DUCTBANK AND SIDE OF BLD/1 LIVE LOAD CONCRETE/CARDELLA | 25.5
44689 | 44685 | 31-1300 | SITE8 EVACUATE AND LOAD OUT/HNS ONSITE/2 LIVE LOAD CONCRETE/CARDELLA | 14.5
44689 | 44685 | 03-1400 | OG2 INSTALL DOWELS FOR MASONRY SHELF | 13
44689 | 44685 | 31-2200 | OG5 BACKFILL DUCTBANK | 2
44689 | 44685 | 31-1830 | SITE8 START LAGGING/SHORING | 4.5
44689 | 44685 | 33-2400 | COVER PUMPS | 2
44689 | 44685 | 02-3000 | OG8 ROOF PENETRATIONS | 55
44689 | 44685 | 03-1000 | OG9 FORM ELECTRICAL PADS | 12
44689 | 44685 | 99-4560 | OG9 REMOVE WORK DESK | 12
44689 | 44685 | 03-2300 | OG9 FORM THRUST BLOCK | 13
44689 | 44685 | 03-2300 | SG7 FORM THRUST BLOCK | 12.5
44689 | 44685 | 99-4560 | LOCK GATES | 0.5
44689 | 44686 | 03-1000 | OG8 LOAD OUT TRAILER | 17
44689 | 44686 | 99-4560 | OG8 SAFETY ITEMS ON 2ND FLOOR | 7
44689 | 44686 | 03-1000 | OG8 FORM EQUIPMENT PADS | 12
44689 | 44686 | 03-1000 | OG9 FORM PADS IN PLUMBING SHAFT | 7
44689 | 44686 | 03-2300 | SG7 FORM THRUST BLOCK | 13.5
44689 | 44686 | 31-1900 | TREE PROTECTION | 11
44689 | 44686 | 03-1100 | SG5 PUT SHOE DOWN FOR FLOOD WALL | 29
44689 | 44686 | 99-4560 | SITE MAINT | 0.5
44689 | 44686 | 31-1000 | OG3 EXCAVATE FOR MASONRY SHELF/DEMO VENT WINDOW - CONCRETE | 4
44689 | 44686 | 31-2200 | OG9 BACKFILL BACK OF BLD (BACKFILL UTILITIES) | 22
44689 | 44686 | 31-2200 | OG10 BACKFILL DUCTBANK | 4
44689 | 44686 | 02-2100 | SITE8 CONCRETE REMOVAL AND LOAD OUT/3 LIVE LOADS | 15.5
44689 | 44686 | 31-1830 | SITE8 CONTINUE LAGGING/LOAD OUT | 34
44689 | 44686 | 33-2400 | COVER PUMPS | 2
44689 | 44686 | 02-6015 | OG2 DEMO VENT (COMP) | 1
44689 | 44686 | 99-4560 | COVER FIRE PROOFER PUMP | 1
44689 | 44686 | 02-6060 | SG5 CLEAN 2ND FLOOR APARTMENT | 4.5
44689 | 44686 | 03-6000 | OG2 FRP ON 2ND FLOOR | 12.5
44689 | 44686 | 03-6000 | OG3 FRP ON 1ST FLOOR | 16.5
44689 | 44686 | 31-1000 | OG1 EXCAVATE AREA FOR MASONRY SHELF | 5.5
44689 | 44686 | 99-4560 | OG9 CLEAN 1ST & 2ND FLOOR | 12.5
44689 | 44686 | 03-1000 | OG8 LOAD TRAILER WITH FORMS | 5.5
44689 | 44686 | 04-6120 | SG6 LOAD MATERIALS FOR FAXA | 1.5
44689 | 44686 | 99-4560 | SG6 PICK UP GARBAGE | 2.5
44689 | 44686 | 99-4560 | OG9 PICK UP GARBAGE | 2.5
44689 | 44686 | 02-1900 | SITE 8 LOAD UP CARDELLA CONTAINERS WITH CONCRETE | 1.5
44689 | 44686 | 02-6015 | OG2 DEMO VENT AT FRONT OF BUILDING | 16.5
44689 | 44687 | 05-6020 | OG2 GROUT STEEL BEAMS - 1ST FLOOR | 7.5
44689 | 44687 | 05-6020 | OG5 GROUT STEEL BEAMS - 1ST FLOOR | 1
44689 | 44687 | 02-2300 | SG4 FIX PIPE LEAK ON 2ND FLOOR | 4
44689 | 44687 | 03-6000 | OG2 FRP INSTALL ON 2ND FLOOR | 18
44689 | 44687 | 03-6000 | OG3 FRP INSTALL | 18
44689 | 44687 | 03-1900 | OG8 CLEAN 2ND AND TOP FLOORS FOR POUR (CONCRETE POUR) | 16
44689 | 44687 | 31-2200 | OG1 BACKFILL TRANCH | 4.5
44689 | 44687 | 33-6010 | PICK UP SAND BAGS IN WELKIN YARD TO SG4 (WELKIN SUPPORT) | 1.5
44689 | 44687 | 31-1000 | OG2 CLEAN DEBRI FROM OG2 FROM VENT DEMO (EXCAVATE FOR MASONRY) | 1.5
44689 | 44687 | 33-6010 | SG6 PICK PIPE FOR WELKIN TO 2ND FLOOR | 2.5
44689 | 44687 | 03-1000 | SG7 FORM GRADE BEAMS | 33
44689 | 44687 | 03-1300 | SG7 SET BOLT PATERNS (ANCHOR BOLTS) | 6
44689 | 44687 | 03-1900 | SG7 WATCH FORMS FOR CONCRETE (CONCRETE POUR) | 5
44689 | 44687 | 03-1000 | OG8 BLOCK OUT HOLES & FINISH BULK HEAD ON ROOF, BLOCK OUT FOR E&Y | 26
44689 | 44687 | 03-1100 | SG5 SET BACK FORM FOR FLOODWALL | 38.5
44689 | 44687 | 99-4560 | OG2 FIX DOOR W/ HASP (SITE MAINTENANCE) | 4
44689 | 44687 | 99-4560 | SITE MAINT | 0.5
44689 | 44687 | 03-1900 | SG7 POUR GRADE BEAMS AND THRUST BLOCK | 4.5
44689 | 44687 | 03-2300 | OG8 POUR THRUST BLOCK | 1.5
44689 | 44687 | 33-3100 | SG2 EXCAVATE PLUMBING RUN TO SG7/ADJUST FENCE - HNS ONSITE MOVING MATERIAL TO OG9 & OG5 | 16.5
44689 | 44687 | 31-2200 | OG5 BACKFILL TRENCH | 17
44689 | 44687 | 31-2200 | OG9 BACKFILL TRENCH | 7
44689 | 44687 | 31-1300 | SITE8 EXCAVATE TO TOP OF WATER TABLE/CONTINUE LAGGING | 23
44689 | 44687 | 33-1000 | SITE8 SUPPORT EXISTING SANITARY LINE (MAINT) | 7
44689 | 44687 | 33-2400 | PUMPS | 2
44689 | 44687 | 32-6520 | OG9 ADJUST FENCE | 8
44682 | 44676 | 31-2200 | SG3 BEGIN TO BACKFILL TRENCH | 17
44682 | 44676 | 02-2100 | SG4 LOAD OUT 3EA 20 YD CONCRETE(CONCRETE DEMO) | 7.5
44682 | 44676 | 31-2200 | HNS ON SITE MOVING MATERIAL FROM SG NORTH TO SG3 (BACKFILL) | 7.5
44682 | 44676 | 26-6030 | OG4 FSE RECEIVE SWITCH GEAR - LULL NEEDED | 5.5
44682 | 44676 | 03-2300 | OG6 POUR DUCTBANK | 8.5
44682 | 44676 | 03-1900 | OG8 POUR COLUMNS | 28
44682 | 44676 | 03-1900 | OG10 POUR PADS 2ND FLOOR | 6
44682 | 44676 | 99-4600 | PROTIRE ON SITE - FIX V2 FLAT TIRE ON 316 MACHINE | 2
44682 | 44676 | 33-2400 | COVER PUMPS | 1
44682 | 44676 | 99-4560 | DEBRIS REMOVAL - SITE MAINT | 3
44682 | 44676 | 03-1900 | OG8 PATCH TOP OF FOP WALLS (POUR CONCRETE) | 17.5
44682 | 44676 | 07-6020 | OG8 GRINDING INSIDE SHAFT (PREP FOR WATERPROOF) | 17.5
44682 | 44676 | 99-4560 | SG6 CLEAN AROUND (SITE MAINT) | 6.5
44682 | 44676 | 99-4560 | OG8 CLEAN AROUND (SITE MAINT) | 6.5
44682 | 44676 | 02-2300 | SG6 CLEN WATER INSIDE SHAFT (BASEMENT MAINT) | 4
44682 | 44676 | 33-3100 | SG3 CLEAN AROUND TRENCH (TRENCH MAINT) | 4.5
44682 | 44676 | 03-2300 | OG6 FORM DUCT BANK (RISERS) | 9
44682 | 44676 | 03-1000 | OG8 FINISH COLUMNS | 11
44682 | 44676 | 99-4560 | OG8 SAFETY RAIL AT TOP OF STAIRS | 5
44682 | 44676 | 31-1900 | OG3 TREE PROTECTION | 40
44682 | 44676 | 02-6060 | OG4 CLOSE WINDOW ON 2ND FL | 5
44682 | 44676 | 03-1900 | OG10 3 EQUIPMENT PADS CLOSE UP | 21
44682 | 44676 | 03-1000 | SG7 FORM FOOTING | 17.5
44682 | 44677 | 02-2300 | SG2 CLEAN BASEMENT (WATER) | 4.5
44682 | 44677 | 99-4560 | OG8 CLEAN AROUND BUILDING (HOUSEKEEPING) | 6.5
44682 | 44677 | 99-4560 | OG10 CLEAN AROUND BUILDING (HOUSEKEEPING) | 8.5
44682 | 44677 | 32-6520 | SITE8 FINISH WALKWAY (FENCING) | 10
44682 | 44677 | 99-4560 | SG6 HOUSEKEEPING ON 2ND FLOOR | 8.5
44682 | 44677 | 33-2400 | OG5 MAINTAIN PUMPS BY FSE YARD | 6
44682 | 44677 | 31-2200 | FLAGGING BY WELKIN YARD DUMP TRUCK - BACKFILL | 2.5
44682 | 44677 | 03-1000 | OG-2 FRP INSTALL 2NND FLOOR | 16.5
44682 | 44677 | 04-6120 | SG5 AND OG10 LOAD BLOCKS FOR FAXA | 2.5
44682 | 44677 | 02-6060 | SG4 FORM HOLE IN 2ND FLR APARTMENT | 5
44682 | 44677 | 03-1000 | SG7 BRACE FOOTING FORMS | 17
44682 | 44677 | 03-1000 | OG8 STRIP ALL COLUMNS | 56
44682 | 44677 | 32-6510 | OG8 INSTALL RELEASES ON 2ND FL CABLES | 4
44682 | 44677 | 03-1000 | OG10 STRIP 2 PADS | 12.5
44682 | 44677 | 31-1900 | OG6 TREE PROTECTION | 16
44682 | 44677 | 33-3100 | OG3 REMOVE TRANCHBOX | 2
44682 | 44677 | 31-2200 | SG3 BACKFILL TRENH/REMOVE TRANCH BOX | 27.5
44682 | 44677 | 31-2200 | SG4 LOAD OUT STOCKPILE TO BACKFILL STEAM TRENCH-SG3 "HNS ONSITE" | 10
44682 | 44677 | 03-1700 | SG7 SHAKE OUT REBAR - MOVE TO FOOTING LOCATION | 3
44682 | 44677 | 03-2300 | OG6 POUR DUCTBANK | 10
44682 | 44677 | 99-4560 | OG10 HOUSEKEEPING | 3.5
44682 | 44677 | 33-6010 | OG4 WELKIN INSTALL PIPE - MACHINE NEEDED | 9.5
44682 | 44677 | 03-6000 | OG3 FRP INTSLL IN BASEMENT (COVER PUMPS() | 9
44682 | 44677 | 33-2400 | COVER PUMPS | 2
44682 | 44678 | 31-2200 | SG3 BACKFILL TRANCH TO OG5 | 20
44682 | 44678 | 31-2200 | SG4 LOAD OUT STOCK PILE TO BACKFILL STEAM TRANCH FROM OG5 TO SG3 | 14
44682 | 44678 | 05-6020 | SG5 GROUT STEEL BEAMS IN EXISTING BUILDINGS | 6
44682 | 44678 | 05-6020 | OG1 GROUT STEEL BEAMS IN EXISTING BUILDINGS | 4
44682 | 44678 | 03-6000 | OG3 FRP INSTALL IN BASEMENT | 17
44682 | 44678 | 33-6010 | OG4 WELKIN INSTALL PIPE ON TRANCH - MACHINE NEEDED | 2.5
44682 | 44678 | 03-1800 | SG5 REBAR DELIVERY - MACHINE NEEDED | 3.5
44682 | 44678 | 03-1000 | OG8 TRAILER FOR FORM LOADOUT - LULL NEEDED | 2
44682 | 44678 | 04-6120 | SG6 BACK UP FAXA - LULL NEEDED | 2.5
44682 | 44678 | 03-1000 | OG10 MOVE FORM FROM 2ND FLOOR - MACHINE NEEDED | 2
44682 | 44678 | 33-3100 | SG5 CLEAN STEAM TRENCH - MOVE FORMS AND LUMBER | 2.5
44682 | 44678 | 33-3100 | SG5 MAINTAIN STEAM TRENCH - FROM SG4 TO SG5 | 4.5
44682 | 44678 | 33-2400 | COVER PUMPS | 3
44682 | 44678 | 05-6020 | OG1 GROUT STEEL BEAM | 4
44682 | 44678 | 05-6020 | SG5 GROUT STEEL BEAM | 5.5
44682 | 44678 | 03-6000 | OG2 FRP AT 2ND FLOOR | 17.5
44682 | 44678 | 32-6520 | SITE8 COMPLETE WALKWAY (TEMP WALKWAY) | 8.5
44682 | 44678 | 33-2400 | SG3 MAINTAIN PUMPS (IN TRENCH) | 2.5
44682 | 44678 | 02-6060 | SG4 CLEAN 2ND FLOOR (SITE MAINT) | 2.5
44682 | 44678 | 99-4560 | OG8 CLEAN AROUND BUILDING (SITE MAINT) | 9.5
44682 | 44678 | 99-4560 | SG7 CLEAN AROUND BUILDING (SITE MAINT) | 4.5
44682 | 44678 | 99-4560 | SG6 CLEAN AROUND 2ND FLOOR (SITE MAINT) | 4.5
44682 | 44678 | 99-4560 | SG3 CLEAN AROUND BUILDING (SITE MAINT) | 5.5
44682 | 44678 | 03-1100 | OG1 CLOSE UP FLOODWALLS | 25.5
44682 | 44678 | 03-2300 | OG6 STRIP RIDERS IN DUCT BANK | 7
44682 | 44678 | 03-1000 | OG8 PUT UP HANDRAIL AT PLUMBING SHAFT | 9
44682 | 44678 | 31-1900 | OG6 TREE PROTECTION | 13
44682 | 44678 | 03-1000 | OG8 LOAD OUT FORMS | 13
44682 | 44678 | 03-1100 | SG4 FORM PAD | 3
44682 | 44678 | 03-1000 | OG8 CLEAN UP SECOND FLOOR (FW) | 20
44682 | 44678 | 03-1000 | OG10 REMOVE FORM FROM 2ND FLOOR (FW) | 17.5
44682 | 44678 | 32-6510 | OG8 SITE MAINTENANCE (REPAIR BUILDING MESH, SET UP PERIMETER CABLE) | 5
44682 | 44679 | 31-2200 | SG3 BACKFILL TRENCH TO OG5 - REMOVE TRENCH BOXES ON 32ND ST WALKWAY | 22
44682 | 44679 | 03-6000 | OG3 FRP INSTALL IN BASEMENT | 17
44682 | 44679 | 33-6010 | OG4 WELKIN INSTALL PIPE TO OG3 - MACHINE NEEDED | 3.5
44682 | 44679 | 31-2000 | OG5 TEST PIT FOR STEAM TRENCH TO OG6 | 15
44682 | 44679 | 33-3100 | SG4 MAINTAIN TRENCH FOR STEAM PIPE TO SG5 | 2.5
44682 | 44679 | 31-2200 | OG9 BEGIN TO BACKFILL TRENCH TO OG3 | 6.5
44682 | 44679 | 31-2200 | OG8 BACKFILL UG PIPE/MAINTAIN FSE TRENCH TO OG4 | 10
44682 | 44679 | 26-6030 | OG10 INSTALL 2 CONEX BOXES FOR FSE - MACHINE NEEDED | 1.5
44682 | 44679 | 03-2100 | SG7 OG1 SG5 OG2 PREP FOR CONCRETE POUR - FOOTINGS AND FLOODWALLS | 2.5
44682 | 44679 | 33-2400 | COVER PUMPS | 2
44682 | 44679 | 32-6520 | SITE8 INSTALL BRIDGE | 24
44682 | 44679 | 03-1100 | OG2 FORM FLOOD WALLS | 44
44682 | 44679 | 03-1100 | SG4 MOVE FORMS BY HAND | 8
44682 | 44679 | 03-2300 | OG10 DUCT BANK | 10
44682 | 44679 | 99-4560 | SAFETY MATERIALS | 10.5
44682 | 44679 | 32-6520 | GATES | 0.5
44682 | 44679 | 33-3100 | SG3 LOAD DUMPTRUCK FROM SITE8 TO SG3 (EXCAVATION) | 4
44682 | 44679 | 33-3100 | SITE8 DIG WALKWAY | 6
44682 | 44679 | 32-6520 | SITE8 FINISH WALKWAY | 12.5
44682 | 44679 | 02-6060 | SG6 CLEAN 2ND & 1ST FLOOR | 9
44682 | 44679 | 99-4560 | PICK UP GARBAGE BY SG5 AND SG4 | 9
44682 | 44679 | 32-6520 | SITE 8 FLAGMAN (TEMP WALKWAY BRIDE) | 8.5
44682 | 44679 | 03-2100 | SG4 PORE PAD ON 2ND FL | 5.5
44682 | 44679 | 04-6120 | SG6 2HRS FOR FAXA WITH LULL MACHINE SG6 | 3
44682 | 44679 | 03-6000 | OG2 FRP INSTALL AT 2ND FLOOR | 16.5
44682 | 44679 | 26-6030 | OG10 MOVE TO PLACE CONEX BOX FOR FSE TOOL BOXES | 2
44682 | 44679 | 99-4560 | CLEAN AROUND OG10 | 5.5
44682 | 44680 | 03-1000 | OG8 LOAD OUT FORMS | 17.5
44682 | 44680 | 03-1000 | OG8 BAND FORMS | 12.5
44682 | 44680 | 03-2300 | OG10 DUCT BANK (CLAIM 10YDS) | 12
44682 | 44680 | 03-2300 | OG5 DUCT BANK (CLAIM 10YDS) | 34
44682 | 44680 | 03-1100 | SG4 & SG5 CLEAN UP + ORGANIZE FORMS | 19
44682 | 44680 | 32-6510 | OG8 SITE MAINTENANCE - INSTALL GUARDRAIL @ 2 LOCATIONS, MAINTAIN ORANGE MESH | 17.5
44682 | 44680 | 99-4560 | CLOSE GATES (SITE MAINT) | 1
44682 | 44680 | 02-6060 | SG5 CLEAN 2ND FLOOR APARTMENT (C/O) | 19
44682 | 44680 | 31-1000 | EXCAVATE DOWN 6" AT FACE OF BUILDING | 14
44682 | 44680 | 02-3000 | SG4 CUT BARS AT MASONRY SHELF STEAM INSTALL | 1.5
44682 | 44680 | 02-3000 | SG5 CUT BARS AT MASONRY SHELF STEAM INSTALL | 1.5
44682 | 44680 | 32-6510 | SITE8 REPLACE WHITE MESH | 18.5
44682 | 44680 | 99-4560 | OG8 CLEAN AROUND BUILDING | 6
44682 | 44680 | 33-1100 | DEMO EXISTING STORM | 10.5
44682 | 44680 | 04-6120 | RUN LULL FOR FAXA | 1
44682 | 44680 | 03-2100 | SG5 POUR FLOODWALL FOOTING | 2.5
44682 | 44680 | 03-1900 | SG7 POUR FOOTING | 12
44682 | 44680 | 03-2100 | OG1 & OG2 POUR FLOODWALL | 12
44682 | 44680 | 03-2300 | OG10 POUR PARTIAL FSE TRENCH/POUR BLOCK | 2.5
44682 | 44680 | 31-2200 | SG6 BACKFILL BACKSIDE OF BUILDING | 23.5
44682 | 44680 | 33-6010 | SG5 WELKIN MOBILIZE FOR UG PIPE | 4
44682 | 44680 | 33-3100 | SITE8 LOADOUT MATERIAL FROM EXCAVATION | 3.5
44682 | 44680 | 33-3100 | OG8 CLEAN AROUND FSE PIPES TRENCH | 10
44682 | 44680 | 31-2200 | OG10 BACKFILL STAYFORM FOR CONCRETE POUR FSE TRENCH | 2.5
44682 | 44680 | 33-2400 | PUMPS | 2
44675 | 44669 | 03-1100 | SG4 STRIP FLOOD WALLS & BRICK SHELF | 42
44675 | 44669 | 03-1000 | OG8 STRIP PLUMBING SHAFT | 78
44675 | 44669 | 03-1000 | OG8 LOAD OUT FORMS | 8.5
44675 | 44669 | 99-4560 | VITAL PUMP DELIVERY | 2
44675 | 44669 | 99-4560 | SG6 FAXA NEEDED MACHINE | 2
44675 | 44669 | 32-6520 | SG2 RELOCATE FENCE/WALKWAY OVER BACKFILLED SECTION OF PIPE | 29
44675 | 44669 | 99-4560 | DYRANTE ON SITE/MAINTENANCE TRACK MACHINE | 1
44675 | 44669 | 00-0017 | SG6 EXCAVATE FOR GAS LINE INSTALL | 17
44675 | 44669 | 33-3100 | SITE8 SAW CUT FOR MANHOLE/DRAINAGE WORK/PREP AREA FOR EXCAVATION | 8.5
44675 | 44669 | 99-4560 | SUNBELT RENTAL ON SITE/REPAIR MACHINE-316 | 2
44675 | 44669 | 33-2400 | COVER PUMPS | 2
44675 | 44669 | 33-3100 | SG2 TO 3 STEAM TRENCH EXCAVATION | 11
44675 | 44669 | 99-4560 | SITE 8 CLEAN UP AROUND SITE | 5.5
44675 | 44669 | 33-3100 | SG3 CLEAN UP AROUND BUILDING AND MAINTAIN TRENCHES | 9.5
44675 | 44669 | 02-6060 | OG4 DEMO 2ND FL FOR PLUMBING | 8.5
44675 | 44669 | 02-6060 | OG5 DEMO 2ND FL FOR PLUMBING | 8.5
44675 | 44669 | 32-6520 | SITE 8 DROP FENCE DELIVERY | 1
44675 | 44669 | 00-0011 | OG1 DEMO 1ST FL WALLS FOR STEEL | 8.5
44675 | 44669 | 02-6060 | OG6 DEMO 2ND FL WALLS FOR PLUMBING | 8.5
44675 | 44669 | 02-6060 | OG5 CLEAN GARBAGE FROM 2ND FLOOR | 2.5
44675 | 44669 | 00-0011 | SG4 CHOP WALLS ON 1ST FL FOR DRAIN PIPES | 3.5
44675 | 44669 | 99-4560 | OG10 CLEAN AROUND SITE | 4.5
44675 | 44669 | 99-4560 | OG8 CLEAN AROUND SITE | 3.5
44675 | 44669 | 99-4560 | SG6 CLEAN AROUND SITE | 4.5
44675 | 44669 | 03-1000 | OG8 LOAD UP TRAILER WITH FORM | 4.5
44675 | 44669 | 33-3100 | SG6 EXCAVATE FOR GAS LINE | 0.5
44675 | 44670 | 03-1100 | SG4 STRIP FLOOD WALLS | 22
44675 | 44670 | 32-6000 | SG6 PATCH CONDUIT RISERS PENETRATIONS THRU ROOF | 22
44675 | 44670 | 03-1000 | OG8 FINISH STRIPPING PLUMBLING SHAFT | 38
44675 | 44670 | 03-1000 | OG8 START FORMNG COLUMNS | 35.5
44675 | 44670 | 99-4560 | SG1 PLYWOOD 2 WINDOWS (SITE MAINT) | 3
44675 | 44670 | 03-1500 | SG2 DEMO BRICK AT CELLAR WINDOWS (WINDOW REMOVAL) | 8.5
44675 | 44670 | 03-1500 | SG3 DEMO BRICK AT CELLAR WINDOWS (WINDOW REMOVAL) | 8.5
44675 | 44670 | 00-0011 | OG1 REMOVE TRACK IN CEILING LEVEL AND CLEAN DEBRI | 8.5
44675 | 44670 | 33-3100 | SG6 EXCAVATE FOR GAS LINE INSTALL | 24.5
44675 | 44670 | 26-6030 | SG6 CLEAN ROOF FOR GENERATORS | 5.5
44675 | 44670 | 33-3100 | OG3 CLEAN AROUND TRANCH AND BUILDING | 8.5
44675 | 44670 | 26-6030 | SG6 PREPAPRE FOR GENERATORS | 5.5
44675 | 44670 | 00-0011 | SG4 PROBE AT 1ST FLOOR WINDOWS AND CLEAN 1ST FLOOR | 3
44675 | 44670 | 00-0011 | SG5 PROBE AT 1ST FLOOR WINDOWS | 2
44675 | 44670 | 02-2300 | SG5 CLEAN WATER FROM BASEMENT | 9.5
44675 | 44670 | 99-4560 | SG4 - SG5 CLEAN AROUND BUILDING | 4.5
44675 | 44670 | 33-3100 | SG3 FINISH EXCAVATION STEAM TRENCH | 19.5
44675 | 44670 | 99-4560 | SG3 LOAD OUT 4EA 20 YD CONTAINERS CARDELLA | 7
44675 | 44670 | 33-1000 | SITE8 SAW CUT PREP FOR MANHOLE/DRAINAGE WORK | 26
44675 | 44670 | 26-6030 | SG6 PREP FOR CRANE/MOVE MATERIAL/CLEAN AREA | 11
44675 | 44670 | 33-3100 | SG6 EXCAVATE FOR GAS LINE | 1
44675 | 44670 | 33-2400 | COVER PUMPS | 3
44675 | 44671 | 02-6015 | SG2 DEMO BRICK AT CELLAR | 4
44675 | 44671 | 02-6015 | SG3 DEMO BRICK AT CELLAR | 4
44675 | 44671 | 99-4560 | SG4 CLEAN 1ST FLOOR (SITE MAINT) | 4
44675 | 44671 | 99-4560 | SG5 CLEAN 1ST FLOOR (SITE MAINT) | 4
44675 | 44671 | 02-2300 | SG3 MAINTAIN PUMPS AND CLEAN AROUND PIPE | 3
44675 | 44671 | 33-6010 | SG6 PREPARE FOR CRANE | 6
44675 | 44671 | 03-1900 | SG6 COMPLETE ROOF CLOSURE AROUND CONDUITS (PATCH) | 5.5
44675 | 44671 | 33-3100 | SG6 EXCAVATE FOR GAS LINE | 24
44675 | 44671 | 03-1900 | OG8 PATCH TIE HOLES IN DECK AND SHAFT | 10
44675 | 44671 | 99-4560 | OG8 CLEAN AROUND BUILDING | 5
44675 | 44671 | 99-4560 | SG6 CLEAN AROUNG CONDUCTS ON STREET | 5
44675 | 44671 | 03-1000 | OG8 CLEAN GARBAGE IN SHAFT (FORM WORK) | 6
44675 | 44671 | 03-1100 | SG5 STRIP FLOOD WALLS | 27
44675 | 44671 | 03-2500 | SG5 STRIP BRICK SHELF | 24
44675 | 44671 | 03-1000 | OG8 FINISH STRIPPING PLUMBING SHAFT | 33.5
44675 | 44671 | 03-1000 | OG8 FORM COLUMNS | 26
44675 | 44671 | 03-2300 | OG6 FORM DUCT BANK | 26
44675 | 44671 | 33-3100 | SG2 LOAD OUT (5 EA, 20 YDS) MATERIAL FROM STEAM TRENCH | 8.5
44675 | 44671 | 31-1300 | SG7 EXCAVATE FOR FOOTING/PLACE STONE | 9
44675 | 44671 | 33-2800 | SITE8 COMPLETE MANHOLE DRAINAGE WORK | 5
44675 | 44671 | 31-1400 | OG10 BACK FILL TO BOTTOM OF CHAS AT SLAB | 6
44675 | 44671 | 31-2000 | OG10 DIG DOWN FOR CONDUIT INSTALL/HAND DIG | 11
44675 | 44671 | 31-2200 | OG6 START BACKFILL FSE CONDUIT-STAY FORM/PREP FOR CONCRETE POUR | 4
44675 | 44671 | 31-1500 | HNS ON SITE W/STONE FOR SG7 FOOTING/MOVE MATERIAL FROM SG4 TO OG10/LOAD HNS | 4
44675 | 44671 | 03-2300 | OG6 INSTALL STAY FORM ON FSE "ELECTRIC TRENCH" | 1
44675 | 44671 | 99-4560 | SG6 CLEAN AREA FOR CRANE/MOVE WIRE MESH TO OG8 | 3.5
44675 | 44671 | 04-6120 | OG9 FAXA MACHINE NEEDED | 3.5
44675 | 44671 | 03-1000 | OG8 CLEAN AREA-LUMBER (FORM WORK) | 1
44675 | 44671 | 33-2400 | COVER PUMPS | 3
44675 | 44672 | 03-1100 | OG1 FORM FLOOD WALLS | 18
44675 | 44672 | 03-1100 | OG2 FORM FLOOD WALLS | 18
44675 | 44672 | 03-1000 | OG8 FORM COLUMNS | 61
44675 | 44672 | 03-1000 | OG8 LOAD OUT FORMS | 9
44675 | 44672 | 99-4560 | OG10 FIX NETTING ON ROOF | 5
44675 | 44672 | 99-4560 | SG6 FIX TOE BOARDS & NETTING ON 2ND FLOOR | 5.5
44675 | 44672 | 99-4560 | OG3 FIX DOOR HASP | 2
44675 | 44672 | 02-2300 | SITE8 HANG SIGN | 2
44675 | 44672 | 02-2300 | SG3 MAINTAIN PUMPS CLEAN STEAM PIPE | 4
44675 | 44672 | 00-0024 | SG6 CHOP FOR GUYWIRE INSTALL | 6.5
44675 | 44672 | 99-4560 | SG6 PREP FOR CRANE MAINTAIN AREA | 5.5
44675 | 44672 | 99-4560 | OG8 CLEAN AROUND BUILDING | 5.5
44675 | 44672 | 99-4560 | OG10 CLEAN AROUND BUILDING | 8
44675 | 44672 | 03-1900 | OG8 PATCH TIE HOLE IN DECK AND TOP OF FOT WALLS | 0.5
44675 | 44672 | 32-6510 | OG3 PUT UP MESH | 11.5
44675 | 44672 | 32-6520 | OG3 INSTALL TEMP FENCE ON WALKWAY | 7
44675 | 44672 | 03-1000 | OG8 LOAD TRAILER WITH FORMS | 11.5
44675 | 44672 | 04-6120 | OG9 LOAD MATERIALS FOR FAXA | 2
44675 | 44672 | 03-1900 | OG8 PREP SHAFT TO PATCH GRINDING | 16.5
44675 | 44672 | 05-6020 | OG4 GROUT BEAMS AT CEILING | 3
44675 | 44672 | 05-6020 | OG4 GROUT STEEL BEAMS | 4.5
44675 | 44672 | 03-2500 | OG6 STAYFORM/BACKFILL DUCT BANK/PREP FOR CONCRETE POUR | 6
44675 | 44672 | 33-6010 | SG2 WELKIN SETTING PIPE IN TRENCH TOSG3/MACHINE NEEDED | 5.5
44675 | 44672 | 03-1900 | OG8 PATCH TIE HOLES IN DECK AND TOP OF FOT WALLS | 17
44675 | 44672 | 31-1500 | SG7 SUBGRADE INSPECTION/PLACE MORE STONE AND COMPACT | 3
44675 | 44672 | 33-3100 | SITE 8 (6) LIVE LOADS OF DEBRIS/START EXCAVATION (120 YDS) | 21.5
44675 | 44672 | 32-6520 | SITE 8 INSTALL TEMP FENCE ON WALKWAY | 6
44675 | 44672 | 99-4560 | SG6 PREP FOR CRANE/CLEAN DEBRIS FROM 2ND FLOOR | 1
44675 | 44672 | 33-2400 | COVER PUMPS | 2
44675 | 44673 | 03-1000 | OG8 FORM COLUMNS | 36
44675 | 44673 | 99-4560 | OG8 ORGANIZE YARD (SITE MAINT) | 2
44675 | 44673 | 03-1900 | OG10 EQUIPMENT PADS | 42
44675 | 44673 | 32-6510 | OG9 FIX FENCING (ORANGE SAFETY NETTING ON BUILDING) | 7.5
44675 | 44673 | 31-1900 | TRUE PROTECTION | 17
44675 | 44673 | 33-6010 | SG6 FLAGGING FOR CRANE WITH GENERATORS | 9
44675 | 44673 | 32-6520 | SG6 REMOVE GATE AND FENCE | 3.5
44675 | 44673 | 32-6510 | SITE8 PUT UP MESH | 14.5
44675 | 44673 | 32-6520 | SG2 PUT UP WALKWAY FECE | 13.5
44675 | 44673 | 02-2300 | SG3 CLEAN UP AROUND PIPE AND PUMPS MAINTENANCE | 2.5
44675 | 44673 | 99-4560 | OG10 CLEAN AROUND SITE | 5.5
44675 | 44673 | 33-6010 | SG2 WELKIN SETTING PIPE IN TRENCH TO SG3/MACHINE NEDED/MOV TWO PALLETS OF SANDBAGS FROM SITE | 11.5
44675 | 44673 | 02-2000 | SG4 REMOVE SIDEWLK AND CURB CONCRETE | 7
44675 | 44673 | 31-1100 | SG5 STAYFORM - BACKFILLFOOTING FOR FLOODWALL | 3
44675 | 44673 | 31-2000 | OG6 DIG AROUND EXISTING OIL TANKS 3FT DOWN (TEST PIT) | 5
44675 | 44673 | 03-1900 | OG8 PATCH TOP OF FOT WALLS (POUR CONCRETE, 10 YD) | 16.5
44675 | 44673 | 33-3100 | SITE 8 - 8 LIVE LOADS OF DEBRI/CONTINUE EXCAVATION | 16
44675 | 44673 | 32-6520 | SITE 8 BEGIN TO FENCE OFF WORK AREA | 0.5
44675 | 44673 | 03-1000 | OG8 PREP FOR CONCRETE PUMP/MOVE FORMS TO OG10/CLEAN AREA | 6.5
44675 | 44673 | 99-4560 | SG6 CRANE ON SITE/SUPPORT AS NEEDED | 1
44675 | 44673 | 04-6120 | OG8 FAXA BACKUP MACHINE NEEDED FOR 2ND FLOOR | 2.5
44675 | 44673 | 02-2300 | SG3 MAINTAIN PUMPS | 3
44675 | 44673 | 99-4560 | OG8 OG9 OG10 CLEAN SITES | 16
44675 | 44673 | 33-2400 | COVER PUMPS | 3
44668 | 44662 | 03-2500 | SG4 INSTALL STAY FORM FOR MASONRY SHELF? | 17
44668 | 44662 | 33-6010 | OG3 WELKIN STEAM PIEPE INSTALL - MACHINE NEEDED | 6
44668 | 44662 | 02-2100 | OG5 CONCRETE REMOVAL FOR STEAM INSTALL | 23
44668 | 44662 | 32-6510 | OG6 OG5 INSTALL WHITE MESH/REPAIR | 9
44668 | 44662 | 03-2300 | OG10 BACKFILL/STAY FORM AT THRUST BLOCKS - PREP FOR CONCRETE POUR | 6
44668 | 44662 | 02-2000 | OG5 2 EA LIVE LOAD CONCRETE/CARBELLA (SIDEWALK REMOVAL/DEMO) | 3.5
44668 | 44662 | 33-2400 | COVER PUMPS | 2
44668 | 44662 | 32-6000 | SAW CUTTING/CORING | 8
44668 | 44662 | 02-2300 | OG6 FINISHING CLEANING BASEMENT (BASEMENT MAINT) | 9
44668 | 44662 | 02-2300 | SG5 CLEAN BASEMENT (BASEMENT MAINT) | 9
44668 | 44662 | 02-3000 | OG2 FINISHING REST OF CUTING DUCT PENETRATIONS | 9
44668 | 44662 | 02-3000 | OG3 CUT FLOOR PENETRATIONS | 17
44668 | 44662 | 02-6005 | OG6 PAINT REMOVAL | 9
44668 | 44662 | 99-4560 | SG6 LOAD CEMENT FOR FAXA | 3.5
44668 | 44662 | 99-4560 | OG6 SG5 OG8 PICK UP GARBAGE | 5.5
44668 | 44662 | 31-1400 | OG10 BACKFILL AROUND BUILDING | 3.5
44668 | 44662 | 03-1000 | OG8 STRIP EQUIPMENT PADS | 60.5
44668 | 44662 | 03-1000 | OG8 STRIP TANK & PUMP ROOMS | 8
44668 | 44662 | 03-2300 | SITE 8 PUT BULKHEAD INSIDE FOUNDATION FOR CONDUIT 8 FORM DUCT BANK | 34
44668 | 44662 | 03-2300 | OG10 FORM 4 THRUST BLOCKS | 26
44668 | 44663 | 03-1000 | OG8 STRIP TANK & PUMP ROOM | 86.5
44668 | 44663 | 03-2300 | OG1 FINISH THRUST BLOCK | 8
44668 | 44663 | 02-6060 | OG3 PATCH PENETRATIONS IN 2ND FLOOR APARTMENT | 6
44668 | 44663 | 03-1100 | SG4 FORM FLOOD WALLS | 28
44668 | 44663 | 03-1000 | OG8 CLEAN AROUND WOOD - FORM WORK | 7
44668 | 44663 | 99-4560 | SITE 8 CLEAN SAND & GARBE (SITE MAINT) | 5.5
44668 | 44663 | 99-4560 | SG6 CLEAN BY YODOCKS (SITE MAINT)?? | 5.5
44668 | 44663 | 99-4560 | OG6 SET PUMP FOR VITAL | 1
44668 | 44663 | 99-4560 | CLEAN AROUND WELKIN YARD (SITE MAIN) | 7
44668 | 44663 | 33-6010 | OG10 LOAD MACHINE FOR WELKIN FROM 2ND FL TO 1ST FL | 3
44668 | 44663 | 33-6010 | OG8 SET UP YODOCKS ON STREET (SUPPORT WELKIN CRANE) | 3
44668 | 44663 | 02-6005 | OG6 PAINT REMOVAL | 17
44668 | 44663 | 32-6000 | OG3 CUT FLOOR PENETRATIONS | 16.5
44668 | 44663 | 31-2000 | OG5 TEST PIT FOR WATER LINE/EXISTING UTILITIES | 20
44668 | 44663 | 02-2100 | OG5 CONCRETE REMOVAL FOR STEAM PIPE INSTALL/2EA LIVE LOADS - CARDELLA | 6.5
44668 | 44663 | 32-6520 | PG6 SET TRENCH BOX FOR TEMP. WALKWAY/REPAIR FENCE | 24
44668 | 44663 | 02-2100 | SG5 DEMO PAVEMENT/BID MAIN ENTRANCE | 13
44668 | 44663 | 99-4000 | OG8 REMOVE MAFIA BLOCK FORM & REET/INSTALL YODOCKS | 4
44668 | 44663 | 31-2000 | OG6 TEST PIT EXISTING UTILITIES FOR FSE TRENCH (HAND DIG) | 13
44668 | 44663 | 33-2400 | PUMPS | 2
44668 | 44664 | 03-1100 | SG4 FORM FLOOD WALLS & BRICK SHELF | 51
44668 | 44664 | 03-2300 | OG6 FORM THRUST BLOCK | 8.5
44668 | 44664 | 03-1000 | OG8 STRIP TANK + PUMP ROOM | 69
44668 | 44664 | 00-0017 | SG6 SAW CUT FOR GAS LINE INSTALL/START CHOP CONCRETE FLOOR | 18
44668 | 44664 | 31-2000 | OG6 VACUUM EXCAVATE AROUND UTILITIES AT MANHOLE RUN/COMPLETE EXCAVATION | 20
44668 | 44664 | 33-1000 | OG6 SHOWING/SUPPORT EXISTING UTILITIES (MAIN PROT EXIST PUT UTILITY) | 9
44668 | 44664 | 00-0023 | SITE 8 BACKFILL FIRE LINE | 11
44668 | 44664 | 31-1000 | SG5 EXCAVATE FOR FLOODWALL | 2.5
44668 | 44664 | 31-2000 | SITE 8 TEST PIT FOR EISTING SEWER WATE PIPE | 7
44668 | 44664 | 32-6510 | REPAIR WHITE MESH | 17
44668 | 44664 | 99-4600 | PRO J ON SITE/REPIR FLT TIRE | 1
44668 | 44664 | 03-1700 | OG10 RELOCATE REBAR AND CLEAN NEAR FRONT FENCE | 2
44668 | 44664 | 99-4560 | SG6 REMOVE GARBAGE | 1
44668 | 44664 | 33-2400 | COVER PUMPS | 3
44668 | 44664 | 32-6510 | OG10 CLEAN UP & REPLACE MECH (MESH INSTALL) | 5
44668 | 44664 | 33-6010 | CLEAN UP BY WELKIN YARD | 5
44668 | 44664 | 00-0011 | OG4 DEMO SHELFS ON 1ST FLOOR | 4
44668 | 44664 | 02-2300 | SG6 CLEAN WATER ON SHAFT (BASEMENT MAINT) | 4
44668 | 44664 | 00-0011 | SG5 DEMO WALL (CHANGE ORDER) | 5.5
44668 | 44664 | 00-0011 | OG2 DEMO WALLS AND BATH FLOOR PLUMBING | 5
44668 | 44664 | 00-0011 | OG3 DEMO WALLS AND BATH FLOOR PLUMBING | 3
44668 | 44664 | 99-4560 | OG7 CLEAN U YODUCKS (SITE MAINT) | 5
44668 | 44664 | 99-4560 | SITE 8 CLEAN AROUND YARD (SITE MAINT) | 4
44668 | 44664 | 02-6005 | OG6 PAINT REMOVAL | 16
44668 | 44665 | 03-1100 | SG4 FINISH FLOOD WALL | 18
44668 | 44665 | 03-2500 | SG4 FINISH BRICK SHELF | 22
44668 | 44665 | 03-1100 | SG5 FORM FOOTING FOR FLOOD WALL | 31
44668 | 44665 | 03-2300 | OG6 FINISH TRUS BLOCK | 3.5
44668 | 44665 | 03-1000 | OG8 STRIP - PUMP ROOM | 42
44668 | 44665 | 03-1000 | OG8 REARRANGE FORM (FORM WORK) | 4
44668 | 44665 | 03-1000 | OG8 BANDFORMS | 8
44668 | 44665 | 32-6520 | MAINTAIN GATES | 0.5
44668 | 44665 | 33-3100 | OG6 MINIMIZE STOCK PILE FRM EXCAVATION/FSE ELECTRIC TRENCH (TRENCH) | 8
44668 | 44665 | 03-2300 | OG10 BACKFILL THRUST BLOCKS FOR CONCRETE POUR | 9
44668 | 44665 | 03-2500 | SG4 INSTALL STAYFORM (MASONRY SHELF) | 3
44668 | 44665 | 31-1100 | SG4 BACKFILL FOR MASONRY SHELF (MASONRY SHELF) | 19
44668 | 44665 | 03-2300 | OG10 POUR THRUST BLOCKS | 5
44668 | 44665 | 03-2300 | SITE 8 POUR DUCTBANK | 2
44668 | 44665 | 00-0023 | SITE 8 BACKFILL DUCTBANK/PREP FOR TEMP. WALKWAY POUR | 13
44668 | 44665 | 03-1000 | OG8 MOVE FORMS/CLEAN AREA- MOVE LUMBER TO SITE 8 | 2
44668 | 44665 | 99-4560 | OG8 CLEAN GARBAGE | 1
44668 | 44665 | 00-0017 | SG6 CHOP FOR GAS LINE INSTALL | 3
44668 | 44665 | 33-2400 | COVER PUMPS | 3
44668 | 44665 | 00-0011 | OG3 FINISHING CHOPING | 5.5
44668 | 44665 | 00-0011 | OG4 FINISHING CHOPING | 8
44668 | 44665 | 00-0011 | OG2 FINISHING CHOPING | 5
44668 | 44665 | 02-6005 | OG6 PAINT REMOVAL | 11.5
44668 | 44665 | 99-4560 | OG8 CLEAN UP | 7
44668 | 44665 | 99-4560 | SG4 CLEAN UP | 9.5
44668 | 44665 | 99-4560 | CLEAN UP AROUND OG10 BETWEEN OG6 | 4
44668 | 44665 | 00-0017 | CHOP FOR GAS LINE INSTALL | 20.5
44668 | 44665 | 33-3100 | OG10 CLEAN UP TRENCH | 5
44668 | 44665 | 32-6510 | OG5 REPLACE WHITE MESH | 2.5
44668 | 44665 | 02-6060 | DELIVER FOOR FRAMES ON EVERY BUILDING TOOK 2 EACH | 7
44668 | 44666 | 03-1900 | OG8 PATCH AROUND WALL | 8.5
44668 | 44666 | 02-6060 | OG1 CHOP DRAIN IN 2ND FL | 2.5
44668 | 44666 | 31-1100 | BACK FILL FROM SG2 WITH DIRT FROM SG6 WITH DUMP TRUCK | 28.5
44668 | 44666 | 02-3000 | OG2 CHOP FOR DUCT PENETRATION (7) | 8.5
44668 | 44666 | 99-4560 | OG8 CLEAN AROUND BUILDING | 8
44668 | 44666 | 33-6010 | SG3 CLEAN AROUND WELKIN YARD | 3.5
44668 | 44666 | 02-6005 | OG6 PAINT REMOVAL | 8.5
44668 | 44666 | 99-4000 | OG8 REMOVE YODUCTS FROM STREET | 2.5
44668 | 44666 | 33-3100 | SG3 MAINTAIN TRENCHES AND PUMPPS | 7.5
44668 | 44666 | 99-4560 | SG3 PICK UP GARBAGE FRON WELIN YARD | 3.5
44668 | 44666 | 32-6520 | SG4 PUT BACK GATE AND FENCE | 3
44668 | 44666 | 99-4560 | SG7 CLEAN AROUND BUILDING | 2.5
44668 | 44666 | 99-4560 | SG6 PICK UP GARBAGE | 2.5
44668 | 44666 | 99-4560 | SG9 PICK UP GARBAGE | 2.5
44668 | 44666 | 31-2200 | FLAG BY SG6 FOR DUMP TRUCK (BACKFILL) | 8
44668 | 44666 | 03-2100 | SG4 POUR FLOODWALLS AND MASONRY SHELF | 48.5
44668 | 44666 | 32-6520 | SITE8 POUR TEMP WALKWAY | 2.5
44668 | 44666 | 33-2400 | PUMPS | 1
44668 | 44666 | 31-1900 | SG4 TREE PROTECTION | 9
44668 | 44666 | 03-1000 | SG6 FORM ROOF PENETRRATION | 26
44668 | 44666 | 03-1100 | SG5 FORM FOOTING FOR FLOOD WALL | 17
44668 | 44666 | 03-1000 | OG8 STRIP PLUMBING SHAFT | 62.5
44668 | 44666 | 03-1000 | OG8 BAND FORMS | 14
44661 | 44655 | 33-1000 | SG2 CUT AND CAP PIPE RUNNING & HMU STEAM TRENCH | 5
44661 | 44655 | 31-1000 | OG1 COMPLETE EXCAVATION FOR MASONRY SHELF | 5
44661 | 44655 | 33-1000 | OG1 BUILD DECK FOR FSP ACCESS/MOVE FENCE (MAINT & PROTECT EXIST PUT UTILITY) | 5
44661 | 44655 | 31-1000 | SG5 EXCAVATE FOR FLOODWALL/ 1 LIVE LOAD CONCRETE - "CARDELLA" | 14
44661 | 44655 | 02-1600 | OG3 FLATTEN THE DIRT/SAND PILES | 5
44661 | 44655 | 03-1900 | OG8 PREP FOR POUR/CLEAN AREA FOR CONCRETE PUMP (CODE TO POUR CONC) | 9.5
44661 | 44655 | 32-6510 | SITE 8 OG3 OG4 MAINTAIN WHITE MESH | 17
44661 | 44655 | 99-4560 | SG6 REPAIR MAIN GATE | 3
44661 | 44655 | 99-4560 | SG6 SG5 SG4 CLEAN UP AROUND BUILDING | 16
44661 | 44655 | 02-3000 | SG4 CORE REMAINING HOLES 2EA 3.5" | 5
44661 | 44655 | 02-6005 | OG6 PAINT REMOVAL | 17
44661 | 44655 | 02-3000 | SITE 8 FINISHING PENETRATION | 9
44661 | 44655 | 02-3000 | SG5 FINISHING PENETRATION | 9
44661 | 44655 | 99-4560 | SG3 CLEAN UP AROUND WELKIN YARD | 8.5
44661 | 44655 | 31-1000 | SG5 REMOVE DIRT FROM EXCAVATION ON FLOORWALL | 3
44661 | 44655 | 03-1900 | OG8 BURN HOLES FOR REBAR (CODE TO POUR CONCRETE) | 12
44661 | 44655 | 03-1000 | OG8 PATCH HOLES IN DECK | 56.5
44661 | 44655 | 03-1000 | OG8 FINISH CLOSING UP WALLS | 79
44661 | 44655 | 33-1000 | MAINT/PROTECT EXISTING PUT UTILIT | 4
44661 | 44656 | 03-1900 | OG8 PREP AND CLEAN DECK FOR CONCRETE POUR | 9
44661 | 44656 | 03-1900 | OG8 POUR OIL TANK AND DECK | 110.5
44661 | 44656 | 03-1900 | OG8 CONCRETE WATCH (POUR CONCRETE) | 43.5
44661 | 44656 | 03-1000 | OG8 INSTALL PIPE BRACE (FORM WORK) | 16
44661 | 44656 | 03-1000 | OG8 START CLOSING UP PLUMBLING SHAFT (FORM WORK) | 50.5
44661 | 44656 | 99-4560 | SG6 CLOSE HOLES ON ROOF (SITE MAINT) | 6
44661 | 44656 | 32-6000 | SG5 COMPLETE SAWCUT AND CLEAN UP | 17
44661 | 44656 | 02-2300 | SG4 CLEAN BASEMENT WATER (BASEMENT MAINT) | 6
44661 | 44656 | 99-4560 | OG9 CLEAN UP AROUND SITE (SITE MAINT) | 8
44661 | 44656 | 99-4560 | SG6 CLEAN UP AROUND SITE (SITE MAINT) | 8
44661 | 44656 | 02-6005 | OG6 PAINT REMOVAL | 17
44661 | 44656 | 03-1900 | OG8 HELP WITH CONCRETE POUR (POUR CONCRETE) | 4
44661 | 44656 | 33-3100 | SG2 MACHINE NEEDED FOR STEAM TRENCH | 8
44661 | 44656 | 31-1100 | SG4 BACKFILL FOR MASONRY SHELF - INSTAL STAYFOEM | 16
44661 | 44656 | 33-2400 | PUMPS | 2
44661 | 44657 | 02-2300 | SG1 PUMP DOWN BASEMENT | 9.5
44661 | 44657 | 02-2300 | SG3 PUMP DOWN BASEMENT | 3
44661 | 44657 | 02-2300 | SG4 PUMP DOWN BASEMENT | 3
44661 | 44657 | 31-1000 | SG5 SAW CUT SIDEWALK - START EXCAVATE FOR FLOODWALL | 12
44661 | 44657 | 00-0023 | SITE 8 ADJUST FENCE AT FIRE STAND PIPE/BACKFILL PARTIAL F.S.P (FSP CHANGE ORDER) | 13.5
44661 | 44657 | 32-6000 | SG5 COMPLETE REMAINING SAWCUTE ON 1ST FLOOR/CLEAN UP | 10.5
44661 | 44657 | 02-6005 | OG6 PAINT REMOVAL | 17
44661 | 44657 | 31-1100 | SG4 BACKFILL FOR MASONRY SHELF | 28.5
44661 | 44657 | 99-4560 | SG6 OG8 OG9 CLEAN UP BUILDINGS - INSIDE AND OUTSIDE | 22
44661 | 44657 | 33-2400 | COVER PUMPS | 3
44661 | 44657 | 99-4560 | OFFLOAD STAIR STRINGERS FOR E&Y | 1
44661 | 44657 | 03-1000 | OG8 FRAME FORMWORK FOR PLUMBLING SHAFT | 100.5
44661 | 44657 | 03-1000 | OG8 START STRIPPING TANKWALL + PUMP ROOM | 24
44661 | 44657 | 02-6008 | LEAD TRAINEE | 4
44661 | 44658 | 99-4560 | SG6 OG8 CLEAN AROUND BUILDING | 17
44661 | 44658 | 02-6005 | OG6 PAINT REMOVAL | 1
44661 | 44658 | 03-1400 | OG8 PREPAIR PADS (DRILL DOWEL) | 18.5
44661 | 44658 | 32-6000 | OG3 CUT OUT OPENINGS ON 2ND FLOOR (SAW CUT) | 20
44661 | 44658 | 03-1000 | OG8 CLOSE UP FORMS ON PLUMBING SHAFT (FW) | 37
44661 | 44658 | 03-1000 | OG8 FORM 7 EQUIPMENT PADS (FW) | 31
44661 | 44658 | 99-4560 | OG8 CLEAN UP | 16
44661 | 44658 | 03-1900 | OG88 BURN HOLES TO POUR CONCRETE (POUR CNCRETE) | 17
44661 | 44658 | 32-6510 | OG8 SAFETY NETTING & TOEBOARD (WHITE MESH INSTALL) | 19.5
44661 | 44658 | 31-1000 | SG5 EXCAVATE FOR FLOODWALL | 20
44661 | 44658 | 33-3100 | OG3 CUT GRADE/MAINTAIN SLOPE ON SIDES ( TEST PIT OR TRENCHING) | 12.5
44661 | 44658 | 02-6008 | CLARITY TESTING ON SITE FOR FIT TEST AND LEAD TEST | 6
44661 | 44658 | 02-6005 | OG6 PAINT REMOVAL | 15
44661 | 44658 | 32-6510 | MAINTAIN WHITE MESH | 10
44661 | 44658 | 99-4560 | PUMP DELIVERY FOR VITAL | 1
44661 | 44658 | 99-4560 | SG6 CLEAN AREA/REMOVE GARBAGE FROM 2ND FLOOR | 2
44661 | 44658 | 99-4560 | OG8 CLEAN AREA | 3
44661 | 44658 | 33-2400 | COVER PUMPS | 3
44661 | 44658 | 02-3000 | CORE DRILL PULL OUT CORES | 4
44661 | 44658 | 33-1000 | MAINT PORT OF EXISTING PUT UNILITIES (CHOP) | 7
44661 | 44659 | 03-1900 | OG8 CLEAN UP (CODE TO POUR CONC, NEW BLD) | 4
44661 | 44659 | 99-4560 | SG6 CLEAN UP AROUND BUILDING (SITE MAINT) | 5
44661 | 44659 | 32-6000 | SG6 CUT PUT ROOF PENETRATION VITAL (SAW CUT) | 9.5
44661 | 44659 | 32-6000 | OG2 CHOP HOLES FOR DUCK PENETRATION | 20
44661 | 44659 | 02-6060 | OG3 CUT OUT OPENINGS ON 2ND FLOOR | 10
44661 | 44659 | 03-1900 | OG 8 POUR SHAFT WALLS & PADS | 11
44661 | 44659 | 31-1100 | SG4 BACKFIL FOR MASONRY SHELF | 23
44661 | 44659 | 31-1000 | SG5 EXCAVATE FOR FLOODWALL | 4.5
44661 | 44659 | 03-1900 | OG8 POUR SHAFTWALLS AND PADS | 50.5
44661 | 44659 | 99-4560 | SG6 FAXA NEED LULL | 2
44661 | 44659 | 03-1900 | OG8 CLEAN AREA - 2ND FLOOR (POUR CONC) | 4.5
44661 | 44659 | 33-6010 | OG3 MACHINE NEEDED FOR WELKIN - MOVE STEAM PIPES | 12
44661 | 44659 | 33-2400 | COVER PUMPS | 3
44661 | 44659 | 03-1000 | OG8 FINISH FOAMING PLUMBLING SHAFT | 14.5
44661 | 44659 | 03-1900 | OG8 FINISH 6" PADS (7) PUTTING GRASE | 8
44661 | 44659 | 03-1000 | OG8 START STRIPPING TANK WALL | 74
44661 | 44659 | 03-1900 | OG8 POUR CONCRETE | 7
44661 | 44659 | 99-4000 | DIVIDING WALL IN SHANTY (SITE SET UP) | 9
44654 | 44648 | 03-1100 | SG4 FORM FLOOD WALLS | 22.5
44654 | 44648 | 03-1700 | OG8 BUILD SCAFFOLDING FOR LATHERS (NOT FORM FORM, SUB SUPPORT OR POUR CONC) | 26
44654 | 44648 | 99-4560 | OG8 PUT UP SAFETY RAIL AROUND PLUMBING SHAFT | 10
44654 | 44648 | 03-1000 | OG8 FORM WALLS | 41
44654 | 44648 | 99-4560 | OG9 SAFETY ITEMS (SITE MAINT) | 7
44654 | 44648 | 03-1100 | SG4 STRIP STYRO FOAM OFF WALLS | 6
44654 | 44648 | 31-1700 | SG7 CLEAN TRENCHES (MAINTAIN PUMPS) | 4.5
44654 | 44648 | 02-2300 | SG6 DRY SHAFT (BASEMENT MAINT) | 20.5
44654 | 44648 | 02-2300 | OG3 CLEAN BASEMENT | 4.5
44654 | 44648 | 02-6050 | OG6 DEMO STAIRS | 24.5
44654 | 44648 | 99-4560 | SG6 PICKUPS FOR FAXA | 2.5
44654 | 44648 | 33-6010 | OG10 PICKUPS FOR WELKIN | 2.5
44654 | 44648 | 99-4560 | OG6 PICK UP GARBAGE (SITE MAINT) | 8
44654 | 44648 | 03-6000 | FRP INSTALL | 17.5
44654 | 44648 | 99-4560 | OG3 PICK UP GARBAGE | 5
44654 | 44648 | 32-6520 | SG2 MOVE FENCE FOR STEAM EXCAVATION | 40
44654 | 44648 | 31-2200 | OG3 BACKFILL FOR MACHINE ACCESS/PREP TO MOVE TRANCH BOX (REWORK @ POE | 6
44654 | 44648 | 26-6030 | OG6 BUILD WORK DECK FOR FSE CONDUIT | 9
44654 | 44648 | 03-1700 | OG8 OG1 OG2 OG3 REBAR DELIVERY | 6
44654 | 44648 | 03-1100 | SG5 CLEAN UP FORMS HARDWARE BY FLOODWALL (FORM WORK) | 3.5
44654 | 44648 | 31-1700 | JUMP/PUMPS | 2
44654 | 44649 | 02-6060 | OG6 DEMO 2ND FLOOR WINDOWS | 9.5
44654 | 44649 | 02-2300 | SG3 FINISHING CLEANING OF BASEMENT (BASE MAINT) | 17
44654 | 44649 | 02-6050 | OG6 DEMO STAIRS | 9.5
44654 | 44649 | 02-3000 | CORE 3.5" HOLES (2 EACH) | 9
44654 | 44649 | 99-4560 | SG4 SG6 SG3 PICK UP DEBRIS AT VARIOUS PLACES (SITE MAINT) | 14
44654 | 44649 | 33-6010 | SG6 OG10 MAKE TWO PICKUPS FOR WELKIN | 5.5
44654 | 44649 | 02-3000 | CUT SLAB PENETRATION | 17
44654 | 44649 | 03-1100 | SG4 FORM FLOOD WALLS | 26
44654 | 44649 | 02-6130 | SG7 PROTECTION FOR ATCO | 10
44654 | 44649 | 03-1700 | OG8 BUILD SCAFFLOLD FOR LATHERS | 47.5
44654 | 44649 | 03-1000 | OG8 START CLOSING UP FORMS | 37
44654 | 44649 | 33-3100 | SG2 CONTINUE EXCAVATION FOR STEAM | 26.5
44654 | 44649 | 02-1900 | SG2 (3) LIVE LOADS/DEBRIS CONCRETE & ASPHALT (ASPHALT REMOVAL) | 6.5
44654 | 44649 | 00-0019 | OG3 OG2 POUR TEMP WALKWAYS (FENCE C/O) | 12
44654 | 44649 | 33-3100 | OG5 RECEIVE AND BUILD BOXES (TRENCH) | 12
44654 | 44649 | 02-1900 | OG5 (1) LIVE LOAD CONCRETE (DEMO/DEBRIS LOADOUT) | 2.5
44654 | 44649 | 00-0019 | OG5 BEGIN TO INSTALL TEMP WALKWAY - EXCAVATE (FENCE C/O) | 13
44654 | 44649 | 31-1700 | COVER PUMPS | 2
44654 | 44650 | 02-2300 | OG6 CLEAN BASEMENT (BASE MAINT) | 21
44654 | 44650 | 02-3000 | OG5 CUT PENETRATIONS (FOR FSE SAW CUT) | 17
44654 | 44650 | 32-6520 | SG6 MOUNT FENCE GATE FOR FAXA (FENCE INSTALL) | 8
44654 | 44650 | 00-0019 | OG3 FIX OR REPAIR GATE BY OG3 (FENCE CO) | 7
44654 | 44650 | 00-0019 | OG3 MOUNT FENCE ON WALKWAY | 11.5
44654 | 44650 | 31-2200 | SG1 BACKFILL STEAM PIPE/hns TRUCK ON SITE | 41.5
44654 | 44650 | 33-3100 | SG2 2 EA 20YD LIVE LOAD/FIX TRENCH | 4.5
44654 | 44650 | 99-4560 | OG6 LOADOUT STAIN DEBRIS | 1
44654 | 44650 | 00-0019 | OG3 INSTALL FENCE TEMP WALKWAY (FENCE CO) | 2
44654 | 44650 | 31-1700 | COVER PUMPS | 3
44654 | 44650 | 00-0019 | FENCE CO | 12
44654 | 44650 | 03-1000 | OG8 CLOSE UP FORMS FOR TANK ROOM AND PUMP ROOM | 128.5
44654 | 44651 | 31-2200 | SG1 BACKFILL STEAM PIPE/HNS TRUCK ON SITE | 42
44654 | 44651 | 02-3000 | SG5 CUT SLAB PENETRATIONS | 16.5
44654 | 44651 | 32-6520 | SG5 PREP AND POUR TEMP WALKWAY (THIS IS FOR FLOOD GATE) | 10
44654 | 44651 | 00-0019 | OG2 INSTALL FENCE AT TEMP WALKWAY (FENCE CO) | 21
44654 | 44651 | 00-0019 | OG3 FINISH FENCE AT TEMP WALKWAY (FENCE CO) | 10
44654 | 44651 | 32-6520 | OG5 POUR TEMP WALKWAY | 4
44654 | 44651 | 99-4560 | OG6 LOAD OUT STAIN DEBRIS | 11
44654 | 44651 | 02-6060 | SG6 CLEAN DEBRIS SENCOND FLOOR | 6
44654 | 44651 | 33-3100 | SG2 WELKIN MOBILIZE PIPE TO TRRENCH/BEGIN STEAM PIPE INSTALLATION TO SG3 | 8
44654 | 44651 | 99-7200 | HOLIDAY PAY | 8
44654 | 44651 | 31-1700 | PUMPS | 3
44654 | 44651 | 03-1000 | OG8 CLOSE UP WALL FORMS | 149.5
44654 | 44652 | 32-6520 | SG5 INSTALL FENCE | 13.5
44654 | 44652 | 31-1000 | OG1 OG2 COMPLETE EXCAVATION FOR MASONRY SHELF | 9
44654 | 44652 | 00-0019 | OG2 INSTALL FENCE AT TEMP WALKWAY (FENCE C/O) | 12
44654 | 44652 | 33-3100 | OG3 MOVE TRENCH BOX - COMPLETE EXCAVATION | 35
44654 | 44652 | 00-0019 | OG5 INSTALL FENCE ON TEMP WALKWAY(FENCE C/O) | 16.5
44654 | 44652 | 33-6010 | SG2 MACHINE NEEDED FOR WELKIN STEAM PIPE INSTALATION | 4.5
44654 | 44652 | 99-4560 | SG6 LULL NEEDED FOR FAXA | 2.5
44654 | 44652 | 99-4560 | OG8 GENERAL CLEAN UP | 16
44654 | 44652 | 99-4560 | SG5 CLEAN UP AROUND BUILDING | 16
44654 | 44652 | 02-3000 | CUT PENETRATIONS FOR FSE ON SITE 8 | 17
44654 | 44652 | 31-1700 | COVER PUMPS | 2
44654 | 44652 | 03-1900 | OG8 POUR CONCRETE CLAIM 3 YDS | 4
44654 | 44652 | 03-1000 | OG8 CLOSE- UP TANK WALL AND PUMP WALL | 153.5
44647 | 44641 | 03-2100 | SG5 CONCRETE POUR (6 YDS) | 10
44647 | 44641 | 03-1000 | SG5 GATHER MATERIAL, BRING IT TO OG8 | 9
44647 | 44641 | 03-1000 | OG10 BRING MATERIAL TO OG8 | 9
44647 | 44641 | 03-1000 | OG8 START FORMING PLUMBING SHAFT, TANK ROOM & PUMP ROOM | 76.5
44647 | 44641 | 03-2100 | SG5 POUR FLOODWALL & MASONRY SHELF (60 YDS) | 63.5
44647 | 44641 | 03-1400 | SG4 EPOXY BARS FOR MASONRY SHELF | 9
44647 | 44641 | 31-1700 | COVER PUMPS | 1
44647 | 44641 | 03-6000 | OG5 PREPARE FOR FRP 1ST FL | 16
44647 | 44641 | 03-6000 | OG3 FINISHED PAIR REMOVAL (FRP) | 16
44647 | 44641 | 33-3100 | SG7 MAINTAIN TRENCHES | 9
44647 | 44641 | 99-4560 | SG6 CLEAN UP AROUND | 10
44647 | 44641 | 99-4560 | OG9 CLEAN UP AROUND BUILDING | 14
44647 | 44641 | 33-6010 | SG3 MOVE 2 SAND PALETS FROM YARD TO YARD WELKIN/FIVESTAR | 5.5
44647 | 44641 | 99-4560 | CLEAN AROUND YARD | 5
44647 | 44641 | 33-6010 | PUT PIPES IN TRENCH FROM SG3 TO OG5 STEAM PIPES | 6
44647 | 44641 | 26-6030 | DROP PALETS OF SAND BY FSE YARD | 1
44647 | 44642 | 99-4560 | SG6 LOAD A PALET OF CEMENT FOR FAXA TO 2ND FLOOR | 2
44647 | 44642 | 99-4560 | SG6 CLEAN AROUND BUILDING | 13
44647 | 44642 | 99-4560 | OG8 CLEAN UP ON THE 2ND FLOOR | 10
44647 | 44642 | 99-4560 | SG4 CLEAN UP 2ND FLOOR | 2
44647 | 44642 | 32-6000 | SAW CUT PENETRATION IN BASEMENT | 4
44647 | 44642 | 03-6000 | SG5 INSTALL FRP ON 1ST FLOOR | 16
44647 | 44642 | 32-6520 | SG2 FENCE OFF PLAY GROUND | 30.5
44647 | 44642 | 02-6015 | OG2 CLEAN UP WINDOWS DEBRI | 2
44647 | 44642 | 31-2000 | EXPOSE MH FOR FSE TO CORE (TEST PIT) | 2
44647 | 44642 | 99-4560 | HOUSE KEEPING BY FSE YARD | 1
44647 | 44642 | 03-6000 | OG3 FRP | 12
44647 | 44642 | 33-3100 | SG2 BEGIN EXCAVATION FOR STEAM | 18
44647 | 44642 | 03-1400 | SG4 EPOXY BARS FOR MASONRY SHELF | 9
44647 | 44642 | 33-3100 | OG1 EXPOSE MANHOLE FOR FSE TO CORE | 11.5
44647 | 44642 | 99-4560 | OG5 CLEAN AREA BY FSE YARD | 2
44647 | 44642 | 33-2600 | SG5 RECEIVE CATCH BASINS | 10
44647 | 44642 | 33-1000 | OG6 FINISH MOVE PLANTS SG1 GARDEN | 3
44647 | 44642 | 33-6010 | OG8 CRANE/OIL TANK DELIVERRY | 3
44647 | 44642 | 31-1700 | PUMPS | 2
44647 | 44642 | 03-1100 | SG4 STRIP FLOOD WALL | 28
44647 | 44642 | 03-1000 | OG8 FORM PLUMBLING SHALF TANK ROOM/PUMP ROOM | 84.5
44647 | 44643 | 03-1700 | REBAR TO SGN AND OG8 | 7
44647 | 44643 | 33-3100 | SG2 CONTINUE EXCAVATION FOR STEAM | 16.5
44647 | 44643 | 33-3100 | SG2 LOAD OUT DEBRIS - 4 LIVE LOADS | 3.5
44647 | 44643 | 33-1000 | REPAIR EXISTING UNTILITY STORM PIPE | 10
44647 | 44643 | 03-1400 | SG4 EPOXY BANS FOR MASONRY SHELF (DRILL + DOWEL) | 9
44647 | 44643 | 33-3100 | OG6 BUILD DECK FOR FSE CONDUIT INSTALL (TRENCH, DONE B/C NO OTCR) | 9
44647 | 44643 | 33-3100 | OG10 LOAD OUT CONCRETE DEBRIS - 2 LIVE LOADS | 2
44647 | 44643 | 02-1600 | CONSOLIDATE STOCK PILES - HNS TRUCK ON SITE - OG6/OG2/OG1 | 17.5
44647 | 44643 | 31-1700 | PUMPS | 2
44647 | 44643 | 99-4560 | SG6 CLEAN UP AROUND BUILDING | 18
44647 | 44643 | 03-1000 | OG8 UNLOAD FORMS TRAILER | 3.5
44647 | 44643 | 32-6000 | OG3 SAWCUT WALL IN BASEMENT (FIVESTAR) | 14
44647 | 44643 | 03-6000 | SG5 INSTALL FRP | 17
44647 | 44643 | 02-2300 | OG2 PUMP WATER BASEMENT (BASEMENT | 3.5
44647 | 44643 | 99-4560 | OG10 CLEAN AROUND BUILDING | 4.5
44647 | 44643 | 99-4560 | OG7 CLEAN UP AROUND BUILDING | 3
44647 | 44643 | 03-6000 | OG3 INSTALL FRP | 16
44647 | 44643 | 03-1100 | SGA STAY FORM FOR FRONT ENTRANCE FOOTING (FLOOD WALLS) | 11
44647 | 44643 | 03-1100 | SG5 STRIP FLOOD WALLS | 16
44647 | 44643 | 99-4560 | SG6 ADDRESS SAFETY ISSUES | 1
44647 | 44643 | 03-1000 | OG8 FORM PLUMBLING SHAFT + PUMP ROOM | 90.5
44647 | 44643 | 03-1000 | OG8 UNLOAD TRAILER W/ FORMS | 2
44647 | 44644 | 32-6000 | SG2 CUT IN 4 PENETRATIONS FOR DUCKWORK (SAWCUTTING) | 12
44647 | 44644 | 99-4560 | SG6 CLEAN 2ND FLOOR AND ADOUND BUILDING (SITE MAINT) | 8
44647 | 44644 | 03-6000 | SG5 INSTALL FRP | 16.5
44647 | 44644 | 03-6000 | OG3 INSTALL FRP IN BASEMENT | 16.5
44647 | 44644 | 33-6010 | SG6 PICK UP FOR WELKIN (SUB SUPPORT) | 3
44647 | 44644 | 33-6010 | SG10 PICK UP FOR WELKIN (SUB SUPPORT) | 3
44647 | 44644 | 03-1700 | OG8 PICK UP FOR IRON WORKERS FOR 2ND FLOOR (FOR TONAGE) | 3
44647 | 44644 | 99-4560 | SG0 CLEAN UP AROUND BUILDING | 2
44647 | 44644 | 33-3100 | SG2 CONTINUE EXCAVATION FOR STEAM TO SG3 | 17
44647 | 44644 | 02-2200 | SG2 LOAD OUT DEBRIS 2 LIVE LOADS 1 LIVELOAD - CONCRETE | 3.5
44647 | 44644 | 03-1400 | SG4 EPOXY BARS FOR MASONRY SHELF (DRILL + DOWEL) | 11
44647 | 44644 | 00-0019 | OGS OG3 PREP FOR TEMP WALKWAY/CLEAN AREA (FENCE C/O) | 11
44647 | 44644 | 02-2100 | OG6 CUT WALL FOR CONDUIT TO PASS THRU | 17
44647 | 44644 | 02-1700 | SG2 CLEAN AREA - IRON BLACK FENCE (DEMO/C+G/CURB REMOVAL) | 1.5
44647 | 44644 | 02-2300 | SG2 REMOVE SCAFFOLD - BASEMENT (BASEMENT MAINT) | 2.5
44647 | 44644 | 31-2200 | OG10 BACKFILL TRENCH (STEAM) | 11
44647 | 44644 | 02-3000 | OG6 CHOP FLOOR DRAINS BASEMENT | 4
44647 | 44644 | 02-2300 | BASEMENT MAINT PUMP SG5 + OG2 | 4.5
44647 | 44644 | 31-1700 | COVER PUMPS | 1
44647 | 44644 | 03-1100 | SG4 FINISH STAY FORM FOR FLOODWALL FOOTING (ENTRANCE) | 5
44647 | 44644 | 03-1100 | SG5 FINISH STRIPPING FLOOD WALL | 18
44647 | 44644 | 03-1100 | SG5 TRANSFER FORMS TO SG4 (CLAIM LOAD OUT ONLY) | 17.5
44647 | 44644 | 03-1000 | OG8 FORM TANK WALL | 88
44647 | 44645 | 03-6000 | SG5 INSTALL FRP 1ST FLOOR | 17
44647 | 44645 | 03-6000 | OG3 INSTALL FRP IN BASEMENT | 17
44647 | 44645 | 99-4560 | SG6 FIX & CLEAN OUTSIDE U DUCKS (SITE MAINT) | 12
44647 | 44645 | 99-4560 | OG7 FIX & CLEAN OUTSIDE U DUCKS (SITE MAINT) | 12
44647 | 44645 | 02-2300 | SG3 CLEAN BOILER ROOM/SANITIZE (BASEMENT MAINT) | 8
44647 | 44645 | 02-6060 | OG1 DEMO WALLS AT 2ND FLOOR FOR VITAL | 3.5
44647 | 44645 | 02-6065 | OG5 DEMO FOR VITAL DRIAN VENTS | 8.5
44647 | 44645 | 02-6065 | OG6 DEMO FOR VITAL FLOOR DRAIN VENTS | 8.5
44647 | 44645 | 03-1000 | OFFLOAD FORMS | 4
44647 | 44645 | 00-0019 | OG3 OG2 PREP FOR TEMP WAKWAY (FENCE C/O) | 5
44647 | 44645 | 32-6510 | OG9 REPAIR AND REPLACE MESH | 7
44647 | 44645 | 31-2200 | OG10 BACKFILL TRENCH | 25.5
44647 | 44645 | 32-6520 | OG10 SG4 REMOVE FENCE NO MORE NEEDED/FENCE SELF PREFORM | 11
44647 | 44645 | 33-2400 | COVER PUMPS | 2
44647 | 44645 | 03-2100 | SG4 PUT IN WATERSTOP | 13
44647 | 44645 | 03-1100 | SG4 START CLOSING UP FLOODWALLS | 22
44647 | 44645 | 03-1000 | OG8 UNLOAD FORM TANK | 4
44647 | 44645 | 03-1000 | OG8 FORM TANK WALL | 65.5
44647 | 44645 | 03-1100 | SG5 OVE FORMS TO SG4 (CLAIM LOAD OUT QTY) | 12
44640 | 44634 | 03-1100 | SG4 CONTINUE FORMING FLOOD WALLS | 28
44640 | 44634 | 03-1000 | OG8 PUT SHOE DOWN FOR WALLS & COLUMNS (FORM WORK) | 14.5
44640 | 44634 | 03-1000 | OG8 START FORMS FOR COLUMNS WITH BRACING (WOOD FORMS) | 14
44640 | 44634 | 99-4560 | OG9 SAFETY ITEMS (SITE MAINT) | 8
44640 | 44634 | 03-1400 | SG4 DRILL DOWELS FOR MASONRY SHELF | 18
44640 | 44634 | 32-6520 | OG1 INSTALL FENCE FOR EXCAVATION | 6
44640 | 44634 | 32-6520 | SG4 REMOVE FENCE NO MORE NEEDED - MOVE FENCE TO OG 1FENCE SELF PREFORM | 4
44640 | 44634 | 31-1000 | OG1 EXCAVATE FOR MASONRY FOUNDATION | 21
44640 | 44634 | 33-3100 | OG6 EXCAVATE FOR ELECTRICAL RUN | 16
44640 | 44634 | 33-6010 | SG6 MACHINE NEEDED FOR WELKIN - STEAM PIPE ON TRENCH | 1.5
44640 | 44634 | 03-6000 | OG3 PREP AND INSTALL FRP | 18
44640 | 44634 | 02-6005 | OG6 PAINT REMOVAL | 16
44640 | 44634 | 33-3100 | OG6 MOVE PILE OF DIRT FROM EXCAVATION "ELECTRIC RUN" (EXCAVATION) | 4
44640 | 44634 | 99-4560 | SG6 CLEAN UP AREA | 18.5
44640 | 44634 | 99-4560 | OG9 CLEAN UP AREA | 22
44640 | 44634 | 33-2400 | PUMPS | 2
44640 | 44634 | 26-6030 | SG6 LULL | 1
44640 | 44635 | 03-1100 | SG4 EXCAVATE FOR FLOODWALL AT FRONT BLD ENTRANCE | 2.5
44640 | 44635 | 99-4560 | SG4 SG5 OG9 CLEAN AREA (SITE MAINT) | 18
44640 | 44635 | 31-2200 | SG6 LEVEL AREA BEHIND BLD FOR MANLIFT ACCESS | 7
44640 | 44635 | 33-3100 | SG7 MAINTAIN TRANCHES | 14
44640 | 44635 | 31-1000 | OG2 EXCAVATE FOR MASONRY FOUNDATION | 19
44640 | 44635 | 31-2200 | SG5 BACKFIL FOR SHELF "CONCRETE POUR" BACKFILL AT BRICK SHELF | 18.5
44640 | 44635 | 32-6520 | OG2 INSTALL FENCE FOR EXCAVATION - FENCE SELF PREFORM | 23
44640 | 44635 | 03-6000 | OG3 PREP AND INSTALL FRP | 25
44640 | 44635 | 03-1000 | OG8 CLEAN AND PREP AREA FOR FORM DELIVERY | 7
44640 | 44635 | 33-3100 | SG7 EXCAVATE AROUND STEAM PIPE FOR ASBESTOS & BACKFILL TRENCH FOR MACHINE ACCESS | 12
44640 | 44635 | 00-0022 | SITE 8 CLEAN AND SANTITIZE BASEMENT & TEM ACTIVITY | 10.5
44640 | 44635 | 31-1000 | OG1 OG2 BUILD PLATFORMS FOR FSP ACCESS | 5
44640 | 44635 | 03-2500 | SG5 INSTALL STAYFORM AROUND BUILDING FOR BRICKSHELF | 22
44640 | 44635 | 03-2500 | SG5 INSTALL BEAM BOTTOM & FACE FOR BRICKSHELF | 22
44640 | 44635 | 03-2300 | SG7 FORM THRUST BRICK | 10.5
44640 | 44635 | 03-1000 | OG8 PUT DOWN SHOE FOR WALLS | 24
44640 | 44635 | 03-1000 | OG8 STRIP PLUMBING PIT | 5
44640 | 44635 | 99-4560 | OG8 SITE MAINTENANCE | 3
44640 | 44635 | 03-1400 | OG8 DRILL & EPOXY REBAR | 2
44640 | 44635 | 33-2400 | JUMPS | 3
44640 | 44636 | 03-1100 | SG5 START CLOSING UP FLOOD WALL | 56
44640 | 44636 | 03-2300 | SG7 FORM 2 THRUST BLOCKS | 10
44640 | 44636 | 03-1000 | OG8 FINISH SHOE FOR WALLS & COLUMNS | 7
44640 | 44636 | 03-1700 | OG8 UNLOAD TRAILER WITH FORMS (QTY ON DELIVERY TICKET) | 4
44640 | 44636 | 02-6015 | OG4 PLYWOOD UP WINDOWS (WINDOWS DEMO) | 10.5
44640 | 44636 | 02-6015 | OG5 PLYWOOD UP WINDOWS (WINDOWS DEMO) | 9
44640 | 44636 | 33-6010 | SG3 MACHINE NEEDED TO LAY PIPE/MOVE FENCE (WELKIN SUPPORT) | 12
44640 | 44636 | 03-2300 | SG7 POUR 3 EA THRUST BLOCKS (6YDS) | 4
44640 | 44636 | 33-3100 | SG7 EXPOSE ASBESTOS PIPE | 14.5
44640 | 44636 | 03-1400 | SG4 DRILL DOWELS FOR MASONRY SHELF | 15
44640 | 44636 | 31-1100 | SG5 BACKFILL AS NEEDED FOR SHELF | 13
44640 | 44636 | 03-1000 | OG8 PREP AREA FOR FORM WORK DELIVERY | 2
44640 | 44636 | 33-3100 | OG6 TRENCH BOX DELIVERY | 4
44640 | 44636 | 03-1000 | OG8 FORM WORK DELIVERY | 8
44640 | 44636 | 33-3100 | OG10 HNS TRUCK ON SITE-LOAD OUT DIRT FROM OG 10 TO SG6 AND SG7 | 8
44640 | 44636 | 99-4560 | OG9 CLEAN AREA | 1
44640 | 44636 | 33-2400 | PUMPS | 2
44640 | 44636 | 99-4560 | SG6 REMOVE TARP SHAFT | 2
44640 | 44636 | 33-3100 | SG7 MAINTAIN TRANCHES | 4
44640 | 44636 | 99-4560 | SG6 CLEAN UP AROUND BUILDING (SITE MAINT) | 15
44640 | 44636 | 02-2300 | SG2 CLEAN UP PTTS WINDOWS (FOR ATCO ABATEMENT) | 6
44640 | 44636 | 02-2300 | SG3 CLEAN UP PTTS WINDOWS (FOR ATCO ABATEMENT) | 3
44640 | 44636 | 99-4560 | OG9 CLEAN UP BUILDING | 8
44640 | 44636 | 03-6000 | OG3 GRININIG CEILING ON 2ND FLOOR (FRP) | 16
44640 | 44636 | 02-6060 | OG4 REMOVE WINDOWS GARBAGE (2ND FL DEMO INSTALL) | 9
44640 | 44636 | 02-6060 | OG5 REMOVE WINDOWS GARBAGE (2ND FL DEMO INSTALL) | 9.5
44640 | 44637 | 03-1100 | SG5 FORM FLOOD WALLS | 67.5
44640 | 44637 | 03-2500 | SG5 FORM BACK SHELF (MASONRY SUPPORT) | 21
44640 | 44637 | 33-6010 | OG10 ADJUST CABLE FOR ACCEPTANCE OF MATERIAL (SUB SUPPORT) | 8
44640 | 44637 | 99-4560 | SG6 CLEAN DEBRIS AROUND BUILDING | 15
44640 | 44637 | 33-3100 | SG7 KEEPING TRENCHES | 5
44640 | 44637 | 03-6000 | OG3 PREP FOR FRP ON 1ST FLOOR | 18
44640 | 44637 | 02-6060 | OG3 REPAIR CEILING ON 2ND FLOOR AND CLEAN UP | 9
44640 | 44637 | 99-4560 | OG8 CLEAN UP AROUND BUILDING | 13.5
44640 | 44637 | 99-4560 | OG10 CLEAN UP AROUND BUILDING | 18
44640 | 44637 | 99-4560 | SG6 FAXA NEED TO LOAD 1ST & 2ND FLOOR | 4
44640 | 44637 | 26-6030 | SG6 FIVE STAR ELECTRIC NEED TO LOAD PIPE ON 1ST FLOOR | 2
44640 | 44637 | 33-6010 | OG10 WELKIN NEED TO LOAD 1ST FLOOR MATERIALS | 3
44640 | 44637 | 99-4560 | OG3 CLEAR GARBAGE ON 2ND FLOOR (WINDOW DEMO) | 2
44640 | 44637 | 02-3000 | OG3 CHOP ELECTRIC PENETRATIONS | 8
44640 | 44637 | 03-1400 | SG4 DRILL DOWELS FOR MASONRY SHELF | 18
44640 | 44637 | 33-1000 | SG7 EXPOSE ASBESTOS PIPE (CUT & CAP UTILITIES) | 13
44640 | 44637 | 31-1000 | OG1 EXCAVATE FOR MASONRY FOUNDATION/TESTPIT | 11
44640 | 44637 | 31-1000 | OG2 EXCAVATE FOR MASONRY FOUNDATION/TESTPIT | 2
44640 | 44637 | 00-0019 | OG6 BUILD IN TRENCH BOXES FOR ELECTRICAL RUN (FENCE C/O) | 9.5
44640 | 44637 | 32-6610 | OG6 LOAD CONCRETE - CARDELLA (OG6 SITE DEMO) | 1.5
44640 | 44637 | 31-2000 | TEST PIT | 10
44640 | 44637 | 31-1700 | COVER PUMPS | 2
44640 | 44638 | 33-3100 | SG7 CLEAN TRENCHES | 8
44640 | 44638 | 32-6000 | OG3 CORE DRILLING AND PREPAIR /CLEAN UP (SAW CUT CODE) | 16
44640 | 44638 | 02-6060 | SG4 REPAIRING CEILING ON 2ND FLOOR | 16
44640 | 44638 | 99-4560 | SG6 CLEAN UP (SITE MAINT) | 16
44640 | 44638 | 99-4560 | OG9 CLEAN UP (SITE MAINT) | 10.5
44640 | 44638 | 99-4560 | OG8 CLEAN UP (SITE MAINT) | 10.5
44640 | 44638 | 99-4560 | SG7 CLEAN UP (SITE MAINT) | 10.5
44640 | 44638 | 33-1000 | SG1 MOVE PLANTS (MAINT/PROTECT EXIST PUT UTLY) | 2
44640 | 44638 | 31-1100 | SG5 BACKFILL FOR MASONRY SHELF (BACKFILL) | 7
44640 | 44638 | 03-1400 | SG4 EPOXY BARS FOR MASONRY SHELF | 13
44640 | 44638 | 32-6520 | OG2 OG1 EXCAVATE FOR MASONRY FOUNDATION /MOVE FENCE FOR EXCAVATION | 19
44640 | 44638 | 33-3100 | OG6 EXCAVATE FOR ELECTRICAL RUN/SET 1 BOX | 20.5
44640 | 44638 | 33-6010 | SG3 MACHINE NEEDED FOR STEAM TRENCH (WELKIN SUPPORT) | 5
44640 | 44638 | 33-1000 | OG2 BUILD PLATFORM FOR FSP (MAINT PROTECT EXST PUT UTILITY) | 3
44640 | 44638 | 33-1000 | OG6 MOVE PLANTS TO SG1 GARDEN (MAINT/PROTECT EXISTING PUT UTILITY) | 5
44640 | 44638 | 31-1700 | JUMP/PUMPS | 2
44640 | 44638 | 03-1900 | OG 8 PUT UP HANDRAILS WHERE NEEDED (WHERE SLAB WAS LEFT OUT) | 6
44640 | 44638 | 33-3100 | OG10 PUT UP HANDRAIL AROUND STEAM PIPES | 6.5
44640 | 44638 | 99-4560 | OG10 COVER HOLE ON ROOF | 3.5
44640 | 44638 | 99-4560 | SGA PUT HANDRAIL ON EDGE OF DITCH | 4.5
44640 | 44638 | 03-1100 | SG5 FINISH FORMING FLOOD WALLS (FORM EXIST BLD) | 38
44640 | 44638 | 03-1100 | SG5 FINISH FORMING BRICK SHELF (FORM EXIST BLD) | 10
44633 | 44627 | 03-1900 | OG8 Pour Slab 191 yds | 104.5
44633 | 44627 | 02-6015 | OG3 REMOVE WINDOWS | 4
44633 | 44627 | 02-6015 | OG1 DEMO VENTS | 11
44633 | 44627 | 33-3100 | OG3 EXPOSE POE TO OG 2 SET BOX 10' STEEL PATE - MOVE FENCE FOR EXCAVATION | 49.5
44633 | 44627 | 02-6005 | OG6 PAINT REMOVAL | 16
44633 | 44627 | 31-1700 | Jump pumps | 3
44633 | 44627 | 99-4560 | OG8 SAFETY (REBAR CAPS) | 8
44633 | 44627 | 03-1100 | OG3 PLYWOOD WINDOWS | 8
44633 | 44627 | 03-1100 | SG5 FORM FLOOD WORK | 26.5
44633 | 44627 | 03-1100 | SG4 & SG5 RELOCATE FORMS | 13
44633 | 44627 | 03-2100 | KEY WAY @ POUR OG 3 (POUR CONCRETE) | 10
44633 | 44628 | 31-1000 | SG4 EXPOSE LOCATIONS FOR ABATEMENT AND CLEAN TRENCH (SHELF EXCAVATION) | 10.5
44633 | 44628 | 03-1400 | OG1 DRILL AND DOWEL FOR WINDOWS INFILL | 2
44633 | 44628 | 03-1400 | OG2 DRILL AND DOWEL FOR WINDOWS INFILL | 12.5
44633 | 44628 | 31-2000 | OG3 EXPOSE POE TO OG2 (HAND DIG UNDER VENT) | 20.5
44633 | 44628 | 33-3100 | OG6 REMOVE KNEE IN PATH OF ELECTRICAL TRENCH/2 LIVE LOADS/CONCRETE AND TREE DEBRIS | 23
44633 | 44628 | 31-1000 | SG4 CHOP CONCRETE FRONT ENTRANCE OF BLD (DEMO FOR FG) | 11.5
44633 | 44628 | 99-4560 | OG8 CLEAN SITE | 13
44633 | 44628 | 02-6005 | OG6 PAINT REMOVAL | 16
44633 | 44628 | 03-1800 | OG3 & OG4 REBAR DELIVERY | 15
44633 | 44628 | 03-1900 | OG8 CUTE IN SLAB JOINTS | 9
44633 | 44628 | 31-1700 | JUMP PUMPS | 5
44633 | 44628 | 99-4560 | FAXA SUPPORT | 1
44633 | 44628 | 03-1100 | SG4 FORM FLOOD WALLS | 36.5
44633 | 44628 | 03-1100 | SG5 FORM FLOOD WALS | 20
44633 | 44629 | 03-1000 | OG8 FORM TANK PAD AND PUMP PAD | 22.5
44633 | 44629 | 03-1000 | OG8 STRIP COLUMN BASES | 10
44633 | 44629 | 03-1000 | OG8 STRIP SLAB EDGE | 20.5
44633 | 44629 | 02-6050 | GS4 FINISH CONCRETE FOR FLOOD WAY (DEMO STAIR CODE) | 3
44633 | 44629 | 03-1400 | OG2 DRILL AND DOWEZ FOR WINDOW INFILL/CLEAN DEBRIS FROM WINDOWS | 40.5
44633 | 44629 | 02-6005 | OG6 PAINT REMOVAL | 25
44633 | 44629 | 02-6065 | OG6 DEMO REMAINING DUCKWORK | 10
44633 | 44629 | 26-6030 | OG10 MOVE MATRIAL 2ND FL FOR FSE LULL NEEDED | 3
44633 | 44629 | 33-6010 | SG6 MOVE MATRIAL 2ND FLOOR FOR JANSONS BOILER FLUE-LULL NEEDED) | 3
44633 | 44629 | 03-1000 | OG8 CLEAN SITE AFTER STRIP FORM AND COLUMN BASES (FORM WORK) | 1
44633 | 44629 | 02-2300 | SG4 CLEAN BASEMENT | 14.5
44633 | 44629 | 31-2000 | SG7 CLEAN AREA FOR TEST PIT ELECTRICAL NUN EXCAVATION | 25
44633 | 44629 | 02-2300 | OG2 PUMP & CLEAN BASEMENT (BASEMENT MAINT) | 4
44633 | 44629 | 99-4560 | OG10 CLEAN AREA MOVE CONCRETE DEBRIS INTO ONE PILE/MOVE DINT (SITE MAINT) | 5
44633 | 44629 | 99-4560 | OG-6 PREP AREA FOR TEST PIT (SITE MAINT) | 3
44633 | 44629 | 31-1700 | JUMP PUMPS | 3
44633 | 44630 | 03-1100 | SG4 FORM FLOOD WALLS | 29.5
44633 | 44630 | 03-1100 | SG4 CLOSE WINDOW WITH PLYWOOD (FOR CONCRETE POUR - PADS 2ND FLOOR) | 3
44633 | 44630 | 03-1100 | SG5 FORM FLOOD WALLS | 30
44633 | 44630 | 03-1000 | SG6 FORM BRICKSHELF BY PLUMBING SHAFT | 4
44633 | 44630 | 99-4560 | SG1 SG2 CLEAN CELLAR WINDOWS - SITE MAINT OR DEMO | 6
44633 | 44630 | 33-3100 | SG3 CLEAN TRENCH - STEAM | 4
44633 | 44630 | 99-4560 | SG6 CLEAN 1ST AND 2ND FLOOR - SITE MAINT | 14.5
44633 | 44630 | 02-6005 | OG6 PAINT REMOVAL | 25
44633 | 44630 | 03-2100 | SG4 POUR PADS 2ND FLOOR (2 YD OPOUR CONC EXISTING BUILDING) | 3
44633 | 44630 | 31-2000 | SG7 TEST PIT | 29
44633 | 44630 | 33-3100 | OG6 EXCAVATE FOR ELECTRICAL RUNS - MOVE STELL PLATES FROM SG6 TO OG6 | 28
44633 | 44630 | 03-1900 | OG8 POUR PADS/POUR COLUMN BASES - 8YDS | 13
44633 | 44630 | 31-2000 | OG6 TEST PIT | 5
44633 | 44630 | 33-2400 | JUMPS/PUMPS | 3
44633 | 44630 | 00-0019 | FENCE/CO | 17
44633 | 44631 | 99-4560 | SG6 DEBRI CLEANUP | 21.5
44633 | 44631 | 03-1400 | SG6 DRILL AND INSTALL DOWELS FOR MASONRY SHELF | 18
44633 | 44631 | 03-1400 | SG5 FINISH AND INSTALL DOWELS FOR MASONRY SHELF | 4
44633 | 44631 | 02-6060 | OG2 CLEAN 2ND FLOOR APARTMENT | 3
44633 | 44631 | 33-3100 | SG7 FINISH TEST PT AND EXCAVATION - CODE TO TEST PIT | 8
44633 | 44631 | 31-2200 | OG8 PREP AREA FOR OIL TANK DELIVERY/CLEAN - BACKFILL | 4
44633 | 44631 | 33-3100 | OG6 EXCAVATE FOR ELECTRICAL RUN | 31.5
44633 | 44631 | 02-6005 | OG6 PAINT REMOVAL | 25
44633 | 44631 | 31-2000 | OG6 TEST PIT | 8
44633 | 44631 | 00-0019 | FENCE CO | 8
44633 | 44631 | 33-1000 | SG7 DEMO/CUT AND CAP UTILITY | 6
44633 | 44631 | 31-1700 | PUMPS/JUMPS/LULL | 3
44633 | 44631 | 99-4560 | SET MATERIAL ON 2ND FL FOR FAXA/WELKIN/FSE SG6 | 1
44633 | 44631 | 03-1100 | SG4 START SHOE FOR FLOOD WALLS | 11.5
44633 | 44631 | 32-6000 | SG6 CUT PENETRATIONS FOR JANSON, INSTALL HANDRAIL, COVER MESH | 10
44633 | 44631 | 03-1000 | OG8 STRIP TANK PAD AND PUMP PAD | 6
44633 | 44631 | 03-1000 | OG8 STRIP SLAB EDGE AND BACKSTRIP | 21
44633 | 44631 | 99-4560 | OG10 TOE BOARD ON ROOF (SITE MAINT) | 12
44626 | 44620 | 02-2300 | og3 fix leak sump pump connection | 3
44626 | 44620 | 33-2400 | SG7 MAINTAIN TRENCHES (ENSURE PUMPS RUNNING & DRY) | 2
44626 | 44620 | 02-2300 | OG5 REPLACE SUMP PUMP | 2
44626 | 44620 | 32-6520 | SG4 FNISH TEMP FENCE ON NEW WALKWAY/OPEN TO PUBLIC | 17.5
44626 | 44620 | 03-1400 | SG5 DRILL & INSTALL DOWELS FOR MASONRY FOUNDATION | 0.5
44626 | 44620 | 02-6015 | OG1 REMOVE CELLAR WINDOWS/CLEAN BASEMENT DEBRIS | 14.5
44626 | 44620 | 31-1000 | OG2 EXCAVATE FOR MASONRY FOUNDATION/CLEAN AREA CONCRETE DEBDRIS | 29
44626 | 44620 | 02-3000 | OG6 CHOP PENETRATIONS FOR DUCTWORK | 17.5
44626 | 44620 | 02-6005 | OG6 PAINT REMOVAL | 17
44626 | 44620 | 32-6610 | OG6 DEMO AREA/CHOP NEAR GAS LINE | 11
44626 | 44620 | 07-1100 | OG8 COMPLETE VAPOR BARRIER | 7
44626 | 44620 | 99-4560 | TRASH REMOVAL OG2 | 2
44626 | 44620 | 31-2000 | TEST PIT AT OG6 | 7
44626 | 44620 | 03-1000 | OG8 FORM SLAB SIDES, BRICKSHELF | 40.5
44626 | 44620 | 99-4560 | OG8 SITE MAINTENANCE | 8
44626 | 44620 | 31-1700 | JUMP PUMPS | 4
44626 | 44621 | 31-1000 | SG4 DEMO/EXCAVATE FOR FLOODGATE | 21.5
44626 | 44621 | 02-6015 | OG1/OG2 REMOVE CELLAR WINDOWS | 16
44626 | 44621 | 02-2000 | OG6 DEMO 3 LIVE LOADS CONCRETE DEBRIS | 11
44626 | 44621 | 02-6005 | OG6 PAINT REMOVAL | 11
44626 | 44621 | 02-2000 | OG8 EXCAVATE STAIR LANDING ( NEW BLD EXC) | 6
44626 | 44621 | 07-6020 | OG10 PATCH /PREP SHAFT FOR WATERPROFING | 25
44626 | 44621 | 33-6010 | SG3 LOADOUT WELKIN TRAILER TO MAIN OFFICE | 6
44626 | 44621 | 02-2300 | OG4 CLEAN/PUMP DOWN BACK ROOM OF BASEMENT | 8.5
44626 | 44621 | 99-4560 | SG6 PUMP DOWN SHAFT CLEAN GARBAGE FROM 2ND FLOOR | 12
44626 | 44621 | 99-4560 | SG4/5 CAP ALL EXPOSED REBAR | 2
44626 | 44621 | 31-2000 | TEST PIT @ SG4 | 6
44626 | 44621 | 32-6520 | SG4 FENCE RELOCATION | 1
44626 | 44621 | 33-2400 | JUMP PUMPS | 4
44626 | 44621 | 03-1000 | OG8 STRAIGHTED OUT FORM SIDES | 21
44626 | 44621 | 99-4560 | OG8 PLUMBING PITS | 9
44626 | 44621 | 03-1000 | OG8 FORM COLUMN BASES | 18.5
44626 | 44621 | 99-4560 | OG8 SITE MAINTENANCE | 8
44626 | 44622 | 03-1000 | OG8 FORM PLUMBING SHAFT FOR DECK POUR | 12
44626 | 44622 | 03-1000 | OG8 FORM PLUMBING LEAVE OUT FOR DECK POUR (DONE BECAUSE OF OTCR) | 20
44626 | 44622 | 03-1400 | OG8 DRILL & EPOXY DOWELS FOR STAIRCASE FOOTING | 9
44626 | 44622 | 03-1900 | OG8 STRIGHTEN OUT SLAB SIDES | 13
44626 | 44622 | 03-1900 | OG8 PREP DOWN PLYWOOD FOR MECHANICAL PAD | 2.5
44626 | 44622 | 03-1000 | OG10 BAND FORMS FOR PICKUP TOMORROW | 8
44626 | 44622 | 31-1000 | SG4 ECAVATE FOR FLOODGATE AT BLD ENTRANCE | 9.5
44626 | 44622 | 03-1400 | SG5 INSTAL DOWELS FOR MASONRY | 13
44626 | 44622 | 33-3100 | OG3 INSTALL GUARD AT TRENCH BOX | 1.5
44626 | 44622 | 07-6020 | OG10 PATCH AND PREP SHAFT FOR WATERPROOFING | 25
44626 | 44622 | 02-6005 | OG6 PAINT REMOVAL | 16
44626 | 44622 | 02-2300 | SG1 CLEAN BASEMENT BOILER ROOM | 5
44626 | 44622 | 02-2300 | OG2 CLEAN SUMP PIT | 4
44626 | 44622 | 02-6060 | SG4 PAINT WALLS IN 2ND FLOOR | 5
44626 | 44622 | 33-3100 | OG5 MAINTAIN LONG TRENCH TO SG3 PREP TO INSTALL STEAM | 16.5
44626 | 44622 | 26-6030 | OG10/SG6 LULL NEEDED TO MOVE MATERIAL FOR FSE 2ND FLOOR | 4
44626 | 44622 | 99-4560 | O9 CLEAN GARBAGE FROM 2ND FLOOR | 2
44626 | 44622 | 33-3100 | SG4 PULL TRENCH BOXED FROM ELEC TRENCH | 9.5
44626 | 44622 | 33-1000 | MAINT AND PROTECT UTILITY - BUILD FIRE STAND PIPE ACCESS | 3
44626 | 44622 | 02-1900 | SG4 SITE DEMO AT ENTRANCE FOR FLOODGATE& SHELF | 13
44626 | 44622 | 31-2200 | SG4 BACKFILL ELEC TRENCH - 10 YDS | 4
44626 | 44622 | 31-1700 | JUMP PUMPS | 1
44626 | 44623 | 33-1000 | SG4 INSTALL FENC TO FIRE STAND PIPE | 10.5
44626 | 44623 | 03-1400 | SG5 INSTALL DOWELS FOR MASONRY FOUNDATION | 17.5
44626 | 44623 | 03-1400 | OG1 DRILL AND DOWEL FOR WINDOW INFILL | 7.5
44626 | 44623 | 02-6015 | OG2 REMOVE WINDOWS | 4.5
44626 | 44623 | 02-6005 | OG6 PAINT REMOVAL | 16
44626 | 44623 | 33-3100 | SGN LOADOUT TRENCH BOXES, RAILS, RIGGING | 6.5
44626 | 44623 | 99-4560 | SG6 LULL NEEDED FR FAXA AND JANSONS INSTALL BOILER FLUTE | 7
44626 | 44623 | 33-3100 | OG5 BEGIN TO INSTALL STEAM PIPE | 8
44626 | 44623 | 02-2300 | SG4 CLEAN WATER BASEMENT/FIX TARP | 3
44626 | 44623 | 33-3100 | OG5 MAINTAIN LONG TRENCH TO SG3 | 5.5
44626 | 44623 | 99-4560 | OG9/10 HANG FIRE EXTINGUISHERS | 2
44626 | 44623 | 02-6015 | OG1 CLEAN DEBRIS FROM BASEMENT WINDOWS | 11
44626 | 44623 | 03-1100 | sg4/5 unload form trailer | 15
44626 | 44623 | 03-1000 | og10 loadouttrailer | 13
44626 | 44623 | 03-1100 | FLAG FOR TRAILER DELIVERY AND LOADOUT | 12
44626 | 44623 | 33-3100 | MACHINE REPAIR (EXCAVATOR) | 2
44626 | 44623 | 32-6510 | WHITE MESH MAINTENANCE | 4
44626 | 44623 | 03-1000 | OG10 INSTALL SAFETY HANDRAIL | 8
44626 | 44623 | 03-1900 | OG8 FINISH GRADE ON COLUMNS | 5.5
44626 | 44623 | 03-1100 | SG5 INSTALL SHOE FOR FLOOD WALLS | 29
44626 | 44624 | 99-4560 | SG3 EXTENSION OF BUILDING | 3
44626 | 44624 | 02-2300 | SG4 HOUSEKEEPING IN BASEMENT | 8
44626 | 44624 | 33-3100 | SG7 MAINTAIN TRENCHES | 3
44626 | 44624 | 03-1900 | OG8 CLEAN/PREP CONCRETE POUR(15CYS) | 15
44626 | 44624 | 31-1000 | OG1 EXCAVATE FOR MASONRY FOUNDATION | 22.5
44626 | 44624 | 03-1400 | OG1 DRILL AND DOWEL FOR WINDOW INFILL | 24
44626 | 44624 | 00-0019 | OG3 RECEIVE TRENCH BOX (FENCE CO) | 4
44626 | 44624 | 02-6005 | OG6 PAINT REMOVAL | 16
44626 | 44624 | 00-0023 | S8 REMOVE ASPHALT/EXCAVATE FOR FIRE STAND PIPE (CHANGE ORDER) | 23.5
44626 | 44624 | 33-3100 | OG5 INSTALL STEAM PIPE | 1
44626 | 44624 | 33-6010 | SG6 JANSONS FLUE - LULL FOR 2ND FLOOR | 1.5
44626 | 44624 | 02-2300 | OG2 REMOVE BASEMENT GARBAGE | 10.5
44626 | 44624 | 03-1900 | OG8 INSTALL WATERSTOP AT PLUMBING SHAFT | 5
44626 | 44624 | 03-1000 | OG8 STRAIGHTEN OUT SLAB EDGE AND ADJUST BRICKSHELF (FORMWORK) | 7
44626 | 44624 | 02-6005 | OG6 BUILD PLATFORMS FOR BOILER ROOM FOR PAINT REMOVAL | 18
44626 | 44624 | 03-1100 | SG4 EXTEND EQUIPMENT PADS FOR SWITCH GEARS (FORMWORK) | 10
44626 | 44624 | 03-1900 | OG8 LAYOUT DOORWAYS & CUT BRICKSHELF | 11
44626 | 44624 | 03-1100 | SG5 FORM FLOOD WALLS | 13.5
44619 | 44613 | 99-4560 | SG3/4/6/OG9 CLEAN AREA | 22
44619 | 44613 | 33-6010 | SG6 LULL NEEDED FOR WELKIN 2ND FLOOR | 2
44619 | 44613 | 02-6005 | OG4 PAINT REMOVAL IN BASEMENT | 17
44619 | 44613 | 03-2100 | SG4/5 PREP FOR FLOODGATE FOOTINGS/POUR | 7
44619 | 44613 | 31-2200 | SG6 BACKFILL SMALL AREA FOR UTILITIES NEXT TO BLD (10 YDS) | 5
44619 | 44613 | 02-1700 | OG6 LOAD OUT DEBRIS/DEMO BLACK FENCE | 7
44619 | 44613 | 07-6020 | OG10 CLEAN/PATCH/PREP WATERPROOFING | 32
44619 | 44613 | 07-6020 | OG9 HOSE DOWN SHAFT FOR WATREPROOFING | 5.5
44619 | 44613 | 33-1000 | SG7 PROTECT EXISTING UTILITY GAS LINE BY SG1 | 8
44619 | 44613 | 03-6000 | SG4 FRP INTALL AT BASEMENT | 16.5
44619 | 44613 | 31-1700 | OG10 LULL NEEDED FOR VITAL 2ND FLOOR (JUMP PUMPS CODE) | 3
44619 | 44613 | 32-6510 | MAINTAIN WHITE MESH | 17
44619 | 44613 | 03-1400 | SG5 DRILL DOWELS FOR MASONRY | 4.5
44619 | 44613 | 03-1000 | OG8 FINISH COLUMN BASES FOR GROUT | 8
44619 | 44613 | 03-1000 | OG8 START FORMING FOR SLAB | 36.5
44619 | 44613 | 03-1000 | OG10 CLEAN STACK AND BAND FORMS | 10
44619 | 44613 | 03-1100 | SG4 STRIP PADS | 10
44619 | 44613 | 99-7200 | holiday pay | 8
44619 | 44614 | 99-4560 | SG3/4 CLEAN AREA AROUND BUILDING | 16
44619 | 44614 | 03-2100 | SG4/5 POUR FLOODGATE FOOTINGS/MOVE FENCE FOR CONC TRUCKS - 60 YDS | 34.5
44619 | 44614 | 03-1400 | SG5 DRILL DOWELS FOR MASONRY FOUNDATION | 9.5
44619 | 44614 | 26-6030 | SG4 SWITCHGEAR DELIVER TO 2ND FLOOR | 7
44619 | 44614 | 31-2000 | OG6 TEST PIT FOR GAS LINES | 9
44619 | 44614 | 02-2300 | OG6 PREP FOR PAINT REMOVAL/CLEAN BASEMENT BOILER ROOM | 16
44619 | 44614 | 07-6020 | OG10 SHAFT CLEAN FOR WATERPROOFING | 19
44619 | 44614 | 02-6060 | OG1 REMMOVE 2ND FLOOR WINODWS FOR DLEIVERY OF FIRE RATED WALLS | 6
44619 | 44614 | 03-6000 | SG4 FRP INSTALL AT 1ST FLOOR | 16
44619 | 44614 | 99-4560 | HANG ADDRESS SIGNS AND ARROWS | 8
44619 | 44614 | 32-6610 | DEMO & LOADOUT @ OGE | 12
44619 | 44614 | 03-1100 | OG1 PLYWOOD WINDOWS | 3
44619 | 44614 | 03-1000 | OG8 NFORM SLAB SIDES AND BRICK SHELF | 17
44619 | 44614 | 03-1000 | OG10 STRIP PLUMBING SHAFT DUMMY DECK & BRIDGE BRACKETS | 26.5
44619 | 44614 | 31-1400 | OG10 BACKFILL & SLAB | 10
44619 | 44614 | 31-1700 | JUMP PUMPS | 3
44619 | 44615 | 32-6510 | SG4/SG6 MAINTAIN MESH | 13
44619 | 44615 | 03-1400 | SG5 DRILL AND DOWEL MASONRY | 9
44619 | 44615 | 02-3000 | OG6 DEMO MARKED OUT IN DUCT IN BASEMENT | 20
44619 | 44615 | 03-1000 | OG8 GROUT COLUMN BASES | 19
44619 | 44615 | 02-2300 | OG6 BASEMENT MAINTENANCE REQURED FOR PAINT REMOVAL | 17
44619 | 44615 | 31-1500 | OG8 SPREAD STONE FOR SLAB INSPECTION | 18
44619 | 44615 | 03-1800 | SG5 REBAR DELIVERY | 9
44619 | 44615 | 26-6030 | SG4 SWITCHGEAR ACCESSORIES DELIVERY TO 2ND FLOOR | 5
44619 | 44615 | 07-6020 | OG10 PREP SHAFT FOR WATERPROOFING | 17
44619 | 44615 | 99-4560 | OG10 CLEAN AREA AROUND BLD (SITE M AIN) | 18
44619 | 44615 | 33-2400 | COVER PUMPS/DEWATER | 3
44619 | 44615 | 03-1000 | OG10 FINISH STRIPPING PLUMBING SHAFT | 9
44619 | 44615 | 99-4560 | OG10 SITE MAIN | 9
44619 | 44615 | 03-1000 | OG8 FORM FOR SLAB & BRICKSHELF | 38.5
44619 | 44615 | 03-1000 | OG10 CLEAN AND BAND FORMS | 8
44619 | 44616 | 32-6520 | SG4 INSTALL TEMP FENCE ON NEW TEMP WALKWAY | 12
44619 | 44616 | 33-3100 | SG7 MAINTAIN TRENCHES/SUPPORT FITTERS | 3
44619 | 44616 | 02-3000 | OG6 DEMO MARKED OUT DUCT IN BASEMENT/ CHP PENETRATIONS FOR DUCTWORK | 17
44619 | 44616 | 02-6005 | OG6 PAINT REMOVAL | 5
44619 | 44616 | 32-6610 | OG6 DEMO AREA/3 LIVE LOADS CONCRETE | 11
44619 | 44616 | 07-1100 | OG8 BEGIN TO LAY FOAM AND VAPOR BARRIER | 28
44619 | 44616 | 99-4560 | OG8 CLEAN ALL AREAS | 22
44619 | 44616 | 99-4560 | SG6 FAXA LULL NEEDED | 1
44619 | 44616 | 32-6510 | MAINTAIN WHITE MESH | 17
44619 | 44616 | 99-7300 | JESSE SIMPSON LOST TIME | 6
44619 | 44616 | 26-6030 | FSE SWITCHGEAR ACCESSORY DELIVERY | 3
44619 | 44616 | 33-2400 | JUMP TO COVER PUMPS | 1
44619 | 44616 | 02-2300 | BASEMENT MAINT, REPLACE BROKEN PUMP | 6
44619 | 44616 | 07-6020 | OG10 HANDRAIL ON TEMP STAIRS | 4
44619 | 44616 | 03-1000 | OG8 STRIP COLUMNS BASES | 7
44619 | 44616 | 03-1000 | OG8 FORM SLAB SIDES AND BRICK SHELF | 53.5
44619 | 44617 | 03-1000 | OG8 FORM SLAB SIDE & BRICKSHELF | 18
44619 | 44617 | 03-1000 | GATHER UP FORMS FROM AROUND JOB FOR PICKUP | 35
44619 | 44617 | 02-2300 | SG1 CLEAN DEBRIS FROM BASEMENT | 14
44619 | 44617 | 02-2300 | SG2 CLEAN DEBRIS IN BASEMENT | 15
44619 | 44617 | 02-6005 | SG4 PAINT WALLS ON 2ND FLOOR | 11
44619 | 44617 | 02-6015 | OG1 REMOVE CELLAR WINDOWS | 10
44619 | 44617 | 03-1400 | OG3 DRILL AND DOWEL WINDOWS FOR INFILL | 8
44619 | 44617 | 03-1400 | OG1 DRILL AND DOWEL WINDOWS FOR INFILL | 11
44619 | 44617 | 02-2300 | OG5 SWAP OUT BROKEN SUMP PUMP | 6
44619 | 44617 | 32-6610 | OG6 DEMO/LOADOUT CONCRETE | 18.5
44619 | 44617 | 02-3000 | OG6 DEMO MARKED OUT DUCT IN BADEMENT/CHOP PENETRATIONS FOR DUCTWORK | 19
44619 | 44617 | 02-6005 | OG6 PAINT REMOVAL | 17
44619 | 44617 | 02-2300 | OG6 CLEAN DEBRIS FROM BASEMENT | 7
44619 | 44617 | 03-1000 | MOVE FORMS TO SITE 8 FOR LOADOUT | 2
44619 | 44617 | 31-1700 | Jump pumps | 3
44612 | 44606 | 03-6000 | FRP INSTALL SG3 | 17
44612 | 44606 | 31-2200 | MOVE STOCKPILE - LOAD HNS TRUCK FOR BACKFILL SG6 TRENCH SG4 | 17
44612 | 44606 | 31-2200 | BACKFILL TRENCH PARTIAL SG6 | 15.5
44612 | 44606 | 33-2400 | SG7 CHECK PUMPS ON TRENCHES | 2
44612 | 44606 | 02-6005 | OG2 PAINT REMOVAL | 18
44612 | 44606 | 99-4560 | OG3 SUPPORT FAXA SET UP SILO | 2
44612 | 44606 | 32-6510 | OG5 WHITE MESH | 8
44612 | 44606 | 32-6610 | OG6 DEMO SREA 11 LIVE LOADS | 26
44612 | 44606 | 07-6020 | OG9 PATCH AND PREP SHAFT FOR WATERPROOFING | 15
44612 | 44606 | 00-0022 | S8 CLEAN (CHANGE O) | 8.5
44612 | 44606 | 03-1100 | SG4/SG5 FORM FOOTING FOR FLOOD GATE | 14
44612 | 44606 | 03-1000 | SG6 STRIP PAD FOR FLUTE STACK | 4
44612 | 44606 | 99-4560 | SG7 CUT HOLE IN DECK, ACCESS TO BOTTOM OF SHAFT | 4
44612 | 44606 | 03-2300 | OG2 BULKHEAD OFF CONDUIT IN FOUNDATION, FORM DUCTBANK | 14
44612 | 44606 | 32-6510 | OG9 ORANGE MESH | 11.5
44612 | 44606 | 00-0022 | S8 CLEAN BASEMENT CHANGE ORDER | 8
44612 | 44606 | 31-1700 | jump pumps | 2
44612 | 44606 | 03-1000 | og9 strip pads | 9
44612 | 44607 | 02-2300 | CHECK PUMPS IN BASEMENT SG1 | 0.5
44612 | 44607 | 03-6000 | SG4 FRP INSTALL | 16
44612 | 44607 | 31-2200 | SG4 PREP FOR TEMP WALKWAY/BACKFILL CORNER OF BLD FOR CONCRETE POUR | 13.5
44612 | 44607 | 99-4560 | SG5 CLEAN TRENCH AROUND BLD FOR ABATEMENT - SITE MAINTENANCE | 9
44612 | 44607 | 31-2200 | SG6 CLEAN AREA AND BLD/ BACKFILL TRENCH | 16
44612 | 44607 | 33-2400 | CHECK PUMPS ON TRENCHES | 8.5
44612 | 44607 | 02-6005 | OG2 PAINT REMOVAL | 9
44612 | 44607 | 02-6005 | OG4 PAINT REMOVAL | 9
44612 | 44607 | 02-2300 | OG5 CLEAN ELECTRIC ROOM (T&M CLEANING) | 9.5
44612 | 44607 | 02-2000 | OG6 DEMO AREA | 32
44612 | 44607 | 32-6510 | OG8 WHITE MESH INSTALL | 8
44612 | 44607 | 03-1900 | OG10 REMOVE BLANKETS (CONCRETE) | 6
44612 | 44607 | 31-2200 | SG1 BACKFILL TRENCH AND REMOVE TREE | 5.5
44612 | 44607 | 03-1100 | SG4 FORM FLOOD WALL FOOTING | 8.5
44612 | 44607 | 03-1100 | SG5 FORM FLOOD WALL FOOTING | 3.5
44612 | 44607 | 32-6520 | SG6 TEMP WALKWAY | 7.5
44612 | 44607 | 32-6520 | SG7 START STRIPPING GRADE BEAM | 9
44612 | 44607 | 03-2300 | OG2 CHOP CONCRETE FOR LATHERS BOTTOM BARS/FINISH STAYFORM FOR DUCT BANK | 10
44612 | 44607 | 03-1000 | OG8 FORM SUMP PIT SLAB | 9.5
44612 | 44607 | 03-1000 | OG9 START STRIPPING DUMMY DECK IN SHAFT | 16
44612 | 44607 | 33-6010 | OG10 BEND & CAP REBAR FOR WELK | 3
44612 | 44608 | 03-6000 | SG4 FRP INSTALL 2ND FLOOR | 17
44612 | 44608 | 32-6520 | SG4 POUR TEMP WALKWAY | 9
44612 | 44608 | 02-2300 | SG4 CHECK PUMPS - PUMP DOWN WATER IN BASEMENT | 6.5
44612 | 44608 | 99-4560 | SG6 CLEAN SGN AND SG4 | 17
44612 | 44608 | 33-2400 | SG7 MAINTAIN TRENCHES/KEEP WATER DOWN | 14
44612 | 44608 | 03-1800 | OG1 TONAGE BACKUP - BACKHOE NEEDED | 1.5
44612 | 44608 | 03-2300 | OG2 POUR DUCTBANK/ START BACKFILL DUCTBANK (125 CY)) | 8.5
44612 | 44608 | 02-6005 | OG4 PAINT REMOVAL | 17
44612 | 44608 | 32-6610 | OG6 DEMO AREA | 19
44612 | 44608 | 31-1400 | OG8 POUR FLOW FILL - MOVE FENCE FOR CONCRETE TRUCK 33 CY | 9
44612 | 44608 | 07-6020 | OG9 PATCH/PREP SHAFT FOR WATERPROOFING | 4.5
44612 | 44608 | 99-4560 | OG10 VITAL RECEIVE LIFT - LULL NEEDED TO SET ON 2ND FLOOR | 2
44612 | 44608 | 33-3100 | S8 FSPE & ELECTRIC POE EXCAVATION /REMOVE FENCE | 24.5
44612 | 44608 | 03-1100 | SG4 FORM EQ PADS | 28.5
44612 | 44608 | 03-1000 | SG7 STRIP GBS | 28
44612 | 44608 | 33-6010 | LAG TRENCH FOR PLUMBERS | 8
44612 | 44608 | 31-1700 | JUMP PUMPS | 3
44612 | 44609 | 03-6000 | SG4 FRP INSTALL AT 2ND FLOOR | 16.5
44612 | 44609 | 02-6005 | OG4 PAINT REMOVAL IN BASEMENT | 16.5
44612 | 44609 | 33-9000 | OG6 DEMO AREA | 14
44612 | 44609 | 03-2300 | OG2 BACKFILL E-DUCTBANK | 8.5
44612 | 44609 | 07-6020 | OG9 PATCH AND PREP FOR WATERPROOFING | 12.5
44612 | 44609 | 07-6020 | CONFINED SPACE TRAINING | 8
44612 | 44609 | 32-6520 | SG4 INSTALL TEMP FENCE AT NEW WALKWAY | 9.5
44612 | 44609 | 31-2200 | OG1 /OG2 BACKFILL STAYFORM/PREP FOR CONCRETE POUR | 3
44612 | 44609 | 99-4560 | SG6 REMOVE DEBRIS (SITE MAINT.) | 12.5
44612 | 44609 | 33-1000 | OG3 INSTALL FSP ACCESS (MAINT. PROTECT EXISTING UTILITIES) | 5
44612 | 44609 | 99-4560 | OG1/OG5 CLEAN AREA (SITE MAIN) | 8.5
44612 | 44609 | 99-4560 | OG9 CLEAN AREA/BLD | 4.5
44612 | 44609 | 31-1400 | OG8 BEGIN BACKFILL FOR SLAB | 6
44612 | 44609 | 03-1900 | OG10 MOVE BLANKETS FOR OG8 (POUR CONC) | 3
44612 | 44609 | 31-1700 | OG8 PUMPS WARER FROM SHAFT | 2
44612 | 44609 | 02-2300 | OG4 PUMP WATER FROM BASEMENT | 6
44612 | 44609 | 03-1100 | SG4 FORM PADS | 18
44612 | 44609 | 99-4560 | SG6 FIX NETTING & TOE BOARDS | 6
44612 | 44609 | 99-4560 | OG10 INSTALL NETTING & TOE BOARDS | 19.5
44612 | 44609 | 07-6020 | CONFINED SPACE SAFETY CLASS | 6
44612 | 44609 | 31-1100 | OG1 BACKFILL ( BACKFILL) | 5.5
44612 | 44609 | 03-1100 | OG2 BACKFILL ( FORMWORK) | 5.5
44612 | 44609 | 99-4560 | OG9 SITE MAINTENANCE | 4
44612 | 44609 | 33-1000 | INSTALL DECK FOR STAND PIPE (MAINT. EXISTING UTILITY) | 4
44612 | 44609 | 00-0019 | INSTALL FNECNING CHANGE ORDER | 4
44612 | 44609 | 31-1700 | JUMP PUMPS | 2
44612 | 44610 | 03-1100 | sg4 form eq pads | 7
44612 | 44610 | 02-6015 | OG2 CLOSE 2 WINDOWS W/ PLYWOOD (WINDOW DEMO) | 3
44612 | 44610 | 03-1000 | OG8 FORM COLUMN BASES FOR GROUT | 48.5
44612 | 44610 | 33-6010 | MOVE STUFF IN WELKIN YARD - RELOCATE STORED MATERIAL | 6
44612 | 44610 | 33-6010 | SG3 MOVE SCAFFOLD OUT OF WELKIN YARD | 3
44612 | 44610 | 03-2100 | SG4 POUR EQ PADS 2ND FLOOR APT | 6
44612 | 44610 | 03-2100 | OG1/OG2 POUR FOOTING | 5
44612 | 44610 | 03-1900 | OG8 POUR PIT SLAB | 4.5
44612 | 44610 | 31-2200 | OG8 BACKFILL/COMPACT FOR SLAB/MOVE STOCKPILED MATERIAL FROM OG10 | 38
44612 | 44610 | 33-6010 | og10 MACHINE ASSISTANCE FOR WELK | 1
44612 | 44610 | 02-6005 | og4 PAINT REMOVAL IN BASEMENT | 5
44612 | 44610 | 99-4560 | OG5 REMOVE GARBAGE/DEBRIS IN FSE YARD | 1
44612 | 44610 | 99-4560 | OG9 CLEAN AREA BLD | 17
44612 | 44610 | 32-6510 | SGN MAINTAIN WHITE MESH | 3
44612 | 44610 | 03-6000 | SG4 FRP INSTALL AT 2ND FLOOR | 18
44612 | 44610 | 02-2300 | SG2 CLEAN/PUMP BASEMENT | 19
44612 | 44610 | 02-6015 | OG1 DEMO WINDOW | 7
44612 | 44610 | 31-2000 | OG3 DEMO/PROBE FOR FSE CMU | 5
44612 | 44610 | 02-2300 | OG6 CLEAN WATER FROM BASEMENT | 5.5
44612 | 44610 | 31-1700 | jump pumps | 2
44605 | 44599 | 03-6000 | SG4 PATCH/PREP FOR FRP | 25.5
44605 | 44599 | 99-4560 | SG6 PREP AREA FOR CMU INSTALL/CLEAN AREA | 13
44605 | 44599 | 31-1000 | OG1 EXC FOR FLOOD WALL/HNS MOVING SOIL | 25
44605 | 44599 | 33-3100 | OG4 EXC STEAM RUN TO OG3 | 13
44605 | 44599 | 02-2300 | OG5 CLEAN AND PUMP BASEMENT | 12.5
44605 | 44599 | 31-2200 | OG2 BACKFILL ALONG SURF FOR TEMP WALKWAY/INSTALL GAS PIPE OG8 | 7
44605 | 44599 | 02-6005 | OG2 PAINT REMOVAL | 9
44605 | 44599 | 99-4560 | OG10 MESH DELIVERY/MOVE MESH TO SECOND FLOOR AND ROOF | 11
44605 | 44599 | 31-1820 | SG7 CUT SHEETS IN PATH | 5
44605 | 44599 | 99-7200 | Holiday pay | 8
44605 | 44599 | 03-1000 | FORM GRADE BEAMS SG7 FORMWORK | 27.5
44605 | 44599 | 03-1000 | FORM FLUE PAD SG6 | 9
44605 | 44599 | 31-1820 | BURN OUT SHEETS IN PATH OF PLUMBING AT SG7 | 12
44605 | 44599 | 33-3100 | GROUND SUPPORT OG8 | 4
44605 | 44599 | 03-1300 | SET ANCHOR BOLTS | 12
44605 | 44599 | 33-2400 | jump pumps | 3
44605 | 44600 | 03-6000 | SG4 FRP INSTALL | 18
44605 | 44600 | 07-6010 | SG6 DRY OUT SHAFT FOR DSTAR, COVER | 11.5
44605 | 44600 | 31-1000 | OG2 EXCAVATE FOR FLOOD BARRIER | 15
44605 | 44600 | 02-2000 | DEMO PLANTER OG2 | 6
44605 | 44600 | 33-3100 | OG4 EXCAVATE STEAM RUN TO OG3 | 27
44605 | 44600 | 33-3100 | OG4 MAINTENANCE EXISTING UTILITY/SUPPORT STEAM PIPE | 7
44605 | 44600 | 02-6005 | OG2 PAINT REMOVAL | 18
44605 | 44600 | 32-6510 | OG10 CLEAN DECKS FOR MESH INSTALL/MOVE MESH TO ROOF | 13
44605 | 44600 | 03-1900 | OG9 REMOVE BLANKETS - MOVE TO OG10 | 3
44605 | 44600 | 00-0021 | OG6 REMOVE PLAYGROUNDS | 19
44605 | 44600 | 03-1000 | og9 form pads | 26
44605 | 44600 | 03-1900 | og10 pour stop | 17.5
44605 | 44600 | 03-1000 | og10 form columns | 11
44605 | 44600 | 31-1830 | OG8 LAGGING | 7
44605 | 44600 | 33-1000 | SUPPPORT EXISTING UTILITU | 3
44605 | 44600 | 31-1700 | JUMP PUMPS | 3
44605 | 44601 | 02-2300 | sg1 pump down basement | 7.5
44605 | 44601 | 03-6000 | SG4 FRP INSTALL/INSPECTION ON SITE | 17
44605 | 44601 | 33-3100 | SG7 MAINTAIN TRENCHES/LEVEL OFF PLUMBING TRENCH/PUMP DOWN NEAR SHAFT | 7
44605 | 44601 | 31-1100 | OG1/OG2 COMPACT FOOTING INSPECTION INSITE/DIG OUT 4" MORE AFTER | 8.5
44605 | 44601 | 32-6610 | OG6 DEMO AREA | 8
44605 | 44601 | 33-3100 | OG4 EXC STEAM TO OG3/ | 18
44605 | 44601 | 02-6005 | OG2 PAINT REMOVAL | 18.5
44605 | 44601 | 03-1900 | OG10 CLEAN DECK FOR CONCRETE POUR/ PREP AND CLEAN | 11
44605 | 44601 | 99-4560 | HANG ADDRESS AND FENCE SIGNS | 9.5
44605 | 44601 | 03-1000 | OG9 FORM ALL PADS ON 2ND FLOOR | 39
44605 | 44601 | 03-1000 | OG10 FORM ALL PENETRATIONS + STOPS FOR POUR | 28
44605 | 44601 | 33-3100 | SET TRENCH BOX AND DIG TRENCH | 5
44605 | 44601 | 33-1000 | MAIN OF EXIT UTILITIES | 9
44605 | 44601 | 31-1700 | jump pumps | 3
44605 | 44601 | 07-6020 | Dry out shaft for dstar SG6 | 4
44605 | 44601 | 31-2000 | Test Pits | 4
44605 | 44601 | 99-4560 | Site maintenance | 8
44605 | 44602 | 03-1000 | OG9 FINISH PADS ON 2ND FLOOR | 4
44605 | 44602 | 03-1000 | OG10 SUPPORT 1 DECK FOR CONCRETE AROUND ELECTRICAL RISERS (FORMWORK) | 9
44605 | 44602 | 03-1000 | SG7 FINISH GRADE BEAMS + BOLT PATTRN - 2 HOURS TO SET ANCHOR BOLTS | 13.5
44605 | 44602 | 03-1100 | OG1 FORM FOOTINGS FOR FLOOD GATES | 14
44605 | 44602 | 03-1100 | OG2 FORM FOOTINGS FOR FLOOD GATES | 18
44605 | 44602 | 03-1400 | SG6 DRILL IN ANCHOR AND PUT REBAR FOR PAD | 4
44605 | 44602 | 00-0019 | LAGGING UTILITIES OG3 FENCE (CO) | 8
44605 | 44602 | 03-1900 | PUTTING PLYWOOD OG9 | 4
44605 | 44602 | 03-1000 | EDGE REPAIR | 4
44605 | 44602 | 03-1900 | POUR CONCRETE OG10 DECK & OG9 83CY | 24
44605 | 44602 | 03-1200 | PUMP OPERATOR OG10 & OG9 | 21
44605 | 44602 | 02-6005 | OG2 PAINT REMOVAL | 18
44605 | 44602 | 33-3100 | OG4 EXC STEAM/ SUPPORT UTIL | 6
44605 | 44602 | 32-6610 | OG6 DEMO AREA / 2 LIVE LOADS | 20
44605 | 44602 | 03-1900 | OG9 AND OG10 POUR 2ND FLOOR | 38
44605 | 44602 | 03-6000 | SG4 FRP INSTALL / CLEAN AREA | 17
44605 | 44602 | 33-2400 | SG6 COVER SHAFT/ OG5 INSTALL FLOAT ON PUMP | 4
44605 | 44602 | 33-3100 | SG7 MAINTAIN TRENCHES | 7
44605 | 44602 | 33-2400 | jump pumps | 2
44605 | 44602 | 03-1300 | SG7 Anchor bolts | 2
44605 | 44602 | 00-0019 | OG4 Fence CO | 6.5
44605 | 44603 | 03-6000 | SG4 FRP INSTALL | 17
44605 | 44603 | 03-1900 | SG7 POUR GRADE BEAMS | 5
44605 | 44603 | 32-6610 | OG6 DEMO AREA 5 LIUVE LOADS | 31.5
44605 | 44603 | 03-1900 | OG10 INSTALL BLNAKETS, 2ND FLOOR, ROOF AND BULKHEAD ROOF | 9
44605 | 44603 | 31-1700 | SG1/7 CHECK PUMPS | 1
44605 | 44603 | 03-1900 | OG9 PATCH & PREP SHAFT FOR WATERPROOFING (PATCH CONC) | 6.5
44605 | 44603 | 31-1400 | OG8 EXPOSE PIPE FOR VITAL/ BACKFILL AT BLD CORNER FOR FLOW FILL | 4.5
44605 | 44603 | 02-6005 | OG2 PAINT REMOVAL | 9
44605 | 44603 | 07-6020 | SG6 COVER SHAFT FOR DSTAR | 3
44605 | 44603 | 00-0022 | S8 CLEAN/ PUMPS BASEMENT (CHANGE ORDER) | 26
44605 | 44603 | 32-6510 | INSTALL WHITE MESH | 8
44605 | 44603 | 03-1100 | OG2 FORM FLOOD WALL FOOTING | 28
44605 | 44603 | 03-1000 | OG9 PUT UP PLYWOOD FR FORMWORK | 4
44605 | 44603 | 00-0022 | S8 CLEAN BASEMENT (CO) | 4
44605 | 44603 | 03-1000 | GATHER FORMS FOR PICKUP | 44.5
44605 | 44603 | 31-1700 | jump pump | 2
44598 | 44592 | 02-6005 | OG2 PAINT REMOVAL | 17
44598 | 44592 | 32-6000 | SG4 PATCH UNDERSIDE OF SAWCUT OPENINGS FOR FRP | 7
44598 | 44592 | 99-4560 | OG4 SNOW REMOVAL/ CONTINUE DEMO OF AREA/ LOADOUT | 19
44598 | 44592 | 99-4560 | OG9 PREP FOR DECK POURS/SNOW REMOVAL | 13
44598 | 44592 | 99-4560 | SNOW REMOVAL IN ALL WORK AREAS/WALKWAYS | 72
44598 | 44592 | 03-1000 | COLUMN FORMWORK AT OG10 | 32.5
44598 | 44592 | 31-1700 | JUMP PUMP | 1
44598 | 44592 | 32-6610 | Clear out OGW area | 7
44598 | 44593 | 03-1000 | FORM COLUMNS OG10 | 15
44598 | 44593 | 03-1000 | BULKHEADS FOR DECK POUR AT OG9 | 6
44598 | 44593 | 99-7200 | HOLIDAY | 8
44598 | 44593 | 99-4560 | SG6 SNOW REMOVAL/2ND FLOOR/CLEAN SHAFT/PREP FOR WATERPROOFING | 17
44598 | 44593 | 02-6005 | OG2 PAINT REMOVAL | 17
44598 | 44593 | 32-6610 | OG4 CONTINUE DEMO OF AREA | 4.5
44598 | 44593 | 03-1800 | SG4/SG5/OG1/OG2 REBAR DELIVERY | 13
44598 | 44593 | 02-2300 | OG2 CLEAN BASEMENT - PAINT REMOVAL DEBRIS/ trash removal SG4 | 19
44598 | 44593 | 03-1900 | OG9/OG10 CLEAN AREA FOR CONCRETE PUMP - CECK POURS AND COLUMNS | 7
44598 | 44593 | 99-4560 | OG9 PREP FOR DECK POURS/SNOW REMOVAL | 22
44598 | 44593 | 33-2400 | jump pumps | 2
44598 | 44593 | 03-1900 | POUR CONCRETE | 24
44598 | 44593 | 02-1900 | Clear OGW | 10.5
44598 | 44593 | 02-2200 | Clear OGW | 10.5
44598 | 44594 | 02-6005 | OG2 PAINT REMOVAL | 18
44598 | 44594 | 32-6610 | OG4 CONTINUE DEMO OF AREA | 30
44598 | 44594 | 02-6060 | OG1 START DEMO | 6
44598 | 44594 | 03-1900 | OG9/OG10 POUR 2ND FLOOR /ROOF/PENTHOUSE/POUR COLUMNS | 45
44598 | 44594 | 02-2300 | SG4 SETUP SMALL PUMP TO SUCK WATER/CHOP CONCRETE | 8
44598 | 44594 | 02-2300 | SG5 INSTALL FAN/BASEMENT | 5.5
44598 | 44594 | 32-6520 | OG1 INSTALL FENCE/FOR DEMO AREA | 11
44598 | 44594 | 99-4560 | REMOVE SNOW BY FENCE AREA OG2/OG10 | 6
44598 | 44594 | 33-2400 | JUMP PUMPS | 2
44598 | 44594 | 03-1900 | POUR COLUMNS OG9/ POUR 2ND FLOOR/ROOF OG10 | 38.5
44598 | 44594 | 99-7200 | holiday pay | 8
44598 | 44594 | 03-1000 | BOX OUTS AT DEK POUR AT OG9 | 4
44598 | 44594 | 03-1000 | FORM COLUMNS OG10 | 16
44598 | 44594 | 03-1900 | POUR CONCRETE | 20
44598 | 44595 | 32-6000 | SG4 PACTH /PREP FOR FRP INSTALL | 17
44598 | 44595 | 02-2100 | OG1 SAWCUT SIDEWALK/DEMO 7 CONTAINERS FOR LOADOUT | 25.5
44598 | 44595 | 02-6005 | OG2 PAINT REMOVAL | 23
44598 | 44595 | 32-6610 | OG4 CLEAN /GRADE AREA | 9
44598 | 44595 | 02-1600 | OG3/SG6/S8 CLEAN/GRADE AREA - "STOCKPILES" | 9
44598 | 44595 | 32-6520 | OG6 REPAIR DAMAFE FENCE/ | 4.5
44598 | 44595 | 03-1900 | OG9 INSTALL BLANKETS ON DECKS | 9.5
44598 | 44595 | 99-4560 | CLEAN/MAINTAIN ALL AREAS | 13.5
44598 | 44595 | 02-2300 | SG5 PUMP DOWN WATER/CLEAN BASEMENT.COVER ALL STCOKPILES | 18
44598 | 44595 | 99-7200 | HOLIDAY PAY | 8
44598 | 44595 | 03-1000 | FORM GRADE BEAMS AT SG7 | 46
44598 | 44595 | 99-4560 | SITE MAINTENANCE | 8
44598 | 44595 | 33-2400 | JUMP PUMPS | 1
44598 | 44596 | 32-6000 | SG4 PATCH AND PREP FOR FRP INSTALL | 26
44598 | 44596 | 02-2300 | SG5 CLEAN AND PUMP BASEMENT | 8
44598 | 44596 | 02-2300 | OG5 CLEAN AND PUMP BASEMENT | 14
44598 | 44596 | 32-6520 | OG8 BUMP OUT FENCE AT STREET | 9.5
44598 | 44596 | 03-1700 | SG6/OG9 CONSOLIDATE REBAR | 18
44598 | 44596 | 03-1000 | SG7 CLEAN AND REMOVE FORMS | 9
44598 | 44596 | 33-3100 | OG8 DIG TRENCH FOR PLUMBINNG | 9
44598 | 44596 | 02-6005 | OG2 PAINT REMOVAL | 18
44598 | 44596 | 99-4560 | CLEAN & MAINTAIN ALL AREAS | 26
44598 | 44596 | 33-2400 | JUMP PUMPS | 3
44598 | 44596 | 99-7200 | holiday pay | 8
44598 | 44596 | 03-1000 | STRIP COLUMNS | 30.5
44598 | 44596 | 03-1900 | REMOVE SCAFFOLD AT COLUMNS, ACCESS TO POUR | 14
44591 | 44585 | 32-6000 | OG2 SAWCUT ELECTRIC POE/ CHOP OUT CONCRETE BLOCK IN PATH/NEW DUCTBANK | 13
44591 | 44585 | 31-1100 | SG4/SG5 COMPACT FLOODGATE AREA FOR INSPECTION - BACKRFILL FOR CONCRETE TRUCK/ REP FOR POUR CONCRETE | 3.5
44591 | 44585 | 03-1500 | 'SG4/SG5 POUR TO INFILL WINDOWS | 2
44591 | 44585 | 03-2300 | 'SG4/SG5 POUR THRUST BLOCK | 1.5
44591 | 44585 | 33-6010 | SG7 CALLAHAN INSTALLING STEAM PIPE | 6
44591 | 44585 | 02-6005 | OG1 PAINT REMOVAL | 17
44591 | 44585 | 31-1000 | SG4 HAND DIG FOR MASONRY | 17
44591 | 44585 | 32-6510 | CLEAN/MAINTAIN ALL AREA/WHITE MESH | 29
44591 | 44585 | 02-6130 | SG3 SETUP SCAFFOLDING STAIRTOWER | 14
44591 | 44585 | 03-1000 | SG7 START FORMING GRADE BEAMS | 14
44591 | 44585 | 03-1100 | SG4 FORM WINDOWS | 26.5
44591 | 44585 | 99-4560 | OG10 STRAIGHTED OUT FOR STAIR GUYS | 10
44591 | 44585 | 31-1700 | JUMP PUMPS | 2
44591 | 44585 | 33-3100 | OG2 CHOP OUT CONCRETE BLOCK IN PATH/NEW DUCTBANK | 17
44591 | 44585 | 32-6610 | Clear OGW AREA | 6
44591 | 44585 | 02-2100 | Demo Curbs OGW | 5.5
44591 | 44585 | 02-1700 | Remove Fence OGW | 5.5
44591 | 44585 | 02-1900 | Demo AsphaltPavement OGW | 5.5
44591 | 44586 | 03-2300 | SG4 POUR THRUST BLOCKS | 4
44591 | 44586 | 31-1300 | SG7 EXC STONE BOX HOELS AT JOINT LOCATIONS /NEED MACHINE | 13
44591 | 44586 | 32-6000 | OG2/3 PATCH CONDUIT PENETRATIONS | 15
44591 | 44586 | 31-1000 | SG4 HAND DIG FOR MASONRY/CHOP CONCRETE | 18
44591 | 44586 | 33-2400 | SG3 CLEAN TRENCH TO OG5 - INSTALL EXTRA PUMP ON TRENCH | 13
44591 | 44586 | 99-4560 | CLEAN MAINTAIN ALL AREAS/ WHITE MESH | 25
44591 | 44586 | 02-6005 | OG1 PAINT REMOVAL | 17
44591 | 44586 | 31-1000 | SG4 SHORE UP RAMP AREA | 4
44591 | 44586 | 03-1000 | OG10 CLOSE UP COLUMN | 20
44591 | 44586 | 03-1000 | SG7 FORM GRADE BEAMS | 26
44591 | 44586 | 99-4560 | OG10 ADJUST LADDER FOR ACCESS TO 2ND FLOOR | 4
44591 | 44586 | 32-6000 | SG6 FIND PENETRATION IN TANK WALL | 2.5
44591 | 44586 | 31-1700 | JUMP PUMPS | 2
44591 | 44586 | 32-6610 | Clear OGW AREA | 6
44591 | 44586 | 02-2100 | Demo Curbs OGW | 6
44591 | 44586 | 02-1700 | Remove Fence OGW | 6
44591 | 44586 | 02-1900 | Demo AsphaltPavement OGW | 5.5
44591 | 44587 | 31-1000 | SG4 HAND DIG FOR MASONRY | 17
44591 | 44587 | 31-1000 | SG7 EXC/STONE FOX HOLES AT JOINT LOCATIONS/MACHINE NEEDED | 15
44591 | 44587 | 02-6005 | OG1 PAINT REMOVAL/ | 16.5
44591 | 44587 | 00-0019 | OG1 START INSTALL TEMP FENCE AT BLDG ENT | 16.5
44591 | 44587 | 33-1000 | SG3 MAINTENANCE EXISTING UTILITY - STORM PIPE | 11.5
44591 | 44587 | 33-3100 | OG2 CUT BACK SLOPE ON TRENCH/CLEAN AREA | 5
44591 | 44587 | 32-6510 | MAINTAIN WHITE MESH | 17
44591 | 44587 | 03-1100 | SG4 STRIP WINDOWS | 14
44591 | 44587 | 31-1000 | SG4 BUILD RAMP W/HANDRAIL | 6
44591 | 44587 | 03-1000 | OG10 TAKE DOWN COLUMN FORMS FOR STAIRS | 2
44591 | 44587 | 03-1000 | SG7 FORM AND BRACE GRADE BEAMS | 21
44591 | 44587 | 32-6000 | SG6 DUCTWORK PENTRATION IN TANK WALL | 8
44591 | 44587 | 32-6000 | SG6 MAKE DUCTWORK PENETRATION BIGGER | 5.5
44591 | 44587 | 31-1700 | JUMP PUMPS | 2
44591 | 44587 | 32-6610 | Clear OGW AREA | 7.5
44591 | 44587 | 02-2100 | Demo Curbs OGW | 7.5
44591 | 44587 | 02-1700 | Remove Fence OGW | 7.5
44591 | 44587 | 02-1900 | Demo AsphaltPavement OGW | 7.5
44591 | 44588 | 33-3100 | SG7 EXCAVATE | 7
44591 | 44588 | 33-3100 | SG3 CLEAN TRENCH TO OG5 | 13.5
44591 | 44588 | 31-1000 | SG4 HAND DIG FOR MASONRY | 17
44591 | 44588 | 02-6005 | OG1 PAINT REMOVAL | 17
44591 | 44588 | 32-6520 | OG1 INSTALL TEMP FENCE AR BLD ENTRANCE | 18.5
44591 | 44588 | 02-2300 | OG2 CLEAN BASEMENT/MAINTAIN ALL AREAS WHITE MESH | 17
44591 | 44588 | 02-6130 | OG3/SG3 REMOVE STAIR TOWER | 22
44591 | 44588 | 02-6130 | OG6 INSTALL STAR TOWER | 18.5
44591 | 44588 | 99-4560 | OG10 SAFETY ITEMS | 2
44591 | 44588 | 32-6000 | SG6 FINISH CHOPPING PENETRATION IN TANK WALL FOR THEMIS | 6
44591 | 44588 | 33-2400 | JUMP PUMPS | 2
44591 | 44588 | 33-2400 | SG7 STONE FOX HOELS AT JOINT LOCATIONS AND INSTALL EXTRA PUMPS | 6.5
44591 | 44588 | 32-6610 | Clear OGW AREA | 8
44591 | 44588 | 02-2100 | Demo Curbs OGW | 8
44591 | 44588 | 02-1700 | Remove Fence OGW | 8
44591 | 44588 | 02-1900 | Demo AsphaltPavement OGW | 8
44591 | 44589 | 03-1900 | SG7 COVER GRADE BEAMS W/BLANKETS FOR SNOW | 10
44591 | 44589 | 32-6000 | SG3 COVER POE WITH PLYWOOD | 5
44591 | 44589 | 32-6000 | OG5 CVER POE WITH PLYWOOD | 5
44591 | 44589 | 31-1900 | TREE PROTECT | 6
44591 | 44589 | 32-6510 | OG9 FIX ORANGE NETTING | 14.5
44591 | 44589 | 99-4560 | SG3 CLEAN DEBRIS FROM BACKSIDE OF BUILDING | 14.5
44591 | 44589 | 32-6000 | SG4 PATCH UNDERSIDE OF SAWCUT OPENINGS | 17
44591 | 44589 | 02-6005 | OG2 PAINT REMOVAL | 25
44591 | 44589 | 32-6610 | OG4 CONTINUE DEMO OF area, 6 containers | 9.5
44591 | 44589 | 03-1900 | OG9 SETUP BLANKETS ON ROOF | 10
44591 | 44589 | 33-1000 | OG2/3 MAINTENANCE EXISTING UTILITIES | 12
44591 | 44589 | 99-4560 | PREP FOR SNOW STORM/SECURE YODOCKS/SALT WALKWAYS | 7
44591 | 44589 | 32-6510 | /MAINTAIN ALL WHITE MESH | 6.5
44591 | 44589 | 31-1700 | Jump pumps | 1
44591 | 44589 | 02-2100 | Demo Curbs OGW | 9
44591 | 44589 | 02-1700 | Remove Fence OGW | 9
44591 | 44589 | 02-1900 | Demo AsphaltPavement OGW | 9
44584 | 44578 | 99-7200 | Holiday Pay | 56
44584 | 44579 | 03-1000 | SG7 STRIP FOOTING | 20.5
44584 | 44579 | 03-1000 | SG7 SITE MAINTNENACE | 8
44584 | 44579 | 03-1000 | OG10 FORM COLUMNS | 20
44584 | 44579 | 03-1000 | OG10 SITE MAINTENANCE | 8
44584 | 44579 | 33-3100 | OG2 DIG TRENCH FOR FSE | 8
44584 | 44579 | 02-6015 | SG5 DEMO VENT/CLEAN DEBRIS | 19
44584 | 44579 | 32-6000 | SG1 SAWCUT HOLE FOR DUCTWORK | 7
44584 | 44579 | 33-6010 | SG7 CALLAHAN INSTALL UG STEAM SUPPORT | 6
44584 | 44579 | 31-1400 | SG7 BACKFILL AND COMPACT AROUND FOOTINGS | 28
44584 | 44579 | 33-3100 | OG2 EXCAVATE ELEC TRENCH MH RUN | 18
44584 | 44579 | 02-6005 | OG1 PAINT REMOVAL | 9
44584 | 44579 | 02-6060 | OG5 SURFACE PREP 2ND FLOOR APT | 17
44584 | 44579 | 99-4560 | CLEAN SITES OG9/OG10 | 21
44584 | 44579 | 31-1700 | JUMP PUMPS | 3
44584 | 44580 | 33-6010 | SG6 SUPPORT WELKIN WITH LULL | 2
44584 | 44580 | 32-6000 | SG6 SAWCUT ROOF PENETRATIONS | 22
44584 | 44580 | 03-1000 | OG10 GROUT COLUMNS | 9.5
44584 | 44580 | 99-4560 | SG6 REMOVE TARPS AND LOADOUT DEBRIS & OG9 CLEAN/MAINTAIN AREA | 35
44584 | 44580 | 33-6010 | SG7 CALLAHAN INSTALL UGB STEAM/SUPPORT W/MACHINE - PIPE IN TRENCH | 9
44584 | 44580 | 31-2200 | OG3 BACKFILL DUCTBANK/COMPACT INSPECTION | 17
44584 | 44580 | 02-6060 | OG5 SURFACE PREP 2ND FLOOR APT | 17
44584 | 44580 | 02-6005 | OG1 PAINT REMOVAL | 17
44584 | 44580 | 03-1000 | OG10 FORM COLUMNS | 42
44584 | 44580 | 32-6000 | SG6 COVER PENETRATIONS IN ROOF | 10.5
44584 | 44580 | 03-1000 | GET MATERIAL FROM OTHER AREAS AND BRING IT TO OG10 | 12
44584 | 44580 | 33-1000 | SG7 BRACE UTILITIES | 8
44584 | 44580 | 31-1700 | JUMP PUMPS | 2
44584 | 44581 | 32-6000 | SG6 COMPLETE ROOF PENETRATIONS/LOAD OUT DEBRIS | 19
44584 | 44581 | 02-6005 | OG1 PAINT REMOVAL | 18
44584 | 44581 | 33-3100 | OG3 EXC FOR POE/INSTALL FENCE TEMP WALKWAY | 14
44584 | 44581 | 33-3100 | SG3 MAINTAIN/CUTBACK/RAMP INTO TENCH TO OG5 | 6
44584 | 44581 | 02-1900 | SG4 ASPHALT/CONCRETE DEMO AT PLAYGROUND AREA/LOAD OUT 5EA 20YD | 18
44584 | 44581 | 31-1000 | SG4 SAWCUT/CHOP CONCRETE/HANDDIG FOR MASONRY | 18
44584 | 44581 | 32-6520 | OG10 REMOVE FENCE | 10
44584 | 44581 | 02-2300 | CLEAN/MAINTAIN BASEMENTS | 26
44584 | 44581 | 03-1000 | OG10 PATCH PLUMBING SHAFT FR COLUMNS AND BEAMS | 32.5
44584 | 44581 | 32-6000 | SG4 PATCH PENTRATIONS 2ND FLOOR | 8
44584 | 44581 | 32-6000 | SG6 PATCH PENTRATINS IN ROOF | 8
44584 | 44581 | 99-4560 | OG10 REMOVE SCAFFOLDING FOR STAIR COMPANY | 8
44584 | 44581 | 99-4560 | OG10 SITE MAINTENANCE | 8
44584 | 44581 | 33-3100 | SG7 FIR TRENCH BY WELKINS YARD | 3
44584 | 44581 | 33-1000 | SG7 INSTALL BEAM FOR WATER ISSUE | 2
44584 | 44581 | 33-3100 | OG2 DUG DOWN TRENCH BOX | 3
44584 | 44581 | 31-1700 | JUMP PUNPS | 1
44584 | 44582 | 32-6000 | SG1 1 HOLES TO CHOP FOR DUCTWORK | 2.5
44584 | 44582 | 02-1900 | SG4 ASPHALT DEMO AT PLAYGROUND, LOADOUT 2 - 20YD | 17
44584 | 44582 | 31-1000 | SG4 HAND DIG FOR MASONRY | 8.5
44584 | 44582 | 31-1000 | SG5 EXCAVATE FOR FLOOTGATES | 5.5
44584 | 44582 | 33-6010 | SG7 CALLAHAN INSTALLING STEAM PIPE SUPPORT | 4
44584 | 44582 | 32-6520 | OG3/OG4 FENCE INSTALL AT TEMPWALKWAY | 24.5
44584 | 44582 | 02-6005 | OG1 PAINT REMOVAL | 17
44584 | 44582 | 32-6510 | FIX MAINTAIN FENCE/WHITE NETTING ALL AREAS | 25
44584 | 44582 | 31-1900 | TREE PROTECTION | 18.5
44584 | 44582 | 03-1100 | SG4 WINDOW FRAMING | 24
44584 | 44582 | 03-2300 | SG4 THRUST BLOCK | 8
44584 | 44582 | 03-1000 | OG10 PLUMBING SHAFT FORMS | 14
44584 | 44582 | 99-4560 | OG10 SITE MAINTENANCE | 8
44584 | 44582 | 31-1700 | jump pumps | 1
44584 | 44582 | 02-2100 | SG4 DEMO HIGH CURBS NEAR ENTRANCE/ | 8.5
44577 | 44571 | 03-1700 | REBAR DELIVERY OG9/SG7 | 7
44577 | 44571 | 31-1300 | PREP AREA OR SUBGRADE INSPECTION SG7 | 2
44577 | 44571 | 31-2200 | BACKFILL DUCTBANK OG3 FSE | 11
44577 | 44571 | 03-1400 | DRILL AND DOWEL CURB WALL - REBAR INSPECTION OG1/2/3 | 9
44577 | 44571 | 02-6005 | PAINT REMVAL OG1 | 8.5
44577 | 44571 | 32-6520 | GRADE AREA /REMOVE FENCEREMOVE FSP BRIDGE/DUCTBANK AREA OG2 | 13
44577 | 44571 | 33-6010 | SUPPORT CALLAHAN W MACHINE - PIPE SUPPORT OG10 | 13
44577 | 44571 | 02-2300 | INSTALL EXTRA 2" PUMP BASEMENT/REMOVE WATER AND CLEAN OG2 | 6
44577 | 44571 | 99-4560 | INSTALL REBAR CAPS SG6/OG8/9 | 8
44577 | 44571 | 03-1900 | CLEAN 2ND FLOOR AN ROOF FOR CONCRET EPOUR OG9 | 15
44577 | 44571 | 99-4560 | SUNBELT PICKUP HEATERS/GENERATR | 4
44577 | 44571 | 07-6320 | CLEAN/LOADOUT FIREPROOFING MATERIAL | 6
44577 | 44571 | 03-1000 | CLOSEUP OPENINGS ON 2ND FLOOR | 17.5
44577 | 44571 | 03-1000 | SG7 FORM BRACE FOOTINGS | 56.5
44577 | 44571 | 31-1700 | jump pumps | 2
44577 | 44571 | 02-6060 | GRINDR 2ND FLOOR APT | 8.5
44577 | 44572 | 31-1000 | SG4 ADJUST FENCE/ DEMO & EXC FOR MASONRY FOUNDATION | 17
44577 | 44572 | 99-4560 | SG6/OG9 CLEANYP FIREPROOFING MATERIAL/CLEAN SITES | 25
44577 | 44572 | 02-6015 | OG1/2/3 LOUVER/FAN DEMO | 17
44577 | 44572 | 02-6005 | OG1 PAINT REMOVAL | 17
44577 | 44572 | 03-1400 | OG3 DOWEL CURB WALL | 2
44577 | 44572 | 03-1000 | og9 close up openings 2nd floor/clean 2nd floor prep for pour | 9
44577 | 44572 | 32-6520 | OG5 INSTALL FENCE FOR POE | 6
44577 | 44572 | 33-3100 | SG3 TRENCH TO OG5 WORK ON STORM PIPE REPAIR/INSTALL 2 MORE PUMPS | 30
44577 | 44572 | 33-1000 | CHECK ALL EXPOSED WATER LINES/INSTALL HEAT CABLE | 11
44577 | 44572 | 32-6000 | OG5 SAWCUT ELECTRICAL PENETRATIONS | 3
44577 | 44572 | 03-1100 | SG4 STRIP WINDOWS | 10
44577 | 44572 | 03-1000 | SG7 FINISH FOOTINGS W/REBAR TEMPATES FOR LATHERS | 13.5
44577 | 44572 | 03-2300 | OG2 STRIP DUCT BANK BULKHEAD | 7
44577 | 44572 | 03-1100 | OG2 FORM CURB WALL | 8
44577 | 44572 | 03-1100 | OG1 FORM CURB WALL | 11
44577 | 44572 | 03-1100 | OG3 FORM CURB WALL | 7
44577 | 44572 | 03-1900 | OG9 FIX DECK | 4
44577 | 44572 | 33-3100 | WORKED IN SHEATHING BOX BETWEEN ELECTRICIAN AND PLUMBERS | 4
44577 | 44572 | 31-1700 | jump pumps | 2
44577 | 44573 | 07-6020 | SG6 CLEAN PLUMBING SHAFT/ PATCH HOLES IN SLABS | 17
44577 | 44573 | 33-3100 | SG7 CHOP OUT CONCRETE OBSTRUCTIONS IN STEAM TRENCH SG3 TO SG1 | 10.5
44577 | 44573 | 33-6010 | IG7 AND OG10 SUPPORT CALLAHAN | 8
44577 | 44573 | 02-6015 | OG4/5 LOUVER /FAN DEMO | 11
44577 | 44573 | 03-1900 | SG7 COVER FOOTING W BLANKET PREP FOR POUR | 7
44577 | 44573 | 32-6000 | OG5 SAWCUT PENETRATIONS FOR FSE | 17
44577 | 44573 | 02-6015 | OG1/2/3/4 CLEAN LOUVER/FAN DEBRIS | 25
44577 | 44573 | 02-6005 | OG1 PAINT REMOVAL | 17
44577 | 44573 | 33-3100 | FINISH STORM PIPE REPAIR SG3 TO OG5 STEAM TRENCH | 8
44577 | 44573 | 33-3100 | SUNBELT TO REPAIR CAT 316 | 4
44577 | 44573 | 31-1000 | SG4 LIVE LOAD CONCRETE CONTAINERS/ EXC MASONRY FOUNDATION | 4
44577 | 44573 | 33-3100 | SHEATHING PIT BETWEEN WELKIN AND FSE YARD | 8
44577 | 44573 | 03-1100 | SG4 REDO DINOWS | 12
44577 | 44573 | 03-1900 | OG9 SPRAY FOAM OPENINGS IN DECK | 8
44577 | 44573 | 33-3100 | OG3 BULKHEAD FOR CONDUIT POE | 13.5
44577 | 44573 | 03-1000 | TAKE OUT FORM & CUT OUT REBAR | 5
44577 | 44573 | 05-6050 | OG10 CHIP OUT CONCRETE IN PLUMBING SHAFT FOR GUYTEC | 11
44577 | 44573 | 03-1400 | OG9 DRILL HOLES FOR LATHERS | 7
44577 | 44573 | 31-1700 | JUMP PUMPS | 2
44577 | 44574 | 03-1900 | SG7 POUR FOOTINGS/COVER FOOTINGS WITH BLANKETS AFTER POUR | 8.5
44577 | 44574 | 05-6020 | OG10 POUR COLUMN BASES/CHOP AND CLEAN ICE BEFORE POUR | 7
44577 | 44574 | 03-2100 | OG1/2/3 POUR CURB WALL | 15
44577 | 44574 | 33-3100 | SG7 CHOP OUT OBSTRUCTION/STEAM TRENCH SG3 TO SG1 | 16
44577 | 44574 | 31-1500 | SG3 GRADE OUT STONE | 6.5
44577 | 44574 | 31-1000 | SG4 EXC FOR MASONRY FOUNDATION | 6.5
44577 | 44574 | 33-3100 | OG10 CLEAN AND PILE UP DIRT | 3.5
44577 | 44574 | 02-2300 | SG4 CLEAN AND LOADOUT DEBRIS FROM BASEMENT | 21
44577 | 44574 | 02-6015 | og4/5/6 clean after demo fan/louver | 9.5
44577 | 44574 | 02-6005 | OG1 PAINT REMOVAL | 21
44577 | 44574 | 02-6015 | OG5/6 DEMO FAN /LOUVER | 8.5
44577 | 44574 | 02-2300 | OG4 PUMP OUT WATER/CHOP TO INSTALL SUMP | 12.5
44577 | 44574 | 32-6000 | OG5 SAWCUT ELECTRICAL PENETRATIONS | 1.5
44577 | 44574 | 02-6130 | OG1 REMOVE STAIR TOWER | 7
44577 | 44574 | 02-6130 | OG2 REMOVE STAI TOWER | 7
44577 | 44574 | 05-6020 | OG10 FORM FOR GROUT | 14
44577 | 44574 | 32-6000 | OG5 SAW CUT WALL | 6
44577 | 44574 | 33-3100 | WORKING TRENCH BETWEEN 5 STAR AND WELKINS YARD | 2
44577 | 44574 | 33-3100 | FIVE STARS C BOX | 21
44577 | 44574 | 03-1000 | OG10 SHOES FOR COLUMNS | 7.5
44577 | 44574 | 31-1700 | jump pumps | 3
44577 | 44575 | 33-3100 | SG3 REMOVE PILE OF DIRT/GRADE STONE/FIX ROAD PLATES | 8.5
44577 | 44575 | 32-6520 | SG4 ADJUST FENCE FOR MASONRY FOUNDATION | 7
44577 | 44575 | 02-2300 | OG4 PUMP OUT WATER | 11
44577 | 44575 | 33-3100 | SG7 CHOP OUT OBSTRUCTION IN STEAM TRENCH | 25
44577 | 44575 | 31-2200 | OG10 BACKFILL LVEL AREA/ CHOP OUT CONCRETE GARAGE FOOTINGS | 19.5
44577 | 44575 | 32-6000 | SG1 SHOP 2 EA HOLES FOR DUCTWORK | 2.5
44577 | 44575 | 32-6000 | SG4 SAWCUT 2ND FLOOR PENETRATIONS | 19
44577 | 44575 | 99-4560 | CLEAN SITES | 17
44577 | 44575 | 02-6005 | OG1 PAINT REMOVAL | 17
44577 | 44575 | 33-1000 | CHECK WATER LINES ARE COVERED/BLANKETS MOVING CURING BOX TO OG9 | 2
44577 | 44575 | 31-1700 | jump pumps | 3
44577 | 44575 | 02-6130 | OG3 PUT UP STAIR TOWER | 13.5
44577 | 44575 | 03-1100 | OG3 STRIP CURB WALL + CONDUIT BLK HEAD | 7
44577 | 44575 | 03-1100 | OG2 STRIP CURB WALL | 7
44577 | 44575 | 03-1100 | OG1 STRIP CURB WALL | 7
44577 | 44575 | 02-2300 | OG6 FASTNER PLYWOOF IN COMPACTER ROOM | 3
44577 | 44575 | 03-1000 | OG10 START FORMING COLUMNS | 19
44570 | 44564 | 03-6000 | SG4 PREP AND GRIND FRP | 17
44570 | 44564 | 32-6520 | SG5 ADJUST FENCE FOR MASONRY/HAND EXC | 22
44570 | 44564 | 33-3100 | SG3 MAINTAIN TRENCH | 7
44570 | 44564 | 33-3100 | OG6 PREP FOR EXCAVATE POE/ADJUTS FENCE/ REMOVE CONCRETE FOR ACCESS AND CLEAN AREA | 30.5
44570 | 44564 | 99-4560 | MOVE MATERIAL FOR CARPENTER FROM OG8 AND OG10 TO SG6 | 8
44570 | 44564 | 31-1400 | OG8 BACKFILL | 25
44570 | 44564 | 33-3100 | SG7 EXC FOR STEAM (3) PLUMBING (3) LOADOUT AND BACKFILL (2) | 26.5
44570 | 44564 | 99-4560 | SG7 SITE MAINTENANCE/CLEANUP | 4
44570 | 44564 | 31-1820 | FIRE WATCH OG8 SHEET BURNING/CUTTING | 4
44570 | 44564 | 33-2400 | SETUP PUMPS @ SG7 STEAM/PLUMBING TRENCH | 2
44570 | 44564 | 02-6130 | OG1 PUT UP STAIR TOWER | 11
44570 | 44564 | 03-2300 | OG2 FORM INSIDE BUILDING WHERE DUCT BANK PENETRATED | 14
44570 | 44564 | 02-6130 | OG4 TAKE DOWN STAIR TOWER | 11
44570 | 44564 | 03-1000 | OG8 STRIP FORMS OFF BACK OF UILDING | 2.5
44570 | 44564 | 03-1000 | OG9 STRIP FORMS OFF PLUMBING SHAFT | 14
44570 | 44564 | 03-1000 | OG9 CLEAN AND STACK FORMS | 8
44570 | 44564 | 05-6020 | OG10 FORM FOR GROUT AT COLUMN BASES | 2
44570 | 44564 | 33-6010 | SG6 REMOVE CABLE FOR WELKIN | 2
44570 | 44564 | 33-6010 | SG6 BUILD REMOVEABLE HANDRAIL | 17.5
44570 | 44564 | 03-1700 | SG7 PLYWOOD AND HANDRAIL FOR TONAGE | 12
44570 | 44564 | 31-1820 | OG8 BURN SHEETS/BACKFILL | 8
44570 | 44564 | 99-4560 | PUNCH LIST FOR OFFICE ENGINEER | 8
44570 | 44564 | 31-1700 | jump pumps | 4
44570 | 44565 | 03-6000 | SG4 PREP/GRIND SURFACE FOR FRP DEMO DMU WALL/CLEAN DEBRIS | 17
44570 | 44565 | 31-1000 | SG5 HAND EXCAVATE FOR MASONRY FOUNDATION | 11
44570 | 44565 | 32-6000 | SG6 SAWCUT PENETRATIONS FROM ROOF TO 2ND FLOOR | 7
44570 | 44565 | 33-3100 | OG6 EXC POE /ADJUST FSP ACCESS/LOADOUT HNS TRUCK ON SITE | 37.5
44570 | 44565 | 33-3100 | SG7 EXC FOR STEAM AND LOADOUT | 27
44570 | 44565 | 32-6520 | RELOCATE FENCE @ SG3 FOR HOUSING ACCESS | 14
44570 | 44565 | 03-2300 | SETUP AND POUR TRUSS BLOCK OG2 (5 CY) | 3
44570 | 44565 | 03-2300 | OG2 POUR DBANK 25CYS /COVER WITH BLANKETS | 6
44570 | 44565 | 33-3100 | MOVE MATERIAL @ OG10 STOCKPILE | 10
44570 | 44565 | 33-6010 | SG6 DEMO CONCRETE | 5
44570 | 44565 | 03-2300 | OG2 FORM TRHUST BLOCK | 22
44570 | 44565 | 02-6130 | OG5 REMOVE STAIR TOWER | 11
44570 | 44565 | 33-3100 | OG6 BUILD PLATFORM FOR FIREMAN STANDPIPE | 18
44570 | 44565 | 03-1000 | OG9 STRIP SHAFT | 16.5
44570 | 44565 | 03-1700 | OG10 REMOVE PLATFORM AT BASE OF PLUMBING SHAFT | 18
44570 | 44565 | 32-6520 | CHECKLIST ITEMSn(fencing) | 4
44570 | 44565 | 03-2300 | CONCRETE POUR DBANK OG2 | 4
44570 | 44565 | 02-6130 | MOVE MATERIAL | 3
44570 | 44565 | 07-1100 | FINISH CHECKLIST FOR OFFICE ENGINEER (drainage) | 8
44570 | 44565 | 31-1700 | jump pumps | 4
44570 | 44566 | 03-6000 | SG4 PREP AND GRINDR SURFACE FOR FRP/CHOP CONCRETE DEMO CMU WALLS AND CLEAN | 17.5
44570 | 44566 | 03-1000 | SG4 CONTINUE EXCAVATE FOR MASONRY AND FOUNDATION/HAND EXC | 16
44570 | 44566 | 03-1000 | OG9 LOAD TRAILER WITH FORMS | 2
44570 | 44566 | 05-6020 | OG10 GROUT COLUMNS BASES | 15
44570 | 44566 | 32-6000 | SG6 CHOP PENTRATIONS FROM ROOF TO 2ND FLOOR | 3
44570 | 44566 | 31-1000 | SG5 EXC/CHOP CONCRETE WALL FOR MASNRY FOUDNATION | 12
44570 | 44566 | 33-6010 | OG5 FIX BROKE STORM PIPE | 7
44570 | 44566 | 33-3100 | OG10 LOADOUT 6 CONTAINERS | 20
44570 | 44566 | 31-2200 | BACKFILL OG2 | 15
44570 | 44566 | 33-3100 | SG7 EXC FOR STEAM | 17.5
44570 | 44566 | 31-1300 | SG7 PREP AREA FOR FOOTING EXC | 14
44570 | 44566 | 33-6010 | OG10 FILL ONE TON BAD FOR STEAM FILL FOR PIPE SUPPORT | 5
44570 | 44566 | 03-1900 | SG7 PATCH SHAFT TIE HOLES | 5
44570 | 44566 | 99-4560 | OG9 CLEANUP | 5.5
44570 | 44566 | 03-2300 | OG2 STRIP THRUST BLOCK | 13
44570 | 44566 | 03-1000 | OG9 LOAD TAG A LONG TO GO TO OG10 | 8
44570 | 44566 | 03-1000 | OG9 BAND FORMS FOR LOAD OUT | 18
44570 | 44566 | 05-6020 | OG10 FORM FOR GROUT | 11
44570 | 44566 | 99-4560 | SG7 HAND RAILS AS PER DOB | 35.5
44570 | 44566 | 31-1830 | sg7 lagging | 6
44570 | 44566 | 02-3000 | cover cored holes w/ plywood | 13
44570 | 44566 | 31-1700 | jump pumps | 9
44570 | 44567 | 03-6000 | SG4 PREP AND GRIND SURFACE FOR FRP | 17
44570 | 44567 | 31-1700 | SG6 CLEAN SHAFT FOR WATERPROOFING/PUMP WATER OUT | 5
44570 | 44567 | 31-2200 | SG4 EXC FOR MASONRY FOUNDATION/BACKFILL STEAM PIPE | 11.5
44570 | 44567 | 33-6010 | SG6 LULL NEEDED FOR WELKIN | 3
44570 | 44567 | 31-2200 | OG2 BACKFILL DUCTBANK | 5
44570 | 44567 | 03-1000 | OG9 TRAILER ON SITE FOR FORM LOADOUT | 2
44570 | 44567 | 03-1000 | SG5 HAND EXC/CHOP CONCRETE FOR MASONRY FOUDNATION | 18
44570 | 44567 | 99-4560 | PREP EXPECTED SNOW/MOVE MAFIA BLOCKS/SALT SITE WALKWAYS | 9
44570 | 44567 | 02-2300 | OG2 PUMP DOWN WATER BASEMENT | 7
44570 | 44567 | 33-2400 | SG3 INSTALL 2ND PUMP IN TRENCH | 3
44570 | 44567 | 31-1300 | SG7 EXC FOR FOOTINGS | 18
44570 | 44567 | 33-3100 | LOADOUT CARDELLA OG10 | 9
44570 | 44567 | 31-2200 | BACKFILL OG2 | 6.5
44570 | 44567 | 03-1000 | COLLECT ALL FORM WORK HARDWAR ROM SGN AND SG7 AND OG9 | 24
44570 | 44567 | 03-1900 | OG9 PATCH 2ND Q DECK | 13
44570 | 44567 | 03-1000 | OG9 FORM PENETRATIONS FIVE STAR 2ND FLOOR & ROOF | 13
44570 | 44567 | 03-1000 | OG10 INSTALL EXPANSION JOINT @ COLUMN BASES | 20
44570 | 44567 | 03-1000 | OG9 LOADOUT FORMS FOR ULMA | 2.5
44570 | 44567 | 31-1300 | SG7 EXC FOR FOOTING | 8
44570 | 44567 | 33-6010 | SG6 INSTALL CABLE RAILING | 8
44570 | 44567 | 31-1700 | jump pumps | 8
44570 | 44568 | 99-4560 | SNOW REMOVAL ALL SITES | 57
44570 | 44568 | 32-6510 | MOVE MESH TO OG9 1ST AND 2ND FLOOR | 16.5
44570 | 44568 | 31-2200 | BACKFILL SGN PLUMBING | 8.5
44570 | 44568 | 31-1700 | HEATERS | 4
44570 | 44568 | 03-1100 | OG3 FORM INSIDE OF WINDOWS | 20
44570 | 44568 | 03-1100 | OG4 FORM INSIDE OF WINDOWS | 20
44570 | 44568 | 03-1400 | OG3,4,5 DRILL AND PUT IN REBAR IN WINDOWS | 8
44570 | 44568 | 99-7200 | VACATION DAY | 8
44570 | 44568 | 31-2200 | SGN BACKFILL STEAM PIPE/LOAD OUT | 2.5
44570 | 44568 | 03-1400 | OG4/5/3 DRILL AND DOWEL WINDOWS | 18
44570 | 44568 | 03-2100 | OG1/2/3 DRILL AND BUSH HAMMER FOR CURB WALL | 17
44570 | 44568 | 02-6060 | OG5 GRIND FLOOR 2ND FLOOR APT | 17
44570 | 44568 | 99-4560 | SNOW REMOVAL | 10
44570 | 44568 | 31-1700 | jump pumps | 2
44570 | 44568 | 99-4560 | clean for carpenters | 8
44563 | 44557 | 02-1900 | SG7 REMOVE BLACK TOP & LOADOUT | 19
44563 | 44557 | 03-2300 | OG5 BACKFILL FOR ELECTRICAL DB POUR | 19
44563 | 44557 | 32-6520 | OG2/3 MOVE FENCE | 18
44563 | 44557 | 33-6010 | SGN MOVE MATERIAL WITH LULL FOR WELKIN | 17
44563 | 44557 | 31-1700 | HEATER/PUMPS | 2
44563 | 44557 | 33-3100 | OG2 EXC FOR POE | 35
44563 | 44557 | 02-6130 | SG4 REMOVE STAIR TOWER | 4
44563 | 44557 | 33-6010 | SG6 REMOVE CABLE FOR WELKIN | 3
44563 | 44557 | 33-6010 | SG6 REINSTALL SAFETY CABLE | 2.5
44563 | 44557 | 02-6130 | OG4 INSTALL STAIR TOWER | 10
44563 | 44557 | 99-4000 | OG2 INSTALL TEMP PLATFORM AND RAMP | 4
44563 | 44557 | 03-1000 | OG9 BRACE AND BAND COLUMNS | 13
44563 | 44557 | 03-1000 | OG9 CLOSE UP PLUMBING SHAFT | 32
44563 | 44557 | 03-1000 | OG9 SITE MAINTENANCE | 8
44563 | 44557 | 03-2300 | OG5 FORM DUCT BANK | 8
44563 | 44557 | 02-6130 | MOVE SCAFFOLDING & GATHER MATERIAL | 4
44563 | 44557 | 99-7300 | out for covid | 8
44563 | 44558 | 02-3000 | SG4 CUT/CHOP FLOOR OPENINGS | 29
44563 | 44558 | 07-6330 | SG6 CLEANUP BUILDING/LOT | 25
44563 | 44558 | 31-1400 | OG8 BACKFILL | 13
44563 | 44558 | 33-3100 | OG5 PREP AREA FOR POE EXC | 14
44563 | 44558 | 33-3100 | SG7 EXC & LOADOUT STEAM/HW TRENCHES | 17
44563 | 44558 | 32-6520 | INSTALL WALK WAY @ OG2 | 11
44563 | 44558 | 32-6520 | LAG @ SG6 UNDER WIDE WALK & BACKFILL | 4
44563 | 44558 | 03-1100 | SG4 PLYWOOD UP WINDOWS | 4
44563 | 44558 | 03-1100 | SG5 FORM WINDOWS | 22
44563 | 44558 | 03-1900 | SG6 PATCH HOLES IN DECK | 1
44563 | 44558 | 33-3100 | SG7 SUPPORT UTLITIES DuRING EXC | 2
44563 | 44558 | 03-1000 | OG9 CLOSE UP COLUMNS | 11
44563 | 44558 | 03-1000 | OG9 CLOSE UP PLUMBING SHAFT | 32
44563 | 44558 | 03-1900 | OG9 SET SCAFFOLDING FOR CONCRETE | 8
44563 | 44558 | 31-1820 | OG9 BURN HOLES TO POUR CONCRETE | 10.5
44563 | 44558 | 33-3100 | LAG PIT FOR SIDEWALK UNDERMINING SG6 | 4
44563 | 44558 | 99-4560 | OG9 SITE MAINTENANCE | 8
44563 | 44558 | 31-1700 | jump pumps | 3
44563 | 44558 | 99-7300 | out for covid | 8
44563 | 44559 | 03-1900 | OG9 SETUP AND POUT SHAFT WALLS/COLUMNS | 20
44563 | 44559 | 02-6065 | OG6 DEMO ABANDONED GAS LINE | 18
44563 | 44559 | 99-4560 | JOB SITE MAINTENANCE | 20
44563 | 44559 | 32-6000 | SG6 PENETRATIONS SAWCUT / BREAK | 27
44563 | 44559 | 03-1900 | SG6 POUR WINDOWS | 21
44563 | 44559 | 32-6520 | SG6 MOVE FENCE FOR BRICK SHELF | 11
44563 | 44559 | 33-3100 | OG5 EXC FOR STEAM POE | 9
44563 | 44559 | 33-3100 | SG7 EXC FOR STEAM | 6
44563 | 44559 | 33-3100 | SG7 EC FOR PLUMBING | 7
44563 | 44559 | 31-1400 | SG7 LOADOUT FOR BACKFILL FROM STOCKPILE | 6
44563 | 44559 | 02-1900 | SG7 REMOVE BLACKTOP AND CONCRETE FOR TRECNHES | 3
44563 | 44559 | 99-4560 | EXC MACHINE MAINTENANCE | 3
44563 | 44559 | 03-1100 | SG5 FINISH FORMING WINDOWS | 4
44563 | 44559 | 03-1100 | SG5 POUR WINDOWS | 14
44563 | 44559 | 03-1700 | SG7 BUILD TEMP PLATFORM FOR LATHERS | 25.5
44563 | 44559 | 03-1100 | OG4 STRIP CURB WALL IN BASEMENT | 3
44563 | 44559 | 03-1100 | OG5 STRIP CURB WALL IN BASEMENT | 3
44563 | 44559 | 99-4560 | OG4 SITE MAINTENANCE | 8
44563 | 44559 | 99-4560 | OG5 SITE MAINTENANCE | 8
44563 | 44559 | 03-1900 | OG9 PUT UP SAFETY NETTING | 7
44563 | 44559 | 03-1900 | OG9 POUR PLUMBING SHAFT AND COLUMNS | 15
44563 | 44559 | 32-6520 | FIX FENCING | 4
44563 | 44559 | 99-4560 | OG9 SITE MAINTENANCE | 8
44563 | 44559 | 03-1000 | STACK FORMS OG9 | 5
44563 | 44559 | 31-1700 | jump pumps | 3
44563 | 44559 | 99-7300 | out for covid | 8
44563 | 44560 | 33-3100 | OG2 VACTRUCK POE | 24
44563 | 44560 | 32-6520 | INSTALL FENCE SG3 BASEKETBALL COURT | 10
44563 | 44560 | 32-6000 | SG6 DEMO FLOOR OPENINGS & CLEANUP | 25
44563 | 44560 | 03-2300 | OG5 POUR DB ELECTRICAL | 12
44563 | 44560 | 33-3100 | SG7 EXC FOR PLUMBING S (3)/STEAM (3)/ LOADOUT (2) | 26
44563 | 44560 | 33-3100 | EXC POE OG5/ CLEANUP TRENCH | 21
44563 | 44560 | 31-1400 | BACKFILL OG8 | 7
44563 | 44560 | 31-1700 | JUMP PUMPS | 3
44563 | 44560 | 99-7300 | out for covid | 8
44563 | 44560 | 07-1100 | INSTALL DRAINAGE MEMBRANE AS PER OFICE ENGINEER | 9
44563 | 44560 | 31-1820 | SG7 BURN SHEETS & WHALERS | 5
44563 | 44560 | 99-4000 | FIX PARKING LOT WITH STONE | 5
44563 | 44560 | 03-1100 | SG5 STRIP WINDOWS THAT WERE POURED | 16
44563 | 44560 | 99-4560 | SG5 SITE MAINTENANCE | 8
44563 | 44560 | 03-1000 | OG9 STRIP COLUMNS AND PLUMBING SHAFT | 42
44563 | 44560 | 99-4560 | OG9 SITE MAINTENANCE | 8
44563 | 44560 | 05-6030 | OG10 FORM FOR GROUT @ COLUMN BASES | 9.5
44563 | 44560 | 03-1000 | OG9 START BANDING FORMS FOR PICKUP | 10
44563 | 44561 | 99-7200 | Holiday | 64
44556 | 44550 | 03-2300 | SG1 CHOP 9 EA POCKETS FOR DUCTBANK | 17.5
44556 | 44550 | 02-6130 | SG4 LEVEL AREA FOR SCAFFOLD | 4
44556 | 44550 | 02-6005 | OG1 PAINT REMOVAL | 17
44556 | 44550 | 02-2300 | OG3/OG5 CLEAN BASEMENT | 26
44556 | 44550 | 33-3100 | OG5 EXCAVATE STEAM TO SG3 LOADOUT | 18
44556 | 44550 | 03-1000 | OG8/OG10 MOVE FORMS TO OG9 | 4
44556 | 44550 | 99-4560 | SG7 CLEAN SITE | 4
44556 | 44550 | 33-3100 | SG7 LOAD OUT 4 TRUCKS | 18
44556 | 44550 | 33-3100 | SG7 MOVE ALL MATERIAL FOR STEAM TRENCH (WELKIN, PLAYGROUND, FORMS) | 20
44556 | 44550 | 02-2300 | og10 clean site during possible shooting scenario | 12
44556 | 44550 | 03-1100 | OG4 FORM CURB WALL | 14.5
44556 | 44550 | 03-1100 | OG5 FORM CURB WALL | 14.5
44556 | 44550 | 02-6130 | SG4 PUT UP STAIR TOWER | 7
44556 | 44550 | 03-1000 | OG8 MOVE FORMS TO OG9 | 10
44556 | 44550 | 03-1000 | OG8 ADJUST ONE KEYWAY FOR IRONWORKERS | 4.5
44556 | 44550 | 03-1100 | OG3 FORM 2 EQUIPMENT PADS | 7
44556 | 44550 | 03-1000 | OG9 FINISH FORMING INSIDE PLUMBING SHAFT | 13
44556 | 44550 | 02-6060 | SG5 INSTALL LOCK HASPS ON APT DOOR, PRUCHASE IT FROM HOME DEPOT | 5
44556 | 44550 | 32-6520 | OG8 FIX GATE | 2
44556 | 44550 | 33-3100 | OG8 HANDRAIL ON FOOTING | 9
44556 | 44550 | 03-1000 | OG9 START FORMING COLUMNS | 10
44556 | 44550 | 99-4560 | OG8 SITE MAINTENANCE | 8
44556 | 44550 | 33-3100 | PREP AREA TO SET TRENCH BOX, PUT HANDRAIL AND OTHER SAFETY ITEMS | 8
44556 | 44550 | 31-1700 | JUMP PUMPS | 1
44556 | 44551 | 02-6005 | OG1 PAINT REMOVAL | 17
44556 | 44551 | 02-3000 | OG2 PULL OUT CONCRETE BLOCKS FOR POE | 3
44556 | 44551 | 03-2100 | OG3 BUSHHAMMER/INSTALL ANCHOR BOLTS - EQUIPMENT PADS | 4
44556 | 44551 | 03-2100 | OG4/OG5 PREP FOR POUR/DEMO WINDOWS FOR CURB WALL IN BASEMENT | 4
44556 | 44551 | 33-3100 | OG5 EXPOSE STEAM/PLUMBING PIPES | 9.5
44556 | 44551 | 99-4560 | OG9/OG10 SITE CLEAN | 32
44556 | 44551 | 07-6230 | SG6 INSTALL DIESEL HEATER | 5
44556 | 44551 | 03-1400 | OG4 DRILL/EPOXY DOWELS IN WINDOW | 5
44556 | 44551 | 99-7300 | COVID TESTS | 9
44556 | 44551 | 07-6230 | SG6 SECURE WHITE MESH - SECURE TARPS FOR FIREPROOFING | 8
44556 | 44551 | 02-1900 | REMOVE BLACKTOP @ SG7 & LOADOUT (2) | 10.5
44556 | 44551 | 33-3100 | EXC STEAM TRENCH SG1 TO SG3 | 11
44556 | 44551 | 99-7300 | COVID TESTING | 4
44556 | 44551 | 03-1100 | SG4 FORM WINDOWS IN & OUT | 26.5
44556 | 44551 | 07-1100 | FIX INSULATION & DRAIN BOARDS AS PER ENGINEER | 10
44556 | 44551 | 03-1000 | OG9 FORM COLUMNS | 50
44556 | 44551 | 03-1000 | OG9 FORM PLUMBING SHAFT | 10
44556 | 44551 | 03-2300 | FORM DUCTBANK, BRACE PIPES, START TRENCH | 8
44556 | 44551 | 31-1700 | jump pumps | 2
44556 | 44552 | 02-6005 | OG1 PAINT REMOVAL | 17
44556 | 44552 | 33-3100 | OG2 EXPOSE MH FOR FS - LOAD OUT CONCRETE AND DIRT TO OG10 HNS TRUCK | 21
44556 | 44552 | 03-2100 | OG4/OG5 POUR CURB WALL IN BASEMENT | 12
44556 | 44552 | 03-2300 | OG3 POUR DUCTBANK AND 2 EQUIPMENT PADS | 5
44556 | 44552 | 32-6520 | OG3 INSTALL FENCE ON TEMP WALKWAY | 7
44556 | 44552 | 32-6510 | OG8/SG7 INSTALL WHITE MESH | 17
44556 | 44552 | 02-1900 | OG10 LIVE LOAD CARDELA - CLEAN SITE | 11
44556 | 44552 | 99-4560 | SG6 CLEAN SITE | 9
44556 | 44552 | 03-2300 | POUR OG3 DB | 9
44556 | 44552 | 33-3100 | EXC SEAM SG1 TO SG3 | 9
44556 | 44552 | 99-7300 | COIVD TESTING | 7
44556 | 44552 | 33-3100 | og8 handral as per dob | 15
44556 | 44552 | 03-1000 | OG9 FORM COLUMNS | 23.5
44556 | 44552 | 03-1000 | OG9 FORM OUTSIDE OF PLUMBING SHAFT | 29
44556 | 44552 | 33-3100 | LAGGING, DIGGING FOR TRENCH BOX | 14.5
44556 | 44552 | 99-4560 | OG9 SITE MAINTENANCE | 6.5
44556 | 44552 | 99-7300 | LOST TIME | 16
44556 | 44553 | 02-2300 | SG4 CHOP/SETUP SUMP IN BASEMENT | 7
44556 | 44553 | 99-4560 | SG6 CLEAN FIRE PROOFING | 11
44556 | 44553 | 32-6510 | SG7 INSTALL WHITE MESH | 7
44556 | 44553 | 33-3100 | OG2 EXPOSE MH FOR FSE TO CORE | 3
44556 | 44553 | 33-6620 | OG2 CLEAN SITE - TREE BRANCHES TO SG4 CONTAINER | 7
44556 | 44553 | 99-4560 | S8/OG8 CLEAN SITE -OG8 INSTALL REBAR CAPS | 17
44556 | 44553 | 32-6520 | OG8 MOVE GATE - FIXE FENCE - INSTALL WHITE MESH | 16
44556 | 44553 | 32-6520 | OG2 MOVE GATE - FIX FENCE | 7.5
44556 | 44553 | 33-2400 | DEWATER & STONE TRENCH @ OG5 TO SG3 | 18
44556 | 44553 | 33-3100 | TRENCH SG1 TO SG3 | 16
44556 | 44553 | 02-6130 | OG5 PUT UP STAIR TOWER | 9
44556 | 44553 | 03-1000 | OG9 FORM COLUMNS | 24
44556 | 44553 | 03-1000 | OG9 FORM PLUMBING SHAFT | 34
44556 | 44553 | 03-1000 | OG9 FIX CABLE HANDRAIL | 3
44556 | 44553 | 03-1000 | OG9 INSTALL HANDRAIL AROUND STAIR LANDINGS | 4
44556 | 44553 | 99-7300 | LOST TIME | 8
44556 | 44553 | 99-4560 | OG9 SITE MAINTENANCE | 8
44556 | 44553 | 03-1000 | GETTING MATERIAL FOR OG9 | 6.5
44556 | 44553 | 33-3100 | TRENCH BOX/LAGGING | 8
44556 | 44554 | 99-7200 | Holiday Pay | 56
44549 | 44543 | 33-3100 | SG3 EXCAVATE FOR STEAM TO OG5, LOAD OUT | 10
44549 | 44543 | 33-3100 | OG4 EXC FOR POE , TRANSPORT AND SET TRENCH BOX AND STEEL PLATE | 17.5
44549 | 44543 | 03-1400 | OG4 DRILL DOWELS in basement curb wall | 7
44549 | 44543 | 02-2300 | og4 chop concrete floor - set up pump - PUMP OUT BASEMENT CLEA DEBRIS | 7
44549 | 44543 | 99-4560 | SG6 CLEAN UP - TARPS - GARBAGE TO CONTAINER | 18
44549 | 44543 | 32-6510 | SG7 INSTALL WHITE MESH | 13
44549 | 44543 | 31-1700 | JUMP PUMPS | 1
44549 | 44543 | 31-1400 | OG8 BACKFILL | 27
44549 | 44543 | 31-2200 | OG5 BACKFILL DB & LOADOUT 12 LOADS | 14
44549 | 44543 | 31-2200 | OG10 BACKFILL DUCTBANK | 8.5
44549 | 44543 | 33-3100 | SG4 LOADOUT | 8
44549 | 44543 | 00-0019 | CHECK LIST ITEMS | 8
44549 | 44543 | 03-1000 | OG8 STRIP FORMS FOR ELECTRICAL POE | 5
44549 | 44543 | 03-1000 | OG8 STRAGHTEN OUT FORMS FOR PICKUP | 5
44549 | 44543 | 03-1300 | OG8 CLEAN BOLT PATTERNS FOR SURVEY | 9.5
44549 | 44543 | 03-1900 | OG9 WATER STOP | 5
44549 | 44543 | 03-1000 | OG9 FORM INSIDE SHAFT FOR DECK POUR | 10
44549 | 44543 | 03-1000 | OG9 EXPANSION JOINT AROUND COLUMN | 14
44549 | 44543 | 03-1000 | OG9 SITE MAINTENANCE | 8
44549 | 44544 | 33-3100 | sg3 exc for steam to og5, use HNS truck to load out, install stone on trench - install sump | 17.5
44549 | 44544 | 00-0011 | sg4 demo 2ND FLOOR WALL FOR PLUMBING PENETRATIONS | 7
44549 | 44544 | 02-3000 | OG1 CHOP TEA HOLES FOR THEMIS & CLEAN DEBRIS | 10
44549 | 44544 | 00-0019 | OG3 SETUP FENCE FOR POE EXC - CHANGE ORDER | 18
44549 | 44544 | 32-6510 | S8/OG9/OG2/OG10/SG3 - FIX AND INSTALL WHITE MESH | 20
44549 | 44544 | 33-3100 | SG5 EXC FOR ELECTRICAL DBANK | 37.5
44549 | 44544 | 99-4560 | OG8 SITE MAINTENANCE | 8
44549 | 44544 | 03-1300 | OG8 STRIP BOLT PATTERNS & KEY WALLS | 4
44549 | 44544 | 31-1400 | OG9 SET GRADE FOR DECK POUR & FLOW FILL FORMWORK | 10
44549 | 44544 | 03-1000 | OG9 PUT IN 8X8 SHELF AROUND BORDER | 10
44549 | 44544 | 33-3100 | BUILT TRENCH BOX | 4
44549 | 44544 | 33-3100 | LAGGED AROUND PLUMBING PIPES | 2
44549 | 44544 | 03-1000 | BRACED FOOTING | 2
44549 | 44544 | 03-1000 | OG9 BOX AROUND COLUMN BASES W /EXPANSION JOITN MATERIAL | 8.5
44549 | 44544 | 03-1400 | OG9 DRILL FOR LATHER | 3
44549 | 44544 | 03-1000 | OG9 SITE MAINTENANCE | 8
44549 | 44544 | 03-1900 | CHIP FOR IRONWORKERS | 6
44549 | 44544 | 31-1700 | JUMP PMPS | 1
44549 | 44545 | 02-2300 | SG1 PUMP OUT BASEMENT | 9
44549 | 44545 | 33-3100 | SG3 OADOUT - 4 EA TRI AX | 10
44549 | 44545 | 02-2300 | OG1 CLEAN BASEMENT - PREP FOR PAINT REMOVAL | 23
44549 | 44545 | 02-2300 | OG2 PUMP OUT BASEMENT | 9
44549 | 44545 | 00-0019 | OG3 POE EXC - SET BOX AND STEEL PLATE - CHANGE ORDR | 18.5
44549 | 44545 | 31-1700 | JUMP PUMPS | 1
44549 | 44545 | 03-1900 | SETUP AND POUT 55 CY OG9 SLAB | 33
44549 | 44545 | 31-1400 | BACKFILL OG8 | 18
44549 | 44545 | 99-4560 | PREP AREA FOR CRANE OG8 | 11
44549 | 44545 | 33-3100 | OG5 HANDDIG UNDER DB FOR 5 STAR POE ON CON ED MANHOLE | 8
44549 | 44545 | 99-4560 | MOVE MAFIA BLOCKS FOR IW @ OG10 | 4
44549 | 44545 | 99-4560 | OWED FRFOM LAST WEEK | 2
44549 | 44545 | 03-1000 | OG8 CUT KEYWAY | 16
44549 | 44545 | 03-1000 | OG8 BAND FORMS | 9
44549 | 44545 | 03-1000 | OG9 FINISH 8X8 SHELF | 16
44549 | 44545 | 03-1000 | OG9 TIGHTEN UP REBAR | 7.5
44549 | 44545 | 03-1900 | OG9 CONCRTE POUR | 7
44549 | 44545 | 03-1400 | OG9 DRILL FOR LATHER | 4
44549 | 44545 | 03-1400 | OG9 INSTALL DOWELS | 5
44549 | 44546 | 05-6040 | OG8 SETUP CRANE | 47
44549 | 44546 | 02-3000 | OG2 PUMP & CUT PENETRATIONS POES | 24
44549 | 44546 | 33-2400 | OG1 DEWATERING | 12
44549 | 44546 | 02-6005 | PAINT REMOVAL | 16
44549 | 44546 | 33-3100 | EXC FOR STEAM OG5 | 21
44549 | 44546 | 33-3100 | OG3 XC FOR ELECTRICAL | 17
44549 | 44546 | 31-1300 | OG8 HAND DIG FOR CON ED MANHOLE | 10
44549 | 44546 | 31-1700 | JUMP PUMPS | 2
44549 | 44546 | 99-4560 | OG8 SITE MAINTENANCE | 8
44549 | 44546 | 03-1000 | OG8 LOAD OUT FORMS | 1
44549 | 44546 | 03-1000 | OG8 CUT AND ADJUST KEYWAYS FOR IWS | 2
44549 | 44546 | 03-1400 | OG4&5 DRILL HOLES AND BUSHHAMMER FOR DOWELS | 8
44549 | 44546 | 33-3100 | LAGGING | 8
44549 | 44546 | 03-1000 | OG9 STRIP COLUMN BASE & FORMS | 15
44549 | 44546 | 03-1900 | OG9 SAFETY ITEMS | 8.5
44549 | 44546 | 03-1000 | OG9 FORM INSIDE PLUMBING SHAFT | 12
44549 | 44546 | 02-3000 | UNLOAD SCAFFOLDING SG4 | 2
44549 | 44547 | 00-0011 | SG5 CLEAN 1ST FLOOR | 11
44549 | 44547 | 02-6005 | OG1 PAINT REMOVAL | 7
44549 | 44547 | 33-3100 | OG2 CUT PULL OUT CONCRETE BLOCK | 17
44549 | 44547 | 03-1400 | OG4 DRILL EPOXY DOWELS IN WINDOWS | 9
44549 | 44547 | 03-1400 | OG5 DRILL EPOXY DOWELS IN WINDOWS | 9
44549 | 44547 | 99-4560 | SG3/SG7 CLEAN SITE | 9
44549 | 44547 | 33-3100 | OG5 EXC STEAM RUN TO SG3 LOAD OUT | 18.5
44549 | 44547 | 03-1900 | POUR COLUMN BASES @ OG9 | 8
44549 | 44547 | 32-6520 | POUR TEMP WALKWAYS @ OG3/OG6 | 18
44549 | 44547 | 05-6040 | ASSIST MOVINB CRANE/TRAILERS TO OG8 FROM OG10 | 16
44549 | 44547 | 03-1700 | MOVE REBAR FROM OG TO OG9 | 6
44549 | 44547 | 33-6010 | ASSIST WELKIN CALLAHANOG10 | 2
44549 | 44547 | 03-2300 | OG8 PUT HANDRAIL ON DUCTBANK AND FOOTINGS | 20
44549 | 44547 | 03-1900 | OG9 BUILD PLATFORM FOR LATHERS | 20.5
44549 | 44547 | 99-4560 | OG8 SITE MAINTENANCE | 7
44549 | 44547 | 99-4560 | OG9 SITE MAINTENANCE | 8
44549 | 44547 | 33-3100 | LAGGING | 8
44549 | 44547 | 31-1700 | jump pumps | 2
44542 | 44536 | 33-3100 | SG3 LOADOUT EXCAVATE MATERIAL | 7.5
44542 | 44536 | 33-3100 | SG3 CONTINUE EXCAVATION STEAM TRENCH - SET2 TRENCH BOES SHORING IN BETWEEN BOXES - MOVE stone from og8 | 14
44542 | 44536 | 00-0011 | sg5 chop openings for fse - demo 1st floor walls | 13
44542 | 44536 | 99-4560 | SG6 - CLEAN 1ST FLOOR AND 2ND FLOOR - MOVE DEBRIS to CONTAINER SG4 | 24
44542 | 44536 | 32-6510 | S8/OG5 COVER PILES ADJUST white MESH ON FENCE | 9
44542 | 44536 | 05-6020 | OG9 GROUT COLUMN BASES | 5
44542 | 44536 | 33-3100 | MOVE TRENCH BOX FROM WELKINS YARD AND INSTALL SG3 | 12
44542 | 44536 | 33-3100 | EXC AROUND UTILITIES FROM SG7 TO SG3 | 11
44542 | 44536 | 03-1900 | PREP FOR CONCRETE @OG8 | 8
44542 | 44536 | 03-1900 | OG10 CHOP OUT FOR BEAM INSTALL INSIDE SHAFT | 10.5
44542 | 44536 | 33-3100 | INSTALL 2 TRENCH BOXES | 4
44542 | 44536 | 33-3100 | INSTALL LAGGING BETWEEN TRENCH BOXES | 4
44542 | 44536 | 32-6510 | SG6 INSTALL SAFETY NETTING (ROOF & PENTHOUSE) | 7
44542 | 44536 | 32-6510 | SG6 INSTALL TOE BOARDS (ROOF & PENTHOUSE) | 6
44542 | 44536 | 03-2300 | OG8 FIX DUCT BANK TO BE POURED | 10
44542 | 44536 | 03-1900 | OG8 PUT UP SCAFOLDING FOR CONCRETE POUR | 18
44542 | 44536 | 05-6020 | OG9 FORM ALL COLUMN BASES FOR GROUT | 19
44542 | 44536 | 03-1300 | OG10 STRIP ANCHOR BOLTS PATTERNS | 10
44542 | 44536 | 03-1900 | OG10 BUILD SCAFFOLD FOR CHOPPING FOR IRONWORKERS | 11
44542 | 44536 | 03-1000 | SG6/OG8/OG9/OG10 SITE MAINTENANCE | 16.5
44542 | 44536 | 99-4560 | Site maintenance all sites | 16.5
44542 | 44537 | 33-3100 | SG3 MOVEOUT EXCAVATE MATERIAL | 3
44542 | 44537 | 32-6520 | SG3 SET STEEL PLATE OVER TRENCH BOX PREP AND POUR TEMP WALKWAY | 10
44542 | 44537 | 07-6320 | SG6 INSTALL TARPS | 40.5
44542 | 44537 | 33-3100 | OG5 LOADOUT EXC MATERIAL | 3
44542 | 44537 | 33-3100 | OG5 CONTINUE STEAM TRENCH - SET TENCH BOX | 7
44542 | 44537 | 02-6000 | OG10 GARAGE DEMO LOADOUT - PREP FOR CRANE | 17
44542 | 44537 | 03-1900 | OG9 SETUP AND POUR DRAINAGE BOXES | 6
44542 | 44537 | 07-6320 | SG6 ASSIST WITH TARPS | 7
44542 | 44537 | 99-4560 | SG6 BRING MAFIA BLOCKS FROM S8 | 5
44542 | 44537 | 03-1000 | SG6 STRIP ALL MISCELLANEOUS STUFF FOR FIREPROOFERS | 12.5
44542 | 44537 | 99-4560 | SG6 SITE MAINTENANCE | 8
44542 | 44537 | 03-1000 | SG7 FORM INSDE PLUMBING SHAFT | 48.5
44542 | 44537 | 03-2300 | OG5 DUCT BANK | 43
44542 | 44537 | 03-1900 | OG8 POUR FOOTINGS/GBS | 7
44542 | 44537 | 99-4560 | SG5 ADDRESS APT DOOR TO BE LOCKED | 2
44542 | 44537 | 03-1900 | SG7 CONCRETE POUR | 4
44542 | 44537 | 33-3100 | TRENCH BOXES | 4
44542 | 44537 | 03-1700 | Jump pumps | 1
44542 | 44538 | 32-6520 | SG3 MOVE FENCE FOR NEW TEMP WALKWAY | 11
44542 | 44538 | 00-0011 | SG5 DEMO 1ST FLOOR WALLS, CHOP FOR FSE, CLEAN AND CLEAR DEBRIS FROM BASEMENT | 31
44542 | 44538 | 02-2300 | SG3 INSTALL PUMP - PUMP DOWN BASEMENT | 5
44542 | 44538 | 02-2300 | OG4 PUMP OUT BASEMENT | 12
44542 | 44538 | 31-1400 | OG9 BACKFILL AND COMPACT INSIDE BUILDING | 14.5
44542 | 44538 | 02-6000 | OG10 GARBAGE DEMO LOADOUT - PREP FOR CRANE | 8
44542 | 44538 | 33-3100 | SG7 EXC/LAG FOR HW TRENCH | 15
44542 | 44538 | 33-6010 | SG7 UNLIOAD SAND BAGS FOR WELKIN | 10.5
44542 | 44538 | 33-3100 | LOAD OUT 5 TRUCKS FROM SG7 TO OG9 | 6
44542 | 44538 | 32-6520 | RELOCATE FENCE @ SG7 SITE | 10
44542 | 44538 | 31-1700 | JUMP PUMPS | 1
44542 | 44538 | 03-2300 | OG5 FINISH DBANK | 16
44542 | 44538 | 03-2300 | OG1 FINISH DBANK | 17
44542 | 44538 | 03-1000 | OG8 START STRIPPING FOOTINGS AND GBS | 24
44542 | 44538 | 03-1000 | OG9 STRIP CLEANOUT SLABS & START TO FORM CLEANOUT SHAFT | 11
44542 | 44538 | 03-1900 | OG10 CHOP POCKETS FOR IRONWORKERS | 23
44542 | 44538 | 33-3100 | TRENCH BOXES AND LAGGING | 8
44542 | 44538 | 03-1000 | OG8 SITE MAINTENANCE | 8
44542 | 44538 | 99-7200 | VACATION DAY | 8
44542 | 44538 | 99-4560 | Site maintenance | 8.5
44542 | 44539 | 33-3100 | SG3 EXCAVATE FOR STEAM TO OG5 FIX DRAIN PIPE MOVE STONE FROM OG8 FOR STEAM TRENCH | 7
44542 | 44539 | 07-6320 | SG6 SECURE TARPS - CLESAN STAND 2ND FLOOR | 21
44542 | 44539 | 02-2300 | SG3 REPLACE PUMP - REMOVE WATER BASEMENT | 4
44542 | 44539 | 05-6020 | OG9 GROUT COLUMN BASES | 5
44542 | 44539 | 31-1400 | OG9 BACKFILL AND COMPACT INSIDE BUILDING/ BEGIN TO PLACE AND COMPACT STONE - MOVE STONE FROM OG8 TO OG9 | 19.5
44542 | 44539 | 00-0019 | OG4 START OF INSTALLATION OF FENCE CHANGE ORDER | 9
44542 | 44539 | 33-3100 | OG5 BACKFILL SIDES DUCTBANK FOR CONCRETE POUR RECEIVE AND PILE HNS TRUCK - EXCAVATOION FROM SG7 PLUMBING TRENCH | 15
44542 | 44539 | 33-3100 | SG7 EXC AND LOADOUT FOR PLUMBING TRENCH TO SG3 | 23
44542 | 44539 | 33-3100 | SG3 TO SG5 PUMP OUT & REPAIR SANITARY | 7
44542 | 44539 | 03-1900 | OG8 PREP FOR CONCRETE/BACKFILL | 11.5
44542 | 44539 | 33-3100 | LAGGING & SUPPORTING PIPE FOR EXCAVATION | 8
44542 | 44539 | 03-1000 | OG8 STRIP AND STACK FORMS | 41
44542 | 44539 | 03-1000 | OG9 FORM WALLS FOR PLUMBING CLEANOUT | 15.5
44542 | 44539 | 03-1900 | OG10 CHOP FOR IRONWORKERS | 26
44542 | 44539 | 99-4560 | SG5 INSTALL PLYWOOD BACKBOARDS FOR VERIZON | 4
44542 | 44539 | 03-1000 | OG9 START ON BEAM BOTTOMS | 8
44542 | 44539 | 03-1000 | OG8 FORM ELECTRICAL RISERS | 10
44542 | 44539 | 31-1700 | jump pumps | 2
44542 | 44540 | 33-3100 | SG3 EXC TRENCH FOR STEAM TO OG5 - LOAD OUT | 18
44542 | 44540 | 02-3000 | OG3 COMPLETE CHOP ELECTRICAL POE. CHOP FOR THEMIS, EXC MH FOR FSE BY HAND | 13
44542 | 44540 | 00-0019 | OG4 FINISH FENCE INSTALL FOR POE, CHANGE ORDER | 7.5
44542 | 44540 | 02-2300 | OG4 PUMP OUT BASEMENT, SET UP SUMP | 4
44542 | 44540 | 07-6320 | SG6 SECURE TARPS | 4
44542 | 44540 | 03-1000 | OG8 CLEANUP, MOVE FORMS - PREP FOR BACKFIL | 17
44542 | 44540 | 07-1100 | OG9 PLACE FOAM AND VAPOR BARRER | 17
44542 | 44540 | 03-2300 | OG10/OG1 POUR 14 CY DUCT BANK | 10
44542 | 44540 | 03-1900 | OG8 POUR 4 CY RISER AND TRUSSBLOCK | 11
44542 | 44540 | 03-2300 | OG5 POUR 37 CY DUCT BANK | 10
44542 | 44540 | 31-2200 | BACKFILL OG5 | 4
44542 | 44540 | 99-4560 | COVER STOCK PILE @ SG6/SG7 | 12
44542 | 44540 | 03-1900 | POUR 2 CY @ OG9 DRAINS | 4
44542 | 44540 | 31-1700 | JUMP PUMPS | 2
44542 | 44540 | 00-0011 | CHANGE ORDER ITEMS | 8
44542 | 44540 | 03-1000 | SG7 FORM PLUMBING SHAFT | 27
44542 | 44540 | 03-1000 | OG8 FORM ELECTRICAL RISERS | 15
44542 | 44540 | 03-2300 | OG8 FORM THRUST BLOCK | 8
44542 | 44540 | 03-1000 | OG9 FORM DOWN TURN BEAMS & DECK | 22.5
44542 | 44540 | 03-1900 | OG10 FINISH CHIPPING FOR IRONWORKERS | 16
44542 | 44540 | 03-1000 | OG10 SITE MAINTENANCE | 8
44542 | 44540 | 99-7200 | VACATION DAY | 8
44535 | 44529 | 33-3100 | SG3 EXC. FOR POS | 21.5
44535 | 44529 | 02-6005 | OG2 PAINT REMOVAL | 17
44535 | 44529 | 03-2300 | OG3 CHOP BLOCK OF CONCRETE TO ALLOW DBANK CLEARANCE, EXC. DBANK UNDER GAS PIPE | 17
44535 | 44529 | 33-3100 | OG5 RECEIVE TRENCH BOXEA | 4
44535 | 44529 | 33-3100 | SG3 RECEIVE TRENCH BOXES | 4
44535 | 44529 | 99-4560 | OG5/SG6/OG8 CLEAN SITE | 25
44535 | 44529 | 03-1000 | OG10 STRIP PLUMBING SHAFT INSIDE AND OUT | 121
44535 | 44529 | 03-1000 | OG10 SITE MAINTNENACE | 8
44535 | 44529 | 33-3100 | EXC. POES SG2 | 10
44535 | 44529 | 33-6010 | ASSIST WELKIN @ OG10 | 6.5
44535 | 44529 | 02-6000 | MOVE MATERIALS NEAR GARAGE FOR DEMO | 4
44535 | 44529 | 31-1400 | OG8 BACKFILL FOR FOOTINGS/COMPACT | 8
44535 | 44529 | 31-1400 | OG8 PREP FOR FLOW FILL | 7
44535 | 44529 | 99-4560 | SG6 ASSIST VITAL | 1
44535 | 44529 | 02-6015 | DEMO WINDOW VENTS SG2 (4) | 8
44535 | 44529 | 31-1700 | JUMP PUMPS | 1
44535 | 44530 | 02-6005 | OG2 PAINT REMOVAL | 17
44535 | 44530 | 32-6520 | OG2 ADJUST FENCE | 21.5
44535 | 44530 | 33-3100 | OG5 DELIVERY TRENCH BOX, BUILD BX AND INSTALL BOX ON TRENCH TO SG3 | 14
44535 | 44530 | 31-1820 | SG7/OG8 FIRE WATCH/BURN SHEETS | 5
44535 | 44530 | 33-3100 | OG2 EXC. FOR POES | 18
44535 | 44530 | 32-6510 | INSTALL WHITE MESH WHERE NEEDED | 9
44535 | 44530 | 33-3100 | OG3 PUT TOGETHER TRENCH BOXES AND SET ONE | 4
44535 | 44530 | 03-1000 | OG8 START TO FORM FOOTINGS | 23
44535 | 44530 | 03-1000 | OG10 STRIP PLUMBING SHAFT | 44
44535 | 44530 | 03-1000 | OG10 MOVE FORMS TO SG7 | 14
44535 | 44530 | 03-1000 | OG10 SITE MAINTENANCE | 8
44535 | 44530 | 03-1000 | OG8 SITE MAINTNENACE | 8
44535 | 44530 | 03-1500 | SG4 STRIP WINDOWS | 7
44535 | 44530 | 03-1500 | SG5 STRIP WINDOWS | 3
44535 | 44530 | 03-1500 | SG5 START FORMING WINDOWS | 10
44535 | 44530 | 31-1820 | SG7 BURNING SHEETS | 4
44535 | 44530 | 31-1400 | OG8 FLOW FILL99CYS | 8
44535 | 44530 | 99-4560 | SG6 ASSIST VITAL WITH PICK TO 2ND FLOOR | 6
44535 | 44530 | 33-3100 | SG1 EXC. FOR POES | 5
44535 | 44530 | 31-1820 | SG7 REMOVE SHEETS FOR STEAM CONNECTION | 6.5
44535 | 44530 | 31-1400 | OG8 COMPACT FOR FOOTINGS | 4
44535 | 44530 | 33-3100 | OG2 PREP FOR POE EXC. | 5
44535 | 44530 | 31-2200 | OG10 BACKFILL DBANK | 7
44535 | 44530 | 31-1700 | JUMP PMPS | 1
44535 | 44531 | 99-4560 | SG6 CLEAN FOR ROOFS AND LANDINGS CONCRETE POUR/ HANG 2 FIRE EXTING ON 2ND FLOOR | 8
44535 | 44531 | 02-6005 | OG2 PAINT REMOVAL - INSTALL PUMP TP REMOVE WATER | 18
44535 | 44531 | 02-2300 | SG4 CLEAN BASEMENT | 17
44535 | 44531 | 32-6000 | OG3 CHOP OPENINGS FOR THEMIS - CHOP ELECTRIC POE | 20
44535 | 44531 | 33-3100 | SG3/SG5 BUILD TRENCH BOXES | 17.5
44535 | 44531 | 33-3100 | OG2 EXC POE | 12
44535 | 44531 | 32-6520 | OG2 SETUP WHITE FENCE | 10
44535 | 44531 | 02-2300 | OG2 PUMP OUT PIT TO ELECTRICAL PANEL | 6
44535 | 44531 | 33-3100 | SG7 EXC FOR PLUBING | 7
44535 | 44531 | 03-1000 | OG10 ASSIST CARP WITH LADDER PLACEMENT IN SHAFT | 6.5
44535 | 44531 | 33-3100 | PUT TRENCH BOXES TOGETHER | 8
44535 | 44531 | 03-1900 | SG6 PATCH HOLES IN ROOF DECK FOR CONCRETE, PUT IN PENETRATION ON ROOFDECK | 29
44535 | 44531 | 03-2300 | OG8 RESUPPORT DUCT BANK | 3
44535 | 44531 | 03-2300 | OG8 FORM DUCT BANK | 9
44535 | 44531 | 03-1000 | OG8 FORM GRADE BEAM | 11
44535 | 44531 | 03-1000 | G10 FINISH STRIPPING FORMS ON PLUMBING SHAFT | 31
44535 | 44531 | 99-4560 | OG10 INSTALL 32' LADDER INSHAFT | 3
44535 | 44531 | 03-1000 | OG10 SITE MAINTENNACE | 16
44535 | 44531 | 03-1300 | OG10 STRIP BOLTS PATTERNS | 3
44535 | 44531 | 31-1700 | JUMP PUMPS | 1
44535 | 44532 | 02-3000 | SG5 CHOP OPENINGS FOR FSE | 13.5
44535 | 44532 | 02-2300 | OG2 PUMP WATER OUT FROM BASEMENT | 9
44535 | 44532 | 33-3100 | OG5 EXCAVATE INSTALL TRENCH BOX AND INSTALL STEEL PLATES ON STEAM TRENCH TO SG3 WALKWAY - REMOVE FENCE | 66
44535 | 44532 | 03-1900 | PICKUP AIR COMPRESSOR TO BROOKLYN BRIDGE | 4
44535 | 44532 | 31-1400 | OG8 LAG & BACKFILL FOR FOOTINGS | 7
44535 | 44532 | 02-6000 | OG10 DEMO GARAGE AND LOADOUT (3) CARDELLA CONTAINERS | 25.5
44535 | 44532 | 02-6000 | OG10 START MOVING MATERIAL FOR CRANE PAD | 13
44535 | 44532 | 32-6520 | SITE SAFETY ( SIGNAGE FOR PEDESTRIANS) | 5
44535 | 44532 | 03-1500 | SG4/5 FORM WINDOWS | 20
44535 | 44532 | 03-1900 | SG6 FIX HOLES IN STAIR LANDING AND STRINGS | 7
44535 | 44532 | 03-1000 | OG8 FORM GRADE BEAMS | 60.5
44535 | 44532 | 31-1820 | OG8 CUT SHEETS | 4
44535 | 44532 | 31-1820 | OG8 BUILD SHEETING PIT | 4
44535 | 44532 | 33-3100 | WELKINS YARD - BUILD SHEETHING PIT BECAUSE SHEETHING BOX DIDN’T FIT | 10
44535 | 44532 | 99-4560 | OG8 SITE MAINTENANCE | 8
44535 | 44532 | 02-6000 | OG10 BURN REBAR FOR DEMO | 2
44535 | 44532 | 03-1000 | MOVE FORMS FROM OG10 TO OG7 | 17.5
44535 | 44532 | 31-1700 | JUMP PUMPS | 1
44535 | 44533 | 31-1300 | SG7 LOAD OUT EXCAVATE MATERIAL | 9.5
44535 | 44533 | 33-3100 | SG3 LOAD OUT EXCAVATE MATERIAL | 9
44535 | 44533 | 02-6000 | OG10 GARAGE DEMO LOAD OUT (4) CONTAINERS | 6
44535 | 44533 | 02-6000 | OG10 MOVE TO REBAR TO OG8. PREP FOR CRANE /BLOCK PARKING SPACES/CLEAN SITE | 16
44535 | 44533 | 03-1900 | SG6 POUR ROOFS AND LANDINGS | 37
44535 | 44533 | 99-4560 | SG6 CLEANUP | 12
44535 | 44533 | 03-1900 | SETUP AND POUR SG6 ROOF/STAIR LANDINGS (66 CY) | 32
44535 | 44533 | 99-4560 | CLEANUP SG6 | 12.5
44535 | 44533 | 31-1820 | OG8 BURN SHEETS | 11
44535 | 44533 | 03-1300 | OG8 SET ANCHOR BOLTS | 12
44535 | 44533 | 03-1000 | OG8 FINISH FORMING FOOTINGS AND GRADE BEAMS | 52
44535 | 44533 | 03-1000 | OG9 START CUTTING PLYWOOD FOR GROUT PADS FORM WORK | 4
44535 | 44533 | 03-1000 | OG10 PUT UP WORK PLATFORM ON PLUMBING SHAFT | 34
44535 | 44533 | 03-1000 | OG8 SITE MAINTENANCE | 8
44535 | 44533 | 03-1000 | OG10 SITE MAINTENANCE | 8
44535 | 44533 | 31-1700 | jump pumps | 2
44528 | 44522 | 99-4000 | SG4 PREP AND POUR WALKWAY TO BASEMENT RAMP POUR 2 WINDOWS | 14.5
44528 | 44522 | 33-6000 | SG7/OG5 RECEIVE STEAM PIPE | 25
44528 | 44522 | 32-6520 | SG3 MOVE FENCE FOR WELKIN YARD - PREP FOR REMOVE ASPHALT AND CONCRETE | 10
44528 | 44522 | 33-3100 | OG5 RECEIVEE M11 MANHOLE | 18
44528 | 44522 | 03-1000 | OG9 UNLOAD FORMS FOR CARPENTERS | 2
44528 | 44522 | 99-4560 | OG10 CLEAN SITE AFTER CARPS | 2
44528 | 44522 | 02-6005 | OG2 PAINT REMOVAL | 17
44528 | 44522 | 03-2300 | OG2/9 POUR 44 CYS DBANK | 8.5
44528 | 44522 | 03-2300 | OG8 POUR 13 CYS DBANK | 3
44528 | 44522 | 31-1500 | OG8 COMPACT STONE IN GRADE BEAM/VAPOR BARRIER | 9
44528 | 44522 | 00-0010 | OG6 INSERT LENTIL INTO BUILDING | 5
44528 | 44522 | 33-6010 | OG10 ASSIST WELKIN WITH PIPES/CORES | 5
44528 | 44522 | 33-3100 | SG2 EXC/EXPOSE UTILITIES POES | 11
44528 | 44522 | 99-4560 | JOB UPKEEP | 16
44528 | 44522 | 03-1000 | OG8 FORM GBS | 6
44528 | 44522 | 03-1000 | SG7 FINISH STRIPPING FORMS | 8
44528 | 44522 | 03-1000 | OG10 FORM PLUMBING SHAFT | 78
44528 | 44522 | 03-1000 | OG9 UNLOAD FORM TRUCK | 8
44528 | 44522 | 03-1300 | OG10 SET ANCHOR BOLTS (8) | 16
44528 | 44522 | 03-2300 | RESHOE ELECTRICAL DBANK | 6
44528 | 44522 | 31-1700 | JUMP PUMPS | 2
44528 | 44523 | 00-0010 | SG1 RECEIVE CONNEX BOX FOR JACOBS/NYCHA | 3
44528 | 44523 | 02-1900 | SG3 MOVE FENCE - ASPHALT/CONCRETE REMOVAL 3 - LIVE LOADS 2 - CONCRETE/ 1 - ASPHALT | 12
44528 | 44523 | 33-3100 | OG2 LOAD OUT DIRT FROM TRENCH, CHOP RAMP WALL POE, CLEAN CONCRETE DEBRIS /HAND DIG UNDER RAMP | 21
44528 | 44523 | 31-2200 | og5 backfill some around manhol/ continue to excavate for eletcrical run to bld | 14
44528 | 44523 | 31-2200 | OG9 BACKFILL ELECTRIC TRENCH/ RECEIVE HNS TRUCK LOADS FROM OG5 EXC | 21.5
44528 | 44523 | 02-6005 | OG2 PAINT REMOVAL | 17
44528 | 44523 | 03-1900 | OG8 SETUP AND POUR DB COLLAR/GB/PIER CAP (8 CY) | 10.5
44528 | 44523 | 03-1900 | OG10 SETUP AND POUR 44 CYS SHAFT WALLS | 17
44528 | 44523 | 33-6010 | OG10N ASSIST WELKIN RELOCATE PIPES | 8
44528 | 44523 | 33-3100 | SG2 EXC FOR UTILITIES/POES | 14
44528 | 44523 | 33-3100 | OG9 dEMO CONCRETE BLOCK FOR WELKIN PLUMBERS | 7
44528 | 44523 | 99-4560 | FLAGGER FOR HNS TRUCK ON SURF | 2
44528 | 44523 | 33-3100 | INSTALL HEAT BLANKETS ON OPEN WATER LINES | 4
44528 | 44523 | 03-1000 | SG7 FORM INSIDE PLUMBING SHAFT | 10
44528 | 44523 | 03-1000 | OG8 SITE MAINETNANCE | 8
44528 | 44523 | 03-1000 | OG9 SITE MIANTENANE | 10
44528 | 44523 | 03-1000 | OG9 DUMMY DECK IN PLUMBING HSAft | 14
44528 | 44523 | 03-1300 | og10 achor boltspattern (8) | 8
44528 | 44523 | 03-1000 | OG10 FINISH CLOSING UP PLUMBING HSAFT | 38
44528 | 44523 | 03-1900 | O10 POUR PLUMBING SHAFT | 9
44528 | 44523 | 03-1900 | OG10 COVER PLUMBING SHAFT WITH BLANKETS | 14
44528 | 44523 | 03-1000 | OG3 SHORING | 6
44528 | 44523 | 31-1700 | JUMP PUMP | 3
44528 | 44524 | 02-1900 | SG3 ASPHALT/CONCRETE REMOVAL - CARDELLA 1 - LIVE LOAD REMOVE WITH RENCE TO SG7 STEEL PIPE | 5
44528 | 44524 | 33-3100 | SG3 EXCAVATE POE START | 18.5
44528 | 44524 | 02-2000 | SG4 DEMO BENCHES/WI FENCE - REMOVE MATERIAL | 16
44528 | 44524 | 02-6005 | OG2 PAINT REMOVAL | 25
44528 | 44524 | 99-4560 | OG5 CHOP CONCRETE AND REMOVAL - WINDOW BASEMENT | 3
44528 | 44524 | 33-3100 | OG5 REMOVE PILE FROM EXCAVATION FINISH EXC. FOR ELETCRIC RUN TO BLDG | 23
44528 | 44524 | 02-6005 | SG4 CLEAN MATERIAL FROM LEAD CONTAINER - PAINT REMOVAL | 3
44528 | 44524 | 99-4560 | SG4/6 COVER STOCK PILES | 3
44528 | 44524 | 33-3100 | OG5 UNLOAD TRENCH BOXES | 4
44528 | 44524 | 99-4560 | SG6 CLEAN BLDG GARBAGE FROM SUBS | 2
44528 | 44524 | 99-4560 | OG8 CLEAN SITE | 2
44528 | 44524 | 31-1400 | OG8 PREP AREA FOR FLOW FILL | 11
44528 | 44524 | 02-1700 | SG7 LOAD OUT STEEL CONT. | 12
44528 | 44524 | 02-6000 | OG10 EMPTY OUT GARBAGE | 8.5
44528 | 44524 | 31-2200 | OG10 BACKFILL DBANKS | 10
44528 | 44524 | 99-4560 | SG6 SAFETY NETTING, TOE KICK, HANDRAIL, | 40
44528 | 44524 | 03-1000 | OG8 STRIP FORMS FOR GRADE BEAMS, PIER, ELECTRICAL RISERS | 16
44528 | 44524 | 03-1000 | OG8 FORM FOR FLOWFILL | 12
44528 | 44524 | 33-3100 | OG10 COVER HOLES FOR POE | 14
44528 | 44524 | 99-4560 | OG10 SITE 8, SG7 - HANFG JOB SIGNS | 5.5
44528 | 44524 | 03-1000 | SHORE UP RAMP @ OG2 | 3.5
44528 | 44524 | 03-1300 | OG8 STRIP ANCHOR BOLT PATTERN | 2
44528 | 44524 | 03-1000 | OG8 SITE MAINTENANCE | 8
44528 | 44524 | 03-1000 | OG10 SITE MAINTENANCE | 8
44528 | 44524 | 31-1700 | JUMP PUMPS | 1
44528 | 44525 | 99-7200 | HOLIDAY | 160
44528 | 44526 | 99-7200 | HOLIDAY | 64
44521 | 44515 | 00-0010 | SG1 CONNEX DELIVERY | 3
44521 | 44515 | 31-1400 | SG7 BACKFILL/COMPACT TO TOP FOOTINGS/ PREPARE FOR STEAM PIPE DELIVERY | 25.5
44521 | 44515 | 02-6005 | OG3 PAINT REMOVAL/CLEAN BASEMENT | 13
44521 | 44515 | 99-4560 | SG6 CLEAN DEBRIS | 6
44521 | 44515 | 00-0016 | OG4 FINISH INSTALL LINTEL - BOLT AND GROUT | 9
44521 | 44515 | 33-3100 | OG5 MOVE STORED MATERIALS AS NEEDED/FOR TRENCH EXC. | 16
44521 | 44515 | 02-1900 | OG5 SAW CUT ASPHALT/CLEAN AREA FOR STEAM PIPE DELIVERY | 9
44521 | 44515 | 33-3100 | HAND DIG OG3 PLUMBER POE | 5
44521 | 44515 | 03-2300 | SETUP AND POUR 40 CYS DBENCH OG10 | 15
44521 | 44515 | 03-1900 | SETUP AND POUR 100 CYS OG10 SLAB | 49.5
44521 | 44515 | 03-1000 | SG7 DUMMY DECK IN PLUMBING SHAFT | 62
44521 | 44515 | 03-1000 | OG8 STRIP FOOTINGS & WALLS | 10
44521 | 44515 | 03-1300 | OG8 STRIP BOLT PATTERN | 8
44521 | 44515 | 03-1000 | OG10 FINISH PACK OUTS FOR SLAB | 18
44521 | 44515 | 03-1900 | OG10 POUR SLAB | 7
44521 | 44515 | 03-1000 | SG7 SITE MAINTENANCE | 8
44521 | 44515 | 03-1000 | OG8 SITE MAINTENANCE | 8
44521 | 44515 | 03-1000 | OG10 SITE MAINTENANCE | 8
44521 | 44515 | 31-1700 | JUMP PUMPS | 1
44521 | 44516 | 00-0010 | SG1 CONNEX DELIVERY/ REMOVE BOLLARDS - BACKFILL HOLES | 14
44521 | 44516 | 33-6010 | SG3 MOVE ITEMS IN WELKINS YARD | 13.5
44521 | 44516 | 33-6000 | SG7/OG5 RECEIVE OFFLOAD STEAM PIPE | 26
44521 | 44516 | 02-6005 | OG3 PAINT REMOVAL | 17
44521 | 44516 | 03-1900 | SG6 PATCH TIE HOLES IN PLUMBING SHAFT | 9
44521 | 44516 | 02-3000 | OG1 CHOP PENETRATIONS FOR THEMIS | 9
44521 | 44516 | 33-6010 | OG8 MOVE PIPE FOR PLUMBERS | 5.5
44521 | 44516 | 03-1000 | OG8 ASSIST CARP WITH FORMS | 5
44521 | 44516 | 31-1400 | OG10 BACKFILL AND COMPACT | 19
44521 | 44516 | 32-6000 | OG10 SAWCUT SLAB JOINTS | 6
44521 | 44516 | 32-6520 | OG10 ASSIST ATCO WITH FENCE REMOVAL | 6
44521 | 44516 | 03-1000 | SG7 START PLUMBING SHAFT | 9
44521 | 44516 | 03-1000 | SG7 FINISH DUMMY DECK W/BEAM | 11
44521 | 44516 | 03-1000 | SG7 START TO CLOSE UP GRADE BEAMS | 7.5
44521 | 44516 | 03-1000 | OG8 FORM PIER | 6
44521 | 44516 | 31-1400 | OG8 BULKHEAD FOR FLOWFILL | 11
44521 | 44516 | 03-1000 | OG8 DUMMY DECK | 18
44521 | 44516 | 03-1000 | OG10 STRIP FORMS FOR DECK | 12
44521 | 44516 | 03-1000 | og10 safety handrail | 14.5
44521 | 44516 | 03-1000 | og10 platform around plumbing shaft | 16
44521 | 44516 | 03-1000 | SG7/OG8/OG10 SITE MAINTENANCE | 24
44521 | 44516 | 31-1700 | JUMP PUMPS | 1
44521 | 44517 | 00-0010 | SG1 CONNEX DELIVERY | 3
44521 | 44517 | 33-3100 | OG3 EXCCAVATE ELECTRICAL POE AT RAMP | 18.5
44521 | 44517 | 32-6000 | OG3 SAWCUT AND CHOP POE | 9
44521 | 44517 | 33-3100 | OG5 EXCAVATE ELECTRIC TRENCH/REMOVE FENCE | 14
44521 | 44517 | 02-6005 | OG3 PAINT REMOVAL | 17
44521 | 44517 | 32-6520 | S8 SAWCUT AND CHOP FLOOR FOR WTAER FLOW TO PUMP/CLEANUP | 11
44521 | 44517 | 03-1400 | OG8 BACKFILL INSIDE GBS | 12
44521 | 44517 | 33-6010 | OG8 ASSIST WELK | 5
44521 | 44517 | 31-1400 | OG10 BACKFILL AROUND BULDG | 20.5
44521 | 44517 | 99-4560 | GENERAL CLEANUP OF ALL SITES | 12
44521 | 44517 | 03-1000 | SG7 CLOSE UP GBS | 66.5
44521 | 44517 | 03-1000 | SG7 SITE MIANTENANCE | 8
44521 | 44517 | 03-1000 | OG10 FINISH SAFETY PLATFORM | 14
44521 | 44517 | 03-1000 | OG10 CLOSE SHAFT | 8
44521 | 44517 | 03-1000 | OG10 SITE MAINTENACE | 8
44521 | 44517 | 03-1000 | MOVE & GATHER PANELS FOR OG10 | 24
44521 | 44517 | 03-2300 | SHORING UNDER DUCT BANK | 7
44521 | 44517 | 31-1700 | JUMP PUMPS | 1
44521 | 44518 | 03-1400 | SG-4 Drill and Dowel Windows / Swap 30 yard container | 5
44521 | 44518 | 02-3000 | SG-5 Chop 1 Location For Duct Peetration / Clean Debris. | 5
44521 | 44518 | 32-6000 | OG-2 Saw Cut At Ramp Wall Poe | 5
44521 | 44518 | 02-1900 | OG-5 Remove Asphalt For Steam Trench / 3-Live Load Asphalt And Contrete. | 7
44521 | 44518 | 32-6000 | OG-5 Saw Cut and Chop concrete Windows Wall / Move Concrete. | 7
44521 | 44518 | 99-4560 | SG-3 - Move Items In Welkins Yard / Clean yard for steam trench | 5
44521 | 44518 | 33-3100 | OG-5-Excavate electric trench / truck on site - move Dirt to SG-4 MAKE PILE. | 22.5
44521 | 44518 | 02-6005 | OG-3 Paint Removal | 17
44521 | 44518 | 33-3100 | OG-8- Excavate trench for 5 star D Bench. | 8
44521 | 44518 | 03-1900 | SG-7-Pour 15 cys grade Beam. | 9
44521 | 44518 | 33-3100 | SG-3- Excavate POE | 14
44521 | 44518 | 07-1100 | SG-7 Install foam around shaft. | 5.5
44521 | 44518 | 03-2300 | OG-10- Pour 7 yards D. Bench | 3
44521 | 44518 | 33-3100 | OG-8- Excavate for Welkin | 3
44521 | 44518 | 99-4560 | General Cleanup | 16
44521 | 44518 | 03-1000 | SG-7- Finish Close-up | 12
44521 | 44518 | 03-1300 | SG-7- Set Anchor Bolts | 12
44521 | 44518 | 03-1900 | SG-7- Pour Concrete | 3
44521 | 44518 | 03-1000 | OG-8- Closeup Pier | 4
44521 | 44518 | 03-2300 | OG-8- Form for Duct Bank Risers. | 4
44521 | 44518 | 03-1000 | OG-10- Start Closing Up plumbing shaft. | 7
44521 | 44518 | 03-1000 | SG-7- Site Maintenance. | 44
44521 | 44518 | 03-1000 | OG-8- Site Maintenance. | 8
44521 | 44518 | 03-1000 | OG-10- Site Maintenance | 8
44521 | 44518 | 03-1000 | Safety (Shore Up) | 15
44521 | 44519 | 02-1900 | SG3 SAWCUT ASPHALT AND CONCRETE/FOR STEAM TRENCH | 4.5
44521 | 44519 | 03-1000 | SG6 OPEN DECK 2ND FLOOR FOR CONDUIT PENETRATIONS | 5.5
44521 | 44519 | 02-6005 | OG3 PAINT REMOVAL/CLEAN BASEMENT | 17
44521 | 44519 | 02-1900 | OG5 REMOVE ASPHALT FOR STEAM TRENCH 3 LIVE LOADS | 8
44521 | 44519 | 33-3100 | OG5 EXAVAVATE ELCTRIC TRENCH/PREP FOR INSTALL ELETCRIC CONCRETE MANHOLE BOX | 17
44521 | 44519 | 32-6000 | OG5 SAWCUT/CHOP CONCRETE WINDOW | 6.5
44521 | 44519 | 33-3100 | SG6 RECEIVEE AND DUMP HNS TRUCK FROM OG5 EC | 17
44521 | 44519 | 33-6000 | PICKUP 2 EA GAS PIPE FRO NG FOR OG8 | 4
44521 | 44519 | 99-4560 | OG10 CLEAN SITE | 4.5
44521 | 44519 | 99-4560 | OG8 CLEAN SITE | 4.5
44521 | 44519 | 03-2300 | SETUP DBANK & STAYFORM & BACKFILL OG9 | 7
44521 | 44519 | 31-1400 | OG8 BACKFILL & STONE GRADE BEAM PREP FOR POUR | 12
44521 | 44519 | 31-1400 | OG10 BACKFILL DBANK AND AROUND BUILDING | 10
44521 | 44519 | 33-3100 | FIX BACK SHELF @ OG10 | 4
44521 | 44519 | 32-6520 | REMOVE FENCNING BEHIND GARAGE OG10 | 8.5
44521 | 44519 | 03-1000 | SG7 STRIP FORMS | 14
44521 | 44519 | 03-1000 | SG7 SITE MAINTENANCE | 8
44521 | 44519 | 03-2300 | OG8 FINISH FORMING FOR ELECTRICAL DUCT BANK & RISERS | 12
44521 | 44519 | 03-2300 | OG9 FORM FOR DUCT BANK | 3.5
44521 | 44519 | 03-1000 | OG10 CLOSE UP PLUMBING SHAFT | 57
44521 | 44519 | 03-1000 | OG10 SITE MAINTENNACE | 8
44521 | 44519 | 99-7200 | PERSONAL DAY | 8
44521 | 44519 | 03-1500 | SG4 CLOSE UP WINDOWS | 18
44521 | 44519 | 31-1700 | JUMP PUMPS | 1
44514 | 44508 | 03-1000 | OG-8 Form Footings | 18
44514 | 44508 | 03-1000 | OG-8 Form For Slab | 20
44514 | 44508 | 03-1000 | OG-9 Adjust Slabs For cleanout | 9
44514 | 44508 | 03-1000 | OG-10 Adjust Slabs For Cleanout | 6
44514 | 44508 | 03-1000 | OG-8 Site Maintanence | 8
44514 | 44508 | 03-1000 | OG-10 Site Maintenance | 8
44514 | 44508 | 03-1300 | OG-9 Adjust Keys For Iron Workers | 7
44514 | 44508 | 03-1000 | OG-9 Site Maintenence | 8
44514 | 44508 | 03-1000 | SG-7 Form Footings | 23
44514 | 44508 | 03-1000 | OG-8 Form For Cleanout Slab | 8
44514 | 44508 | 03-1000 | SG-7 Site Maintenance | 8
44514 | 44508 | 05-6020 | SG-4 - Grout Beams In Perambulator Rooms | 11.5
44514 | 44508 | 32-6000 | SG-4-SG-5 Chop Openings For Sheet Metal penetrations | 7
44514 | 44508 | 33-3100 | SG-7 Excavate POE'S AT SG-3 | 9
44514 | 44508 | 02-6005 | OG-3 Paint Removal | 17
44514 | 44508 | 33-3100 | OG-8-Maintain Steam trench - Dig Holes And Maintain Water. | 4
44514 | 44508 | 99-4560 | OG-9- Prep. For Crane / Clean And Back Plate Move Rear And Sandbags. Compact For Crane And Trailers / Clean Site. | 28
44514 | 44508 | 33-3100 | OG-10- Excavate balance Of Ductbank to OG-1- Load out Asphalt. (2) 20yd containers. | 30
44514 | 44508 | 99-7200 | Holiday Pay | 8
44514 | 44508 | 32-6620 | OG10 cut down tree and clan to container by SG4/clean site | 6
44514 | 44508 | 31-1700 | jump pumps | 1
44514 | 44509 | 33-6000 | SG-7 - Pipe Delivery | 13.5
44514 | 44509 | 33-3100 | SG-7- Excavate POE'S at SG-3 / Clean Site | 26.5
44514 | 44509 | 00-0016 | OG-4 Drill / Epoxy Anchors For Lintel. | 19
44514 | 44509 | 02-6005 | OG-3- Paint Removal | 17
44514 | 44509 | 07-1100 | OG-10 Install Foam And Vapor Barrier / | 13.5
44514 | 44509 | 02-3000 | SG-4 Chop Penetration For FSE In Cellar. | 4.5
44514 | 44509 | 32-6510 | OG-4 Fix White Mesh On Fence. | 13
44514 | 44509 | 33-6000 | Pick up Pipe From National Grid - For - OG-10 | 4
44514 | 44509 | 03-1000 | SG-7 Form Footings & Brace | 25
44514 | 44509 | 03-1000 | SG-7 Templates For Lather | 3.5
44514 | 44509 | 03-1000 | SG-7 Site Maintenance | 8
44514 | 44509 | 03-1000 | OG8_ Close Up Wall Forms | 52
44514 | 44509 | 03-1000 | OG-8 Site Maintenance | 8
44514 | 44509 | 03-1000 | OG-10 Box Out Column Bases | 17
44514 | 44509 | 03-1900 | OG-10 Put In Pour Stop | 7.5
44514 | 44509 | 03-1000 | OG-10 Site Maintenance | 8
44514 | 44509 | 99-7200 | Holiday Pay | 8
44514 | 44509 | 31-1700 | jump pumps | 1
44514 | 44509 | 33-3100 | OG10 Finish Excavation - Ductbank to OG-1-Live Load Container Asphalt | 7.5
44514 | 44509 | 99-4560 | SG-4- Swap Candella - 30yd - SG-6- Fix White Mesh On Fence / Cover Dirt Piles. | 4.5
44514 | 44509 | 03-1900 | OG10 Pour Pit Slab / | 6
44514 | 44510 | 07-1100 | OG-10-Install Foam & Vapor Barrier For Slab | 6
44514 | 44510 | 02-3000 | OG-10 Core For Gas Ex | 6.5
44514 | 44510 | 31-2200 | OG-10 Backfill | 5
44514 | 44510 | 03-1900 | SG-7- Setup & Pour 28 CYS Footings | 8
44514 | 44510 | 31-1400 | OG-8 Backfill & Prep for Wall / Footing Pour | 11
44514 | 44510 | 00-0016 | Install Lentil / OG-4 | 2
44514 | 44510 | 33-3100 | Dig Foxhole For Welkin | 3
44514 | 44510 | 02-3000 | SG-4 Chop Penetrations For FSE In Cellar. | 17
44514 | 44510 | 99-4560 | OG-2- Move Concrete to OG-10 Make Pile for Load out - cardella Cont. | 13
44514 | 44510 | 02-6005 | OG-3 Paint Removal | 17
44514 | 44510 | 00-0016 | OG-4 Epoxy In Anchors For Lintel / Install Lintel | 6
44514 | 44510 | 33-3100 | OG-5 Expose Concrete At Ductbank | 3
44514 | 44510 | 32-6510 | SG-5 Install White Mesh On New Fence | 7
44514 | 44510 | 02-3000 | OG-10 Core 10" Hole In Grade Beam For Gas Pipe | 4
44514 | 44510 | 03-1000 | SG-7- Finish Bracing Footings | 10
44514 | 44510 | 03-1000 | SG-7- Site Maintenance | 8
44514 | 44510 | 03-1300 | OG-8 Set Bolt Pattern. | 4
44514 | 44510 | 03-1000 | OG-8 Brace Wall Forms & Footing. | 32
44514 | 44510 | 03-1000 | OG-10 Form Stop For Deck Pour. | 16
44514 | 44510 | 03-1000 | OG-8 SITE Maintenance | 8
44514 | 44510 | 03-1900 | OG-10 - Waterstop | 23
44514 | 44510 | 03-1000 | OG-10 Site Maintenance | 8
44514 | 44510 | 31-1700 | jump pumps | 1
44514 | 44510 | 33-3100 | OG2 Excavate POE AT Ramp / | 7
44514 | 44510 | 32-6520 | Adjust Fence at Fire Stand Pipe | 6.5
44514 | 44511 | 99-7200 | Holiday Pay | 56
44514 | 44512 | 02-6060 | SG4 LEVEL ARA FOR ACCESS TO 2ND FLOOR - USE HNS TRUCK FROM OG2 EXC. | 17
44514 | 44512 | 02-3000 | SG5 CHOP PENETRATIONS FOR THEMIS/CLEAN DEBIRS | 17
44514 | 44512 | 32-6520 | /ADJUST FENCE AT FIRE STAND PIPE | 14
44514 | 44512 | 02-6005 | OG3 PAINT REMOVAL | 17
44514 | 44512 | 00-0010 | SG1 CONNEX DELIVERY | 2
44514 | 44512 | 03-1900 | SETUP AND POUR WALLS /FOOTINGS OG8 DELIVERY (44 CY) | 14
44514 | 44512 | 03-2300 | SETUP AND POUT DBANK OG8 ELECTRCI (28 CY) | 8
44514 | 44512 | 03-1900 | PREP FOR SLAB POUR OG10 | 9
44514 | 44512 | 03-1700 | UNLOAD REBAR OG10 | 8.5
44514 | 44512 | 99-4560 | LOAD OUT CARDELLA OG10 | 4
44514 | 44512 | 31-1700 | JUMP PUMPS | 1
44514 | 44512 | 33-3100 | OG2 LOAD OUT - USE HNS TRUCK TO SG4/ EXC. POE AT RAMP | 13.5
44514 | 44512 | 03-1000 | OG8 FINISH BRACING WALL & FOOTINGS | 26
44514 | 44512 | 03-1300 | OG8 SET BOLT PATTERN | 4
44514 | 44512 | 03-1900 | OG8 POUR CONCRETE | 5
44514 | 44512 | 03-1000 | SG7 STRIP FOOTINGS | 18
44514 | 44512 | 03-1000 | OG10 FORM FOR DECK POUR | 18
44514 | 44512 | 07-1100 | OG10 PREP STRYOFOAM FOR SHELF AROUND BUILDING | 6
44514 | 44512 | 03-1000 | OG8 SITE MIANTENANCE | 8
44514 | 44512 | 03-1000 | OG10 SITE MAINTENANCE | 8
44514 | 44512 | 03-1000 | SG7 SITE MAINTENANCE | 8
44507 | 44501 | 02-6005 | OG3 PAINT REMOVAL | 17
44507 | 44501 | 32-6520 | OG2 INSTALL FENCE FOR PLUMBING TRENCH | 12
44507 | 44501 | 33-3100 | OG2 BEGIN TO EXCAVATE | 8.5
44507 | 44501 | 33-3100 | OG5 LOAD OUT 20 CY CONTAINER CONCRETE | 7
44507 | 44501 | 32-6520 | OG5 REMOVE FENCE ADJOINING FSE YARD | 7
44507 | 44501 | 33-3100 | og5 CLOSE EXISTING RAMP EXCAVATE FOR POE | 14.5
44507 | 44501 | 33-3100 | SG6 MAINTAIN TRENCH/PICK UP DEBRIS | 3
44507 | 44501 | 32-6510 | SG3 INSTALL WHITE MESH | 4
44507 | 44501 | 31-1700 | JUMP PUMPS | 2
44507 | 44501 | 32-6520 | OG8 REMOVE FENCE & EXC FOR ELECTRIC TO OG5 | 18
44507 | 44501 | 03-1900 | OG9 SETUP & POUR GB (30 CY) | 17
44507 | 44501 | 03-2300 | OG8 SETUP & POUT DBANK (5 CY) | 6
44507 | 44501 | 99-4560 | REMOVE DEBRIS OG5 | 10
44507 | 44501 | 33-3100 | EXC ELECTRICAL TRENCH OG10 | 10
44507 | 44501 | 31-1400 | OG10 PREP FOR BACKFILL | 8
44507 | 44501 | 03-1000 | OG8 FORM STEP FOOTING | 40
44507 | 44501 | 03-1000 | OG8 SITE MAINTENANCE | 8
44507 | 44501 | 03-1000 | OG9 FINISH GBS | 24
44507 | 44501 | 03-1900 | OG9 POUR CONC | 4
44507 | 44501 | 03-1000 | OG10 FORM FOR STEAMFITTERS | 20
44507 | 44501 | 03-2300 | OG10 DBANK | 9
44507 | 44501 | 03-1000 | OG10 SITE MAINTENANCE | 8
44507 | 44501 | 99-4000 | LABORERS SHANTY | 8
44507 | 44502 | 03-2300 | OG1 CHOP HOLES FOR DUCTBANK | 14.5
44507 | 44502 | 33-6010 | OG2 MOVE PIPE FOR PLUMBERS WHEN TRENCH IS COMPLETE | 11.5
44507 | 44502 | 32-6520 | OG2 MOVE SOME FENCE FOR EXCAVATION | 9
44507 | 44502 | 33-3100 | OG2 COMPLETE EXCAVATION/LOAD OUT DIRT | 11.5
44507 | 44502 | 33-3100 | OG5 LOAD OUT DIRT AT POE EXC | 9
44507 | 44502 | 02-6005 | OG3 PAINT REMOVAL | 17
44507 | 44502 | 31-1700 | JUMP PUMPS | 1
44507 | 44502 | 31-1400 | OG9 BACKFILL | 25
44507 | 44502 | 33-6010 | OG8 MOVE PIPE FOR WELKIN/5 STAR | 10
44507 | 44502 | 31-2200 | OG8 BACKFILL FOR VITAL | 6.5
44507 | 44502 | 03-1000 | OG8 FORM FOOTINGS | 30
44507 | 44502 | 03-1000 | OG8 SET WALL TEMPLATES FOR LATHERS | 5
44507 | 44502 | 03-1000 | OG9 STRIP INSIDE GBS | 31
44507 | 44502 | 03-1300 | OG9 STRIP ANCHOR BOLTS | 7
44507 | 44502 | 03-1000 | OG8 SITE MAINTENANCE | 8
44507 | 44502 | 03-1000 | OG9 SITE MAINTENANCE | 8
44507 | 44502 | 03-2300 | OG10 FORM DBS | 23
44507 | 44502 | 99-5100 | PUT SHELVES IN OFFICE | 5
44507 | 44503 | 31-1000 | SG5 EXC BOND BEAM | 15.5
44507 | 44503 | 32-6520 | SG5 FENCE REMOVAL | 9
44507 | 44503 | 02-2300 | SG5 PUMP WATER DOWN BASEMENT/INSTALL NEW LINE FOR SUMP | 12
44507 | 44503 | 02-3000 | OG1 CLEAN UP FROM DUCT WORK PENETRATIONS DEMO | 10
44507 | 44503 | 02-6005 | OG3 PAINT REMOVAL | 17
44507 | 44503 | 32-6520 | OG5 FENCE REMOVAL | 5
44507 | 44503 | 03-2300 | OG10 SETUP & POUR DBANK (22 CY) | 6
44507 | 44503 | 07-1100 | SG7 SET INSUALTION AROUND SHAFT | 7
44507 | 44503 | 03-1700 | SG7 MOVE REBAR | 9.5
44507 | 44503 | 31-1300 | SG7 GRADE FOR FOOTINGS | 7
44507 | 44503 | 02-3000 | og8 move lentil into bldg for setup | 4
44507 | 44503 | 99-4560 | OG10 LOADOUT CARDELLA (CONCRETE) | 3
44507 | 44503 | 32-6520 | SG7 REMOVE FENCING | 5
44507 | 44503 | 03-1000 | OG8 FORM FOOTINGS | 53.5
44507 | 44503 | 03-1000 | OG9 BOTTOM SLAB FOR CLEAN OUTS | 14.5
44507 | 44503 | 03-1000 | OG9 SITE MAINTNENACE | 8
44507 | 44503 | 03-1000 | OG10 BOTTOM SLAB FOR CLEAN OUTS | 14.5
44507 | 44503 | 03-1000 | SG6 STRIP DUMMY DECK IN PLUMBING HSAFT | 17
44507 | 44503 | 03-1000 | OG10 FORM INSIDE WALLS OF PLUMBING SHAFT | 17
44507 | 44503 | 99-4560 | SAFETY SG6 HANDRAILS | 8
44507 | 44503 | 99-4560 | SAFETY SG5 FLATORM | 5
44507 | 44503 | 03-1000 | OG9 MOVE FORMS | 8
44507 | 44503 | 31-1700 | JUMP PUMPS | 1
44507 | 44504 | 31-1000 | SG-5 Excavate For Bond Beam/ Brace Under FSP Deck /Move Fence Relocate Fence | 29.5
44507 | 44504 | 02-6060 | SG-6 Remove Items 2nd Floor - Rebar/Lumber/Forms Clean Up-1st Floor | 15
44507 | 44504 | 02-6005 | OG-3 Paint Removal | 17
44507 | 44504 | 33-3100 | SG-7 Excavate And Expose Electric Ductbank by SG-1 | 7
44507 | 44504 | 31-1400 | OG-9-OG-10 Clean Site / BackFill | 13
44507 | 44504 | 03-1300 | OG-8 Set Anchor Bolts (8) | 8
44507 | 44504 | 03-1900 | OG-8 Pour Footings | 9
44507 | 44504 | 03-1000 | OG-8 Form Walls | 36
44507 | 44504 | 03-1000 | OG-8 Brace Footings | 16
44507 | 44504 | 03-1000 | OG-10 Form Plumbing Shaft | 36
44507 | 44504 | 03-1000 | SAFETY | 8
44507 | 44504 | 03-1000 | OG-8 Site Maintenance | 8
44507 | 44504 | 03-1000 | OG-10 Site Maintenance | 8
44507 | 44504 | 03-1900 | OG-8 Setup & Pour 48 cys footings /grade Beam | 14.5
44507 | 44504 | 31-1400 | OG-10 Backfill - Bank & Compact | 12
44507 | 44504 | 31-1400 | OG-8 Backfill Formwork | 12
44507 | 44504 | 33-3100 | OG-9 Hand dig trench for gas line. | 3
44507 | 44505 | 03-1000 | OG-8 Strip Footing Forms | 22.5
44507 | 44505 | 03-1000 | OG-8 Start Forming For Slab | 22
44507 | 44505 | 03-1000 | OG-10 Form For Slab | 18
44507 | 44505 | 03-1000 | Load Out Trailer For ULMA | 40.5
44507 | 44505 | 03-1000 | OG-10 Site Maintenance | 8
44507 | 44505 | 03-1000 | OG-8 Site Maintenance | 8
44507 | 44505 | 32-6520 | SG-3 Adjust Fence to Excavate POE / Fence Removal | 25.5
44507 | 44505 | 33-3100 | SG-7 Excavate POE AT SG-1 | 13
44507 | 44505 | 02-6005 | OG-3 Paint Removal | 17
44507 | 44505 | 02-2300 | SG-5 Remove Water Basement | 7
44507 | 44505 | 02-2300 | OG-4 Remove Water Basement | 11
44507 | 44505 | 33-3100 | OG-10 Excavate Balance of Ductbank toOG-1 | 5.5
44507 | 44505 | 31-1500 | OG-10 Place Stone in Building FootPring | 20
44507 | 44505 | 02-1900 | OG-10 Loadout 1-Container of Asphalt | 10
44507 | 44505 | 31-1400 | OG-10 Backfill Inside Bldg. For Inspection | 5
44500 | 44494 | 99-7300 | Shooting /lost time | 104
44500 | 44495 | 03-1900 | SG6 PATCH TIE HOLES | 17.5
44500 | 44495 | 02-2300 | OG4/OG6 DEMO FLOOR DRAIN VENTS | 21
44500 | 44495 | 03-1000 | SG6 LOAD OUT FORMS TO SITE 8/OG8 | 15
44500 | 44495 | 99-4560 | SG7/SG6 CLEAN AREA FROM CARPENTERS LUMBER | 27
44500 | 44495 | 03-1700 | OG10 UNLOAD/FLAG FOR REBAR DELIVERY | 10
44500 | 44495 | 03-1700 | S8 UNLOAD/FLAG FOR REBAR DELIVERY | 13
44500 | 44495 | 31-1700 | OG8 PREP & PUMP OUT FLOODED AREAS | 6
44500 | 44495 | 31-1700 | SG7 SETUP PUMPS | 3.5
44500 | 44495 | 03-1000 | SG6 LOAD OUT FORMS TO BRING TO S8 | 47.5
44500 | 44495 | 03-1000 | SG6 CLEAN OUT PLUMBING SHAFT | 16.5
44500 | 44495 | 03-1500 | OG5 PUT PLYWOOD ON WINDOWS IN BASEMENT | 17
44500 | 44495 | 31-1700 | JUMP PUMPS | 1
44500 | 44496 | 03-1000 | SG6 LOAD OUT FORMS TO SITE 8 | 6.5
44500 | 44496 | 03-2300 | SG6 POUR THRUST BLOCK | 10.5
44500 | 44496 | 99-4560 | SG6 CLEAN AREA - PREP FOR CRANE DELIVERY | 10.5
44500 | 44496 | 03-1900 | SG6 WATERPROOF PADS 2ND FLOOR/PATCH COLUMNS | 7
44500 | 44496 | 02-2300 | OG2 HOUSEKEEPING IN BASEMENT | 17
44500 | 44496 | 32-6510 | S8/SG5 INSTALL WHITE MESH ON FENCE | 9
44500 | 44496 | 33-3100 | OG10 LOAD OUT DIRTY | 4
44500 | 44496 | 02-6008 | lead training | 8
44500 | 44496 | 31-1700 | OG8 SETUP PUMPS AND INSTALL BULKHEAD IN DRAIN PIPE | 5.5
44500 | 44496 | 31-2200 | OG9 BACKFILL DBANKS AND INSIDE FOOT PRINT OF BUILDING | 18
44500 | 44496 | 33-3100 | OG10 EXC FOR DBANK | 9
44500 | 44496 | 31-1400 | OG10 LOAD TRUCKS FOR OG9 BACKFILL | 3
44500 | 44496 | 31-1700 | OG10 STOP WATER FROM BACKFLOWING INTO SITE | 3
44500 | 44496 | 31-1700 | SG7 SETUP PUMPS | 3
44500 | 44496 | 03-2300 | SG6 THRUST BLOCK | 22.5
44500 | 44496 | 03-1000 | SG6 LOAD FORMS & DELIVER TO SITE 8 | 25
44500 | 44496 | 99-4560 | SG6 CLEAN UP FOR CRANE/1ST AND 2ND FLOOR | 22
44500 | 44496 | 03-1300 | OG8 PREP FOR BOLT PATTERNS | 9
44500 | 44496 | 03-1000 | OG9 PUT SHOE DOWN FOR GRADE BEAM | 21
44500 | 44496 | 03-1300 | OG8 START BOLT, PATTERN ON 2 FOOITINGS | 6.5
44500 | 44496 | 03-1000 | SG6 PREP PLUMBING SHAFT FOR STEAMFITTEERS | 6
44500 | 44496 | 03-1300 | OG9 FIX BOLT PATT | 9
44500 | 44496 | 31-1700 | Jump Pumps | 1
44500 | 44497 | 32-6520 | SG6 ASSIST CRANE OPERATION- MOVE FENCE/FLAGING | 19.5
44500 | 44497 | 03-2300 | SG6 POUR 3 EA THRUST BLOCKS | 4
44500 | 44497 | 02-6005 | OG3 PAINT REMOVAL | 17
44500 | 44497 | 03-1000 | OG9 UNLOAD FORMS AND LUMBER | 2
44500 | 44497 | 99-4000 | OG5 RAMP RECONFIG - POUR CONCRETE | 22
44500 | 44497 | 03-1000 | SG6 CLEAN PLUMBING SHAFT REMOVE WATER AND MUD | 9
44500 | 44497 | 32-6520 | SG3/SG2 ASSIST ATLAS INSTALL FENCE | 8
44500 | 44497 | 03-1700 | OG8 UNLOAD REBAR TRAILER | 11
44500 | 44497 | 31-2200 | OG9 BACKFILL | 24
44500 | 44497 | 02-3000 | DISCOVER LENTIL @OG4 BUILDING | 6
44500 | 44497 | 31-2000 | HAND DIG FOR ASBESTOS TESTING SG7 AND S8 | 4
44500 | 44497 | 03-2300 | SG6 THRUST BLOCKS (FORM) | 28
44500 | 44497 | 03-1000 | OG9 START FORMING GRADE BEAM | 74.5
44500 | 44497 | 03-1000 | GATHER UP FORMS TO BRING TO OG9 | 20.5
44500 | 44497 | 33-3100 | OG10 LOAD OUT TRUCKS | 6
44500 | 44497 | 31-1700 | Jump Pumps | 1
44500 | 44498 | 31-2200 | SG4 BACKFILL ENCASED DUCTBANK/EXCAVATE BOND BEAM | 13.5
44500 | 44498 | 33-3100 | SG6 CLEAN PLUMBING SHAFT - CLEAN TRENCH | 11
44500 | 44498 | 03-1900 | SG6 PATCH TIE HOLES IN SHAFT | 9
44500 | 44498 | 02-6005 | OG3 PAINT REMOVAL | 17
44500 | 44498 | 02-2300 | OG5 CLEAN BASEMENT FOR ATCO | 11
44500 | 44498 | 99-4000 | OG5 RAMP RECONFIG - FINISH CHOPPING CONCRETE WALL | 9
44500 | 44498 | 99-4560 | CLEAN ALL SIES | 18
44500 | 44498 | 32-6520 | SG3/SG6 ASSIST ATLAS INSTALL FENCE | 9
44500 | 44498 | 33-3100 | OG9 CHOP OUT THRUST BLOCK FOR PLUMBING | 20
44500 | 44498 | 31-1400 | OG9 BACKFILL TO GRADE/PREP FOR CONCRETE PUMP | 10
44500 | 44498 | 31-1700 | OG8/SG7 COLLECT PUMPS | 7
44500 | 44498 | 33-3100 | OG8 EXC FOR FIVE STAR ELECTRICAL TRENCH | 4.5
44500 | 44498 | 31-1700 | JUMP PUMPS | 1
44500 | 44498 | 03-2300 | SG6 THRUST BLOCKS (3) | 24
44500 | 44498 | 03-1000 | OG9 FORM GBS | 41
44500 | 44498 | 03-1300 | OG9 SET ANCHOR BOLTS (40 bolts) | 40
44500 | 44498 | 03-1000 | OG9 SITE MAINTNENANCE | 8
44493 | 44487 | 02-2300 | SG4 INSTALL DRAINAGE TARP | 2
44493 | 44487 | 31-1000 | SG5 EXCAVATE FOR BOND BEAM | 10.5
44493 | 44487 | 33-2900 | SG6 REMOVE MH "PARTIAL" | 5
44493 | 44487 | 02-6005 | OG3 PAINT REMOVAL | 17
44493 | 44487 | 03-2300 | OG9 POUR CONDUIT ENCASEMENT | 6
44493 | 44487 | 31-2200 | OG9 BACKFILL AND PREP FOR POUR CONDUIT | 8.5
44493 | 44487 | 03-2100 | SG2/OG2 BUSH HAMMER/INSTALL EXPANSION BOLTS/EQUIPMENT PADS | 13
44493 | 44487 | 31-2000 | OG3 EXPOSE SIDE MH FOR FSE | 14.5
44493 | 44487 | 03-1000 | SG6 MOVE MATERIAL FOR CARPENTERS FROM OG9 AND SG7 | 2
44493 | 44487 | 99-4560 | OG9 LOAD ELECTRICAL PIPE AND UNLOAD FROM FIVE STAR YARD | 2
44493 | 44487 | 33-6010 | OG10 ASSIST WELKIN WIT PIPE | 12
44493 | 44487 | 03-2300 | OG10 POUR 6CY DUCT BANK | 3
44493 | 44487 | 32-6520 | OG8 RELOCATE FENCE AT 33RD ST | 14
44493 | 44487 | 31-1400 | SG7 INSTALL FOAM & backfill | 12.5
44493 | 44487 | 31-1700 | jump pumps | 1
44493 | 44487 | 03-1000 | SG6 FORM COLUMNS | 24
44493 | 44487 | 03-1000 | SG6 FORM PADS | 21
44493 | 44487 | 03-1000 | SG6 STRIP PLUMBING SHAFT | 36.5
44493 | 44487 | 03-1000 | SG6 SITE MAINTENANCE | 8
44493 | 44487 | 03-1400 | OG9 DRILL DOWELS IN ON PLUMBING SHAFT | 7
44493 | 44487 | 33-3100 | OG9 SHORE EXCAVATION | 4
44493 | 44487 | 31-1820 | OG10 BURN SHEETS | 3
44493 | 44487 | 03-2300 | OG10 DUCT BANK | 11
44493 | 44487 | 03-1000 | OG10 START PLUMBING SHAFT | 8
44493 | 44487 | 03-1000 | GATHER MATERIAL FOR SG6 | 5
44493 | 44488 | 03-2100 | SG2/OG2 POUR PADS | 14
44493 | 44488 | 31-1000 | SG5 EXC FOR BOND BEAM/MOVE DIRT | 13
44493 | 44488 | 33-3100 | SG6 EXC MEP TRENCH | 9
44493 | 44488 | 03-1900 | SG6 BUSH/DRILL DOWELS FOR EQUIP PAD | 17.5
44493 | 44488 | 02-2300 | SG4 REMOVE DEBRIS FOR ELECTRICIANS/CLEAN BASEMENT | 13
44493 | 44488 | 02-2300 | SG5 REMOVE WATER FROM BASEMENT | 5
44493 | 44488 | 31-1400 | OG9 BACKFILL/BOTTOM GRADE BEAMS/SLAB PIPING LOAD MATERIAL FROM OG10 TO OG9 HNS TRUCK | 13
44493 | 44488 | 33-6010 | OG10 MOVE PIPE FOR WELKIN | 11.5
44493 | 44488 | 33-3100 | OG8 EXC TO LOCATE MEP 33RD ST TO SG5 | 30
44493 | 44488 | 03-1000 | SG6 SITE MAINTENANCE | 8
44493 | 44488 | 03-1000 | SG6 FORM COLUMNS | 84
44493 | 44488 | 03-1000 | SG6 EQIP PADS 2ND FLOOR | 28
44493 | 44488 | 03-1000 | GATHER MATERIAL TO COMPLETE SG6 | 9
44493 | 44488 | 31-1700 | JUMP PUMPS | 1
44493 | 44488 | 33-2900 | SG6 REMOVE MH/PLUG PIPE ENDS | 4
44493 | 44489 | 00-0014 | SG4/SG5 DEMO CMU FOR STEEL INSTALL/1ST FLOOR | 13
44493 | 44489 | 33-3100 | SG6 PATCH TIE HOLES/CUT THRI CONRETE BLOCK FOR WATER CROSSING | 9
44493 | 44489 | 02-2300 | SG5 PUMP OUT WATER/CLEAN GARBAGE FROM BASEMENT | 21
44493 | 44489 | 31-1000 | SG5 EXCAVATE FOR BOND BEAM | 9
44493 | 44489 | 32-6610 | SITE 8 DEMO AREA/FILL CONTAINER-STEEL LOAD OUT /PREP TO RECEIVEE DELIVERIES | 22.5
44493 | 44489 | 31-1400 | OG9 BACKFILL IN SLAB PIPING | 3
44493 | 44489 | 02-6015 | OG3 REMOVE WINDOWS/DRILL AND DOWEL FOR WINDOW INFILL | 9
44493 | 44489 | 33-6010 | SG6 MOVE SAND BAGS FOR PLUMBERS FROM OG10 O SG6 | 2
44493 | 44489 | 03-1700 | OG10 LOAD & MOVE REBAR TO OG9 | 11.5
44493 | 44489 | 33-3100 | OG8 EXC TO EXPOSE D BANK AND PLUMBIN G/STEAM | 20
44493 | 44489 | 33-3100 | OG8 EXC FOR ELECETRCIAL DB | 10
44493 | 44489 | 03-1000 | SG6 CLOSE UP COLUMNS | 46
44493 | 44489 | 03-1900 | SG6 BUILD SCAFFOLD FOR CONCRETE POUR | 22.5
44493 | 44489 | 03-1000 | SG6 BUILD COLUMN WOOD FORMS | 11
44493 | 44489 | 03-1000 | SG6 SITE MAINTENANCE | 8
44493 | 44489 | 99-4560 | SEABOX FOR 5STAR | 12.5
44493 | 44489 | 03-1000 | GATHER MATERIAL TO BRING TO SG6 | 17
44493 | 44489 | 03-1000 | OG8 PREP FOOTINGS | 4
44493 | 44489 | 31-1700 | JUMP PUMPS | 1
44493 | 44490 | 03-1900 | SG6 POUR COLUMNS AND EQUIPMENT PADS - 1ST FLOOR | 35.5
44493 | 44490 | 02-6005 | OG3 PAINT REMOVAL | 1
44493 | 44490 | 00-0015 | SG5 DEMO MORE CMU FOR STEEL INSTALL - 1ST FLOOR | 17
44493 | 44490 | 03-1900 | SG6 PATCH TIE HOLES | 9
44493 | 44490 | 03-2300 | SG4 BLOCK OUT AT MANHOLE/DUCTBANK TOCONCRETE POUR | 3
44493 | 44490 | 32-6610 | S8 DEMO AREA/PREP TO RECEIVE DELIVERIES | 2
44493 | 44490 | 05-6010 | S8 STEEL DELIVERY | 6.5
44493 | 44490 | 32-6610 | S8 DEMO/CLEANUP | 23
44493 | 44490 | 31-2000 | OG5 EXPOSE CONDUIT FOR 5 STAR | 13
44493 | 44490 | 03-2300 | OG10 POUR 11CY DBANK | 10
44493 | 44490 | 03-1000 | OG9 PREP FOR FORMS & POUR | 11
44493 | 44490 | 03-1900 | CONCRETE PUMP/FLAGGER SGN | 8
44493 | 44490 | 33-6010 | MOVE PIPE FOR WELKIN | 2
44493 | 44490 | 03-1100 | SG2 STRIP EQUIPMENT PADS | 1.5
44493 | 44490 | 03-1100 | OG2 STRIP EQUIPMENT PADS | 1.5
44493 | 44490 | 03-2300 | SG4 FORM DUCTBANK | 11
44493 | 44490 | 03-1900 | SG6 POUR COLUMNS & EQUIPMENT PADS ON 2ND FLOOR | 12
44493 | 44490 | 03-1000 | SG6 STRIP PLUMBING SHAFT | 19
44493 | 44490 | 03-1000 | SG6 SITE MAINTENANCE | 8
44493 | 44490 | 03-2300 | OG9 FORM DUCT BANK | 18
44493 | 44490 | 03-1000 | OG9 SITE MAINTENANCE | 8
44493 | 44490 | 03-1000 | OG10 FORMING PLUMBING SHAFT | 13
44493 | 44490 | 03-1000 | OG10 SITE MAINTENANCE | 8
44493 | 44490 | 99-4560 | FINISH 5STAR SEABOX | 13
44493 | 44490 | 31-1700 | jump pumps | 1
44493 | 44491 | 03-2100 | SG2/OG2 WATER PROOF EQUIPMENT PADS | 5
44493 | 44491 | 02-6005 | OG3 PAINT REMOVAL | 17
44493 | 44491 | 02-2300 | OG4 CEAN DRAIN IN TANKROOM | 2
44493 | 44491 | 31-2200 | SG4 BACKFILL/PREP FOR POUR DUCT BANKS | 6
44493 | 44491 | 02-2300 | S8 INTALL PUMP IN BASEMENT/REMOVE AFTER | 5
44493 | 44491 | 03-1000 | SG6 LOAD OUT FORMS | 3
44493 | 44491 | 32-6610 | S8 LOAD OUT 4 CONTAINERS LIVE LOAD CONCRETE INSTALL WHITE MESH ON FENCE/DEMO AREA | 22.5
44493 | 44491 | 99-4560 | OG10/OG8/SG6 CLEAN SITES | 19
44493 | 44491 | 03-1000 | OG10 MOVE FORMS | 2
44493 | 44491 | 03-1900 | SG6 PATCH TIE HOLES | 7
44493 | 44491 | 03-2300 | OG9 SETUP POUR DUCTBANK 33CY | 15.5
44493 | 44491 | 31-2200 | OG8 BACKFILL FOR PLUMBING | 15
44493 | 44491 | 33-3100 | OG8 CHOP OUT EXT CONCRETE AT OG6 BUILDING | 2
44493 | 44491 | 99-4560 | OG8 SET PIPE FOR 5 STAR | 1
44493 | 44491 | 32-6610 | S8 SET TRAILERS X2 SLED | 2
44493 | 44491 | 31-2200 | OG8 BACKFILL | 6
44493 | 44491 | 03-1000 | SG6 STRIP COLUMNS | 36
44493 | 44491 | 03-1000 | SG6 LOAD OUT FORMS | 9.5
44493 | 44491 | 03-1000 | SG6 SITE MAINTENANCW | 8
44493 | 44491 | 03-1000 | OG9 FORM GRADE BEAMS | 18
44493 | 44491 | 03-1000 | OG9 SITE MIANTENANCE | 8
44493 | 44491 | 03-1000 | OG10 FORM SINSIDE PLUMBING SHAFT | 18
44493 | 44491 | 03-1000 | OG10 SITE MAINTENANCE | 8
44493 | 44491 | 03-1000 | GATHER AND DEIVERY MATERIAL | 11.5
44493 | 44491 | 31-1700 | JUMP PUMPS | 1
44486 | 44480 | 02-2300 | OG3 CLEAN BASEMENT/PREP FOR PAINT REMOVAL | 17
44486 | 44480 | 32-6520 | OG5 INSTALL FENCE FOR UPCOMING UTILITY WORK | 25
44486 | 44480 | 33-3100 | OG9 DEMO REMAINING AREAWAY/EXCAVATE FOR CONDUIT RUN 2 TRUCKS LOAD OUT | 26.5
44486 | 44480 | 99-4560 | OG9 CLEAN SITE/MOVE GARBAGE TO CONTAINER SG4 | 4
44486 | 44480 | 33-3100 | OG9 EXC/LOADOUT (10) TRUCKLOADS FOR MEP | 18
44486 | 44480 | 33-3100 | OG9 EXC ELECTRICAL TRENCHES | 8
44486 | 44480 | 31-1400 | OG8 PREP FOR FLOW FILL | 10.5
44486 | 44480 | 33-6010 | OG8 ASSIST WELKIN WITH PIPES/PUMPS | 9
44486 | 44480 | 99-4560 | OG9 MOVE GARBAGE/DEBIRS TO SGN | 4
44486 | 44480 | 03-1000 | SG6 FINISH CLOSE UP ON PLUMBING SHAFT | 13
44486 | 44480 | 03-1000 | SG6 START STRIPPING TANK WALLS | 60
44486 | 44480 | 03-1000 | SG6 SITE MAINTENANCE | 8
44486 | 44480 | 03-1000 | SG7 START STRIPPING PLUMBING SHAFT + PIERS | 24
44486 | 44480 | 03-1000 | SG7 SITE MAINTENANCE | 8
44486 | 44480 | 31-1700 | JUMP PUMPS | 1
44486 | 44481 | 02-1900 | REMOVE/LOADOUT ASPHALT OG10 | 15
44486 | 44481 | 33-3100 | EXC FOR MEP OG10 LOADOUT (10 TRUCKS) | 19.5
44486 | 44481 | 31-1400 | OG8 PREP FOR FLOW FILL | 7
44486 | 44481 | 03-1000 | SG7 ASSIST CARP/FORMWORK | 8
44486 | 44481 | 03-1000 | SGN ASSIST CARP FORMWORK | 8
44486 | 44481 | 03-1000 | SG6 STRIP TANK WALLS | 38
44486 | 44481 | 03-1900 | SG6 PATCH 2ND FLOOR DECK FOR POUR | 8
44486 | 44481 | 03-1000 | SG6 SITE MAINTENANCE | 8
44486 | 44481 | 03-1000 | SG6 MOVE ALL FORMS SO PUMP CAN FIT ON SITE | 2.5
44486 | 44481 | 03-1000 | SG7 TAKE FORMS OUT OF HOLE PREPARE FOR FLOW FILL | 28
44486 | 44481 | 03-1000 | OG8 PUT IN ALL BULKHEADS FOR FLOW FILL | 18
44486 | 44481 | 31-1820 | BURN SHEETS & H BEAMS OG9 | 11.5
44486 | 44481 | 33-3100 | OG9 CREATE WALKWAY FOR STAND PIPE | 7
44486 | 44481 | 02-6005 | OG3 PAINT REMOVAL | 17
44486 | 44481 | 32-6520 | OG5 COMPLETE FENCE FOR UPCOMING UTILITY WORK | 19
44486 | 44481 | 32-6520 | OG10 REMOVE EXISTING FENCE | 7
44486 | 44481 | 32-6520 | OG9 REMOVE FENCE FOR EXCAVATION/PUT BACK FENCE AFTER EXC. | 7
44486 | 44481 | 33-3100 | OG9 1 20 YD LIVE LOAD CONT/ EXCAVATE FOR CONDUIT RUN | 17.5
44486 | 44481 | 33-6000 | OG10 PIPE DELIVERY | 5
44486 | 44481 | 31-1700 | Jump Pumps | 1
44486 | 44482 | 31-1400 | OG8 SETUP AND POUR 136 CY OF FLOW FILL | 18.5
44486 | 44482 | 99-4560 | OG8 FLAG FOR SGN TRUCK WASHOUT | 6
44486 | 44482 | 03-1000 | OG9 ASSIST CARP MOVE FORMS | 8
44486 | 44482 | 02-1900 | OG10 REMOVE/LOADOUT ASPHALT | 11
44486 | 44482 | 33-3100 | OG10 EXC FOR MEP/LOADOUT | 11
44486 | 44482 | 32-6520 | OG5 REMOVE FENCING & PREP FOR TEST PIT | 9.5
44486 | 44482 | 03-1000 | SG7 ASSIST CARP WITH FORMWORK REMOVAL | 9
44486 | 44482 | 03-1000 | SG6 STRIP TANK WALLS | 36
44486 | 44482 | 03-1000 | SG6 SITE MAINTENANCE | 8
44486 | 44482 | 03-1000 | SG7 FINISH TAKING FORMS OUT OF HOLE | 12
44486 | 44482 | 03-1000 | OG9 START FORMING GRADE BEAMS | 26
44486 | 44482 | 31-1820 | OG9 BURN PILES | 2
44486 | 44482 | 03-1000 | OG10 START DUMMY DECK | 14.5
44486 | 44482 | 31-1820 | OG10 BURN SHEETS | 14.5
44486 | 44482 | 03-1000 | SG7 SITE MAINTENANCE | 8
44486 | 44482 | 31-1700 | JUMP PUMPS | 1
44486 | 44482 | 03-1900 | SG6 POUR SHAFT WALLS AND 2ND FLOOR SLAB | 31
44486 | 44482 | 02-6005 | OG3 PAINT REMOAL | 17.5
44486 | 44482 | 02-6015 | OG3 REMOVE WINDOWS | 6.5
44486 | 44482 | 31-2200 | SG5 BACKFILL ELECTRIC TRENCH | 4
44486 | 44482 | 03-1900 | SG6 POUR 2ND FLOOR SLAB | 45
44486 | 44482 | 03-1500 | OG3 DRILL AND DOWEL FOR WINDOW INFILL | 6.5
44486 | 44483 | 02-2300 | SG2 CLEAN BASEMENT/MOVE GARBAGE CONTAINER | 18
44486 | 44483 | 02-2300 | SG5 SETUP PUMPS AND HOSES/REMOVE WATER FROM BASEMENT | 13
44486 | 44483 | 03-1000 | SG6 MOVE FORMS FOR CARPENTERS/CLEAN ENTIRE AREA | 15
44486 | 44483 | 31-2200 | SG5 FINISH BACKFILL ELECTRICAL TRENCH | 7
44486 | 44483 | 33-3100 | OG5 EXPOSE BURIED CONDUITS/ ELECTRIC | 12
44486 | 44483 | 31-1400 | SG6 BACKFILL AROUND BLDG | 9.5
44486 | 44483 | 03-1500 | OG3 REMOVE WINDOWS/DRILL AND DOWEL FOR WINDOW INFILL | 5
44486 | 44483 | 99-4560 | OG9 PICKUP GAS PIPE FROM NATIONAL GRID | 3
44486 | 44483 | 33-3100 | OG10 EXC FOR MEP | 18
44486 | 44483 | 33-6010 | OG9 ASSIST WELKIN WITH PIPE MOVING | 9
44486 | 44483 | 07-1100 | SG7 INSTALL NAILS FOR FOAM INSULATION | 8
44486 | 44483 | 31-1400 | OG8 BACKFILL & PREP FOR FOOTING FORMING | 6.5
44486 | 44483 | 03-1000 | SG6 STRIP TANK WALLS | 46
44486 | 44483 | 03-1000 | SG6 SITE MAINTENANCE | 8
44486 | 44483 | 03-2300 | OG9 DUCT BANK | 22
44486 | 44483 | 03-1000 | OG10 DUMMY DECK | 13
44486 | 44483 | 03-2300 | OG10 DUCT BANK | 19
44486 | 44483 | 02-6060 | SG6 SAFETY NETTING 2ND FLOOR | 4
44486 | 44483 | 31-1820 | BRUN SHEETS @ MULTIPLE SITES | 17
44486 | 44483 | 31-1700 | JUMP PUMPS | 1
44486 | 44483 | 99-4560 | SG6 CLEAN ENTIRE AREA/20 YD CONTAINER TO BE DROPPED | 10
44486 | 44483 | 32-6510 | OG5 - INSTALL WHITE MESH FENCE | 4
44486 | 44484 | 07-1100 | SG7 INSTALL FOAM | 10
44486 | 44484 | 31-1400 | SG7 BACKFILL | 10
44486 | 44484 | 31-1300 | OG8 EXC FOR FOOTINGS AND WALLS | 14
44486 | 44484 | 33-6010 | MOVE PIPE FOR WELKIN | 7.5
44486 | 44484 | 02-6005 | OG3 PAINT REMOVAL | 17.5
44486 | 44484 | 03-1500 | OG3 REMOVE WINDOWS/DRILL & DOWEL FOR WINDOW INFILL | 25
44486 | 44484 | 03-1000 | SG6 LOAD OUT FORMS TO TRAILER | 10.5
44486 | 44484 | 99-4560 | SG6 LOAD OUT CONTAINER CONCRETE | 5.5
44486 | 44484 | 99-4560 | SGN 1 CONTAINER PICKUP/1 SKID OF SIKA TO UNLOAD | 1
44486 | 44484 | 33-2600 | SG6 RECEIVE DRAINAGE MHS | 8
44486 | 44484 | 33-2600 | S8 RECEIVE DRAINAGE MHS | 11.5
44486 | 44484 | 99-4560 | SG6 MOVE CONCRETE PILE/CLEAN SITE | 10
44486 | 44484 | 31-1700 | JUMP PUMPS | 1
44486 | 44484 | 03-1100 | SG2 EQUIPMENT PADS FOR WELKIN | 6
44486 | 44484 | 03-1100 | OG2 EQUIPMENT PADS FOR WELKIN | 6
44486 | 44484 | 02-6060 | SG6 SAFETY NETTING 2ND FLOOR | 11
44486 | 44484 | 03-1000 | SG6 STRIP PLUMBING SHAFT | 51.5
44486 | 44484 | 03-1000 | SG6 SHIPPED OUT FORMS | 9
44486 | 44484 | 03-2300 | OG9 DUCT BANK | 17
44486 | 44484 | 03-2300 | OG10 DUCT BANK | 15
44486 | 44484 | 03-1000 | SG6 SITE MAINTENANCE | 8
44486 | 44484 | 31-1820 | BURN SHEETS | 9.5
44479 | 44473 | 02-2300 | S8 BASEMENT CLEANUP | 5.5
44479 | 44473 | 02-6005 | LEAD PAINT REMOVAL/PREP OG3 BASEMENT | 14.5
44479 | 44473 | 02-1900 | OG10 REMOVE ASPHALT/LOADOUT | 13.5
44479 | 44473 | 31-1700 | ASSIST TONAGE SGN | 10.5
44479 | 44473 | 02-6009 | ELEVATOR PAINT REMOVAL OG5 | 7
44479 | 44473 | 02-3000 | CORE DRILL SG4 GAS VENTS | 7.5
44479 | 44473 | 33-3100 | OG8 EXC AROUND UTILITIES FOR MEP | 19.5
44479 | 44473 | 33-6010 | OG8 ASSIST WELKIN | 9.5
44479 | 44473 | 33-3100 | OG8 LOADOUT 5 LOADS | 10.5
44479 | 44473 | 33-3100 | OG9 LOADOUT 8 LOADS | 14
44479 | 44473 | 31-1400 | OG9 BACKFILL | 11
44479 | 44473 | 07-1100 | OG9 INSTALL INSULATION AROUND SHAFT | 3
44479 | 44473 | 02-6009 | PREP & MOVE MATERIAL FOR LEAD REMOVAL | 1.5
44479 | 44473 | 03-1000 | SG6 FORM TANK WALLS | 51.5
44479 | 44473 | 03-1400 | SG6 DRILL DOWELS FOR PLUMBING | 4.5
44479 | 44473 | 03-1000 | SG6 SITE MAINTNENACE | 8.5
44479 | 44473 | 03-1000 | SG7 CLOSE UP PLUMBING WALL & PIERS | 39
44479 | 44473 | 03-1000 | SG7 SITE MAINTNENACE | 8
44479 | 44473 | 31-1820 | BURN SHEETS OG8, OG9L AND OG10 | 19.5
44479 | 44473 | 31-1700 | Jump Pumps | 1
44479 | 44474 | 03-1400 | SG4 DRILL AND DOWEL FOR WINDOW INFILL | 5
44479 | 44474 | 02-6005 | OG3 PREP FOR AINT REMOVAL | 17
44479 | 44474 | 02-6009 | OG5 ELEVATOR PIT PAINT REMOVAL | 2
44479 | 44474 | 32-6520 | OG5 FENCE INSTALL FOR UTILITY WORK | 6
44479 | 44474 | 32-6520 | OG10 FENCE INSTALL FOR UTILITY WORK TO OG1 | 6
44479 | 44474 | 33-3100 | OG9 EXCAVATE FOR CONDUIT RUNS/ 6 TRUCKS X2 ROUNDS LOAD OUT | 27.5
44479 | 44474 | 31-1820 | OG10 CUT SHEETS/SUPPORT WITH EXCAVATOR | 9
44479 | 44474 | 33-3100 | og8 exc/loadout for mep | 30
44479 | 44474 | 33-6010 | OG10 ASSIST WELKIN WITH PIPE DELIVERY | 13
44479 | 44474 | 03-1900 | SG7 SETUP AND POUR 40 CYS OF SHAFT | 25
44479 | 44474 | 31-1820 | BURN SHEETS OG8/OG9/OG10 | 14
44479 | 44474 | 03-1000 | SG6 FORM TANK WALLS/MAKUP | 79.5
44479 | 44474 | 03-1000 | SG6 SITE MAINTENANCE | 8
44479 | 44474 | 03-1300 | SG7 SET ANCHOR BOLTS | 8
44479 | 44474 | 03-1000 | SG7 FINISHING CLOSE UP | 9
44479 | 44474 | 03-1000 | SG7 SITE MAINTENNACE | 8
44479 | 44474 | 03-1900 | SG7 CONCRETE POUR | 2.5
44479 | 44474 | 31-1700 | Jump Pumps | 2.5
44479 | 44475 | 03-1900 | SG6 PREP COLUMN BASES | 9
44479 | 44475 | 02-6005 | OG3 PAINT REMOVAL | 17.5
44479 | 44475 | 33-3100 | OG9 EXCAVATE FOR CONDUIT RUNS AND LOAD OUT 13 TRUCKS | 22
44479 | 44475 | 03-2300 | OG9 MOVE FORMS FOR 2ND CONDUIT TRENCH | 7.5
44479 | 44475 | 32-6520 | OG10 CLOSE FENCE TO OG1 | 9.5
44479 | 44475 | 99-4560 | SG6 SITE CLEAN | 9.5
44479 | 44475 | 33-3100 | OG10 EXC/LOADOUT FOR MEP (8) LOADS | 24.5
44479 | 44475 | 33-3100 | OG10 LOADOUT (5) LOADS (Stockpile) | 10.5
44479 | 44475 | 33-6010 | OG8 MOVE PIPE FOR WELKIN/TRENCH | 9.5
44479 | 44475 | 31-1820 | FIRE WATCH FOR BURNING SHEETS OG10 | 6.5
44479 | 44475 | 03-1000 | MOVE FORMS FROM OG10 TO OG6 | 5.5
44479 | 44475 | 99-4560 | LOADOUT STEEL FROM OG9/10 TO SG1 SCRAP CONT. | 4.5
44479 | 44475 | 03-1000 | UNLOAD LUMBER DELIVERY @OG8 | 8
44479 | 44475 | 31-1820 | BURN SHEETS OG10 | 7.5
44479 | 44475 | 33-3100 | OG8 SHORING UP EXCAVATION | 3.5
44479 | 44475 | 03-1000 | SG6 CLOSE UP TANK WALLS | 86.5
44479 | 44475 | 03-1000 | SG6 SITE MAINTENANCE | 8.5
44479 | 44475 | 03-1000 | OG10 SITE MAINTENANCE | 8.5
44479 | 44475 | 99-7200 | PTO | 8
44479 | 44476 | 02-6005 | OG3 PAINT REMOVAL | 17
44479 | 44476 | 33-3100 | OG9 EXCAVATE FOR 2 CONDUIT RUNS AND LOAD OUT | 29.5
44479 | 44476 | 32-6510 | OG9 INSTALL WHITE MESH ON FENCE | 7
44479 | 44476 | 32-6520 | OG10 CLOSE FENCE TO OG1 | 19
44479 | 44476 | 33-3100 | OG8 EXC/LOADOUT FOR MEP (4) LOADS | 20
44479 | 44476 | 33-3100 | OG10 LOADOUT (8) LOADS | 20
44479 | 44476 | 33-3100 | OG10 EXC FOR MEP | 10
44479 | 44476 | 99-4560 | OG10 LOADOUT 1 STEEL DUMPSTER | 9
44479 | 44476 | 33-3100 | OG9 PREP MEP TRENCH | 4
44479 | 44476 | 33-3100 | UTILITY TRENCH @ OG10 FOR 5 STAR | 2.5
44479 | 44476 | 03-1000 | SG6 CLOSE UP TANK WALLS/PLUMBING SHAFT | 96
44479 | 44476 | 03-1900 | SG6 BURN HOLES IN DECK TO POUR | 4.5
44479 | 44476 | 03-1900 | SG6 DRILL HOLES IN DECK TO ALLOW DOWELS TO GO INTO WALLS | 4
44479 | 44476 | 03-1000 | SG6 SITE MAINTENANCE | 8
44479 | 44476 | 99-7200 | PTO | 8
44479 | 44477 | 02-6005 | OG3 PAINT REMOVAL | 17.5
44479 | 44477 | 32-6520 | OG5 INSTAL FENCE FOR UPCOMING UTILITY WORK | 6.5
44479 | 44477 | 03-1900 | SG6 POUR CONCRETE AT INTERIOR WALLS/COLUMN BASES | 60.5
44479 | 44477 | 33-3100 | OG9 EXC FOR STEAM/WATER | 22
44479 | 44477 | 33-3100 | OG9 DEMO AREAWAY/LOAD OUT DEBRIS | 19
44479 | 44477 | 02-1900 | OG10 EXC ELECTICAL TO OG1 REMOVE BLACK TOP | 10
44479 | 44477 | 99-4560 | OG10 LOADOUT 2 TRUCKS + CARDELLA | 10.5
44479 | 44477 | 33-6010 | MOVE PIPE FOR WELKIN | 6
44479 | 44477 | 03-1000 | SG6 FINISH TANK WALLS | 33
44479 | 44477 | 03-1900 | SG6 WATCH CONCRETE | 17.5
44479 | 44477 | 03-1000 | SG6 FORM PLUMBING SHAFT | 31
44479 | 44477 | 03-1000 | SG6 SITE MAINTENANCE | 8
44479 | 44477 | 03-1000 | SG6 GATHER MATERIAL FOR CLOSEUP | 12
44472 | 44466 | 22-6025 | OG3 REMOVE PIPE INSULATION | 22
44472 | 44466 | 02-2300 | SG1 BASEMENT CLEANUP | 4
44472 | 44466 | 03-2300 | SG5 DUCTBANK POUR CONCRETE | 5
44472 | 44466 | 99-4000 | SG5 REMOVE YODOCKS FOR CNCRETE TRUCKS/REFIL WITH WATER | 2
44472 | 44466 | 03-1700 | SG6 REBAR DELIVERY FOR 2ND FLOOR | 5
44472 | 44466 | 99-4560 | OG2 DROP 20 YD CONT. | 1.5
44472 | 44466 | 03-2100 | SG5 POUR FLOOR DRAIN | 2
44472 | 44466 | 99-4560 | OG10 LULL DELIVERY | 1.5
44472 | 44466 | 33-3100 | SG6 STEAM/PLUMBING RUN EXACAVATION/SHOE TO GET PAST TREE | 19.5
44472 | 44466 | 99-4560 | SGN CLEAN SITE | 2
44472 | 44466 | 05-6030 | S8 (3) TRAILER DELIVERY | 10
44472 | 44466 | 31-2000 | S8 TEST PIT | 10
44472 | 44466 | 03-1900 | OG9 PREP AREA FOR CONCRETE PUMP | 9
44472 | 44466 | 33-3100 | OG10 EXC ELECTRICAL TRENCH | 9
44472 | 44466 | 07-1100 | OG10 INSTALL NAILS FOR INSUALTION | 7
44472 | 44466 | 03-1000 | OG10 ASSIST CARPS REMOVING FORMS | 9
44472 | 44466 | 31-1700 | OG10 INSTALL DRAIN SUMP PUMP | 3.5
44472 | 44466 | 03-2300 | SGN DUCT BANK & FOUNDATION PENETRATION FORMING | 13.5
44472 | 44466 | 33-3100 | SGN SHORING PIT | 7
44472 | 44466 | 03-1900 | SGN WATCH CONCRETE | 1
44472 | 44466 | 03-1000 | OG9 CLOSE UP PLUMBING SHAFT & PIERS | 88
44472 | 44466 | 03-1000 | OG9 SITE MAINTENANCE | 8
44472 | 44466 | 03-1000 | OG10 PULL FORMS OUT OF HOLE &PLUMBING SHAFT | 19.5
44472 | 44466 | 03-1000 | OG10 SITE MAINTENANCE | 8
44472 | 44466 | 31-1700 | Jump Pumps | 2
44472 | 44466 | 99-1000 | Supervision | 8
44472 | 44467 | 02-2300 | SG1 BASEMENT CLEANUP | 11
44472 | 44467 | 99-4560 | SG5/SGN CUT GRASS/CLEAN SITE | 6
44472 | 44467 | 03-1700 | OG10/SG6 UNLOAD REBAR | 10
44472 | 44467 | 02-6060 | OG5/OG4 LOAD OUT /APT DEMO | 35
44472 | 44467 | 33-3100 | SG6 MOVE PILE WITH BACKHOE/STEAM/PLUMBING RUN EXCAVATION/SHORE TO GET PAST TREE | 15.5
44472 | 44467 | 33-6000 | SG3 PARKING LOT UNLOAD SUBS WELKIN | 1.5
44472 | 44467 | 02-2300 | SG4 REMOVE LIFT FROM BASEMENT | 1.5
44472 | 44467 | 07-1100 | INSTALL INSULATION FOAM OG10 SHAFT | 4
44472 | 44467 | 03-1900 | SETUP & POUR OG9 PIERS/SHAFT (40 CY) | 12.5
44472 | 44467 | 33-3100 | OG8 EXC MEP TRENCHES & LOCATE EXISTING MEP | 31
44472 | 44467 | 31-1820 | ASSIST CARP RMEOVE SHEETS OG8 | 2
44472 | 44467 | 33-3100 | sgn bracing | 7.5
44472 | 44467 | 03-1000 | sg6 put up wall forms | 45
44472 | 44467 | 03-1000 | SG6 SITE MAINTENANCE | 8
44472 | 44467 | 31-1820 | OG8 BURNING SHEETS & BRACING | 12
44472 | 44467 | 03-1000 | OG9 FINISH CLOSE UP | 45.5
44472 | 44467 | 03-1300 | OG9 ANCHOR BOLT PATTERN (SET) | 4
44472 | 44467 | 03-1900 | OG9 POUR CONCRETE | 5
44472 | 44467 | 03-1000 | OG10 FINISH TAKING STUFF FRM HOLE | 10
44472 | 44467 | 03-1000 | OG10 SITE MAINTENANCE | 8
44472 | 44467 | 31-1700 | Jump Pumps | 2.5
44472 | 44468 | 02-6020 | SG4 DEMO ROLL UP GATE IN PERAMBULATOR ROOM | 5
44472 | 44468 | 02-6060 | OG1/OG2 2ND FLOOR APT. LOAD OUT | 34
44472 | 44468 | 02-2300 | OG2 REMOVE WATER/BASEMENT | 4
44472 | 44468 | 99-4560 | SG4 CLEAN SITE | 4
44472 | 44468 | 33-3100 | OG8 EXPOSE STEAM/PLUMBING AT GATE/BACKFILL | 1
44472 | 44468 | 31-1400 | OG10 BACKFILL AND COMPACT | 24.5
44472 | 44468 | 31-2000 | OG8 TEST PIT TO FIND ELECTRIC/STEAM/PLUMBING | 16.5
44472 | 44468 | 33-3100 | OG8 EXC FOR STEAM/ELEC | 10
44472 | 44468 | 32-6620 | OG8 SUPPORT ASPEN | 20
44472 | 44468 | 33-3100 | OG8 LOADOUT (10) TRUCKS | 10
44472 | 44468 | 33-6010 | OG8 SUPPORT WELKIN | 1
44472 | 44468 | 33-3100 | SGN SAFETY HANDRAIL AROUND OPEN PIT | 10
44472 | 44468 | 99-4560 | SG4 BUILD DOORWAY IN BASEMENT | 10
44472 | 44468 | 99-4560 | SG4 BUILD CONTAINMENT AROUND TEMP ELEC | 10.5
44472 | 44468 | 03-1000 | SG6 FORM WALL | 30
44472 | 44468 | 03-1000 | SG6 SITE MIANTENANCE | 8
44472 | 44468 | 03-1000 | OG9 STRIP FORMS | 45.5
44472 | 44468 | 03-1000 | OG9 SITE MAINTENANCE | 8
44472 | 44468 | 03-1000 | OG10 STACK AND BAND FORMS FOR PICKUP | 9
44472 | 44468 | 03-1000 | OG10 SITE MAINTENANCE | 8
44472 | 44468 | 03-1900 | SG7 WATERSTOP | 6
44472 | 44468 | 31-1700 | JUMP PUMPS | 2
44472 | 44469 | 02-6060 | SG3 LOAD OUT 2ND FLOOR APT | 28.5
44472 | 44469 | 02-2300 | OG2 REMOVE SEWER WATER/BASEMENT - 2" PUMP | 7
44472 | 44469 | 03-1000 | OG9 REMOVE ALL MATERIALS FROM HOLE - 2 HOURS/ | 7.5
44472 | 44469 | 31-1400 | OG9 BEGIN BACKFILL/COMPACT 2 HOURS | 8
44472 | 44469 | 31-1400 | OG10 BACKFILL AND COMPACT | 11
44472 | 44469 | 99-4000 | OG3 BLOCK PARKING SPACES/CONCRETE MAFIA BLOCKS | 4
44472 | 44469 | 33-6010 | OG9 TRANSPORT SAND BAGS FOR WELKIN TO OG8 | 4.5
44472 | 44469 | 33-3100 | OG8 EXC & LOADOUT (9) TRUCKS FOR MEP | 23.5
44472 | 44469 | 33-3100 | OG8 ORGANIZING PIPE AND REBAR FOR EXC | 10
44472 | 44469 | 99-4560 | OG8 LOADOUT TREE/STEEL | 15
44472 | 44469 | 33-6010 | ASSIST WELKIN WITH PIPE OG8 | 5
44472 | 44469 | 31-1700 | JUMP PUMPS | 2
44472 | 44469 | 33-3100 | EXCAVATION SAFETY CLASS | 7
44472 | 44469 | 99-4560 | SAFETY (FIRE EXTINGUISHER STANDS) | 8
44472 | 44469 | 03-1000 | OG10 LOAD OUT FORMS | 15
44472 | 44469 | 03-1000 | OG10 SITE MAINTENANCE | 8
44472 | 44469 | 03-1000 | OG9 SITE MAINTENANCE | 8
44472 | 44469 | 03-1900 | SG7 WATER STOP | 10
44472 | 44469 | 03-1000 | SG7 SITE MAINTENANCE | 8
44472 | 44469 | 03-1000 | SG6 FORM WALLS | 66
44472 | 44469 | 03-1000 | SG6 SITE MAINTENANCE | 8
44472 | 44469 | 00-0010 | ELECTRICAL SHED FOR SG4 | 15
44472 | 44469 | 99-1000 | Supervision | 8
44472 | 44470 | 33-3100 | OG8 MEP EXC | 21.5
44472 | 44470 | 33-3100 | OG8 LOADOUT (10 LOADS) | 12
44472 | 44470 | 31-1400 | OG8 BACKFILL FOOTING | 10
44472 | 44470 | 31-1300 | SAFETY CLASS WITH MIKE | 7
44472 | 44470 | 03-1000 | SG6 FORM TANK WALLS | 18
44472 | 44470 | 03-1000 | SG6 SETUP PLATFORM OFF OF PLUMBING SHAFT FOR LATHERS | 10
44472 | 44470 | 03-1000 | SG6 SITE MAINTENANCE | 8
44472 | 44470 | 03-1000 | SG7 FORM PLUMBING SHAFT | 28
44472 | 44470 | 03-1000 | SG7 SITE MAINTENANCE | 7
44472 | 44470 | 03-1000 | OG10 SITE MAINTENANCE | 8
44472 | 44470 | 31-1820 | CUT SHEETS OG9 & OG10 | 19
44472 | 44470 | 02-6015 | MAKE UP WINDOW CLOSURES FOR SG5 | 16
44472 | 44470 | 02-6065 | SG4 DEMO POKER FOR WELKIN IN PERAMBULATOR ROOM | 3
44472 | 44470 | 02-2300 | OG2 BASEMENT MAINTNENACE - CLEAN/PUMP OUT WATER/ BLEACH APPLY | 17
44472 | 44470 | 02-6060 | OG3 2ND FLOOR APT. LOADOUT/REMOVE BLOCK SPACES FROM STREET | 32
44472 | 44470 | 31-1400 | OG9 BACKFILL AND COMPACT | 7
44472 | 44470 | 31-1820 | OG9 CUT H PILES 3' BELOW | 7
44472 | 44470 | 33-3100 | OG10 20 YD SWAP CONTAINER GARBAGE/EXCAVATE TO CUT SHEETS TO ACCOMMODATE UTILITY/SLAB INSTALL | 14.5
44472 | 44470 | 31-1700 | JUMP PUMPS | 2
44465 | 44459 | 32-6520 | SG5 FENCE REMOVAL/INSTALL WHITE NETTING ON NEW TEMP WALKWAY | 10.5
44465 | 44459 | 03-1700 | SG6 BEND DOWN DOWELS FOR OIL TANK INSTALLATION | 2
44465 | 44459 | 03-1000 | SG6 CLEAN BLDG FORMS/LUMBER LEFT/CARP WORK | 10
44465 | 44459 | 33-3100 | SGN DISASSEMBLE TRENCH BOXES | 10
44465 | 44459 | 03-1000 | OG8 MOVE MATERIAL FOR CARP TO SG7 | 1
44465 | 44459 | 33-3100 | SG6 START TRENCH FOR STEAM/PLUMBING - CLEAN AREA/CHOP CONCRETE SIDEWALK - FILL ONE CONT. CONCRETE | 17
44465 | 44459 | 02-6060 | OG6 CLEAN APARTMEN AFTER DEMO | 23
44465 | 44459 | 03-1000 | SG7 UNLOAD FORMS & PLACE IN HOLE | 10
44465 | 44459 | 33-3100 | OG10 EXC ELEC TRENCH | 6
44465 | 44459 | 31-1400 | OG9 BACKFILL FOOTINGS | 5
44465 | 44459 | 33-3100 | OG9 EXC FOR PLUMBING TRENCH | 9
44465 | 44459 | 33-6000 | OG9 ASSIST WELKIN TRANSPORT PIPE | 4.5
44465 | 44459 | 32-6520 | OG3 INSTALL FENCE ON PEDESTRIAN RAMP/ REMOVE OLD ONE | 7
44465 | 44459 | 99-4560 | JOB CLEANUP/MAINTENANCE | 8
44465 | 44459 | 03-1000 | SG7 START FORM PLUMBING SHAFT | 20
44465 | 44459 | 03-1000 | SG7 SITE MAINTENANCE | 4.5
44465 | 44459 | 03-1000 | OG8 FORMING STEP FOOTING, TEMPLATES FOR LATHERS | 18
44465 | 44459 | 03-1000 | OG8 SITE MAINTENANCE | 12.5
44465 | 44459 | 03-1000 | OG9 FORMING PLUMBING SHAFT & PIERS | 44
44465 | 44459 | 03-1000 | OG10 FORM BEAM BOTTOMS, CONTINUE CLOSING UP PLUMBING SHAFT | 30
44465 | 44459 | 03-1000 | OG10 SITE MAINTENANCE | 2
44465 | 44459 | 03-1000 | OG9 SITE MAINTENANCE | 14
44465 | 44460 | 02-6060 | SG3 2ND FLOOR APARTMENT DEMO | 29.5
44465 | 44460 | 33-3100 | SG6 CARDELLA TO SWAP CONT. CONCRETE/ EXC TRENCH FOR STEAM/PLUMBING - 4 LOADOUTS | 19
44465 | 44460 | 99-4560 | SG6 OIL TANK DELIVERY - UNLOAD TANK FROM TRAILER | 5
44465 | 44460 | 99-4560 | SGN CLEAN SITE | 19
44465 | 44460 | 99-4560 | S8 MOVE MATERIAL FROM CBOX TO OFFICE | 3
44465 | 44460 | 99-4000 | SG6 REMOVE YODOCKS/PUT BACK AND FILL WITH WATER FOR OIL TANK DELIV | 2
44465 | 44460 | 99-4000 | INSTALL PLATES/NEW PICKUP TRUCK DUE NYC INSPECTION | 3
44465 | 44460 | 03-1900 | OG8 SETUP AND POUR 88CY FOOTINGS | 22
44465 | 44460 | 03-1000 | UNLOAD LUMBER OG10 | 3
44465 | 44460 | 33-3100 | EXC PLUMBING TRENCH OG9 | 10
44465 | 44460 | 33-6000 | OG8 PREP AREA FOR WELKIN DELIV | 7.5
44465 | 44460 | 99-4560 | JOB MAINTENANCE /UPKEEP | 4
44465 | 44460 | 07-1100 | GLUE NAILS FOR FOAM INSULATION OG8 PLUMBING SHAFT | 5
44465 | 44460 | 03-1000 | SG7 FORM PLUMBING SHAFT AND PIERS | 35
44465 | 44460 | 03-1000 | SG7 SITE MAINTENANCE | 9
44465 | 44460 | 03-1000 | OG8 FINISH FORM STEP FOOTINGS & BRACE IT | 7
44465 | 44460 | 03-1900 | OG8 CONCRETE POUR | 5
44465 | 44460 | 03-1000 | OG8 SITE MAINTENANCE | 11
44465 | 44460 | 03-1000 | OG9 FORM PLUMBING SHAFT & PIERS | 25
44465 | 44460 | 03-1000 | OG9 SITE MAINTENANCE | 9.5
44465 | 44460 | 03-1000 | OG10 FORM GBS + PIERS | 37
44465 | 44460 | 03-1000 | OG10 SITE MAINTENANCE | 8.5
44465 | 44460 | 03-1200 | Concrete pump operator | 19
44465 | 44461 | 02-6060 | SG3 2ND FLOOR APT DEMO | 25
44465 | 44461 | 33-3100 | SG6 3 TRUCKS X2 ROUNDS LOADING OUT CARDELLA/SWAP CONT./ (1) CARDELLA concrete/ total (2) | 13
44465 | 44461 | 99-4560 | SG6 MOVE MATERIAL CLOSE TO BLD, FORMS AND REBAR | 9.5
44465 | 44461 | 33-3100 | SG6 STEAM/PLUMN RUN EXCAVATION | 4
44465 | 44461 | 33-6010 | SG6 MOVE PLUMBING PIPES TO TRENCH | 4
44465 | 44461 | 99-4560 | OG8 MOVE MATERIAL OSHA PLANKS TO SG6 | 0.5
44465 | 44461 | 99-4560 | OG10 MOVE MATERIAL, PLYWOOD TO SG6 | 0.5
44465 | 44461 | 33-3100 | SGN PREP TRENCH BOXES MATERIAL FOR LOAD OUT, FILL CONT. GARBAGE FOR LOAD OUT | 10
44465 | 44461 | 31-1400 | FLOW FILL OG8 | 13.5
44465 | 44461 | 31-2000 | TEST PITS W VAC TRUCK SITE 8/OG3 | 21
44465 | 44461 | 31-1400 | BACKFILL OG9 | 6
44465 | 44461 | 07-1100 | OG8 INSTALL FOAM AROUND SHAFT | 4
44465 | 44461 | 33-6000 | WELKIN DELIVERY OG8 | 13
44465 | 44461 | 03-1000 | SG6 FORM PLUMBING HSAFT & START CLOSING TANK WALL | 37
44465 | 44461 | 03-1000 | SG6 SITE MAINTENANCE | 8
44465 | 44461 | 03-1000 | SG7 FINISH FORMING INSIDE PLUMBING SHAFT | 13
44465 | 44461 | 03-1000 | SG7 SITE MAINTENANCE | 8
44465 | 44461 | 03-1000 | OG8 STRIP FORMS | 20
44465 | 44461 | 03-1000 | OG8 SITE MAINTENANCE | 8
44465 | 44461 | 03-1000 | OG9 FORM PIERS | 8
44465 | 44461 | 03-1000 | OG10 FORM GRADE BEAMS & PIERS | 27
44465 | 44461 | 03-1000 | OG10 SITE MAINTENANCE | 8
44465 | 44461 | 03-1000 | REBAR INSPECTION | 3
44465 | 44462 | 02-6060 | SG3 2ND FLOOR APARTMENT DEMO | 27
44465 | 44462 | 33-3100 | SG6 - 4 TRUCKS X 2 (8 LOADOUTS) | 11.5
44465 | 44462 | 33-3100 | SG6 STEAM/PLUMBING EXC. | 10
44465 | 44462 | 02-6060 | SG4 REMOVE PILE FOR CARDELLA CONT./START LOADOUT 2ND FLOOR DEMO | 7
44465 | 44462 | 33-6010 | SG4 CLEAN AND MOVE MATRIAL FOR WELKIN INSTALL UG STEAM/PLUMBIGN | 7
44465 | 44462 | 33-3100 | SG6 FIX WASTE DRAIN PIPE | 2
44465 | 44462 | 33-2400 | SG6 INSTALL (2) 2" PUMPS TO REMOVE WATER FROM TRENCH | 3
44465 | 44462 | 03-1900 | OG10 SETUP AND POUR (50 CY) | 13
44465 | 44462 | 33-3100 | OG8 DIG OUT PLUMBING TRENCH | 14
44465 | 44462 | 31-1400 | OG9 LOADOUT HNS TRUCK TO OG8 FOR BACKFILL | 22.5
44465 | 44462 | 05-6030 | S8 BLOCKYARD/STREET FOR TRAILER DELIVERY | 11
44465 | 44462 | 03-1000 | SG6 CLOSE UP TANK WALL AND SET DOOR FRAMES | 32.5
44465 | 44462 | 03-1000 | SG6 STE MAINTENANCE | 8
44465 | 44462 | 03-1000 | OG8 BAND UP FORMS FOR REMOVAL /OG8 &OG10 | 30
44465 | 44462 | 03-1000 | OG8 SITE MAINTENANCE | 8
44465 | 44462 | 31-1820 | OG8 BURN SHEETS | 10
44465 | 44462 | 03-1900 | OG9 WATER STOP | 6
44465 | 44462 | 03-1000 | OG9 PREP FOR CLOSEUP | 6
44465 | 44462 | 03-1000 | OG9 SITE MAINTENANCE | 8
44465 | 44462 | 03-1300 | OG10 SET ANCHOR BOLTS | 9
44465 | 44462 | 03-1000 | OG10 FINISH CLOSE UP | 10
44465 | 44462 | 03-1900 | OG10 CONCRETE POUR | 5.5
44465 | 44462 | 03-1000 | OG10 SITE MAINTENANCE | 9
44465 | 44462 | 03-1000 | OG8 STRIP ANCHOR BOLTS | 3
44465 | 44462 | 03-1900 | Concrete pump operator | 19
44465 | 44463 | 02-6060 | SG4 LOADOUT 2ND FLOOR DEMO | 20
44465 | 44463 | 02-2300 | SG5 REMOVE WATER BASEMENT | 3
44465 | 44463 | 33-3100 | SG6 4 TRUCKS X 2 ROUNDS LOADING OUT (160 CY) | 11.5
44465 | 44463 | 33-3100 | SG6 LOADOUT TRENCH BOXES | 15
44465 | 44463 | 00-0010 | SG1 INSTALL 2 GATES | 4
44465 | 44463 | 03-1000 | OG8/OG9 MOVE MATERIAL fOR CARPENTERS TO SG6 | 1
44465 | 44463 | 33-3100 | SG6 STEAM/PLUMBING RUN EXACVATION | 2
44465 | 44463 | 33-3100 | OG8 ORGANIZING & PREP AREA FOR TRENCHING | 12.5
44465 | 44463 | 05-6030 | SITE 8 ASSIST/PLAC 2 STEEL TRAILERS | 10
44465 | 44463 | 99-4560 | WEED WHACK ALL SITES | 8
44465 | 44463 | 03-1000 | LOAD FORM TRAILER/OG8 | 14
44465 | 44463 | 32-6520 | REMOVE FENCE OG8 TO BUILDING | 3
44465 | 44463 | 03-1000 | REMOVE FORMS OG10 | 10
44465 | 44463 | 03-2300 | SGN FORM DUCTBANK | 29
44465 | 44463 | 03-1000 | SG6 SITE MAINTENANCE | 8
44465 | 44463 | 31-1820 | OG8 BURN SHEETS | 17.5
44465 | 44463 | 03-1000 | OG8 SITE MAINTENANCE | 8
44465 | 44463 | 03-1000 | OG8 LOAD OUT FORMS | 4
44465 | 44463 | 03-1000 | OG10 SITE MAINTENANCE | 8
44465 | 44463 | 03-1000 | OG10 STRIP FORMS | 64
44465 | 44463 | 03-1900 | OG9 WATER STOP | 6.5
44465 | 44463 | 31-1700 | Jump Pumps | 2
44458 | 44452 | 00-0010 | SG1 FENCE INSTALL/PARKING LOT | 35.5
44458 | 44452 | 02-6060 | SG4 2ND FLOOR INTERIOR WALL DEMO | 7
44458 | 44452 | 02-6060 | OG1 2ND FLOOR INTERIOR WALL DEMO | 11
44458 | 44452 | 33-3100 | SG5 EXCVATE TRENCH TO MH/CLEAN SITE | 5
44458 | 44452 | 33-3100 | SG4 BEGIN TO PULL TRENCH BOXES/BACKFILL DUCTBANK | 9
44458 | 44452 | 99-4560 | SGN CLEAN SITE/MOVE BOXES FROM SG4 TO SGN | 6
44458 | 44452 | 31-1300 | OG8 EXCAVATE FOR FOOTINGS | 18
44458 | 44452 | 03-1900 | OG10 SETUP AND POUR GRADE BEAM | 10.5
44458 | 44452 | 03-1700 | SG7 LOWR REBAR FOR TONAGE | 5
44458 | 44452 | 03-1000 | CARP HELPER OG8/OG10 | 24
44458 | 44452 | 99-4560 | HOUSEKEEPING OG10 | 8
44458 | 44452 | 31-1700 | PUMP OG10 | 1
44458 | 44452 | 03-2300 | SG5 FORM FOR PENETRATIONS THRU FOUNDATION FOR DUCT BANK | 16
44458 | 44452 | 99-4560 | OG8 SITE MAINTENANCE | 4
44458 | 44452 | 03-1000 | OG8 FORM FOR STEP FOOTINGS | 2
44458 | 44452 | 03-1000 | OG9 FORM FOOTINGS | 36
44458 | 44452 | 03-1300 | OG10 FINISH ANCHOR BOLTS FOR GRADE BEAMS | 18
44458 | 44452 | 03-1300 | OG10 CUT REBAR FOR ANCHOR BOLTS | 7
44458 | 44452 | 03-1900 | OG10 WATCH CONCRETE FOR GRADE BEAMS | 5
44458 | 44452 | 03-1000 | OG10 LOCATE AND PUT FORMS IN HOLE FOR PLUMBING SHAFT | 19
44458 | 44452 | 33-3100 | PULL BOXES | 6
44458 | 44453 | 00-0010 | SG1 FENCE INSTALL/PARKING LOT | 17.5
44458 | 44453 | 33-3100 | SG5 EXCAVATE AND CHIP FOR POE WORK | 2
44458 | 44453 | 03-2300 | SG5 POUR ELEC DUCTBANK (19CY) | 6
44458 | 44453 | 02-6060 | OG1 2ND FLOOR DEMO | 7
44458 | 44453 | 02-6060 | OG2 2ND FLOOR DEMO | 11
44458 | 44453 | 33-3100 | SG4 PULL OUT TRENCH BOXES/BACKFILL DUCTBANKS/MOVE 5 BOXES TO SGN/SITE TRUCK TO MOVE MATERIAL FROM OG10 TO SG4 | 26
44458 | 44453 | 03-2300 | SG4 LIVE LOAD - CONCRET/CLEAN SITE/REMOVE SHEETING - DUCTBANK | 13
44458 | 44453 | 31-1300 | OG8 EXC/LOADOUT 5 LOADS | 20
44458 | 44453 | 33-3100 | OG8 PLUMBING TRENCH EXC | 10.5
44458 | 44453 | 03-1900 | OG9 PREP AREA FOR CONCRETE PUMP | 7
44458 | 44453 | 31-1700 | PUMPS @ OG10 | 5
44458 | 44453 | 31-1820 | OG8 SITE MAINTENANCE/BURN SHEETS | 12
44458 | 44453 | 03-1000 | OG8 FORMWORK FOR STEP FOOTINGS | 5
44458 | 44453 | 03-1000 | SG7 LAYOUT FOR LATHER | 6
44458 | 44453 | 03-1000 | OG9 BRACE FOOTING COMPLETE | 42
44458 | 44453 | 03-1000 | OG9 TAKE DOWN FORMS + RECONSTRUCT TO FIND REBAR (DETAILER SENT BARS BIGGER THAN FOOTING) | 14
44458 | 44453 | 03-1000 | OG10 STRIP INSIE GRADE BEAMS | 15
44458 | 44453 | 03-1300 | OG10 STRIP ANCHOR BOLT TEMPLATES | 5
44458 | 44453 | 03-1000 | OG10 PUT DOWN SHOE FOR PLUMBING SHAFT | 6
44458 | 44453 | 99-4560 | OG10 SITE MAINTENANCE (HARDWARE) | 19
44458 | 44453 | 33-3100 | PULL BOXES (MANNY) | 5
44458 | 44454 | 33-3100 | SG5 EXCAVATE ELETCRICAL TRENCH TO MH | 7.5
44458 | 44454 | 32-6520 | SG5 PREP NEW WALKWAY FOR POUR CONCRETE | 2.5
44458 | 44454 | 33-3100 | SG4 PULL BOXES/MOVE 1 BOX TO SGN | 4.5
44458 | 44454 | 31-2200 | SG5 BACKFILL DUCTBANK/SG4 BACKFILL DUCTBANK | 9
44458 | 44454 | 33-3100 | SG4 EXCAVATE ELECTRCIAL TRENCH TO MH | 7
44458 | 44454 | 03-1700 | SG6 UNLOAD REBAR | 5
44458 | 44454 | 99-4560 | sg4/sg5 clean site | 5
44458 | 44454 | 02-6060 | OG2 2ND FLOOR DEMO | 7
44458 | 44454 | 02-6060 | OG3 2ND FLOOR DEMO | 11.5
44458 | 44454 | 03-1900 | SG7 SETUP AND POUR 154 CY | 57
44458 | 44454 | 33-3100 | OG9 EXCAVATE + STOCKPILE PLUMBING TRENCH | 16
44458 | 44454 | 03-1000 | OG8 ASSIST CARPS W/FORMS | 4
44458 | 44454 | 03-1900 | OG9 PREP AREA FOR POUR | 7
44458 | 44454 | 33-3100 | SGN PULL BOXES/SHORING | 5
44458 | 44454 | 03-1000 | OG8 FORM 4 FOOTINGS | 20
44458 | 44454 | 03-1000 | OG8 BRACED BACKSIDE OF STEP FOOTING | 8.5
44458 | 44454 | 99-4560 | OG8 SITE MAINTENANCE | 5.5
44458 | 44454 | 03-1000 | OG9 SET ALL TEMPLATES FOR LATHER AFTER SURVEY | 24
44458 | 44454 | 99-4560 | OG10 SAFETY REBAR CAPS | 10
44458 | 44454 | 03-1000 | OG10 PREP FOR CLOSEUP | 13
44458 | 44454 | 03-1000 | OG10 STRIP WEST SIDE OF GRADE BEAM (160 SF) + HOUSEKEEPING | 15
44458 | 44454 | 03-1900 | OG10 WATERSTOP | 8
44458 | 44454 | 03-1000 | SG7 CUT KEYWAY FOR PLUMBING SHAFT | 4
44458 | 44455 | 99-4560 | SG5 POUR TEMP SIDEWALK | 8.5
44458 | 44455 | 33-3100 | SG5 EXCAVATE TRENCH TO MH/MAKE IT WIDER FOR ELECTRICIAN | 4
44458 | 44455 | 99-4560 | OG4 EXCAVATE FOR TEMP BASEMENT ACCESS/POUR CONCRETE/CLEAN ALL EXTRA DIRT TO OG8 | 19
44458 | 44455 | 02-2300 | OG4 BASEMENT CLEAN/PUMP OUT WATER/REMOVE STORED MATERIAL REMOVE POLY COMPACTOR ROOM | 17
44458 | 44455 | 02-6060 | OG3 2ND FLOOR DEMO | 13
44458 | 44455 | 02-6060 | OG6 2ND FLOOR DEMO | 5
44458 | 44455 | 03-1900 | OG9 SETUP & POUR FOOTINGS | 45
44458 | 44455 | 03-1000 | OG8 ASSIST CARP SETTING FOOTINGS | 5
44458 | 44455 | 31-1300 | OG8 EXCAVATE FOR FOOTINGS | 8
44458 | 44455 | 33-3100 | OG10 EXCAVATE FOR DUCTBANKS ELECTRIC | 6
44458 | 44455 | 03-1000 | SG7 STRIP KEY | 4
44458 | 44455 | 03-1000 | SG7 SITE SAFETY (REBAR CAPS) | 14.5
44458 | 44455 | 03-1000 | SG7 PUT DOWN SHOE FOR PLUMBING SHAFT AND 2 PIERS | 16
44458 | 44455 | 99-4560 | OG8 SITE MAINTENANCE | 15
44458 | 44455 | 03-1000 | OG8 WAIT ON SURVEY | 12
44458 | 44455 | 03-1000 | OG8 FORM AND BRACE | 12
44458 | 44455 | 03-1000 | OG9 POUR CONCRETE (WATCH POUR) | 8
44458 | 44455 | 03-1000 | OG10 WAIT ON INSPECTION | 18
44458 | 44455 | 03-1000 | OG10 WAIT ON TNAGE TO FIX FROM INSPECTION | 9.5
44458 | 44455 | 03-1000 | OG10 START CLOSING UP | 8
44458 | 44455 | 03-1900 | WATERSTOP | 8
44458 | 44456 | 32-6520 | SG5 FENCE RELOCATION FOR NEW TEMP WALKWAY | 24.5
44458 | 44456 | 99-4560 | SG6 PREP FOR OIL TANK DELIVERY/RELOCATE REBAR/CLEAN,LEVEL AREA | 5
44458 | 44456 | 33-6000 | SG6 UNLOAD SAND BAGS FOR WELKIN | 1
44458 | 44456 | 33-3100 | SGN DISSASSEMBLE TRENCH BOXES | 8
44458 | 44456 | 03-1700 | SG6 UNLOAD WIRE MESH FOR 2ND FLOOR | 0.5
44458 | 44456 | 02-2300 | OG4 JEL CLEAN FLOOR DRAINS/PUMP OUT WATER BASEMENT | 9
44458 | 44456 | 03-1000 | SG10 MOVE VENDOR MACHINE FOR TONAGE | 1
44458 | 44456 | 02-6060 | OG6 2ND FLOOR APARTMENT DEMO | 17
44458 | 44456 | 31-1400 | OG9 BACKFILL FOOTINGS | 17.5
44458 | 44456 | 33-3100 | OG9 PLUMBING TRENCH | 18
44458 | 44456 | 03-1000 | OG8 ASISST LATHERS MOVE STEEL | 7
44458 | 44456 | 33-3100 | OG10 UTILITY TRENCH FOR 5 STAR | 8
44458 | 44456 | 03-1000 | OG8 FORMWORK | 8
44458 | 44456 | 03-1300 | OG8 ANCHOR BOLT TEMPLATES | 9
44458 | 44456 | 99-4560 | OG8 SITE MAINTENANCE | 9
44458 | 44456 | 03-1000 | OG9 STRIPPED FORMS | 26.5
44458 | 44456 | 03-1000 | OG9 STARTED TO SET SHOE | 18
44458 | 44456 | 99-4560 | OG9 SITE MAINTENANCE | 21.5
44458 | 44456 | 03-1000 | OG10 CLOSEUP PLUMBING SHAFT | 26
44451 | 44445 | 99-7200 | Holiday Pay | 96
44451 | 44446 | 03-2300 | SG4 POUR DUCTBANK | 8
44451 | 44446 | 22-6025 | SG4 REMOVE/CLEANUP PIPE INSULATION | 19.5
44451 | 44446 | 02-2300 | SG5 REMOVE WATER/BASEMENT | 6
44451 | 44446 | 31-1700 | SG6 PUMP OUT PLUMBING SHAFT | 2
44451 | 44446 | 03-1700 | OG10 BACKUP TONAGE/MOVE REBAR | 6
44451 | 44446 | 02-6060 | OG5 2ND FLOOR INTERIOR WALL DEMO | 17
44451 | 44446 | 31-1840 | SG7 SETUP AND POUT 20 CY TOPPING SLAB | 26.5
44451 | 44446 | 03-1900 | OG8 POUR PIER | 10
44451 | 44446 | 99-4560 | OG9 TRANSPORT T2150 FROM SG7 TO OG9 | 5
44451 | 44446 | 03-1000 | OG8 STRIP FORMS | 51.5
44451 | 44446 | 03-1000 | OG10 FORM INSIDE PLUMBING SHAFT | 20.5
44451 | 44446 | 03-1000 | SG6 FORM WALLS | 37
44451 | 44446 | 99-7200 | SICK DAY | 8
44451 | 44447 | 00-0010 | SG1 FENCE INSTALL AT PARKING LOT/UNLOAD MATEIRAL | 20.5
44451 | 44447 | 02-2300 | SG5 CLEAN BASEMENT | 15
44451 | 44447 | 03-2100 | OG6 START MOVE CONCRETE BAGS TO BASEMENT FOR FLOOR DRAIN POUR | 7
44451 | 44447 | 02-6060 | OG5 2ND FLOR EXTERIOR WALL DEMO AND FLOOR | 17
44451 | 44447 | 03-2100 | OG1 POUR FLOOR DRAINS | 13
44451 | 44447 | 33-6000 | OG9 PIPE DELIVERY UNLOAD | 3
44451 | 44447 | 33-6010 | SG4 WELKIN TO BEGIN NEW STEAM INSTALL BACKUP | 7
44451 | 44447 | 31-1840 | SG7 PREPAREA FOR SUBGRADE INSPECTION | 6
44451 | 44447 | 31-1840 | OG9 DIG OUT & STONE SUBGRADE | 31.5
44451 | 44447 | 33-6000 | FLAG FOR WELKIN DELIVERY | 2
44451 | 44447 | 00-0010 | UNLOAD FENCE SG1 | 2
44451 | 44447 | 03-1000 | SG6 FINISH PUTTING UP FORMS THAT CAN BE ON WALLS | 28.5
44451 | 44447 | 03-1000 | SG6 START DUMMY PLATFORM | 19.5
44451 | 44447 | 03-1000 | OG8 FINISH STRIPPING FORMS | 29.5
44451 | 44447 | 03-1000 | OG8 MOVE FORMS AND MATERIAL TO SG6 AND OG10 | 12
44451 | 44447 | 03-1000 | OG10 PUT BACK FORM ON GRADEBEAMS THAT LATHERS DROPPED | 8
44451 | 44447 | 03-1000 | OG10 START CLOSING GRADE BEAMS | 20
44451 | 44447 | 03-1000 | OG10 FORMING SHELF IN PLUMBING SHAFT | 9
44451 | 44447 | 31-1830 | OG9 INSTALL PLYWOOD ON LAGGING FOR EXCAVATION | 5.5
44451 | 44448 | 02-6060 | SG4 2ND FLOOR INTERIOR WALL DEMO | 34.5
44451 | 44448 | 22-6025 | SG4 REMOVE PIPE INSULATION LITTLE ROOM | 10
44451 | 44448 | 02-3000 | SG1 CORE DRILL (1) - 6" HOLE FOR VITAL | 7
44451 | 44448 | 02-2300 | SG5 INSTALL BEAM TO BLOCK WATER | 3
44451 | 44448 | 99-4560 | OG8 HOUSE KEEPING/CLEANUP | 17
44451 | 44448 | 33-6010 | SG4 WELKIN TO INSTALL UG STEAM & PLUMBING | 10
44451 | 44448 | 02-2300 | SG1/SG2/SG3 CLEAN BASEMENTS | 17
44451 | 44448 | 31-1840 | OG9 STONE AND GRADE | 20
44451 | 44448 | 33-3100 | OG9 STEAM TRENCH EXC | 10
44451 | 44448 | 03-1700 | SG7 UNLOAD REBAR TRAILER | 11.5
44451 | 44448 | 03-1000 | CARP HELPER | 8
44451 | 44448 | 03-1000 | SG6 FINISH FORMING TOP OF WALLS, MAKE UP PANELS, | 52
44451 | 44448 | 03-1000 | SG6 START PLUMBING SHAFT, DUMMY PLATFORM + START FORMING | 30
44451 | 44448 | 03-1000 | OG10 FINISH FORMING GRADE BEAMS | 28.5
44451 | 44448 | 03-1000 | MOVE FORMS FROM OG8 TO OG10 | 8.5
44451 | 44448 | 03-1000 | CHOP OUT KEY @ SG6 | 10
44451 | 44449 | 00-0010 | SG1 FENCE INSTALL AT PARKING LOT | 36.5
44451 | 44449 | 00-0011 | SG4 PERAMBULATOR ROOM DEMO | 7
44451 | 44449 | 02-6060 | SG4 2ND FLOOR INTERIOR WALL DEMO | 19
44451 | 44449 | 31-2200 | SG4 STAGE MATERIAL FOR BACKFILL | 1
44451 | 44449 | 03-2100 | OG1 CLEAN BASEMENT/ AFTER FLOOR DRAINS POUR | 3
44451 | 44449 | 22-6025 | SG4 CLEAN BASEMENT /INSULATION REMOVAL | 3
44451 | 44449 | 03-2100 | OG6 MOVE MATERIAL TO BASEMENT - CONCRETE BAGS FOR FLOOR DRAINS | 3
44451 | 44449 | 31-1300 | OG8 LOAD OUT 5 TRUCKS X2 | 24
44451 | 44449 | 31-1300 | OG9 LOAD OUT 3 TRUCKS X 2 | 10
44451 | 44449 | 03-1700 | SG7 UNLOAD REBAR TRAILER | 12
44451 | 44449 | 31-1400 | LOAD HNS TRUCK OG9 AND OG8 BACKFILL MATERIAL (7) | 7.5
44451 | 44449 | 33-6010 | WELKIN PIPE SGN | 6
44451 | 44449 | 03-1000 | SG6 FORM SHAFT WALS 2 SIDES | 29
44451 | 44449 | 03-1000 | SG6 CUT OUT HOLE IN DUMMY DECK FOR ACES FOR PLUMBERS | 9
44451 | 44449 | 03-1000 | SG6 1/3 OF ALL BRACING FOR WALLS | 32
44451 | 44449 | 99-4560 | SG6 SITE MAINTENANCE | 8.5
44451 | 44449 | 03-1000 | SG7 LAY OUT FOOTING AND ELEVATION FOR LATHRS | 4
44451 | 44449 | 31-1820 | OG8 BURN SHEETS FOR STEP FOOTINGS | 6
44451 | 44449 | 03-1000 | OG8 STRIP COLUMN (PIER) | 5
44451 | 44449 | 03-1000 | OG8 FORM 1/2 OF STEP FOOTINGS | 4
44451 | 44449 | 03-1000 | OG10 COMPLETELY BRACE GRADE BEAMS IN + OUT | 18
44451 | 44449 | 03-1000 | OG10 START TEMPLATES FOR ANCHOR BOLTS | 18
44444 | 44438 | 00-0004 | SG3 DRILL INSTALL DOWELS | 17.5
44444 | 44438 | 02-3000 | SG5 COMPLETE ELECTRICAL POE | 18
44444 | 44438 | 99-4560 | OG3 ADJUST TEMP BASEMENT ACCESS RAMP FOR POUR | 2
44444 | 44438 | 33-3100 | SG5 START DIG FROM MEP CORES | 11
44444 | 44438 | 03-2100 | SG3 TAKE 2 SKIDS CONCRETE BAGS TO BASEMENT | 17
44444 | 44438 | 03-1000 | OG10 ASSIST CARPS REMOVE FORMWORK | 9
44444 | 44438 | 31-1400 | PREP OG10 FOR FLOW FILL | 14.5
44444 | 44438 | 31-1820 | SG7 LOAD STEEL BRACING/PIPES TO CONTINUE | 12
44444 | 44438 | 03-1000 | OG8 ASSIST CARP | 8
44444 | 44438 | 99-4560 | HOUSEKEEPING OG10/SG7 | 6
44444 | 44438 | 03-1000 | OG10 STRIP FOOTINGS & CLEAR OUT FOR BACKFILL | 27
44444 | 44438 | 03-1000 | OG8 CLOSE UP FORMS | 35
44444 | 44438 | 31-1300 | SG7 SAFETY ISSUE (LADDER & PLATFORM) | 5
44444 | 44438 | 31-1820 | OG8 CUT SHEETS | 3
44444 | 44438 | 03-1000 | OG8 TEMPLATES FOR LATHER | 3
44444 | 44439 | 02-3000 | SG2 CORE DRILL 6" WALL PENETRATION FOR VITAL | 1
44444 | 44439 | 02-2300 | SG2 SETUP TEMP PUMP REMOVE WATER FROM BASEMENT | 5
44444 | 44439 | 99-4560 | OG3 POUR TEMP ACCESS RAMP | 7
44444 | 44439 | 33-3100 | SG5 CONTINUE TO DIG FOR MEP CORES | 8.5
44444 | 44439 | 99-4560 | SG6 CLEAN AND PUMP OUT WATER FOR IRONWORKERS WELD BASE PLATES | 6
44444 | 44439 | 99-4560 | SG6 PUMP OUT WATER LEFT LITLE GIANT PUMP | 1
44444 | 44439 | 00-0004 | SG3 DRILL/INSTALL DOWELS FOR FLOOR DRAINS | 9
44444 | 44439 | 03-1700 | OG8 REBAR DELIVRY | 7
44444 | 44439 | 02-3000 | SG4 CLEAN/CONCRETE CORE DRILL MEP PENETRATION | 3
44444 | 44439 | 03-2300 | SG4 CLEAN ELECETRICAL TRENCH FOR POUR | 2
44444 | 44439 | 02-3000 | SG5 CLEAN ELECTRICAL TRENCH/AFTER PULLOUT CONCRETE BLOCKS AND CHOPPING - CLEAN BASEMENT | 8
44444 | 44439 | 31-1400 | OG10 POUR 99 CY FLOW FILL | 25.5
44444 | 44439 | 31-1300 | SG7 FLAG FOR EXCAVATOR PICKUP | 2.5
44444 | 44439 | 33-6000 | OG9 FLAG FOR WELKIN PIPE DELIVERY | 6
44444 | 44439 | 33-6000 | OG9 UNLOAD PIPE (WELKIN) | 6
44444 | 44439 | 03-1000 | OG9 ASSIST CARP MOVE FORMS TO OG8 | 4
44444 | 44439 | 03-1000 | CARP HELPER @ OG10/OG8 | 16
44444 | 44439 | 03-1000 | OG10 STRIP FORMS FOR FOOTING | 7
44444 | 44439 | 03-1000 | OG10 SET SHOE FOR PLUMBING SHAFT | 12.5
44444 | 44439 | 99-4560 | OG10 SITE MAINTENANCE | 3
44444 | 44439 | 03-1000 | OG8 CLOSE UP FORMS | 36
44444 | 44439 | 03-1000 | OG8 TEMPLATES | 17
44444 | 44439 | 03-1000 | OG8 SITE MAINTENANCE/ GATHERING MATERIAL FOR OG8 CLOSEUP | 11
44444 | 44439 | 03-1000 | GATHER MATERIAL TO CLOSEUP OG8 | 1.5
44444 | 44439 | 31-1820 | BURNING SHEETS FOR REBAR INSTALLATION | 1
44444 | 44440 | 03-2100 | SG3 POUR FLOOR DRAINS | 20
44444 | 44440 | 00-0004 | OG6 SAW CUT AND DRILL DOWELS FOR FLOOR DRAINS | 20.5
44444 | 44440 | 99-4560 | OG10 CLEAN SITE/MOVE H PILES | 2
44444 | 44440 | 03-2100 | OG8 MOVE MATERIAL TO OG6 - CONCRETE BAGS & GROUT BAGS | 2
44444 | 44440 | 31-1700 | OG10/OG8/SG7 COVER PUMPS | 5
44444 | 44440 | 31-1400 | OG8 CLEAN BACKFILL | 1
44444 | 44440 | 31-2000 | SG7 VAC TRUCKING FOR TOPPING SLAB | 22.5
44444 | 44440 | 99-4560 | OG10 PREP FOR STORM | 10
44444 | 44440 | 31-1400 | OG10 BACKFILL AROUND FOOTINGS | 6
44444 | 44440 | 31-1820 | LOAD STEEL @ SG7 FOR LOADOUT | 3
44444 | 44440 | 99-4560 | OG8 SITE MAINTENANCE | 8.5
44444 | 44440 | 03-1000 | OG8 FORMWORK | 77
44444 | 44440 | 03-1000 | OG8 TEMPLATE WORK | 20
44444 | 44440 | 99-4560 | OG6 SITE MAINTENANCE | 1.5
44444 | 44441 | 02-2300 | SG5 CLEAN AND REMOVE WATER FROM BASEMENT INSTALL ANOTHER 2" PUMP BASEMENT | 7
44444 | 44441 | 02-2300 | SG4 CLEAN MUD AND REMOVE WATER FROM BASEMENT | 13
44444 | 44441 | 03-2300 | SG4 FORM ELECTRCIAL DUCTBANK/ INSTALL BOND BREAKER | 10
44444 | 44441 | 00-0004 | OG6 SAWCUT AND DRILL DOWELS FOR FLOOR DRAINS | 9
44444 | 44441 | 02-6060 | OG4 2ND FLOOR INTERIOR WALL DEMO | 21.5
44444 | 44441 | 03-1000 | OG10 ASSIST CARPS LOWER FORMS | 11
44444 | 44441 | 03-1900 | OG8 ORGANIZE & PREP FOR CONCRETE POUR | 8
44444 | 44441 | 33-3100 | OG9 START EXCAVATING FOR STEAM PIPE TRENCH | 16
44444 | 44441 | 03-1000 | ASSIST CARPS | 16
44444 | 44441 | 31-1700 | SET PUMPS @ OG8 | 13
44444 | 44441 | 99-4560 | OG8 SITE MAINTENANCE/CLEAN/PUMP WATER | 9.5
44444 | 44441 | 03-1300 | OG8 TEMPLATE ( Anchor Bolts) | 21.5
44444 | 44441 | 03-1000 | OG8 FORMWORK | 27
44444 | 44441 | 99-4560 | OG8 SITE MAINTENANCE (ACCESS LADDER) | 3
44444 | 44441 | 03-1000 | OG10 PUT UP FORMS (PLUMBING SHAFT & PIERS) | 44
44444 | 44442 | 03-1700 | SG7 REBAR OFFLOAD | 10
44444 | 44442 | 99-4560 | OG3 OPEN TEMP ACCESS RAMP TO PUBLIC/ CLOSE EXISTING RAMP | 1
44444 | 44442 | 22-6025 | SG4 REMOVE PIPE INSULATION | 29.5
44444 | 44442 | 99-4560 | SG6 PUMP OUT PLUMBING SHAFT | 1
44444 | 44442 | 03-1000 | SG6 BEGIN FORM SHAFT AND INTERIOR WALLS/MOVE FORMS | 5
44444 | 44442 | 31-1700 | OG8 PUMP OUT WATER - BIG PUMP | 2.5
44444 | 44442 | 02-6060 | OG4 2ND FLOOR INTERIOR WALL DEMO | 18
44444 | 44442 | 03-1900 | SETUP & POUR OG8 FOOTINGS/WALLS | 42
44444 | 44442 | 03-1200 | concrete pump operator | 13
44444 | 44442 | 03-1900 | OG8 POUR CONCRETE | 19.5
44444 | 44442 | 03-1000 | OG8 FINISH CLOSING UP | 30.5
44444 | 44442 | 03-1000 | OG10 FORM PLUMBING SHAFT | 32
44444 | 44442 | 03-1000 | SG6 START FORMING WALLSS | 34.5