## Sheet1
Freeze | Bill Code | Contract Code | Job | Phase | Name | Shared Saving | Category | Phase Type | Type | Method | Current Cost Budget | Spent/Committed Against Base Contract | Spent/Committed Total | Actual Cost | Spent/Committed (In Scope) | Complete % | Pending Internal PCI | Pending Internal PCI Cost To Complete | Pending External PCI Cost To Complete | Cost to Complete | Cost to Complete Override | Projected Cost Forecast | Projected Cost Forecast Override | Cost Variance | Pending CO | Pending CO (Incl. Risk) | Projected Cost Budget | Spent/Committed (Pending CO) | Cost To Complete (Pending CO) | Proj Cost Forecast (Incl. Pending CO) | Projected Cost Forecast (Incl Pending CO) Override | Cost Variance (Incl Pending CO) | Current Bill Budget | Pending CO | Original Cost<br/> Budget Amount | Original Bill<br/> Budget Amount | Pending CO (Incl. Risk) | Projected Bill Budget | Billed To Date | Revenue Forecast | Revenue Forecast Override | Revenue Variance | Adj Rev Forecast | Projected Profit | Current Period Cost | Previous Period Cost | Last Period Forecast | Cost Forercast /<br>Variance | Current Period Changes | Previous Period Changes | Current Period Commitments | Previous Period Commitments | Shared Saving Amt | Profit Incl Shared Saving | Pending PCI including Risk (revenue) | Pending PCI including Risk (Cost) | WIP Projected cost forecast including Risk | WIP Projected cost forecast | WIP Revenue amount | WIP adjusted Revenue amount | Adj Rev Forecast <br/> Variance | Billed Budget Qty | Billed Completed Qty | Billed Remaining Qty | Billed Projected Qty | Input Budget Qty | Input Completed Qty | Input Remaining Qty | Input Projected Qty | Input WM Code | Output Budget Qty | Output Completed Qty | Output Remaining Qty | Output Projected Qty | Output WM Code | Committed Amount | Committed Remaining Amount | Spent Against Commitment Amount | Total Cost to Complete Amt | Notes
N | M007-00-0001-L | M007 | M007 | 00-0001 | SECOND FLOOR APARTMENT REMOVALS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 0
N | M007-00-0001-R | M007 | M007 | 00-0001 | SECOND FLOOR APARTMENT REMOVALS | N | R |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 17585 | 0 | 0 | 0 | 0 | 17585 | 17585 | 0 | N | 17585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17585 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 0
N | M007-00-0001-S | M007 | M007 | 00-0001 | SECOND FLOOR APARTMENT REMOVALS | N | S |  | NR | A | 16705.75 | 19333.9 | 19333.9 | 14032 | 19333.9 | 83.995 | 0 | 0 | 0 | -2628.15 | Y | 16705.75 | Y | 0 | 0 | 0 | 16705.75 | 0 | 0 | 16705.75 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16705.75 | 0 | 0 | 16705.75 | 0 | 0 | 0 | 0 | 0 | 0 | -16705.75 | 0 | 0 | 16705.75 | 16705.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 6 | 2 | 8 | NA | 7 | 0 | 7 | 7 | EA | 19333.9 | 5301.9 | 14032 | -2628.15
N | M007-00-0002-C | M007 | M007 | 00-0002 | SITE 8 SLAB SHORING | N | C |  | NR | U | 9214.7 | 9214.7 | 9214.7 | 9214.7 | 9214.7 | 100 | 0 | 0 | 0 | 0 | Y | 9214.7 | Y | 0 | 0 | 0 | 9214.7 | 0 | 0 | 9214.7 | Y | 0 | 9214.7 | 0 | 0 | 0 | 0 | 9214.7 | 0 | 0 | N | 9214.7 | 0 | -9214.7 | 0 | 0 | 9214.7 | 0 | 0 | 0 | 0 | 0 | 0 | -9214.7 | 0 | 0 | 9214.7 | 9214.7 | 0 | 0 | 9214.7 | 1 | 0 | 0 |  | 1 | 2 | 3.33 | 5.33 | NA | 0 | 60 | 0 | 60 | HR | 9214 | -0.7 | 9214.7 | 0
N | M007-00-0002-L | M007 | M007 | 00-0002 | SITE 8 SLAB SHORING | N | L |  | NR | P | 6521.61 | 6521.61 | 6521.61 | 6521.61 | 6521.61 | 100 | 0 | 0 | 0 | 0 | Y | 6521.61 | Y | 0 | 0 | 0 | 6521.61 | 0 | 0 | 6521.61 | Y | 0 | 6521.61 | 0 | 0 | 0 | 0 | 6521.61 | 0 | 0 | N | 6521.61 | 0 | -6521.61 | 0 | 0 | 6521.61 | 0 | 0 | 0 | 0 | 0 | 0 | -6521.61 | 0 | 0 | 6521.61 | 6521.61 | 0 | 0 | 6521.61 | 1 | 0 | 60 | 60 | 1 | 60 | 0 | 60 | HR | 0 | 60 | 0 | 60 | HR | 0 | 0 | 0 | 0
N | M007-00-0002-R | M007 | M007 | 00-0002 | SITE 8 SLAB SHORING | N | R |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 39587.72 | 0 | 0 | 0 | 0 | 39587.72 | 39587.72 | 0 | N | 39587.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39587.72 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 60 | 0 | 60 | HR | 0 | 0 | 0 | 0
N | M007-00-0003-L | M007 | M007 | 00-0003 | OG8 Obstruction Removal | N | L |  | NR | P | 0 | 17042.53 | 17042.53 | 17042.53 | 17042.53 | 100 | 0 | 0 | 0 | 0 | Y | 17042.53 | Y | -17042.53 | 0 | 0 | 0 | 0 | 0 | 17042.53 | Y | -17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17042.53 | 0 | 0 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | -17042.53 | 0 | 0 | 17042.53 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 155.5 | 155.5 | 0 | 155.5 | 0 | 155.5 | HR | 0 | 144 | 0 | 144 | HR | 0 | 0 | 0 | 0
N | M007-00-0004-C | M007 | M007 | 00-0004 | Floor Drain PCO | N | C |  | NR | U | 0 | 2562.38 | 2562.38 | 1546.35 | 2562.38 | 0 | 0 | 0 | 0 | -2562.38 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 218 | 0 | 218 | NA | 0 | 180.5 | -180.5 | 0 | NA | 2562.38 | 1016.03 | 1546.35 | -2562.38
N | M007-00-0004-L | M007 | M007 | 00-0004 | Floor Drain PCO | N | L |  | NR | P | 0 | 16245.04 | 16245.04 | 16245.04 | 16245.04 | 0 | 0 | 0 | 0 | -16245.04 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.5 | -164.5 | 0 | HR | 0 | 180.5 | -180.5 | 0 | NA | 0 | 0 | 0 | -16245.04
N | M007-00-0005-C | M007 | M007 | 00-0005 | Equipment Pad PCO | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 30.52 | 0 | 30.52 | NA | 0 | 0 | 0 | 0
N | M007-00-0005-L | M007 | M007 | 00-0005 | Equipment Pad PCO | N | L |  | NR | P | 0 | 5253 | 5253 | 5253 | 5253 | 21.012 | 0 | 0 | 0 | 19747 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 2376.78 | 2780.38 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 260.85 | 260.85 | 0 | 47 | 213.85 | 260.85 | HR | 0 | 30.52 | 0 | 30.52 | NA | 0 | 0 | 0 | 19747
N | M007-00-0006-C | M007 | M007 | 00-0006 | Additional Windows PCO | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0006-L | M007 | M007 | 00-0006 | Additional Windows PCO | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | Y | 7500 | Y | -7500 | 0 | 0 | 0 | 0 | 0 | 7500 | Y | -7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7500 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | -7500 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 7500
N | M007-00-0007-C | M007 | M007 | 00-0007 | IRMA PAGAN APARTMENT MOVE | N | C |  | NR | U | 0 | 2500 | 2500 | 2500 | 2500 | 100 | 0 | 0 | 0 | 0 | Y | 2500 | Y | -2500 | 0 | 0 | 0 | 0 | 0 | 2500 | Y | -2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | -2500 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | NA | 0 | 0 | 0 | 0 | NA | 2500 | 0 | 2500 | 0
N | M007-00-0007-L | M007 | M007 | 00-0007 | IRMA PAGAN APARTMENT MOVE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0008-C | M007 | M007 | 00-0008 | National Grid Gas Line Relocation | N | C |  | NR | U | 0 | 1747.75 | 1747.75 | 1747.75 | 1747.75 | 100 | 0 | 0 | 0 | 0 | Y | 1747.75 | Y | -1747.75 | 0 | 0 | 0 | 0 | 0 | 1747.75 | Y | -1747.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1747.75 | 0 | 0 | 1747.75 | 0 | 0 | 0 | 0 | 0 | 0 | -1747.75 | 0 | 0 | 1747.75 | 1747.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | 0 | 2 | NA | 0 | 90.5 | 0 | 90.5 | NA | 0 | 0 | 0 | 0
N | M007-00-0008-L | M007 | M007 | 00-0008 | National Grid Gas Line Relocation | N | L |  | NR | P | 0 | 9920.13 | 9920.13 | 9920.13 | 9920.13 | 100 | 0 | 0 | 0 | 0 | Y | 9920.13 | Y | -9920.13 | 0 | 0 | 0 | 0 | 0 | 9920.13 | Y | -9920.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9920.13 | 0 | 0 | 9920.13 | 0 | 0 | 0 | 0 | 0 | 0 | -9920.13 | 0 | 0 | 9920.13 | 9920.13 | 0 | 0 | 0 | 0 | 0 | 90.5 | 90.5 | 0 | 90.5 | 0 | 90.5 | HR | 0 | 90.5 | 0 | 90.5 | NA | 0 | 0 | 0 | 0
N | M007-00-0009-C | M007 | M007 | 00-0009 | Bracing for POE Penetration Through SG4 Wall | N | C |  | NR | U | 0 | 3742.08 | 3742.08 | 2522 | 3742.08 | 0 | 0 | 0 | 0 | -3742.08 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13 | 2 | 15 | NA | 0 | 44.5 | 0 | 44.5 | NA | 3742.08 | 1220.08 | 2522 | -3742.08
N | M007-00-0009-L | M007 | M007 | 00-0009 | Bracing for POE Penetration Through SG4 Wall | N | L |  | NR | P | 0 | 4946.26 | 4946.26 | 4946.26 | 4946.26 | 0 | 0 | 0 | 0 | -4946.26 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.5 | 44.5 | 0 | 44.5 | 0 | 44.5 | HR | 0 | 44.5 | 0 | 44.5 | NA | 0 | 0 | 0 | -4946.26
N | M007-00-0010-C | M007 | M007 | 00-0010 | SG1 RELOCATE BELONGINGS | N | C |  | NR | U | 0 | 3714.82 | 3714.82 | 3412 | 3714.82 | 91.8483 | 0 | 0 | 0 | 0 | Y | 3714.82 | Y | -3714.82 | 0 | 0 | 0 | 0 | 0 | 3714.82 | Y | -3714.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3714.82 | 0 | 0 | 3714.82 | 0 | 0 | 0 | 0 | 0 | 0 | -3714.82 | 0 | 0 | 3714.82 | 3714.82 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 370.4 | 371.4 | NA | 0 | 161 | 0 | 161 | NA | 3714.82 | 302.82 | 3412 | 0
N | M007-00-0010-L | M007 | M007 | 00-0010 | SG1 RELOCATE BELONGINGS | N | L |  | NR | P | 0 | 18361.44 | 18361.44 | 18361.44 | 18361.44 | 84.3295 | 0 | 0 | 0 | 3412 | Y | 21773.44 | Y | -21773.44 | 0 | 0 | 0 | 0 | 0 | 21773.44 | Y | -21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21773.44 | 0 | 0 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | -21773.44 | 0 | 0 | 21773.44 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 193 | 193 | 0 | 193 | 0 | 193 | HR | 0 | 161 | 0 | 161 | NA | 0 | 0 | 0 | 3412
N | M007-00-0011-L | M007 | M007 | 00-0011 | PERAMBULATOR ROOM DEMO | N | L |  | NR | P | 0 | 16007.97 | 16007.97 | 16007.97 | 16007.97 | 78.5546 | 0 | 0 | 0 | 4370.17 | Y | 20378.14 | Y | -20378.14 | 0 | 0 | 0 | 0 | 0 | 20378.14 | Y | -20378.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20378.14 | 0 | 1900.91 | 20378.14 | 0 | 0 | 0 | 0 | 0 | 0 | -20378.14 | 0 | 0 | 20378.14 | 20378.14 | 0 | 0 | 0 | 0 | 0 | 138.5 | 138.5 | 0 | 157 | -18.5 | 138.5 | HR | 0 | 157 | 0 | 157 | NA | 0 | 0 | 0 | 4370.17
N | M007-00-0012-C | M007 | M007 | 00-0012 | OG8 Tank Removal | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0012-L | M007 | M007 | 00-0012 | OG8 Tank Removal | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0013-L | M007 | M007 | 00-0013 | Exist Bldgs Bracing due to Penetrations | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0013-M | M007 | M007 | 00-0013 | Exist Bldgs Bracing due to Penetrations | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0014-L | M007 | M007 | 00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | N | L |  | NR | P | 0 | 1285.34 | 1285.34 | 1285.34 | 1285.34 | 8.0333 | 0 | 0 | 0 | 14714.9 | Y | 16000.24 | Y | -16000.24 | 0 | 0 | 0 | 0 | 0 | 16000.24 | Y | -16000.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16000.24 | 0 | 0 | 16000.24 | 0 | 0 | 0 | 0 | 0 | 0 | -16000.24 | 0 | 0 | 16000.24 | 16000.24 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 13 | HR | 0 | 13 | 0 | 13 | NA | 0 | 0 | 0 | 14714.9
N | M007-00-0015-L | M007 | M007 | 00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | N | L |  | NR | P | 0 | 1678.93 | 1678.93 | 1678.93 | 1678.93 | 0 | 0 | 0 | 0 | -1678.93 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0 | 17 | 0 | 17 | HR | 0 | 17 | 0 | 17 | NA | 0 | 0 | 0 | -1678.93
N | M007-00-0016-C | M007 | M007 | 00-0016 | OG4 BRACING FOR POE PENETRATION | N | C |  | NR | U | 0 | 2585.78 | 2585.78 | 2585.78 | 2585.78 | 0 | 0 | 0 | 0 | -2585.78 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | NA | 0 | 81 | -81 | 0 | NA | 2585.78 | 0 | 2585.78 | -2585.78
N | M007-00-0016-L | M007 | M007 | 00-0016 | OG4 BRACING FOR POE PENETRATION | N | L |  | NR | P | 0 | 8079.59 | 8079.59 | 8079.59 | 8079.59 | 0 | 0 | 0 | 0 | -8079.59 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | -81 | 0 | HR | 0 | 81 | -81 | 0 | NA | 0 | 0 | 0 | -8079.59
N | M007-00-0017-L | M007 | M007 | 00-0017 | National Grid Additional Allowance | N | L |  | NR | P | 0 | 5887.46 | 5887.46 | 5887.46 | 5887.46 | 100 | 0 | 0 | 0 | 0 | N | 5887.46 | N | -5887.46 | 0 | 0 | 0 | 0 | 0 | 5887.46 | N | -5887.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5887.46 | 0 | 0 | 5887.46 | 0 | 0 | 0 | 0 | 0 | 0 | -5887.46 | 0 | 0 | 5887.46 | 5887.46 | 0 | 0 | 0 | 0 | 0 | 58.5 | 58.5 | 0 | 58.5 | 0 | 58.5 | HR | 0 | 58.5 | 0 | 58.5 | NA | 0 | 0 | 0 | 0
N | M007-00-0017-S | M007 | M007 | 00-0017 | National Grid Additional Allowance | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199833 | 199883 | Y | 199883 | Y | -199883 | 199833 | 199833 | 199833 | 0 | 199833 | 399716 | Y | -199883 | 0 | 199833 | 0 | 0 | 199833 | 199833 | 0 | 0 | N | 199833 | 0 | -399716 | 0 | 0 | 199883 | 0 | 0 | 0 | 0 | 0 | 0 | -399716 | 0 | 0 | 199883 | 199883 | 0 | 0 | 199833 | 0 | 0 | 0 |  | 1 | 0 | 1 | 1 | NA | 0 | 58.5 | 0 | 58.5 | NA | 0 | 0 | 0 | 399716
N | M007-00-0018-S | M007 | M007 | 00-0018 | SG6 Additional Strobe | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361.7 | Y | 2361.7 | Y | -2361.7 | 0 | 0 | 0 | 0 | 0 | 2361.7 | Y | -2361.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2361.7 | 0 | 0 | 2361.7 | 0 | 0 | 0 | 0 | 0 | 0 | -2361.7 | 0 | 0 | 2361.7 | 2361.7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 2361.7
N | M007-00-0019-L | M007 | M007 | 00-0019 | ODWYER FENCE INSTALL | N | L |  | NR | P | 0 | 38592.79 | 38592.79 | 38592.79 | 38592.79 | 26.8061 | 0 | 0 | 0 | 105377.61 | Y | 143970.4 | Y | -143970.4 | 0 | 0 | 0 | 0 | 0 | 143970.4 | Y | -143970.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -143970.4 | 0 | 4773.95 | 143970.4 | 0 | 0 | 0 | 0 | 0 | 0 | -143970.4 | 0 | 0 | 143970.4 | 143970.4 | 0 | 0 | 0 | 0 | 0 | 1356.85 | 1356.85 | 0 | 369 | 987.85 | 1356.85 | HR | 0 | 320.04 | 0 | 320.04 | NA | 0 | 0 | 0 | 105377.61
N | M007-00-0021-L | M007 | M007 | 00-0021 | MOVE PLAYGROUNDS | N | L |  | NR | P | 0 | 1941.36 | 1941.36 | 1941.36 | 1941.36 | 100 | 0 | 0 | 0 | 0 | Y | 1941.36 | Y | -1941.36 | 0 | 0 | 0 | 0 | 0 | 1941.36 | Y | -1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1941.36 | 0 | 0 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | -1941.36 | 0 | 0 | 1941.36 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 0 | 19 | 0 | 19 | HR | 0 | 19 | 0 | 19 | HR | 0 | 0 | 0 | 0
N | M007-00-0022-L | M007 | M007 | 00-0022 | SITE 8 CLEANING | N | L |  | NR | P | 0 | 5968.61 | 5968.61 | 5968.61 | 5968.61 | 100 | 0 | 0 | 0 | 0 | Y | 5968.61 | Y | -5968.61 | 0 | 0 | 0 | 0 | 0 | 5968.61 | Y | -5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5968.61 | 0 | 0 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | -5968.61 | 0 | 0 | 5968.61 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 57 | 57 | 0 | 57 | 0 | 57 | HR | 0 | 57 | 0 | 57 | HR | 0 | 0 | 0 | 0
N | M007-00-0023-L | M007 | M007 | 00-0023 | S8 FIRE STAND PIPE ACCESS | N | L |  | NR | P | 0 | 7156.91 | 7156.91 | 7156.91 | 7156.91 | 11.1293 | 0 | 0 | 0 | 57149.88 | Y | 64306.79 | Y | -64306.79 | 0 | 0 | 0 | 0 | 0 | 64306.79 | Y | -64306.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -64306.79 | 0 | 0 | 64306.79 | 0 | 0 | 0 | 0 | 0 | 0 | -64306.79 | 0 | 0 | 64306.79 | 64306.79 | 0 | 0 | 0 | 0 | 0 | 531.21 | 531.21 | 0 | 61 | 470.21 | 531.21 | HR | 0 | 61 | 549 | 610 | HR | 0 | 0 | 0 | 57149.88
N | M007-00-0024-L | M007 | M007 | 00-0024 | Boiler Stack Support | N | L |  | NR | P | 0 | 796.41 | 796.41 | 796.41 | 796.41 | 1.2286 | 0 | 0 | 0 | 64024.43 | Y | 64820.84 | Y | -64820.84 | 0 | 0 | 0 | 0 | 0 | 64820.84 | Y | -64820.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -64820.84 | 0 | 0 | 64820.84 | 0 | 0 | 0 | 0 | 0 | 0 | -64820.84 | 0 | 0 | 64820.84 | 64820.84 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 0 | 6.5 | 0 | 6.5 | HR | 0 | 6.5 | 0 | 6.5 | NA | 0 | 0 | 0 | 64024.43
N | M007-00-0025-C | M007 | M007 | 00-0025 | Bulletin 1 Civil PCO 44 | N | C |  | NR | U | 0 | 2587.16 | 2587.16 | 2587.16 | 2587.16 | 15.5478 | 0 | 0 | 0 | 14052.84 | Y | 16640 | Y | -16640 | 0 | 0 | 0 | 0 | 0 | 16640 | Y | -16640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16640 | 2587.16 | 0 | 16640 | 0 | 0 | 0 | 2587.15 | 0 | 0 | -16640 | 0 | 0 | 16640 | 16640 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 66.11 | -66.11 | 0 | NA | 0 | 121 | 5659 | 5780 | NA | 2587.15 | -0.01 | 2587.16 | 14052.84
N | M007-00-0025-L | M007 | M007 | 00-0025 | Bulletin 1 Civil PCO 44 | N | L |  | NR | P | 0 | 14056.57 | 14056.57 | 14056.57 | 14056.57 | 8.087 | 0 | 0 | 0 | 159760.88 | Y | 173817.45 | Y | -173817.45 | 0 | 0 | 0 | 0 | 0 | 173817.45 | Y | -173817.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -173817.45 | 1970.3 | 11242.63 | 173817.45 | 0 | 0 | 0 | 0 | 0 | 0 | -173817.45 | 0 | 0 | 173817.45 | 173817.45 | 0 | 0 | 0 | 0 | 0 | 1445.37 | 1445.37 | 0 | 117.5 | 1327.87 | 1445.37 | HR | 0 | 121 | 5659 | 5780 | NA | 0 | 0 | 0 | 159760.88
N | M007-00-0026-L | M007 | M007 | 00-0026 | DOOR HARDWARE CHANGES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21947.23 | Y | 21947.23 | Y | -21947.23 | 0 | 0 | 0 | 0 | 0 | 21947.23 | Y | -21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21947.23 | 0 | 0 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | -21947.23 | 0 | 0 | 21947.23 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 21947.23
N | M007-00-0027-L | M007 | M007 | 00-0027 | BOILER ACCESSORY SUPPLY | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185547.35 | Y | 185547.35 | Y | -185547.35 | 0 | 0 | 0 | 0 | 0 | 185547.35 | Y | -185547.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -185547.35 | 0 | 0 | 185547.35 | 0 | 0 | 0 | 0 | 0 | 0 | -185547.35 | 0 | 0 | 185547.35 | 185547.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 185547.35
N | M007-00-0028-L | M007 | M007 | 00-0028 | SITE 8 ELECTRICAL REPAIRS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21203.36 | Y | 21203.36 | Y | -21203.36 | 0 | 0 | 0 | 0 | 0 | 21203.36 | Y | -21203.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21203.36 | 0 | 0 | 21203.36 | 0 | 0 | 0 | 0 | 0 | 0 | -21203.36 | 0 | 0 | 21203.36 | 21203.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 21203.36
N | M007-00-0029-L | M007 | M007 | 00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69207.97 | Y | 69207.97 | Y | -69207.97 | 0 | 0 | 0 | 0 | 0 | 69207.97 | Y | -69207.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -69207.97 | 0 | 0 | 69207.97 | 0 | 0 | 0 | 0 | 0 | 0 | -69207.97 | 0 | 0 | 69207.97 | 69207.97 | 0 | 0 | 0 | 0 | 0 | 640.82 | 640.82 | 0 | 0 | 640.82 | 640.82 | HR | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 69207.97
N | M007-00-0029-S | M007 | M007 | 00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 0
N | M007-00-0030-L | M007 | M007 | 00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120833.26 | Y | 120833.26 | Y | -120833.26 | 0 | 0 | 0 | 0 | 0 | 120833.26 | Y | -120833.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120833.26 | 0 | 0 | 120833.26 | 0 | 0 | 0 | 0 | 0 | 0 | -120833.26 | 0 | 0 | 120833.26 | 120833.26 | 0 | 0 | 0 | 0 | 0 | 1118.83 | 1118.83 | 0 | 0 | 1118.83 | 1118.83 | HR | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 120833.26
N | M007-00-0030-S | M007 | M007 | 00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 0
N | M007-00-0031-L | M007 | M007 | 00-0031 | PCO 55 ACM ABATEMENT UTILITY WATERPROOF | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241793.37 | Y | 241793.37 | Y | -241793.37 | 0 | 0 | 0 | 0 | 0 | 241793.37 | Y | -241793.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -241793.37 | 0 | 0 | 241793.37 | 0 | 0 | 0 | 0 | 0 | 0 | -241793.37 | 0 | 0 | 241793.37 | 241793.37 | 0 | 0 | 0 | 0 | 0 | 2238.83 | 2238.83 | 0 | 0 | 2238.83 | 2238.83 | HR | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 241793.37
N | M007-00-0032-S | M007 | M007 | 00-0032 | PCO 64 OG10 ADDITIONAL SWITCH | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2369.68 | Y | 2369.68 | Y | -2369.68 | 0 | 0 | 0 | 0 | 0 | 2369.68 | Y | -2369.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2369.68 | 0 | 0 | 2369.68 | 0 | 0 | 0 | 0 | 0 | 0 | -2369.68 | 0 | 0 | 2369.68 | 2369.68 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 2369.68
N | M007-00-0033-L | M007 | M007 | 00-0033 | PCO 66 ELECTRICAL DB FOUNDATION CONFLICT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24604.63 | Y | 24604.63 | Y | -24604.63 | 0 | 0 | 0 | 0 | 0 | 24604.63 | Y | -24604.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24604.63 | 0 | 0 | 24604.63 | 0 | 0 | 0 | 0 | 0 | 0 | -24604.63 | 0 | 0 | 24604.63 | 24604.63 | 0 | 0 | 0 | 0 | 0 | 227.82 | 227.82 | 0 | 0 | 227.82 | 227.82 | HR | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 24604.63
N | M007-00-0034-C | M007 | M007 | 00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 16 | 16 | NA | 0 | 0 | 0 | 0
N | M007-00-0034-L | M007 | M007 | 00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.76 | Y | 3809.76 | Y | -3809.76 | 0 | 0 | 0 | 0 | 0 | 3809.76 | Y | -3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3809.76 | 0 | 0 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | -3809.76 | 0 | 0 | 3809.76 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 35.28 | 35.28 | 0 | 0 | 35.28 | 35.28 | HR | 0 | 0 | 16 | 16 | NA | 0 | 0 | 0 | 3809.76
N | M007-00-0035-L | M007 | M007 | 00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111590.33 | Y | 111590.33 | Y | -111590.33 | 0 | 0 | 0 | 0 | 0 | 111590.33 | Y | -111590.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111590.33 | 0 | 0 | 111590.33 | 0 | 0 | 0 | 0 | 0 | 0 | -111590.33 | 0 | 0 | 111590.33 | 111590.33 | 0 | 0 | 0 | 0 | 0 | 1033.24 | 1033.24 | 0 | 0 | 1033.24 | 1033.24 | HR | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 111590.33
N | M007-00-0035-S | M007 | M007 | 00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | NA | 0 | 0 | 0 | 0
N | M007-00-0036-C | M007 | M007 | 00-0036 | PCO 99 SG5 APARTMENT RENO | N | C |  | NR | U | 0 | 6694.95 | 6694.95 | 6694.95 | 6694.95 | 100 | 0 | 0 | 0 | 0 | N | 6694.95 | N | -6694.95 | 0 | 0 | 0 | 0 | 0 | 6694.95 | N | -6694.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6694.95 | 0 | 6694.95 | 6694.95 | 0 | 0 | 0 | 0 | 0 | 0 | -6694.95 | 0 | 0 | 6694.95 | 6694.95 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 56.74 | 0 | 56.74 | NA | 0 | 0 | 0 | 0
N | M007-00-0036-L | M007 | M007 | 00-0036 | PCO 99 SG5 APARTMENT RENO | N | L |  | NR | P | 0 | 3197.22 | 3197.22 | 3197.22 | 3197.22 | 100 | 0 | 0 | 0 | 0 | N | 3197.22 | N | -3197.22 | 0 | 0 | 0 | 0 | 0 | 3197.22 | N | -3197.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3197.22 | 0 | 2810.67 | 3197.22 | 0 | 0 | 0 | 0 | 0 | 0 | -3197.22 | 0 | 0 | 3197.22 | 3197.22 | 0 | 0 | 0 | 0 | 0 | 30.5 | 30.5 | 0 | 30.5 | 0 | 30.5 | HR | 0 | 56.74 | 0 | 56.74 | NA | 0 | 0 | 0 | 0
N | M007-00-0037-L | M007 | M007 | 00-0037 | JACOBS TRAILER MOVE | N | L |  | NR | P | 0 | 2879.76 | 2879.76 | 2879.76 | 2879.76 | 100 | 0 | 0 | 0 | 0 | N | 2879.76 | N | -2879.76 | 0 | 0 | 0 | 0 | 0 | 2879.76 | N | -2879.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2879.76 | 0 | 2879.76 | 2879.76 | 0 | 0 | 0 | 0 | 0 | 0 | -2879.76 | 0 | 0 | 2879.76 | 2879.76 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 26 | 0 | 26 | HR | 0 | 26 | 0 | 26 | NA | 0 | 0 | 0 | 0
N | M007-00-0038-L | M007 | M007 | 00-0038 | PCO 59 SGS REDESIGN | N | L |  | NR | P | 0 | 4726.71 | 4726.71 | 4726.71 | 4726.71 | 6.336 | 0 | 0 | 0 | 69874.25 | Y | 74600.96 | Y | -74600.96 | 0 | 0 | 0 | 0 | 0 | 74600.96 | Y | -74600.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -74600.96 | 1354.27 | 3372.44 | 74600.96 | 0 | 0 | 0 | 0 | 0 | 0 | -74600.96 | 0 | 0 | 74600.96 | 74600.96 | 0 | 0 | 0 | 0 | 0 | 30.5 | 30.5 | 0 | 42.5 | -12 | 30.5 | HR | 0 | 42.5 | 0 | 42.5 | NA | 0 | 0 | 0 | 69874.25
N | M007-00-0038-S | M007 | M007 | 00-0038 | PCO 59 SGS REDESIGN | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517295.88 | Y | 517295.88 | Y | -517295.88 | 0 | 0 | 0 | 0 | 0 | 517295.88 | Y | -517295.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -517295.88 | 0 | 0 | 517295.88 | 0 | 0 | 0 | 0 | 0 | 0 | -517295.88 | 0 | 0 | 517295.88 | 517295.88 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 42.5 | 0 | 42.5 | NA | 0 | 0 | 0 | 517295.88
N | M007-00-0039-L | M007 | M007 | 00-0039 | AC UNIT DEMO | N | L |  | NR | P | 0 | 7582.95 | 7582.95 | 7582.95 | 7582.95 | 100 | 0 | 0 | 0 | 0 | N | 7582.95 | N | -7582.95 | 0 | 0 | 0 | 0 | 0 | 7582.95 | N | -7582.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7582.95 | 961.69 | 6621.26 | 6621.26 | -961.69 | 0 | 0 | 0 | 0 | 0 | -7582.95 | 0 | 0 | 7582.95 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 74.5 | 74.5 | 0 | 74.5 | 0 | 74.5 | HR | 0 | 74.5 | 0 | 74.5 | NA | 0 | 0 | 0 | 0
N | M007-00-0040-L | M007 | M007 | 00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6533.27 | Y | 6533.27 | Y | -6533.27 | 0 | 0 | 0 | 0 | 0 | 6533.27 | Y | -6533.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6533.27 | 0 | 0 | 6533.27 | 0 | 0 | 0 | 0 | 0 | 0 | -6533.27 | 0 | 0 | 6533.27 | 6533.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 6533.27
N | M007-00-0040-S | M007 | M007 | 00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38953 | Y | 38953 | Y | -38953 | 0 | 0 | 0 | 0 | 0 | 38953 | Y | -38953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38953 | 0 | 0 | 38953 | 0 | 0 | 0 | 0 | 0 | 0 | -38953 | 0 | 0 | 38953 | 38953 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 38953
N | M007-00-0041-S | M007 | M007 | 00-0041 | PCO 19 WINDOW INFILL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | Y | 7500 | Y | -7500 | 0 | 0 | 0 | 0 | 0 | 7500 | Y | -7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7500 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | -7500 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 7500
N | M007-00-0042-S | M007 | M007 | 00-0042 | PCO 40 SG6 STUD RELOCATION | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10923.98 | Y | 10923.98 | Y | -10923.98 | 0 | 0 | 0 | 0 | 0 | 10923.98 | Y | -10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10923.98 | 0 | 0 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | -10923.98 | 0 | 0 | 10923.98 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 10923.98
N | M007-00-0043-L | M007 | M007 | 00-0043 | PCO 59 SGS ELECTRICAL CHANGES | N | L |  | NR | P | 0 | 213.43 | 213.43 | 213.43 | 213.43 | 100 | 0 | 0 | 0 | 0 | N | 213.43 | N | -213.43 | 0 | 0 | 0 | 0 | 0 | 213.43 | N | -213.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -213.43 | 0 | 213.43 | 213.43 | 0 | 0 | 0 | 0 | 0 | 0 | -213.43 | 0 | 0 | 213.43 | 213.43 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | HR | 0 | 2 | 0 | 2 | NA | 0 | 0 | 0 | 0
N | M007-00-0043-S | M007 | M007 | 00-0043 | PCO 59 SGS ELECTRICAL CHANGES | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 2 | 0 | 2 | NA | 0 | 0 | 0 | 0
N | M007-00-0044-S | M007 | M007 | 00-0044 | PCO 74 OG9 AND S8 GENERATOR SUPPORTS | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66085.26 | Y | 66085.26 | Y | -66085.26 | 0 | 0 | 0 | 0 | 0 | 66085.26 | Y | -66085.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -66085.26 | 0 | 0 | 66085.26 | 0 | 0 | 0 | 0 | 0 | 0 | -66085.26 | 0 | 0 | 66085.26 | 66085.26 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 66085.26
N | M007-00-0045-C | M007 | M007 | 00-0045 | PCO 79 ACM FILING | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | Y | 4500 | Y | -4500 | 0 | 0 | 0 | 0 | 0 | 4500 | Y | -4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4500 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | -4500 | 0 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 4500
N | M007-00-0046-S | M007 | M007 | 00-0046 | PCO 85 OG4 & OG5 TANK INSULATION ACM | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128260 | Y | 128260 | Y | -128260 | 0 | 0 | 0 | 0 | 0 | 128260 | Y | -128260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -128260 | 0 | 0 | 128260 | 0 | 0 | 0 | 0 | 0 | 0 | -128260 | 0 | 0 | 128260 | 128260 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 128260
N | M007-00-0047-S | M007 | M007 | 00-0047 | PCO 90 ODYWER TRAILER POWER | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12046.77 | Y | 12046.77 | Y | -12046.77 | 0 | 0 | 0 | 0 | 0 | 12046.77 | Y | -12046.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12046.77 | 0 | 0 | 12046.77 | 0 | 0 | 0 | 0 | 0 | 0 | -12046.77 | 0 | 0 | 12046.77 | 12046.77 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 12046.77
N | M007-00-0048-S | M007 | M007 | 00-0048 | PCO 45 BULLETIN 1 MECHANICAL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154900.73 | Y | 154900.73 | Y | -154900.73 | 0 | 0 | 0 | 0 | 0 | 154900.73 | Y | -154900.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -154900.73 | 0 | 0 | 154900.73 | 0 | 0 | 0 | 0 | 0 | 0 | -154900.73 | 0 | 0 | 154900.73 | 154900.73 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 154900.73
N | M007-00-0049-L | M007 | M007 | 00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-0049-S | M007 | M007 | 00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70919.49 | Y | 70919.49 | Y | -70919.49 | 0 | 0 | 0 | 0 | 0 | 70919.49 | Y | -70919.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -70919.49 | 0 | 0 | 70919.49 | 0 | 0 | 0 | 0 | 0 | 0 | -70919.49 | 0 | 0 | 70919.49 | 70919.49 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 70919.49
N | M007-00-1000-L | M007 | M007 | 00-1000 | Revenue | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-00-1000-R | M007 | M007 | 00-1000 | Revenue | N | R |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 186800000 | 0 | 0 | 186800000 | 0 | 186800000 | 100087280.73 | 0 | N | 186800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186800000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-01-6000-L | M007 | M007 | 01-6000 | BUILDING CONDITIONS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-01-6000-S | M007 | M007 | 01-6000 | BUILDING CONDITIONS SUB | N | S |  | NR | A | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | Y | 100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-01-6100-L | M007 | M007 | 01-6100 | CPM SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 15 | 22 | 37 | MO | 0 | 0 | 0 | 0
N | M007-01-6100-S | M007 | M007 | 01-6100 | CPM SUB | N | S |  | NR | A | 84508 | 69685 | 69685 | 54930 | 69685 | 75.0923 | 0 | 0 | 0 | 3465 | Y | 73150 | Y | 11358 | 0 | 0 | 84508 | 0 | 0 | 73150 | Y | 11358 | 0 | 0 | 84508 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -73150 | 1167.5 | 1155 | 73150 | 0 | 0 | 0 | 0 | 0 | 0 | -73150 | 0 | 0 | 73150 | 73150 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 25.23 | 20.85 | 46.08 | MO | 37 | 15 | 22 | 37 | MO | 69685 | 14755 | 54930 | 3465
N | M007-01-6200-L | M007 | M007 | 01-6200 | PHOTO SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 15 | 22 | 37 | MO | 0 | 0 | 0 | 0
N | M007-01-6200-S | M007 | M007 | 01-6200 | PHOTO SUB | N | S |  | NR | A | 33522 | 87990 | 87990 | 37450 | 87990 | 42.5617 | 0 | 0 | 0 | 0 | Y | 87990 | Y | -54468 | 0 | 0 | 33522 | 0 | 0 | 87990 | Y | -54468 | 0 | 0 | 33522 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -87990 | 0 | 0 | 87990 | 0 | 0 | 0 | 0 | 0 | 0 | -87990 | 0 | 0 | 87990 | 87990 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 205.28 | 434.76 | 640.04 | MO | 37 | 15 | 22 | 37 | MO | 87990 | 50540 | 37450 | 0
N | M007-01-6300-L | M007 | M007 | 01-6300 | OVERHEAD PROTECTION LABOR | N | L |  | NR | P | 0 | 1472.69 | 1472.69 | 1472.69 | 1472.69 | 3.2726 | 0 | 0 | 0 | 43527.31 | Y | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45000 | 0 | 1472.69 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 172.8 | 172.8 | 0 | 12 | 160.8 | 172.8 | HR | 864 | 60 | 804 | 864 | SF | 0 | 0 | 0 | 43527.31
N | M007-01-6300-M | M007 | M007 | 01-6300 | OVERHEAD PROTECTION LABOR | N | M |  | NR | U | 0 | 5820 | 5820 | 0 | 5820 | 0 | 0 | 0 | 0 | 0 | Y | 5820 | Y | -5820 | 0 | 0 | 0 | 0 | 0 | 5820 | Y | -5820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5820 | 0 | 0 | 5820 | 0 | 0 | 0 | 0 | 0 | 0 | -5820 | 0 | 0 | 5820 | 5820 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 864 | 60 | 804 | 864 | SF | 5820 | 5820 | 0 | 0
N | M007-01-6300-S | M007 | M007 | 01-6300 | OVERHEAD PROTECTION LABOR | N | S |  | NR | A | 1561237.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1561237.56 | 0 | 0 | 1561237.56 | 0 | 0 | 0 | Y | 1561237.56 | 0 | 0 | 1561237.56 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0 | 0 | 12 | 12 | EA | 864 | 60 | 804 | 864 | SF | 0 | 0 | 0 | 0
N | M007-01-6310-C | M007 | M007 | 01-6310 | OVERHEAD PROTECTION MATERIALS | N | C |  | NR | P | 0 | 2573.81 | 2573.81 | 0 | 2573.81 | 0 | 0 | 0 | 0 | 0 | N | 2573.81 | N | -2573.81 | 0 | 0 | 0 | 0 | 0 | 2573.81 | N | -2573.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2573.81 | 0 | 0 | 2573.81 | 0 | 0 | 0 | 0 | 2573.81 | 0 | -2573.81 | 0 | 0 | 2573.81 | 2573.81 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4 | 4 | NA | 0 | 0 | 239 | 239 | LF | 2573.81 | 2573.81 | 0 | 0
N | M007-01-6310-L | M007 | M007 | 01-6310 | OVERHEAD PROTECTION MATERIALS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 239 | 239 | LF | 0 | 0 | 0 | 0
N | M007-01-6310-M | M007 | M007 | 01-6310 | OVERHEAD PROTECTION MATERIALS | N | M |  | NR | P | 0 | 1652.77 | 1652.77 | 0 | 1652.77 | 0 | 0 | 0 | 0 | 33347.23 | Y | 35000 | Y | -35000 | 0 | 0 | 0 | 0 | 0 | 35000 | Y | -35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35000 | 0 | 0 | 35000 | 0 | 0 | 0 | 1652.77 | 0 | 0 | -35000 | 0 | 0 | 35000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 239 | 239 | LF | 1652.77 | 1652.77 | 0 | 33347.23
N | M007-01-6320-E | M007 | M007 | 01-6320 | OVERHEAD PROTECTION EQUIPMENT | N | E |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 864 | 0 | 864 | 864 | SF | 0 | 0 | 0 | 0
N | M007-01-6320-L | M007 | M007 | 01-6320 | OVERHEAD PROTECTION EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 864 | 0 | 864 | 864 | SF | 0 | 0 | 0 | 0
N | M007-01-6400-C | M007 | M007 | 01-6400 | RODENT CONTROL SUB | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-01-6400-L | M007 | M007 | 01-6400 | RODENT CONTROL SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-01-6400-S | M007 | M007 | 01-6400 | RODENT CONTROL SUB | N | S |  | NR | A | 63824 | 38642.09 | 38642.09 | 12173.9 | 38642.09 | 42.5707 | 0 | 0 | 0 | -10045.19 | Y | 28596.9 | Y | 35227.1 | 0 | 0 | 63824 | 0 | 0 | 28596.9 | Y | 35227.1 | 0 | 0 | 63824 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28596.9 | 0 | 0 | 28596.9 | 0 | 0 | 0 | 0 | 0 | 0 | -28596.9 | 0 | 0 | 28596.9 | 28596.9 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 26.44 | 58.95 | 85.39 | LS | 1 | 0 | 1 | 1 | LS | 38642.09 | 26468.19 | 12173.9 | -10045.19
N | M007-01-6410-L | M007 | M007 | 01-6410 | RODENT CONTROL SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-01-6410-S | M007 | M007 | 01-6410 | RODENT CONTROL SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-02-1000-L | M007 | M007 | 02-1000 | EROSION CONTROL FABRIC | N | L |  | NR | P | 32963.2 | 970.55 | 970.55 | 970.55 | 970.55 | 3.5302 | 0 | 0 | 0 | 26522.26 | Y | 27492.81 | Y | 5470.39 | 0 | 0 | 32963.2 | 0 | 0 | 27492.81 | Y | 5470.39 | 0 | 0 | 32963.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27492.81 | 760.17 | 0 | 27492.81 | 0 | 0 | 0 | 0 | 0 | 0 | -27492.81 | 0 | 0 | 27492.81 | 27492.81 | 0 | 0 | 0 | 320 | 0 | 261.36 | 261.36 | 320 | 9.5 | 251.86 | 261.36 | HR | 34000 | 1200 | 32800 | 34000 | SF | 0 | 0 | 0 | 26522.26
N | M007-02-1100-L | M007 | M007 | 02-1100 | INLET PROTECTION | N | L |  | NR | P | 16481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 0 | 160 | 160 | HR | 96 | 0 | 96 | 96 | EA | 0 | 0 | 0 | 0
N | M007-02-1200-L | M007 | M007 | 02-1200 | SILT FENCE | N | L |  | NR | P | 16481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 0 | 160 | 160 | HR | 7500 | 0 | 7500 | 7500 | LF | 0 | 0 | 0 | 0
N | M007-02-1300-L | M007 | M007 | 02-1300 | STABILIZED CONSTRUCTION ENTRANCE | N | L |  | NR | P | 20282.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 20282.8 | 0 | 0 | 20282.8 | 0 | 0 | 0 | Y | 20282.8 | 0 | 0 | 20282.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 200 | 200 | 0 | 200 | 200 | HR | 8000 | 0 | 8000 | 8000 | SF | 0 | 0 | 0 | 0
N | M007-02-1400-L | M007 | M007 | 02-1400 | MANTAIN EROSION CONTROL | N | L |  | NR | P | 32644.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 32644.04 | 0 | 0 | 32644.04 | 0 | 0 | 0 | Y | 32644.04 | 0 | 0 | 32644.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312 | 0 | 312 | 312 | 312 | 0 | 312 | 312 | HR | 52 | 0 | 52 | 52 | WK | 0 | 0 | 0 | 0
N | M007-02-1500-L | M007 | M007 | 02-1500 | REMOVE EROSION CONTROL | N | L |  | NR | P | 16481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | Y | 16481.6 | 0 | 0 | 16481.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 160 | 160 | 160 | 0 | 160 | 160 | HR | 5 | 0 | 5 | 5 | LO | 0 | 0 | 0 | 0
N | M007-02-1600-L | M007 | M007 | 02-1600 | STOCKPILE | N | L |  | NR | P | 231216.48 | 4496.62 | 4496.62 | 4496.62 | 4496.62 | 46.8398 | 0 | 0 | 0 | 5103.38 | Y | 9600 | Y | 221616.48 | 0 | 0 | 231216.48 | 0 | 0 | 9600 | Y | 221616.48 | 0 | 0 | 231216.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9600 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | -9600 | 0 | 0 | 9600 | 9600 | 0 | 0 | 0 | 2112 | 0 | 96 | 96 | 2112 | 41 | 55 | 96 | HR | 6 | 2.61 | 3.39 | 6 | EA | 0 | 0 | 0 | 5103.38
N | M007-02-1700-L | M007 | M007 | 02-1700 | REMOVE FENCE | N | L |  | NR | P | 16481.6 | 21773.52 | 21773.52 | 21773.52 | 21773.52 | 34.6793 | 0 | 0 | 0 | 41011.74 | Y | 62785.26 | Y | -46303.66 | 0 | 0 | 16481.6 | 0 | 0 | 62785.26 | Y | -46303.66 | 0 | 0 | 16481.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -62785.26 | 0 | 0 | 62785.26 | 0 | 0 | 0 | 0 | 0 | 0 | -62785.26 | 0 | 0 | 62785.26 | 62785.26 | 0 | 0 | 0 | 160 | 0 | 581.54 | 581.54 | 160 | 202.5 | 379.04 | 581.54 | HR | 9050 | 3720 | 5330 | 9050 | LF | 0 | 0 | 0 | 41011.74
N | M007-02-1800-L | M007 | M007 | 02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | N | L |  | NR | P | 51378.15 | 627.92 | 627.92 | 627.92 | 627.92 | 1.2222 | 0 | 0 | 0 | 50750.23 | Y | 51378.15 | Y | 0 | 0 | 0 | 51378.15 | 0 | 0 | 51378.15 | Y | 0 | 0 | 0 | 51378.15 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -51378.15 | 0 | 0 | 51378.15 | 0 | 0 | 0 | 0 | 0 | 0 | -51378.15 | 0 | 0 | 51378.15 | 51378.15 | 0 | 0 | 0 | 511.99 | 0 | 511.99 | 511.99 | 511.99 | 6 | 505.99 | 511.99 | HR | 32 | 12 | 20 | 32 | EA | 0 | 0 | 0 | 50750.23
N | M007-02-1900-L | M007 | M007 | 02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | N | L |  | NR | P | 27728.24 | 62132.58 | 62132.58 | 62132.58 | 62132.58 | 81.7773 | 0 | 0 | 0 | 13845.25 | Y | 75977.83 | Y | -48249.59 | 0 | 0 | 27728.24 | 0 | 0 | 75977.83 | Y | -48249.59 | 0 | 0 | 27728.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -75977.83 | 2933.48 | 4702.74 | 75977.83 | 0 | 0 | 0 | 0 | 0 | 0 | -75977.83 | 0 | 0 | 75977.83 | 75977.83 | 0 | 0 | 0 | 253.44 | 0 | 703.16 | 703.16 | 253.44 | 547.5 | 155.66 | 703.16 | HR | 79200 | 58363.38 | 20836.62 | 79200 | SF | 0 | 0 | 0 | 13845.25
N | M007-02-2000-L | M007 | M007 | 02-2000 | REMOVE SITE FURNISHING | N | L |  | NR | P | 77397.6 | 26748.13 | 26748.13 | 26748.13 | 26748.13 | 34.5594 | 0 | 0 | 0 | 50649.47 | Y | 77397.6 | Y | 0 | 0 | 0 | 77397.6 | 0 | 0 | 77397.6 | Y | 0 | 0 | 0 | 77397.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -77397.6 | 0 | 0 | 77397.6 | 0 | 0 | 0 | 0 | 0 | 0 | -77397.6 | 0 | 0 | 77397.6 | 77397.6 | 0 | 0 | 0 | 751.36 | 0 | 751.43 | 751.43 | 751.36 | 247.5 | 503.93 | 751.43 | HR | 117 | 38 | 79 | 117 | EA | 0 | 0 | 0 | 50649.47
N | M007-02-2100-L | M007 | M007 | 02-2100 | REMOVE CONCRETE CURB & STEPS | N | L |  | NR | P | 26257.8 | 53339.64 | 53339.64 | 53339.64 | 53339.64 | 82.6584 | 0 | 0 | 0 | 11190.59 | Y | 64530.23 | Y | -38272.43 | 0 | 0 | 26257.8 | 0 | 0 | 64530.23 | Y | -38272.43 | 0 | 0 | 26257.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -64530.23 | 1332.96 | 2387.34 | 64530.23 | 0 | 0 | 0 | 0 | 0 | 0 | -64530.23 | 0 | 0 | 64530.23 | 64530.23 | 0 | 0 | 0 | 240 | 0 | 640 | 640 | 240 | 489 | 151 | 640 | HR | 13000 | 7749.4 | 5250.6 | 13000 | LF | 0 | 0 | 0 | 11190.59
N | M007-02-2200-L | M007 | M007 | 02-2200 | REMOVE PVMTS | N | L |  | NR | P | 107421.11 | 12018.39 | 12018.39 | 12018.39 | 12018.39 | 11.1881 | 0 | 0 | 0 | 95402.72 | Y | 107421.11 | Y | 0 | 0 | 0 | 107421.11 | 0 | 0 | 107421.11 | Y | 0 | 0 | 0 | 107421.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -107421.11 | 0 | 0 | 107421.11 | 0 | 0 | 0 | 0 | 0 | 0 | -107421.11 | 0 | 0 | 107421.11 | 107421.11 | 0 | 0 | 0 | 998.75 | 0 | 1091.82 | 1091.82 | 998.75 | 109 | 982.82 | 1091.82 | HR | 156053 | 12627.4 | 143425.6 | 156053 | SF | 0 | 0 | 0 | 95402.72
N | M007-02-2300-C | M007 | M007 | 02-2300 | BASEMENT MAINTENANCE | N | C |  | NR | U | 0 | 17373.79 | 17373.79 | 17373.79 | 17373.79 | 100 | 0 | 0 | 0 | 0 | Y | 17373.79 | Y | -17373.79 | 0 | 0 | 0 | 0 | 0 | 17373.79 | Y | -17373.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17373.79 | 0 | 383.78 | 17373.79 | 0 | 0 | 0 | 0 | 383.78 | 0 | -17373.79 | 0 | 0 | 17373.79 | 17373.79 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 361.62 | -336.62 | 25 | NA | 960 | 1987 | 17.09 | 2004.09 | HR | 13718.95 | -3654.84 | 17373.79 | 0
N | M007-02-2300-L | M007 | M007 | 02-2300 | BASEMENT MAINTENANCE | N | L |  | NR | P | 0 | 203017.73 | 203017.73 | 203017.73 | 203017.73 | 102.178 | 0 | 0 | 0 | -4327.41 | Y | 198690.32 | Y | -198690.32 | 0 | 0 | 0 | 0 | 0 | 198690.32 | Y | -198690.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -198690.32 | 4821.71 | 6350.92 | 198690.32 | 0 | 0 | 0 | 0 | 0 | 0 | -198690.32 | 0 | 0 | 198690.32 | 198690.32 | 0 | 0 | 0 | 0 | 0 | 2004.09 | 2004.09 | 0 | 2047 | -42.91 | 2004.09 | HR | 960 | 1987 | 17.09 | 2004.09 | HR | 0 | 0 | 0 | -4327.41
N | M007-02-2300-M | M007 | M007 | 02-2300 | BASEMENT MAINTENANCE | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 960 | 1987 | 17.09 | 2004.09 | HR | 0 | 0 | 0 | 0
N | M007-02-3000-C | M007 | M007 | 02-3000 | CORE DRILLING | N | C |  | NR | U | 0 | 245820.04 | 245820.04 | 224048.73 | 245820.04 | 94.9514 | 0 | 0 | 0 | -9858.64 | Y | 235961.4 | Y | -235961.4 | 0 | 0 | 0 | 0 | 0 | 235961.4 | Y | -235961.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -235961.4 | 5555 | 0 | 235961.4 | 0 | 0 | 0 | 9858.64 | 0 | 0 | -235961.4 | 0 | 0 | 235961.4 | 235961.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 140 | -2 | 138 | NA | 0 | 188.19 | 0 | 188.19 | EA | 245820.04 | 21771.31 | 224048.73 | -9858.64
N | M007-02-3000-L | M007 | M007 | 02-3000 | CORE DRILLING | N | L |  | NR | P | 0 | 139225.3 | 139225.3 | 139225.3 | 139225.3 | 59.8735 | 0 | 0 | 0 | 93307.03 | Y | 232532.33 | Y | -232532.33 | 0 | 0 | 0 | 0 | 0 | 232532.33 | Y | -232532.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -232532.33 | 5383.87 | 5163.19 | 232532.33 | 0 | 0 | 0 | 0 | 0 | 0 | -232532.33 | 0 | 0 | 232532.33 | 232532.33 | 0 | 0 | 0 | 0 | 0 | 1316.5 | 1316.5 | 0 | 1370 | -53.5 | 1316.5 | HR | 0 | 188.19 | 0 | 188.19 | EA | 0 | 0 | 0 | 93307.03
N | M007-02-3000-S | M007 | M007 | 02-3000 | CORE DRILLING | N | S |  | NR | A | 0 | 145190 | 145190 | 65285 | 145190 | 100 | 0 | 0 | 0 | -79905 | Y | 65285 | Y | -65285 | 0 | 0 | 0 | 0 | 0 | 65285 | Y | -65285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65285 | 0 | 0 | 65285 | 0 | 0 | 0 | 0 | -89310 | 0 | -65285 | 0 | 0 | 65285 | 65285 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 32.5 | -32.5 | 0 | NA | 0 | 188.19 | 0 | 188.19 | EA | 145190 | 79905 | 65285 | -79905
N | M007-02-6000-C | M007 | M007 | 02-6000 | OG-7 DEMO LABOR | N | C |  | NR | U | 0 | 8802.55 | 8802.55 | 8802.55 | 8802.55 | 100 | 0 | 0 | 0 | 0 | N | 8802.55 | N | -8802.55 | 0 | 0 | 0 | 0 | 0 | 8802.55 | N | -8802.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8802.55 | 0 | 0 | 8802.55 | 0 | 0 | 0 | 0 | 0 | 0 | -8802.55 | 0 | 0 | 8802.55 | 8802.55 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 0 | 4 | NA | 1 | 1 | 0 | 1 | EA | 0 | -8802.55 | 8802.55 | 0
N | M007-02-6000-L | M007 | M007 | 02-6000 | OG-7 DEMO LABOR | N | L |  | NR | P | 0 | 12757.46 | 12757.46 | 12757.46 | 12757.46 | 100 | 0 | 0 | 0 | 0 | Y | 12757.46 | Y | -12757.46 | 0 | 0 | 0 | 0 | 0 | 12757.46 | Y | -12757.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12757.46 | 0 | 0 | 12757.46 | 0 | 0 | 0 | 0 | 0 | 0 | -12757.46 | 0 | 0 | 12757.46 | 12757.46 | 0 | 0 | 0 | 0 | 0 | 116.5 | 116.5 | 0 | 116.5 | 0 | 116.5 | HR | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
N | M007-02-6000-S | M007 | M007 | 02-6000 | OG-7 DEMO LABOR | N | S |  | NR | A | 1600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 1600000 | 0 | 0 | 1600000 | 0 | 0 | 0 | Y | 1600000 | 0 | 0 | 1600000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 0 | 1 | 1 | LS | 1 | 1 | 0 | 1 | EA | 0 | 0 | 0 | 0
N | M007-02-6001-E | M007 | M007 | 02-6001 | OG-7 DEMO EQUIPMENT | N | E |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
N | M007-02-6001-L | M007 | M007 | 02-6001 | OG-7 DEMO EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
N | M007-02-6002-L | M007 | M007 | 02-6002 | OG-7 DEMO MATERIAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 70 | 0 | 70 | 70 | CY | 0 | 0 | 0 | 0
N | M007-02-6002-M | M007 | M007 | 02-6002 | OG-7 DEMO MATERIAL | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 70 | 0 | 70 | 70 | CY | 0 | 0 | 0 | 0
N | M007-02-6005-C | M007 | M007 | 02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | N | C |  | NR | U | 0 | 1537.73 | 1537.73 | 1537.73 | 1537.73 | 100 | 0 | 0 | 0 | 0 | Y | 1537.73 | Y | -1537.73 | 0 | 0 | 0 | 0 | 0 | 1537.73 | Y | -1537.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1537.73 | 0 | 0 | 1537.73 | 0 | 0 | 0 | 0 | 0 | 0 | -1537.73 | 0 | 0 | 1537.73 | 1537.73 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.5 | 38.52 | 52.02 | NA | 33320 | 28889.75 | 4430.25 | 33320 | SF | 659.9 | -877.83 | 1537.73 | 0
N | M007-02-6005-L | M007 | M007 | 02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | N | L |  | NR | P | 0 | 326430.15 | 326430.15 | 326430.15 | 326430.15 | 87.8323 | 0 | 0 | 0 | 45221.29 | Y | 371651.44 | Y | -371651.44 | 0 | 0 | 0 | 0 | 0 | 371651.44 | Y | -371651.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -371651.44 | 0 | 3876.77 | 371651.44 | 0 | 0 | 0 | 0 | 0 | 0 | -371651.44 | 0 | 0 | 371651.44 | 371651.44 | 0 | 0 | 0 | 0 | 0 | 3788.98 | 3788.98 | 0 | 3326 | 462.98 | 3788.98 | HR | 33320 | 28889.75 | 4430.25 | 33320 | SF | 0 | 0 | 0 | 45221.29
N | M007-02-6005-S | M007 | M007 | 02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 33320 | 28889.75 | 4430.25 | 33320 | SF | 0 | 0 | 0 | 0
N | M007-02-6006-C | M007 | M007 | 02-6006 | LEAD CONSULTANT | N | C |  | NR | U | 0 | 38243.07 | 38243.07 | 19466.75 | 38243.07 | 77.867 | 0 | 0 | 0 | -13243.07 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 5988.13 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 86.5 | -15.52 | 70.98 | NA | 1 | 0 | 1 | 1 | LS | 38243.07 | 18776.32 | 19466.75 | -13243.07
N | M007-02-6006-L | M007 | M007 | 02-6006 | LEAD CONSULTANT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-02-6007-C | M007 | M007 | 02-6007 | LEAD DISPOSAL | N | C |  | NR | U | 0 | 20005.08 | 20005.08 | 5400.21 | 20005.08 | 41.9858 | 0 | 0 | 0 | -7143.08 | Y | 12862 | Y | -12862 | 0 | 0 | 0 | 0 | 0 | 12862 | Y | -12862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12862 | 0 | 0 | 12862 | 0 | 0 | 0 | 0 | 0 | 0 | -12862 | 0 | 0 | 12862 | 12862 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 60 | 2004 | 2064 | NA | 13.19 | 0 | 13.19 | 13.19 | CY | 20005.08 | 14604.87 | 5400.21 | -7143.08
N | M007-02-6007-L | M007 | M007 | 02-6007 | LEAD DISPOSAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 13.19 | 0 | 13.19 | 13.19 | CY | 0 | 0 | 0 | 0
N | M007-02-6008-C | M007 | M007 | 02-6008 | LEAD TRAINING | N | C |  | NR | U | 0 | 6125.6 | 6125.6 | 3932 | 6125.6 | 100 | 0 | 0 | 0 | -2193.6 | Y | 3932 | Y | -3932 | 0 | 0 | 0 | 0 | 0 | 3932 | Y | -3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3932 | 0 | 492 | 3932 | 0 | 0 | 0 | 0 | 0 | 0 | -3932 | 0 | 0 | 3932 | 3932 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 42 | -18.89 | 23.11 | NA | 14 | 6 | 8 | 14 | EA | 5665.6 | 2193.6 | 3472 | -2193.6
N | M007-02-6008-L | M007 | M007 | 02-6008 | LEAD TRAINING | N | L |  | NR | P | 0 | 4317.33 | 4317.33 | 4317.33 | 4317.33 | 31.4216 | 0 | 0 | 0 | 9422.67 | Y | 13740 | Y | -13740 | 0 | 0 | 0 | 0 | 0 | 13740 | Y | -13740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13740 | 0 | 0 | 13740 | 0 | 0 | 0 | 0 | 0 | 0 | -13740 | 0 | 0 | 13740 | 13740 | 0 | 0 | 0 | 0 | 0 | 143.51 | 143.51 | 0 | 45 | 98.51 | 143.51 | HR | 14 | 6 | 8 | 14 | EA | 0 | 0 | 0 | 9422.67
N | M007-02-6009-L | M007 | M007 | 02-6009 | Paint Removal Elevator Pits | N | L |  | NR | P | 0 | 1052.44 | 1052.44 | 1052.44 | 1052.44 | 1.5661 | 0 | 0 | 0 | 66147.56 | Y | 67200 | Y | -67200 | 0 | 0 | 0 | 0 | 0 | 67200 | Y | -67200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -67200 | 0 | 0 | 67200 | 0 | 0 | 0 | 0 | 0 | 0 | -67200 | 0 | 0 | 67200 | 67200 | 0 | 0 | 0 | 0 | 0 | 671.98 | 671.98 | 0 | 10.5 | 661.48 | 671.98 | HR | 0 | 0.2 | 11.8 | 12 | EA | 0 | 0 | 0 | 66147.56
N | M007-02-6010-L | M007 | M007 | 02-6010 | REMOVE SUMP PUMPS | N | L |  | NR | P | 0 | 13724.47 | 13724.47 | 13724.47 | 13724.47 | 34.7169 | 0 | 0 | 0 | 25808.01 | Y | 39532.48 | Y | -39532.48 | 0 | 0 | 0 | 0 | 0 | 39532.48 | Y | -39532.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39532.48 | 506.78 | 2335.62 | 39532.48 | 0 | 0 | 0 | 0 | 0 | 0 | -39532.48 | 0 | 0 | 39532.48 | 39532.48 | 0 | 0 | 0 | 0 | 0 | 416 | 416 | 0 | 131 | 285 | 416 | HR | 36 | 16 | 20 | 36 | EA | 0 | 0 | 0 | 25808.01
N | M007-02-6010-M | M007 | M007 | 02-6010 | REMOVE SUMP PUMPS | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 36 | 16 | 20 | 36 | EA | 0 | 0 | 0 | 0
N | M007-02-6015-L | M007 | M007 | 02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | N | L |  | NR | P | 0 | 56737.21 | 56737.21 | 56737.21 | 56737.21 | 72.81 | 0 | 0 | 0 | 21187.79 | Y | 77925 | Y | -77925 | 0 | 0 | 0 | 0 | 0 | 77925 | Y | -77925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -77925 | 846.78 | 4030.63 | 77925 | 0 | 0 | 0 | 0 | 0 | 0 | -77925 | 0 | 0 | 77925 | 77925 | 0 | 0 | 0 | 0 | 0 | 755.53 | 755.53 | 0 | 551 | 204.53 | 755.53 | HR | 185 | 145 | 40 | 185 | EA | 0 | 0 | 0 | 21187.79
N | M007-02-6015-S | M007 | M007 | 02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 185 | 145 | 40 | 185 | EA | 0 | 0 | 0 | 0
N | M007-02-6020-E | M007 | M007 | 02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | N | E |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 24 | 1 | 23 | 24 | EA | 0 | 0 | 0 | 0
N | M007-02-6020-L | M007 | M007 | 02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | N | L |  | NR | P | 0 | 1088.47 | 1088.47 | 1088.47 | 1088.47 | 5.5067 | 0 | 0 | 0 | 18677.77 | Y | 19766.24 | Y | -19766.24 | 0 | 0 | 0 | 0 | 0 | 19766.24 | Y | -19766.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19766.24 | 0 | 0 | 19766.24 | 0 | 0 | 0 | 0 | 0 | 0 | -19766.24 | 0 | 0 | 19766.24 | 19766.24 | 0 | 0 | 0 | 0 | 0 | 208 | 208 | 0 | 11 | 197 | 208 | HR | 24 | 1 | 23 | 24 | EA | 0 | 0 | 0 | 18677.77
N | M007-02-6025-L | M007 | M007 | 02-6025 | REMOVE AREAWAYS LABOR | N | L |  | NR | P | 0 | 34193.61 | 34193.61 | 34193.61 | 34193.61 | 27.3599 | 0 | 0 | 0 | 90783.51 | Y | 124977.12 | Y | -124977.12 | 0 | 0 | 0 | 0 | 0 | 124977.12 | Y | -124977.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -124977.12 | 4437.26 | 20745.9 | 124977.12 | 0 | 0 | 0 | 0 | 0 | 0 | -124977.12 | 0 | 0 | 124977.12 | 124977.12 | 0 | 0 | 0 | 0 | 0 | 1239.98 | 1239.98 | 0 | 325.5 | 914.48 | 1239.98 | HR | 52.17 | 27 | 25.17 | 52.17 | CY | 0 | 0 | 0 | 90783.51
N | M007-02-6025-S | M007 | M007 | 02-6025 | REMOVE AREAWAYS LABOR | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 52.17 | 27 | 25.17 | 52.17 | CY | 0 | 0 | 0 | 0
N | M007-02-6026-E | M007 | M007 | 02-6026 | REMOVE AREAWAYS EQUIPMENT | N | E |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7750 | Y | 7750 | Y | -7750 | 0 | 0 | 0 | 0 | 0 | 7750 | Y | -7750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7750 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 | -7750 | 0 | 0 | 7750 | 7750 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 52.17 | 0 | 52.17 | 52.17 | CY | 0 | 0 | 0 | 7750
N | M007-02-6026-L | M007 | M007 | 02-6026 | REMOVE AREAWAYS EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 52.17 | 0 | 52.17 | 52.17 | CY | 0 | 0 | 0 | 0
N | M007-02-6030-L | M007 | M007 | 02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | N | L |  | NR | P | 0 | 385.53 | 385.53 | 385.53 | 385.53 | 0.16927 | 0 | 0 | 0 | 227375.93 | Y | 227761.46 | Y | -227761.46 | 0 | 0 | 0 | 0 | 0 | 227761.46 | Y | -227761.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -227761.46 | 0 | 0 | 227761.46 | 0 | 0 | 0 | 0 | 0 | 0 | -227761.46 | 0 | 0 | 227761.46 | 227761.46 | 0 | 0 | 0 | 0 | 0 | 2363.1 | 2363.1 | 0 | 4 | 2359.1 | 2363.1 | HR | 9460 | 880 | 8580 | 9460 | SF | 0 | 0 | 0 | 227375.93
N | M007-02-6030-S | M007 | M007 | 02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9460 | 880 | 8580 | 9460 | SF | 0 | 0 | 0 | 0
N | M007-02-6035-L | M007 | M007 | 02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520.48 | Y | 1520.48 | Y | -1520.48 | 0 | 0 | 0 | 0 | 0 | 1520.48 | Y | -1520.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1520.48 | 0 | 0 | 1520.48 | 0 | 0 | 0 | 0 | 0 | 0 | -1520.48 | 0 | 0 | 1520.48 | 1520.48 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 16 | 16 | HR | 0.22 | 0 | 0.22 | 0.22 | CY | 0 | 0 | 0 | 1520.48
N | M007-02-6035-S | M007 | M007 | 02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0.22 | 0 | 0.22 | 0.22 | CY | 0 | 0 | 0 | 0
N | M007-02-6040-L | M007 | M007 | 02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18245.76 | Y | 18245.76 | Y | -18245.76 | 0 | 0 | 0 | 0 | 0 | 18245.76 | Y | -18245.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18245.76 | 0 | 0 | 18245.76 | 0 | 0 | 0 | 0 | 0 | 0 | -18245.76 | 0 | 0 | 18245.76 | 18245.76 | 0 | 0 | 0 | 0 | 0 | 192 | 192 | 0 | 0 | 192 | 192 | HR | 0.77 | 0 | 0.77 | 0.77 | CY | 0 | 0 | 0 | 18245.76
N | M007-02-6040-S | M007 | M007 | 02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0.77 | 0 | 0.77 | 0.77 | CY | 0 | 0 | 0 | 0
N | M007-02-6045-L | M007 | M007 | 02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | N | L |  | NR | P | 0 | 3487.09 | 3487.09 | 3487.09 | 3487.09 | 11.4671 | 0 | 0 | 0 | 26922.51 | Y | 30409.6 | Y | -30409.6 | 0 | 0 | 0 | 0 | 0 | 30409.6 | Y | -30409.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30409.6 | 0 | 3487.09 | 30409.6 | 0 | 0 | 0 | 0 | 0 | 0 | -30409.6 | 0 | 0 | 30409.6 | 30409.6 | 0 | 0 | 0 | 0 | 0 | 320 | 320 | 0 | 34.5 | 285.5 | 320 | HR | 114 | 14 | 100 | 114 | EA | 0 | 0 | 0 | 26922.51
N | M007-02-6045-S | M007 | M007 | 02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 114 | 14 | 100 | 114 | EA | 0 | 0 | 0 | 0
N | M007-02-6050-L | M007 | M007 | 02-6050 | DEMO STAIRS AND RAMPS LABOR | N | L |  | NR | P | 0 | 6717.56 | 6717.56 | 6717.56 | 6717.56 | 39.2458 | 0 | 0 | 0 | 10399.08 | Y | 17116.64 | Y | -17116.64 | 0 | 0 | 0 | 0 | 0 | 17116.64 | Y | -17116.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17116.64 | 0 | 0 | 17116.64 | 0 | 0 | 0 | 0 | 0 | 0 | -17116.64 | 0 | 0 | 17116.64 | 17116.64 | 0 | 0 | 0 | 0 | 0 | 168.01 | 168.01 | 0 | 62.5 | 105.51 | 168.01 | HR | 15.07 | 9 | 6.07 | 15.07 | CY | 0 | 0 | 0 | 10399.08
N | M007-02-6050-S | M007 | M007 | 02-6050 | DEMO STAIRS AND RAMPS LABOR | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 15.07 | 9 | 6.07 | 15.07 | CY | 0 | 0 | 0 | 0
N | M007-02-6051-E | M007 | M007 | 02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | N | E |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | Y | 3000 | Y | -3000 | 0 | 0 | 0 | 0 | 0 | 3000 | Y | -3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 5 | 0 | 5 | 5 | DY | 0 | 0 | 0 | 3000
N | M007-02-6051-L | M007 | M007 | 02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5 | 0 | 5 | 5 | DY | 0 | 0 | 0 | 0
N | M007-02-6055-L | M007 | M007 | 02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34210.8 | Y | 34210.8 | Y | -34210.8 | 0 | 0 | 0 | 0 | 0 | 34210.8 | Y | -34210.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34210.8 | 0 | 0 | 34210.8 | 0 | 0 | 0 | 0 | 0 | 0 | -34210.8 | 0 | 0 | 34210.8 | 34210.8 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 0 | 0 | 360 | 360 | HR | 2.06 | 0 | 2.06 | 2.06 | CY | 0 | 0 | 0 | 34210.8
N | M007-02-6055-S | M007 | M007 | 02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 2.06 | 0 | 2.06 | 2.06 | CY | 0 | 0 | 0 | 0
N | M007-02-6060-L | M007 | M007 | 02-6060 | DEMO SECOND FLOOR APARTMENTS | N | L |  | NR | P | 0 | 110480.81 | 110480.81 | 110480.81 | 110480.81 | 67.2659 | 0 | 0 | 0 | 53764.03 | Y | 164244.84 | Y | -164244.84 | 0 | 0 | 0 | 0 | 0 | 164244.84 | Y | -164244.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -164244.84 | 1345.24 | 6353.34 | 164244.84 | 0 | 0 | 0 | 0 | 0 | 0 | -164244.84 | 0 | 0 | 164244.84 | 164244.84 | 0 | 0 | 0 | 0 | 0 | 1728.35 | 1728.35 | 0 | 1079 | 649.35 | 1728.35 | HR | 9 | 6.26 | 2.74 | 9 | EA | 0 | 0 | 0 | 53764.03
N | M007-02-6060-S | M007 | M007 | 02-6060 | DEMO SECOND FLOOR APARTMENTS | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 9 | 6.26 | 2.74 | 9 | EA | 0 | 0 | 0 | 0
N | M007-02-6065-L | M007 | M007 | 02-6065 | DEMO FOR MECHANICAL | N | L |  | NR | P | 0 | 11078.48 | 11078.48 | 11078.48 | 11078.48 | 5.5392 | 0 | 0 | 0 | 188921.52 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 1999.73 | 1999.73 | 0 | 107 | 1892.73 | 1999.73 | HR | 0 | 148.5 | 2101.5 | 2250 | HR | 0 | 0 | 0 | 188921.52
N | M007-02-6065-S | M007 | M007 | 02-6065 | DEMO FOR MECHANICAL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 148.5 | 2101.5 | 2250 | HR | 0 | 0 | 0 | 0
N | M007-02-6066-L | M007 | M007 | 02-6066 | FLOOR DRAIN DEMO | N | L |  | NR | P | 0 | 70083.35 | 70083.35 | 70083.35 | 70083.35 | 100 | 0 | 0 | 0 | 0 | Y | 70083.35 | Y | -70083.35 | 0 | 0 | 0 | 0 | 0 | 70083.35 | Y | -70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -70083.35 | 0 | 0 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | -70083.35 | 0 | 0 | 70083.35 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 725.5 | 725.5 | 0 | 725.5 | 0 | 725.5 | HR | 48 | 48 | 0 | 48 | EA | 0 | 0 | 0 | 0
N | M007-02-6070-L | M007 | M007 | 02-6070 | DEMO FOR ELECTRICAL | N | L |  | NR | P | 0 | 9920.34 | 9920.34 | 9920.34 | 9920.34 | 4.409 | 0 | 0 | 0 | 215079.66 | Y | 225000 | Y | -225000 | 0 | 0 | 0 | 0 | 0 | 225000 | Y | -225000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -225000 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 0 | -225000 | 0 | 0 | 225000 | 225000 | 0 | 0 | 0 | 0 | 0 | 2214.2 | 2214.2 | 0 | 97.5 | 2116.7 | 2214.2 | HR | 0 | 97.5 | 2116.41 | 2213.91 | HR | 0 | 0 | 0 | 215079.66
N | M007-02-6070-S | M007 | M007 | 02-6070 | DEMO FOR ELECTRICAL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 97.5 | 2116.41 | 2213.91 | HR | 0 | 0 | 0 | 0
N | M007-02-6075-L | M007 | M007 | 02-6075 | DEMO FOR PLUMBING | N | L |  | NR | P | 0 | 14739.37 | 14739.37 | 14739.37 | 14739.37 | 6.9565 | 0 | 0 | 0 | 197140.25 | Y | 211879.62 | Y | -211879.62 | 0 | 0 | 0 | 0 | 0 | 211879.62 | Y | -211879.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -211879.62 | 0 | 858.06 | 211879.62 | 0 | 0 | 0 | 0 | 0 | 0 | -211879.62 | 0 | 0 | 211879.62 | 211879.62 | 0 | 0 | 0 | 0 | 0 | 2187.93 | 2187.93 | 0 | 140.5 | 2047.43 | 2187.93 | HR | 0 | 140.5 | 2047.44 | 2187.94 | HR | 0 | 0 | 0 | 197140.25
N | M007-02-6075-S | M007 | M007 | 02-6075 | DEMO FOR PLUMBING | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 140.5 | 2047.44 | 2187.94 | HR | 0 | 0 | 0 | 0
N | M007-02-6100-L | M007 | M007 | 02-6100 | ASBESTOS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-02-6100-S | M007 | M007 | 02-6100 | ASBESTOS SUB | N | S |  | NR | A | 1658000.22 | 1569944.22 | 1569944.22 | 1123327.96 | 1569944.22 | 72.2442 | 0 | 0 | 0 | -15041.08 | Y | 1554903.14 | Y | 103097.08 | 0 | 0 | 1658000.22 | 0 | 0 | 1554903.14 | Y | 103097.08 | 0 | 0 | 1658000.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1554903.14 | 0 | 110836.36 | 1554903.14 | 0 | 0 | 0 | 0 | 0 | 0 | -1554903.14 | 0 | 0 | 1554903.14 | 1554903.14 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 14817.73 | 3839.27 | 18657 | LS | 1 | 0 | 1 | 1 | LS | 1569944.22 | 446616.26 | 1123327.96 | -15041.08
N | M007-02-6110-L | M007 | M007 | 02-6110 | ASBESTOS SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79433.41 | Y | 79433.41 | Y | -79433.41 | 0 | 0 | 0 | 0 | 0 | 79433.41 | Y | -79433.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -79433.41 | 0 | 0 | 79433.41 | 0 | 0 | 0 | 0 | 0 | 0 | -79433.41 | 0 | 0 | 79433.41 | 79433.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 79433.41
N | M007-02-6110-S | M007 | M007 | 02-6110 | ASBESTOS SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
N | M007-02-6120-C | M007 | M007 | 02-6120 | ASEBESTOS CONSULTANT | N | C |  | NR | U | 0 | 84866.98 | 84866.98 | 23896.55 | 84866.98 | 47.7931 | 0 | 0 | 0 | -34866.98 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 149.5 | -62.89 | 86.61 | NA | 9 | 0 | 9 | 9 | EA | 84866.98 | 60970.43 | 23896.55 | -34866.98
N | M007-02-6120-L | M007 | M007 | 02-6120 | ASEBESTOS CONSULTANT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9 | 0 | 9 | 9 | EA | 0 | 0 | 0 | 0
N | M007-02-6130-C | M007 | M007 | 02-6130 | ASBESTOS SUB ACCESS | N | C |  | NR | U | 0 | 6029.52 | 6029.52 | 1720.79 | 6029.52 | 31.6104 | 0 | 0 | 0 | -585.77 | Y | 5443.75 | Y | -5443.75 | 0 | 0 | 0 | 0 | 0 | 5443.75 | Y | -5443.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5443.75 | 0 | 0 | 5443.75 | 0 | 0 | 0 | 585.77 | 0 | 0 | -5443.75 | 0 | 0 | 5443.75 | 5443.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1652.88 | 0 | 1652.88 | NA | 0 | 172 | 0 | 172 | HR | 6596.11 | 4308.73 | 2287.38 | -585.77
N | M007-02-6130-L | M007 | M007 | 02-6130 | ASBESTOS SUB ACCESS | N | L |  | NR | P | 0 | 20099.71 | 20099.71 | 20099.71 | 20099.71 | 100.4985 | 0 | 0 | 0 | -99.71 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 750.99 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 167.35 | 167.35 | 0 | 170 | -2.65 | 167.35 | HR | 0 | 172 | 0 | 172 | HR | 0 | 0 | 0 | -99.71
N | M007-02-7000-C | M007 | M007 | 02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | N | C |  | NR | A | 72024.12 | 1900.42 | 1900.42 | 1900.42 | 1900.42 | 100 | 0 | 0 | 0 | 0 | Y | 1900.42 | Y | 70123.7 | 0 | 0 | 72024.12 | 0 | 0 | 1900.42 | Y | 70123.7 | 0 | 0 | 72024.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1900.42 | 0 | 0 | 1900.42 | 0 | 0 | 0 | 0 | 0 | 0 | -1900.42 | 0 | 0 | 1900.42 | 1900.42 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 60.19 | 2220.95 | 2281.14 | LS | 1 | 0 | 1 | 1 | LS | 1900.42 | 0 | 1900.42 | 0
N | M007-02-7000-L | M007 | M007 | 02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-02-7100-C | M007 | M007 | 02-7100 | STONE FOR EROSION CONTROL | N | C |  | NR | P | 11024.1 | 47286.55 | 47286.55 | 32281.37 | 47286.55 | 100 | 0 | 0 | 0 | -15005.18 | Y | 32281.37 | Y | -21257.27 | 0 | 0 | 11024.1 | 0 | 0 | 32281.37 | Y | -21257.27 | 0 | 0 | 11024.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32281.37 | 0 | 0 | 32281.37 | 0 | 0 | 0 | 0 | 4439.26 | 0 | -32281.37 | 0 | 0 | 32281.37 | 32281.37 | 0 | 0 | 0 | 405 | 0 | 0 |  | 405 | 1025.6 | -252.91 | 772.69 | CY | 405 | 0 | 405 | 405 | CY | 47286.55 | 15005.18 | 32281.37 | -15005.18
N | M007-02-7100-L | M007 | M007 | 02-7100 | STONE FOR EROSION CONTROL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 405 | 0 | 405 | 405 | CY | 0 | 0 | 0 | 0
N | M007-02-7200-C | M007 | M007 | 02-7200 | SOIL TESTING | N | C |  | NR | P | 21776 | 93315 | 93315 | 83535 | 93315 | 100 | 0 | 0 | 0 | -9780 | Y | 83535 | Y | -61759 | 0 | 0 | 21776 | 0 | 0 | 83535 | Y | -61759 | 0 | 0 | 21776 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -83535 | 0 | 0 | 83535 | 0 | 0 | 0 | 0 | 0 | 0 | -83535 | 0 | 0 | 83535 | 83535 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 72.96 | -7.65 | 65.31 | LS | 35 | 0 | 35 | 35 | EA | 93315 | 9780 | 83535 | -9780
N | M007-02-7200-L | M007 | M007 | 02-7200 | SOIL TESTING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 35 | 0 | 35 | 35 | EA | 0 | 0 | 0 | 0
N | M007-03-1000-L | M007 | M007 | 03-1000 | FORMWORK NEW BUILDING | N | L |  | NR | P | 1767696.75 | 2013716.53 | 2013716.53 | 2013716.53 | 2013716.53 | 97.8741 | 0 | 0 | 0 | 43739.41 | Y | 2057455.94 | Y | -289759.19 | 0 | 0 | 1767696.75 | 0 | 0 | 2057455.94 | Y | -289759.19 | 0 | 0 | 1767696.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2057455.94 | 31433.11 | 24522.57 | 2057455.94 | 0 | 0 | 0 | 0 | 0 | 0 | -2057455.94 | 0 | 0 | 2057455.94 | 2057455.94 | 0 | 0 | 0 | 15573 | 0 | 18185.24 | 18185.24 | 15573 | 17815 | 370.24 | 18185.24 | HR | 62292 | 57754.13 | 4537.87 | 62292 | SF | 0 | 0 | 0 | 43739.41
N | M007-03-1100-L | M007 | M007 | 03-1100 | FORMWORK EXIST BLDGS | N | L |  | NR | P | 520331.61 | 326006.64 | 326006.64 | 326006.64 | 326006.64 | 50.1816 | 0 | 0 | 0 | 323646.68 | Y | 649653.32 | Y | -129321.71 | 0 | 0 | 520331.61 | 0 | 0 | 649653.32 | Y | -129321.71 | 0 | 0 | 520331.61 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -649653.32 | 22554.86 | 34812.02 | 649653.32 | 0 | 0 | 0 | 0 | 0 | 0 | -649653.32 | 0 | 0 | 649653.32 | 649653.32 | 0 | 0 | 0 | 4584 | 0 | 6001 | 6001 | 4584 | 2864.5 | 3136.5 | 6001 | HR | 22920 | 10086.9 | 13880.1 | 23967 | SF | 0 | 0 | 0 | 323646.68
N | M007-03-1200-L | M007 | M007 | 03-1200 | OPERATOR FOR CONCRETE WORK | N | L |  | NR | P | 149912.4 | 29756.82 | 29756.82 | 29756.82 | 29756.82 | 100 | 0 | 0 | 0 | 0 | Y | 29756.82 | Y | 120155.58 | 0 | 0 | 149912.4 | 0 | 0 | 29756.82 | Y | 120155.58 | 0 | 0 | 149912.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29756.82 | 0 | 0 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 0 | -29756.82 | 0 | 0 | 29756.82 | 29756.82 | 0 | 0 | 0 | 1056 | 0 | 196 | 196 | 1056 | 196 | 0 | 196 | HR | 3100 | 993 | 0 | 993 | CY | 0 | 0 | 0 | 0
N | M007-03-1300-L | M007 | M007 | 03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | N | L |  | NR | P | 27242.54 | 63065.21 | 63065.21 | 63065.21 | 63065.21 | 100 | 0 | 0 | 0 | 0 | Y | 63065.21 | Y | -35822.67 | 0 | 0 | 27242.54 | 0 | 0 | 63065.21 | Y | -35822.67 | 0 | 0 | 27242.54 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63065.21 | 0 | 0 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 0 | -63065.21 | 0 | 0 | 63065.21 | 63065.21 | 0 | 0 | 0 | 240 | 0 | 543 | 543 | 240 | 543 | 0 | 543 | HR | 240 | 308 | 0 | 308 | EA | 0 | 0 | 0 | 0
N | M007-03-1400-L | M007 | M007 | 03-1400 | DRILL & GROUT DOWELS | N | L |  | NR | P | 106416.19 | 197415.14 | 197415.14 | 197415.14 | 197415.14 | 71.8375 | 0 | 0 | 0 | 77392.97 | Y | 274808.11 | Y | -168391.92 | 0 | 0 | 106416.19 | 0 | 0 | 274808.11 | Y | -168391.92 | 0 | 0 | 106416.19 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -274808.11 | 42993.5 | 23599.08 | 274808.11 | 0 | 0 | 0 | 0 | 0 | 0 | -274808.11 | 0 | 0 | 274808.11 | 274808.11 | 0 | 0 | 0 | 1112.5 | 0 | 2695.49 | 2695.49 | 1112.5 | 1935 | 760.49 | 2695.49 | HR | 4450 | 8668.75 | 3045.25 | 11714 | EA | 0 | 0 | 0 | 77392.97
N | M007-03-1500-L | M007 | M007 | 03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | N | L |  | NR | P | 162759.95 | 78701.51 | 78701.51 | 78701.51 | 78701.51 | 48.3546 | 0 | 0 | 0 | 84057.68 | Y | 162759.19 | Y | 0.76 | 0 | 0 | 162759.95 | 0 | 0 | 162759.19 | Y | 0.76 | 0 | 0 | 162759.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -162759.19 | 704.35 | 0 | 162759.19 | 0 | 0 | 0 | 0 | 0 | 0 | -162759.19 | 0 | 0 | 162759.19 | 162759.19 | 0 | 0 | 0 | 1530.67 | 0 | 1416.38 | 1416.38 | 1530.67 | 711.5 | 704.88 | 1416.38 | HR | 164 | 115.4 | 48.6 | 164 | CY | 0 | 0 | 0 | 84057.68
N | M007-03-1600-L | M007 | M007 | 03-1600 | FORMWORK SITE CONCRETE LABOR | N | L |  | NR | P | 209994.21 | 41551.12 | 41551.12 | 41551.12 | 41551.12 | 19.7868 | 0 | 0 | 0 | 168443.09 | Y | 209994.21 | Y | 0 | 0 | 0 | 209994.21 | 0 | 0 | 209994.21 | Y | 0 | 0 | 0 | 209994.21 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -209994.21 | 13760.23 | 19570.77 | 209994.21 | 0 | 0 | 0 | 0 | 0 | 0 | -209994.21 | 0 | 0 | 209994.21 | 209994.21 | 0 | 0 | 0 | 1850 | 0 | 1701.87 | 1701.87 | 1850 | 357 | 1344.87 | 1701.87 | HR | 7400 | 1593 | 5807 | 7400 | SF | 0 | 0 | 0 | 168443.09
N | M007-03-1610-L | M007 | M007 | 03-1610 | FORMWORK SITE CONCRETE MATERIAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-03-1610-M | M007 | M007 | 03-1610 | FORMWORK SITE CONCRETE MATERIAL | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
Y | M007-03-1700-L | M007 | M007 | 03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | N | L |  | NR | P | 6814.2 | 56763.12 | 56763.12 | 56763.12 | 56763.12 | 100 | 0 | 0 | 0 | 0 | Y | 56763.12 | Y | -49948.92 | 0 | 0 | 6814.2 | 0 | 0 | 56763.12 | Y | -49948.92 | 0 | 0 | 6814.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56763.12 | 0 | 0 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 0 | -56763.12 | 0 | 0 | 56763.12 | 56763.12 | 0 | 0 | 0 | 48 | 0 | 487 | 487 | 48 | 487 | 0 | 487 | HR | 550000 | 393500 | 0 | 393500 | LB | 0 | 0 | 0 | 0
N | M007-03-1800-L | M007 | M007 | 03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | N | L |  | NR | P | 3407.1 | 30918.35 | 30918.35 | 30918.35 | 30918.35 | 93.3835 | 0 | 0 | 0 | 2190.65 | Y | 33109 | Y | -29701.9 | 0 | 0 | 3407.1 | 0 | 0 | 33109 | Y | -29701.9 | 0 | 0 | 3407.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33109 | 6934 | 2253.93 | 33109 | 0 | 0 | 0 | 0 | 0 | 0 | -33109 | 0 | 0 | 33109 | 33109 | 0 | 0 | 0 | 24 | 0 | 293 | 293 | 24 | 273.5 | 19.5 | 293 | HR | 180100 | 249000 | 5277 | 254277 | LB | 0 | 0 | 0 | 2190.65
N | M007-03-1900-L | M007 | M007 | 03-1900 | POUR CONCRETE NEW BUILDINGS | N | L |  | NR | P | 334540.26 | 458075.28 | 458075.28 | 458075.28 | 458075.28 | 101.2859 | 0 | 0 | 0 | -5815.79 | Y | 452259.49 | Y | -117719.23 | 0 | 0 | 334540.26 | 0 | 0 | 452259.49 | Y | -117719.23 | 0 | 0 | 334540.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -452259.49 | 8191.25 | 15436.52 | 452259.49 | 0 | 0 | 0 | 0 | 0 | 0 | -452259.49 | 0 | 0 | 452259.49 | 452259.49 | 0 | 0 | 0 | 3312 | 0 | 4067.56 | 4067.56 | 3312 | 4124.5 | -56.94 | 4067.56 | HR | 3100 | 4497.2 | 0 | 4497.2 | CY | 0 | 0 | 0 | -5815.79
N | M007-03-2000-L | M007 | M007 | 03-2000 | FINISH SLABS - NEW BLDGS | N | L |  | NR | P | 122527.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 122527.5 | 0 | 0 | 122527.5 | 0 | 0 | 0 | Y | 122527.5 | 0 | 0 | 122527.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | HR | 49280 | 0 | 0 | 0 | SF | 0 | 0 | 0 | 0
N | M007-03-2100-L | M007 | M007 | 03-2100 | POUR CONC EXIST BLDGS | N | L |  | NR | P | 98900.64 | 100028.49 | 100028.49 | 100028.49 | 100028.49 | 62.3695 | 0 | 0 | 0 | 60352.06 | Y | 160380.55 | Y | -61479.91 | 0 | 0 | 98900.64 | 0 | 0 | 160380.55 | Y | -61479.91 | 0 | 0 | 98900.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -160380.55 | 9790.19 | 6680.33 | 160380.55 | 0 | 0 | 0 | 0 | 0 | 0 | -160380.55 | 0 | 0 | 160380.55 | 160380.55 | 0 | 0 | 0 | 1008 | 0 | 1561.43 | 1561.43 | 1008 | 970 | 591.43 | 1561.43 | HR | 1020 | 401.9 | 637.6 | 1039.5 | CY | 0 | 0 | 0 | 60352.06
N | M007-03-2110-S | M007 | M007 | 03-2110 | SHOTCRETE SUB | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-03-2120-C | M007 | M007 | 03-2120 | SHOTCRETE SUB CLEANUP | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 118 | 0 | 118 | NA | 0 | 0 | 0 | 0
N | M007-03-2120-L | M007 | M007 | 03-2120 | SHOTCRETE SUB CLEANUP | N | L |  | NR | P | 0 | 12865.02 | 12865.02 | 12865.02 | 12865.02 | 64.3251 | 0 | 0 | 0 | 7134.98 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 5832.17 | 7032.85 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 67.5 | 67.5 | 0 | 118 | -50.5 | 67.5 | HR | 0 | 118 | 0 | 118 | NA | 0 | 0 | 0 | 7134.98
N | M007-03-2200-L | M007 | M007 | 03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | N | L |  | NR | P | 13759.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13759.32 | N | 13759.32 | N | 0 | 0 | 0 | 13759.32 | 0 | 0 | 13759.32 | N | 0 | 0 | 0 | 13759.32 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13759.32 | 0 | 0 | 13759.32 | 0 | 0 | 0 | 0 | 0 | 0 | -13759.32 | 0 | 0 | 13759.32 | 13759.32 | 0 | 0 | 0 | 144 | 0 | 144 | 144 | 144 | 0 | 144 | 144 | HR | 150 | 0 | 150 | 150 | CY | 0 | 0 | 0 | 13759.32
N | M007-03-2300-L | M007 | M007 | 03-2300 | CONCRETE DUCTBANKS | N | L |  | NR | P | 45864.4 | 207296.65 | 207296.65 | 207296.65 | 207296.65 | 94.2258 | 0 | 0 | 0 | 12703.35 | Y | 220000 | Y | -174135.6 | 0 | 0 | 45864.4 | 0 | 0 | 220000 | Y | -174135.6 | 0 | 0 | 45864.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -220000 | 7562.41 | 6981.31 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | -220000 | 0 | 0 | 220000 | 220000 | 0 | 0 | 0 | 480 | 0 | 1968.33 | 1968.33 | 480 | 1853.5 | 114.83 | 1968.33 | HR | 1000 | 1472 | 0 | 1472 | CY | 0 | 0 | 0 | 12703.35
N | M007-03-2400-L | M007 | M007 | 03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | N | L |  | NR | P | 36435.9 | 4805.73 | 4805.73 | 4805.73 | 4805.73 | 13.1895 | 0 | 0 | 0 | 31630.17 | Y | 36435.9 | Y | 0 | 0 | 0 | 36435.9 | 0 | 0 | 36435.9 | Y | 0 | 0 | 0 | 36435.9 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36435.9 | 0 | 4805.73 | 36435.9 | 0 | 0 | 0 | 0 | 0 | 0 | -36435.9 | 0 | 0 | 36435.9 | 36435.9 | 0 | 0 | 0 | 360 | 0 | 356.34 | 356.34 | 360 | 47 | 309.34 | 356.34 | HR | 171 | 60 | 111 | 171 | CY | 0 | 0 | 0 | 31630.17
N | M007-03-2500-L | M007 | M007 | 03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | N | L |  | NR | P | 143548.86 | 63504.47 | 63504.47 | 63504.47 | 63504.47 | 44.2389 | 0 | 0 | 0 | 80044.39 | Y | 143548.86 | Y | 0 | 0 | 0 | 143548.86 | 0 | 0 | 143548.86 | Y | 0 | 0 | 0 | 143548.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -143548.86 | 9240.95 | 0 | 143548.86 | 0 | 0 | 0 | 0 | 0 | 0 | -143548.86 | 0 | 0 | 143548.86 | 143548.86 | 0 | 0 | 0 | 1350 | 0 | 1218.35 | 1218.35 | 1350 | 559 | 659.35 | 1218.35 | HR | 270 | 275.25 | 0 | 275.25 | CY | 0 | 0 | 0 | 80044.39
N | M007-03-2600-L | M007 | M007 | 03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | N | L |  | NR | P | 13834.32 | 726.04 | 726.04 | 726.04 | 726.04 | 5.2481 | 0 | 0 | 0 | 13108.28 | Y | 13834.32 | Y | 0 | 0 | 0 | 13834.32 | 0 | 0 | 13834.32 | Y | 0 | 0 | 0 | 13834.32 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13834.32 | 0 | 0 | 13834.32 | 0 | 0 | 0 | 0 | 0 | 0 | -13834.32 | 0 | 0 | 13834.32 | 13834.32 | 0 | 0 | 0 | 144 | 0 | 114.33 | 114.33 | 144 | 6 | 108.33 | 114.33 | HR | 6650 | 0 | 6650 | 6650 | SF | 0 | 0 | 0 | 13108.28
N | M007-03-2700-L | M007 | M007 | 03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | N | L |  | NR | P | 0 | 95.84 | 95.84 | 95.84 | 95.84 | 100 | 0 | 0 | 0 | 0 | Y | 95.84 | Y | -95.84 | 0 | 0 | 0 | 0 | 0 | 95.84 | Y | -95.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -95.84 | 0 | 0 | 95.84 | 0 | 0 | 0 | 0 | 0 | 0 | -95.84 | 0 | 0 | 95.84 | 95.84 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | HR | 0 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 0
N | M007-03-5000-L | M007 | M007 | 03-5000 | FURNISH CONCRETE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6341 | 3993 | 2348 | 6341 | CY | 0 | 0 | 0 | 0
N | M007-03-5000-M | M007 | M007 | 03-5000 | FURNISH CONCRETE | N | M |  | NR | A | 1070542.12 | 1249892.89 | 1249892.89 | 1029452.75 | 1249892.89 | 82.3633 | 0 | 0 | 0 | 0 | N | 1249892.89 | N | -179350.77 | 0 | 0 | 1070542.12 | 0 | 0 | 1249892.89 | N | -179350.77 | 0 | 0 | 1070542.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1249892.89 | 5282.4 | 777.57 | 1341498.46 | 91605.57 | 0 | 0 | 5757.34 | -916654.04 | 0 | -1249892.89 | 0 | 0 | 1249892.89 | 1249892.89 | 0 | 0 | 0 | 6341 | 0 | 0 |  | 0 | 12349.78 | 12915.47 | 25265.25 | CY | 6341 | 3993 | 2348 | 6341 | CY | 1249892.89 | 220440.14 | 1029452.75 | 0
N | M007-03-5100-L | M007 | M007 | 03-5100 | FURNISH INSULATION | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 19200 | 14912 | 4288 | 19200 | SF | 0 | 0 | 0 | 0
N | M007-03-5100-M | M007 | M007 | 03-5100 | FURNISH INSULATION | N | M |  | NR | A | 38520 | 50669.81 | 50669.81 | 39414.64 | 50669.81 | 77.7872 | 0 | 0 | 0 | 0 | Y | 50669.81 | Y | -12149.81 | 0 | 0 | 38520 | 0 | 0 | 50669.81 | Y | -12149.81 | 0 | 0 | 38520 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50669.81 | 0 | 0 | 50669.81 | 0 | 0 | 0 | 0 | 0 | 0 | -50669.81 | 0 | 0 | 50669.81 | 50669.81 | 0 | 0 | 0 | 19199.52 | 0 | 0 |  | 0 | 3654 | 7786 | 11440 | SF | 19200 | 14912 | 4288 | 19200 | SF | 50669.81 | 11255.17 | 39414.64 | 0
N | M007-03-5200-C | M007 | M007 | 03-5200 | FURNISH REBAR | N | C |  | NR | U | 0 | 4357.53 | 4357.53 | 4002.31 | 4357.53 | 91.6179 | 0 | 0 | 0 | 10.95 | Y | 4368.48 | Y | -4368.48 | 0 | 0 | 0 | 0 | 0 | 4368.48 | Y | -4368.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4368.48 | 0 | 0 | 4368.48 | 0 | 0 | 0 | 0 | 0 | 0 | -4368.48 | 0 | 0 | 4368.48 | 4368.48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2023 | 5.08 | 2028.08 | NA | 1873520 | 0 | 1714793 | 1714793 | LB | 4357.53 | 355.22 | 4002.31 | 10.95
N | M007-03-5200-L | M007 | M007 | 03-5200 | FURNISH REBAR | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1873520 | 0 | 1714793 | 1714793 | LB | 0 | 0 | 0 | 0
N | M007-03-5200-M | M007 | M007 | 03-5200 | FURNISH REBAR | N | M |  | NR | P | 603180.6 | 10293.94 | 10293.94 | 9708.24 | 10293.94 | 94.3102 | 0 | 0 | 0 | 0 | Y | 10293.94 | Y | 592886.66 | 0 | 0 | 603180.6 | 0 | 0 | 10293.94 | Y | 592886.66 | 0 | 0 | 603180.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10293.94 | 0 | 0 | 10293.94 | 0 | 0 | 0 | 0 | 0 | 0 | -10293.94 | 0 | 0 | 10293.94 | 10293.94 | 0 | 0 | 0 | 1873231.68 | 0 | 0 |  | 0 | 7638 | -4.45 | 7633.55 | LB | 1873520 | 0 | 1714793 | 1714793 | LB | 10293.94 | 585.7 | 9708.24 | 0
N | M007-03-5250-L | M007 | M007 | 03-5250 | FURNISH WIREMESH | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 51750 | 0 | 51750 | 51750 | SF | 0 | 0 | 0 | 0
N | M007-03-5250-M | M007 | M007 | 03-5250 | FURNISH WIREMESH | N | M |  | NR | A | 13041 | 47788.8 | 47788.8 | 32356.38 | 47788.8 | 67.7448 | 0 | 0 | 0 | -26.67 | Y | 47762.13 | Y | -34721.13 | 0 | 0 | 13041 | 0 | 0 | 47762.13 | Y | -34721.13 | 0 | 0 | 13041 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -47762.13 | 0 | 0 | 47762.13 | 0 | 0 | 0 | 0 | 26.67 | 0 | -47762.13 | 0 | 0 | 47762.13 | 47762.13 | 0 | 0 | 0 | 51750 | 0 | 0 |  | 0 | 35652 | 12008 | 47660 | SF | 51750 | 0 | 51750 | 51750 | SF | 47788.8 | 15432.42 | 32356.38 | -26.67
N | M007-03-5400-L | M007 | M007 | 03-5400 | FURNISH SAKCRETE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 12100 | 0 | 12100 | 12100 | BG | 0 | 0 | 0 | 0
N | M007-03-5400-M | M007 | M007 | 03-5400 | FURNISH SAKCRETE | N | M |  | NR | A | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181500 | N | 181500 | N | 0 | 0 | 0 | 181500 | 0 | 0 | 181500 | N | 0 | 0 | 0 | 181500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -181500 | 0 | 0 | 181500 | 0 | 0 | 0 | 0 | 0 | 0 | -181500 | 0 | 0 | 181500 | 181500 | 0 | 0 | 0 | 12100 | 0 | 0 |  | 0 | 0 | 0 | 0 | BG | 12100 | 0 | 12100 | 12100 | BG | 0 | 0 | 0 | 181500
N | M007-03-5500-L | M007 | M007 | 03-5500 | FURNISH CONC PATCH MATERIAL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6650 | 0 | 6650 | 6650 | SF | 0 | 0 | 0 | 0
N | M007-03-5500-M | M007 | M007 | 03-5500 | FURNISH CONC PATCH MATERIAL | N | M |  | NR | P | 13300 | 9627.4 | 9627.4 | 9174.5 | 9627.4 | 68.9812 | 0 | 0 | 0 | 3672.6 | Y | 13300 | Y | 0 | 0 | 0 | 13300 | 0 | 0 | 13300 | Y | 0 | 0 | 0 | 13300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13300 | 0 | 0 | 13300 | 0 | 0 | 0 | 0 | 0 | 0 | -13300 | 0 | 0 | 13300 | 13300 | 0 | 0 | 0 | 6650 | 0 | 0 |  | 0 | 105 | 163.45 | 268.45 | SF | 6650 | 0 | 6650 | 6650 | SF | 9627.4 | 452.9 | 9174.5 | 3672.6
N | M007-03-6000-L | M007 | M007 | 03-6000 | FRP WORK | N | L |  | NR | P | 0 | 196878.37 | 196878.37 | 196878.37 | 196878.37 | 65.903 | 0 | 0 | 0 | 101861.05 | Y | 298739.42 | Y | -298739.42 | 0 | 0 | 0 | 0 | 0 | 298739.42 | Y | -298739.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -298739.42 | 0 | 1096.55 | 298739.42 | 0 | 0 | 0 | 0 | 0 | 0 | -298739.42 | 0 | 0 | 298739.42 | 298739.42 | 0 | 0 | 0 | 0 | 0 | 2966.33 | 2966.33 | 0 | 1980 | 986.33 | 2966.33 | HR | 560 | 6781.75 | 2190.25 | 8972 | SF | 0 | 0 | 0 | 101861.05
N | M007-03-6000-M | M007 | M007 | 03-6000 | FRP WORK | N | M |  | NR | U | 0 | 171113.96 | 171113.96 | 161202.96 | 171113.96 | 94.208 | 0 | 0 | 0 | 0 | N | 171113.96 | N | -171113.96 | 0 | 0 | 0 | 0 | 0 | 171113.96 | N | -171113.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -171113.96 | 1487.59 | 0 | 177683.92 | 6569.96 | 0 | 0 | 1599.42 | 0 | 0 | -171113.96 | 0 | 0 | 171113.96 | 171113.96 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 87 | 0 | 87 | NA | 560 | 6781.75 | 2190.25 | 8972 | SF | 171113.96 | 9911 | 161202.96 | 0
N | M007-03-6000-S | M007 | M007 | 03-6000 | FRP WORK | N | S |  | NR | P | 378800.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 378800.8 | 0 | 0 | 378800.8 | 0 | 0 | 0 | Y | 378800.8 | 0 | 0 | 378800.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 560 | 6781.75 | 2190.25 | 8972 | SF | 0 | 0 | 0 | 0
N | M007-03-6010-C | M007 | M007 | 03-6010 | FRP Self Perform | N | C |  | NR | U | 0 | 33476.69 | 33476.69 | 33476.69 | 33476.69 | 100 | 0 | 0 | 0 | 0 | N | 33476.69 | N | -33476.69 | 0 | 0 | 0 | 0 | 0 | 33476.69 | N | -33476.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -33476.69 | 0 | 0 | 33476.69 | 0 | 0 | 0 | 0 | 0 | 0 | -33476.69 | 0 | 0 | 33476.69 | 33476.69 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 213 | 0 | 213 | NA | 0 | 0 | 0 | 0 | HR | 33275.23 | -201.46 | 33476.69 | 0
N | M007-03-6010-L | M007 | M007 | 03-6010 | FRP Self Perform | N | L |  | NR | P | 0 | 383.93 | 383.93 | 383.93 | 383.93 | 100 | 0 | 0 | 0 | 0 | Y | 383.93 | Y | -383.93 | 0 | 0 | 0 | 0 | 0 | 383.93 | Y | -383.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -383.93 | 0 | 0 | 383.93 | 0 | 0 | 0 | 0 | 0 | 0 | -383.93 | 0 | 0 | 383.93 | 383.93 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 0 | 3 | HR | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
N | M007-03-6100-L | M007 | M007 | 03-6100 | REBAR SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-03-6100-S | M007 | M007 | 03-6100 | REBAR SUB | N | S |  | NR | A | 1079926.48 | 1420047.7 | 1420047.7 | 1024496.93 | 1420047.7 | 68.5554 | 0 | 0 | 0 | 74360.38 | Y | 1494408.08 | Y | -414481.6 | 0 | 0 | 1079926.48 | 0 | 0 | 1494408.08 | Y | -414481.6 | 0 | 0 | 1079926.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1494408.08 | 0 | 132586.25 | 1494408.08 | 0 | 0 | 0 | 0 | 0 | 0 | -1494408.08 | 0 | 0 | 1494408.08 | 1494408.08 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 1533539.09 | -1437870.91 | 95668.18 | LS | 1 | 0 | 1 | 1 | LS | 1420047.7 | 395550.77 | 1024496.93 | 74360.38
N | M007-03-6110-L | M007 | M007 | 03-6110 | REBAR SUB SUPPORT | N | L |  | NR | P | 0 | 347.15 | 347.15 | 347.15 | 347.15 | 2.1287 | 0 | 0 | 0 | 15960.69 | Y | 16307.84 | Y | -16307.84 | 0 | 0 | 0 | 0 | 0 | 16307.84 | Y | -16307.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16307.84 | 0 | 0 | 16307.84 | 0 | 0 | 0 | 0 | 0 | 0 | -16307.84 | 0 | 0 | 16307.84 | 16307.84 | 0 | 0 | 0 | 0 | 0 | 155.31 | 155.31 | 0 | 3 | 152.31 | 155.31 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 15960.69
N | M007-03-6110-S | M007 | M007 | 03-6110 | REBAR SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-03-6120-L | M007 | M007 | 03-6120 | REBAR DELIVERY SUPPORT | N | L |  | NR | P | 0 | 4041.34 | 4041.34 | 4041.34 | 4041.34 | 100 | 0 | 0 | 0 | 0 | Y | 4041.34 | Y | -4041.34 | 0 | 0 | 0 | 0 | 0 | 4041.34 | Y | -4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4041.34 | 0 | 0 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | -4041.34 | 0 | 0 | 4041.34 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 35 | 0 | 35 | HR | 0 | 36660 | 0 | 36660 | LB | 0 | 0 | 0 | 0
N | M007-03-7000-C | M007 | M007 | 03-7000 | FORMWORK MATERIAL | N | C |  | NR | A | 302507.84 | 550968.75 | 550968.75 | 446794.86 | 550968.75 | 97.9466 | 0 | 0 | 0 | -94807.03 | Y | 456161.72 | Y | -153653.88 | 0 | 0 | 302507.84 | 0 | 0 | 456161.72 | Y | -153653.88 | 0 | 0 | 302507.84 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -456161.72 | 10106.93 | 43271.41 | 456161.72 | 0 | 0 | 0 | 21227.26 | 73579.77 | 0 | -456161.72 | 0 | 0 | 456161.72 | 456161.72 | 0 | 0 | 0 | 92612 | 0 | 0 |  | 0 | 226338.17 | 32070.13 | 258408.3 | SF | 92612 | 37044.59 | 55567.41 | 92612 | SF | 550968.75 | 104173.89 | 446794.86 | -94807.03
N | M007-03-7000-L | M007 | M007 | 03-7000 | FORMWORK MATERIAL | N | L |  | NR | P | 0 | 1687.22 | 1687.22 | 1687.22 | 1687.22 | 18.1311 | 0 | 0 | 0 | 7618.44 | Y | 9305.66 | Y | -9305.66 | 0 | 0 | 0 | 0 | 0 | 9305.66 | Y | -9305.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9305.66 | 0 | 0 | 9305.66 | 0 | 0 | 0 | 0 | 0 | 0 | -9305.66 | 0 | 0 | 9305.66 | 9305.66 | 0 | 0 | 0 | 0 | 0 | 76.82 | 76.82 | 0 | 1 | 75.82 | 76.82 | HR | 92612 | 37044.59 | 55567.41 | 92612 | SF | 1687.22 | 0 | 1687.22 | 7618.44
N | M007-03-7100-C | M007 | M007 | 03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | N | C |  | NR | U | 0 | 196356.98 | 196356.98 | 152745.59 | 196356.98 | 84.8587 | 0 | 0 | 0 | -16356.98 | Y | 180000 | Y | -180000 | 0 | 0 | 0 | 0 | 0 | 180000 | Y | -180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -180000 | 0 | 0 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | -180000 | 0 | 0 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1585.58 | -1585.58 | 0 | CY | 0 | 920 | 0 | 920 | CY | 196356.98 | 43611.39 | 152745.59 | -16356.98
N | M007-04-1000-L | M007 | M007 | 04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | N | L |  | NR | P | 6917.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6917.16 | N | 6917.16 | N | 0 | 0 | 0 | 6917.16 | 0 | 0 | 6917.16 | N | 0 | 0 | 0 | 6917.16 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6917.16 | 0 | 0 | 6917.16 | 0 | 0 | 0 | 0 | 0 | 0 | -6917.16 | 0 | 0 | 6917.16 | 6917.16 | 0 | 0 | 0 | 72 | 0 | 72 | 72 | 72 | 0 | 72 | 72 | HR | 995 | 0 | 995 | 995 | SF | 0 | 0 | 0 | 6917.16
N | M007-04-6000-L | M007 | M007 | 04-6000 | GROUT INJECTION SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-04-6000-S | M007 | M007 | 04-6000 | GROUT INJECTION SUB | N | S |  | NR | A | 182750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 182750 | 0 | 0 | 182750 | 0 | 0 | 0 | Y | 182750 | 0 | 0 | 182750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-04-6100-L | M007 | M007 | 04-6100 | MASONRY SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-04-6100-M | M007 | M007 | 04-6100 | MASONRY SUB | N | M |  | NR | U | 0 | 511620 | 511620 | 511619.31 | 511620 | 99.9999 | 0 | 0 | 0 | 0 | Y | 511620 | Y | -511620 | 0 | 0 | 0 | 0 | 0 | 511620 | Y | -511620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -511620 | 0 | 255809.31 | 511620 | 0 | 0 | 0 | 0 | 0 | 0 | -511620 | 0 | 0 | 511620 | 511620 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 274800 | 0 | 274800 | NA | 1 | 0 | 1 | 1 | LS | 511620 | 0.69 | 511619.31 | 0
N | M007-04-6100-S | M007 | M007 | 04-6100 | MASONRY SUB | N | S |  | NR | A | 8687564.43 | 8578380 | 8578380 | 3073295.25 | 8578380 | 35.8261 | 0 | 0 | 0 | 0 | Y | 8578380 | Y | 109184.43 | 0 | 0 | 8687564.43 | 0 | 0 | 8578380 | Y | 109184.43 | 0 | 0 | 8687564.43 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8578380 | 0 | 0 | 8578380 | 0 | 0 | 0 | 0 | 0 | 0 | -8578380 | 0 | 0 | 8578380 | 8578380 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 29.76 | -28.76 | 1 | LS | 1 | 0 | 1 | 1 | LS | 8578380 | 5505084.75 | 3073295.25 | 0
N | M007-04-6110-L | M007 | M007 | 04-6110 | MASONRY SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23034 | Y | 23034 | Y | -23034 | 0 | 0 | 0 | 0 | 0 | 23034 | Y | -23034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -23034 | 0 | 0 | 23034 | 0 | 0 | 0 | 0 | 0 | 0 | -23034 | 0 | 0 | 23034 | 23034 | 0 | 0 | 0 | 0 | 0 | 230.34 | 230.34 | 0 | 0 | 230.34 | 230.34 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 23034
N | M007-04-6110-M | M007 | M007 | 04-6110 | MASONRY SUB SUPPORT | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-04-6110-S | M007 | M007 | 04-6110 | MASONRY SUB SUPPORT | N | S |  | NR | A | 0 | 126966 | 126966 | 25393.2 | 126966 | 29.0711 | 0 | 0 | 0 | -39617.52 | Y | 87348.48 | Y | -87348.48 | 0 | 0 | 0 | 0 | 0 | 87348.48 | Y | -87348.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -87348.48 | 0 | 0 | 87348.48 | 0 | 0 | 0 | 0 | 0 | 0 | -87348.48 | 0 | 0 | 87348.48 | 87348.48 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0.4 | -0.4 | 0 | NA | 0 | 0 | 1 | 1 | LS | 126966 | 101572.8 | 25393.2 | -39617.52
N | M007-04-6120-L | M007 | M007 | 04-6120 | MASON EUIP SUPPORT | N | L |  | NR | P | 0 | 57671.12 | 57671.12 | 57671.12 | 57671.12 | 136.0642 | 0 | 0 | 0 | -15285.88 | Y | 42385.24 | Y | -42385.24 | 0 | 0 | 0 | 0 | 0 | 42385.24 | Y | -42385.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -42385.24 | 8685.52 | 13757.84 | 42385.24 | 0 | 0 | 0 | 0 | 0 | 0 | -42385.24 | 0 | 0 | 42385.24 | 42385.24 | 0 | 0 | 0 | 0 | 0 | 342.5 | 342.5 | 0 | 435 | -92.5 | 342.5 | HR | 0 | 442.5 | 0 | 442.5 | HR | 0 | 0 | 0 | -15285.88
N | M007-04-6120-M | M007 | M007 | 04-6120 | MASON EUIP SUPPORT | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 442.5 | 0 | 442.5 | HR | 0 | 0 | 0 | 0
N | M007-04-6130-C | M007 | M007 | 04-6130 | ANGLE FOR FACADE | N | C |  | NR | U | 0 | 6532.07 | 6532.07 | 5766.58 | 6532.07 | 115.3316 | 0 | 0 | 0 | -1532.07 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 1485.25 | 5000 | 0 | 0 | 0 | 0 | 1617.07 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 243 | -61.92 | 181.08 | NA | 0 | 511 | 209 | 720 | LF | 6532.07 | 765.49 | 5766.58 | -1532.07
N | M007-04-6130-L | M007 | M007 | 04-6130 | ANGLE FOR FACADE | N | L |  | NR | P | 0 | 35217.74 | 35217.74 | 35217.74 | 35217.74 | 78.2616 | 0 | 0 | 0 | 9782.26 | Y | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45000 | 0 | 25433.71 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 424.89 | 424.89 | 0 | 318.5 | 106.39 | 424.89 | HR | 0 | 511 | 209 | 720 | LF | 0 | 0 | 0 | 9782.26
N | M007-04-6200-L | M007 | M007 | 04-6200 | STONE SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-04-6200-S | M007 | M007 | 04-6200 | STONE SUB | N | S |  | NR | A | 774577.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | Y | 135000 | Y | 639577.03 | 0 | 0 | 774577.03 | 0 | 0 | 135000 | Y | 639577.03 | 0 | 0 | 774577.03 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -135000 | 0 | 0 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | -135000 | 0 | 0 | 135000 | 135000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 135000
N | M007-04-7000-C | M007 | M007 | 04-7000 | MASONRY CLEANER | N | C |  | NR | P | 2166.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166.71 | N | 2166.71 | N | 0 | 0 | 0 | 2166.71 | 0 | 0 | 2166.71 | N | 0 | 0 | 0 | 2166.71 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2166.71 | 0 | 0 | 2166.71 | 0 | 0 | 0 | 0 | 0 | 0 | -2166.71 | 0 | 0 | 2166.71 | 2166.71 | 0 | 0 | 0 | 995 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 995 | 0 | 995 | 995 | SF | 0 | 0 | 0 | 2166.71
N | M007-04-7000-L | M007 | M007 | 04-7000 | MASONRY CLEANER | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 995 | 0 | 995 | 995 | SF | 0 | 0 | 0 | 0
N | M007-05-6000-C | M007 | M007 | 05-6000 | STRUCTURAL STEEL SUB | N | C |  | NR | U | 0 | 51965 | 51965 | 51965 | 51965 | 100 | 0 | 0 | 0 | 0 | Y | 51965 | Y | -51965 | 0 | 0 | 0 | 0 | 0 | 51965 | Y | -51965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -51965 | 0 | 0 | 51965 | 0 | 0 | 0 | 0 | 0 | 0 | -51965 | 0 | 0 | 51965 | 51965 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | NA | 1 | 0 | 1 | 1 | LS | 51965 | 0 | 51965 | 0
N | M007-05-6000-L | M007 | M007 | 05-6000 | STRUCTURAL STEEL SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-05-6000-S | M007 | M007 | 05-6000 | STRUCTURAL STEEL SUB | N | S |  | NR | P | 6186009.29 | 5838000 | 5838000 | 5332637.92 | 5838000 | 90.9049 | 0 | 0 | 0 | 28168.95 | Y | 5866168.95 | Y | 319840.34 | 0 | 0 | 6186009.29 | 0 | 0 | 5866168.95 | Y | 319840.34 | 0 | 0 | 6186009.29 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5866168.95 | 0 | 809000 | 5866168.95 | 0 | 0 | 0 | 0 | 0 | 0 | -5866168.95 | 0 | 0 | 5866168.95 | 5866168.95 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 63.45 | -6.92 | 56.53 | LS | 1 | 0 | 1 | 1 | LS | 5838000 | 505362.08 | 5332637.92 | 28168.95
N | M007-05-6010-L | M007 | M007 | 05-6010 | STRUCTURAL STEEL SUB SUPPORT | N | L |  | NR | P | 0 | 3804.57 | 3804.57 | 3804.57 | 3804.57 | 103.8847 | 0 | 0 | 0 | -142.27 | Y | 3662.3 | Y | -3662.3 | 0 | 0 | 0 | 0 | 0 | 3662.3 | Y | -3662.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3662.3 | 0 | 142.27 | 3662.3 | 0 | 0 | 0 | 0 | 0 | 0 | -3662.3 | 0 | 0 | 3662.3 | 3662.3 | 0 | 0 | 0 | 0 | 0 | 37.5 | 37.5 | 0 | 38.5 | -1 | 37.5 | HR | 0 | 32.86 | 0 | 32.86 | HR | 0 | 0 | 0 | -142.27
N | M007-05-6010-S | M007 | M007 | 05-6010 | STRUCTURAL STEEL SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29638.4 | Y | 29638.4 | Y | -29638.4 | 0 | 0 | 0 | 0 | 0 | 29638.4 | Y | -29638.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29638.4 | 0 | 0 | 29638.4 | 0 | 0 | 0 | 0 | 0 | 0 | -29638.4 | 0 | 0 | 29638.4 | 29638.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 32.86 | 0 | 32.86 | HR | 0 | 0 | 0 | 29638.4
N | M007-05-6020-L | M007 | M007 | 05-6020 | GROUT STEEL COLUMNS | N | L |  | NR | P | 0 | 22622.53 | 22622.53 | 22622.53 | 22622.53 | 62.1994 | 0 | 0 | 0 | 13748.47 | Y | 36371 | Y | -36371 | 0 | 0 | 0 | 0 | 0 | 36371 | Y | -36371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -36371 | 1685.65 | 961.69 | 36371 | 0 | 0 | 0 | 0 | 0 | 0 | -36371 | 0 | 0 | 36371 | 36371 | 0 | 0 | 0 | 0 | 0 | 363.71 | 363.71 | 0 | 214 | 149.71 | 363.71 | HR | 0 | 84.6 | 14.4 | 99 | EA | 0 | 0 | 0 | 13748.47
N | M007-05-6030-L | M007 | M007 | 05-6030 | STEEL & CRANE DELIVERIES | N | L |  | NR | P | 0 | 9097.96 | 9097.96 | 9097.96 | 9097.96 | 50.5442 | 0 | 0 | 0 | 8902.04 | Y | 18000 | Y | -18000 | 0 | 0 | 0 | 0 | 0 | 18000 | Y | -18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18000 | 0 | 1111.43 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | -18000 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 138.53 | 138.53 | 0 | 58.5 | 80.03 | 138.53 | HR | 0 | 58.16 | 43.84 | 102 | HR | 2475 | 0 | 2475 | 8902.04
N | M007-05-6040-L | M007 | M007 | 05-6040 | Ground Prep For Crane | N | L |  | NR | P | 0 | 8898.32 | 8898.32 | 8898.32 | 8898.32 | 104.7907 | 0 | 0 | 0 | -406.8 | Y | 8491.52 | Y | -8491.52 | 0 | 0 | 0 | 0 | 0 | 8491.52 | Y | -8491.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8491.52 | 385.05 | 1184.97 | 8491.52 | 0 | 0 | 0 | 0 | 0 | 0 | -8491.52 | 0 | 0 | 8491.52 | 8491.52 | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 0 | 75 | -12 | 63 | HR | 0 | 76.5 | 0 | 76.5 | HR | 0 | 0 | 0 | -406.8
N | M007-05-6050-L | M007 | M007 | 05-6050 | PREP COLUMNS FOR STEEL INSTALL | N | L |  | NR | P | 0 | 2237.81 | 2237.81 | 2237.81 | 2237.81 | 44.7562 | 0 | 0 | 0 | 2762.19 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 1022.06 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 45.24 | 45.24 | 0 | 21 | 24.24 | 45.24 | HR | 0 | 10 | 35 | 45 | HR | 0 | 0 | 0 | 2762.19
N | M007-05-6100-L | M007 | M007 | 05-6100 | MISC METALS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-05-6100-S | M007 | M007 | 05-6100 | MISC METALS SUB | N | S |  | NR | P | 3133071.92 | 2010175 | 2010175 | 306115.85 | 2010175 | 15.2283 | 0 | 0 | 0 | 0 | Y | 2010175 | Y | 1122896.92 | 0 | 0 | 3133071.92 | 0 | 0 | 2010175 | Y | 1122896.92 | 0 | 0 | 3133071.92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2010175 | 0 | 181347.25 | 2010175 | 0 | 0 | 0 | 0 | 0 | 0 | -2010175 | 0 | 0 | 2010175 | 2010175 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 6.28 | -6.28 | 0 | LS | 1 | 0 | 1 | 1 | LS | 2010175 | 1704059.15 | 306115.85 | 0
N | M007-05-6110-L | M007 | M007 | 05-6110 | MISC METALS SUB SUPPORT | N | L |  | NR | P | 0 | 6196.07 | 6196.07 | 6196.07 | 6196.07 | 122.5404 | 0 | 0 | 0 | -1139.72 | Y | 5056.35 | Y | -5056.35 | 0 | 0 | 0 | 0 | 0 | 5056.35 | Y | -5056.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5056.35 | 1139.72 | 0 | 5056.35 | 0 | 0 | 0 | 0 | 0 | 0 | -5056.35 | 0 | 0 | 5056.35 | 5056.35 | 0 | 0 | 0 | 0 | 0 | 36.5 | 36.5 | 0 | 47 | -10.5 | 36.5 | HR | 0 | 0.59 | 0.41 | 1 | LS | 0 | 0 | 0 | -1139.72
N | M007-05-6110-S | M007 | M007 | 05-6110 | MISC METALS SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96158.52 | Y | 96158.52 | Y | -96158.52 | 0 | 0 | 0 | 0 | 0 | 96158.52 | Y | -96158.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -96158.52 | 0 | 0 | 96158.52 | 0 | 0 | 0 | 0 | 0 | 0 | -96158.52 | 0 | 0 | 96158.52 | 96158.52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0.59 | 0.41 | 1 | LS | 0 | 0 | 0 | 96158.52
N | M007-05-6200-L | M007 | M007 | 05-6200 | SIGNAGE SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-05-6200-S | M007 | M007 | 05-6200 | SIGNAGE SUB | N | S |  | NR | P | 183200 | 138024 | 138024 | 0 | 138024 | 0 | 0 | 0 | 0 | 0 | Y | 138024 | Y | 45176 | 0 | 0 | 183200 | 0 | 0 | 138024 | Y | 45176 | 0 | 0 | 183200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -138024 | 0 | 0 | 138024 | 0 | 0 | 0 | 0 | 0 | 0 | -138024 | 0 | 0 | 138024 | 138024 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 0 | 1 | 1 | LS | 138024 | 138024 | 0 | 0
N | M007-05-6210-L | M007 | M007 | 05-6210 | SIGNAGE SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-05-6210-S | M007 | M007 | 05-6210 | SIGNAGE SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 10000
N | M007-06-6000-L | M007 | M007 | 06-6000 | CARPENTRY SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-06-6000-S | M007 | M007 | 06-6000 | CARPENTRY SUB | N | S |  | NR | P | 2828660 | 1840000 | 1840000 | 1039771 | 1840000 | 56.5093 | 0 | 0 | 0 | 0 | Y | 1840000 | Y | 988660 | 0 | 0 | 2828660 | 0 | 0 | 1840000 | Y | 988660 | 0 | 0 | 2828660 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1840000 | 0 | 320883 | 1840000 | 0 | 0 | 0 | 0 | 0 | 0 | -1840000 | 0 | 0 | 1840000 | 1840000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 86.39 | -86.39 | 0 | LS | 1 | 0 | 1 | 1 | LS | 1840000 | 800229 | 1039771 | 0
N | M007-06-6010-L | M007 | M007 | 06-6010 | CARPENTRY SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-06-6010-S | M007 | M007 | 06-6010 | CARPENTRY SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 50000
N | M007-07-1000-L | M007 | M007 | 07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | N | L |  | NR | P | 1589.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589.15 | N | 1589.15 | N | 0 | 0 | 0 | 1589.15 | 0 | 0 | 1589.15 | N | 0 | 0 | 0 | 1589.15 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1589.15 | 0 | 0 | 1589.15 | 0 | 0 | 0 | 0 | 0 | 0 | -1589.15 | 0 | 0 | 1589.15 | 1589.15 | 0 | 0 | 0 | 14 | 0 | 14 | 14 | 14 | 0 | 14 | 14 | HR | 30 | 0 | 30 | 30 | CF | 0 | 0 | 0 | 1589.15
N | M007-07-1100-L | M007 | M007 | 07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | N | L |  | NR | P | 38139.48 | 34165.69 | 34165.69 | 34098.54 | 34165.69 | 89.4048 | 0 | 0 | 0 | 3973.79 | Y | 38139.48 | Y | 0 | 0 | 0 | 38139.48 | 0 | 0 | 38139.48 | Y | 0 | 0 | 0 | 38139.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38139.48 | 0 | 0 | 38139.48 | 0 | 0 | 0 | 0 | 0 | 0 | -38139.48 | 0 | 0 | 38139.48 | 38139.48 | 0 | 0 | 0 | 336 | 0 | 367.14 | 367.14 | 336 | 329 | 38.14 | 367.14 | HR | 19200 | 18486 | 714 | 19200 | SF | 823.71 | 67.15 | 756.56 | 3973.79
N | M007-07-1200-L | M007 | M007 | 07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | N | L |  | NR | P | 55337.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55337.28 | N | 55337.28 | N | 0 | 0 | 0 | 55337.28 | 0 | 0 | 55337.28 | N | 0 | 0 | 0 | 55337.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55337.28 | 0 | 0 | 55337.28 | 0 | 0 | 0 | 0 | 0 | 0 | -55337.28 | 0 | 0 | 55337.28 | 55337.28 | 0 | 0 | 0 | 576 | 0 | 576 | 576 | 576 | 0 | 576 | 576 | HR | 12 | 0 | 12 | 12 | BL | 0 | 0 | 0 | 55337.28
N | M007-07-1300-L | M007 | M007 | 07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | N | L |  | NR | P | 27668.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27668.64 | N | 27668.64 | N | 0 | 0 | 0 | 27668.64 | 0 | 0 | 27668.64 | N | 0 | 0 | 0 | 27668.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27668.64 | 0 | 0 | 27668.64 | 0 | 0 | 0 | 0 | 0 | 0 | -27668.64 | 0 | 0 | 27668.64 | 27668.64 | 0 | 0 | 0 | 288 | 0 | 288 | 288 | 288 | 0 | 288 | 288 | HR | 6 | 0 | 6 | 6 | BL | 0 | 0 | 0 | 27668.64
N | M007-07-1400-L | M007 | M007 | 07-1400 | JOINT SEALANTS EXTG BLDGS | N | L |  | NR | P | 55337.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55337.28 | N | 55337.28 | N | 0 | 0 | 0 | 55337.28 | 0 | 0 | 55337.28 | N | 0 | 0 | 0 | 55337.28 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55337.28 | 0 | 0 | 55337.28 | 0 | 0 | 0 | 0 | 0 | 0 | -55337.28 | 0 | 0 | 55337.28 | 55337.28 | 0 | 0 | 0 | 576 | 0 | 576 | 576 | 576 | 0 | 576 | 576 | HR | 12 | 0 | 12 | 12 | BL | 0 | 0 | 0 | 55337.28
N | M007-07-1500-L | M007 | M007 | 07-1500 | JOINT SEALANTS NEW BLDGS | N | L |  | NR | P | 27668.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27668.64 | N | 27668.64 | N | 0 | 0 | 0 | 27668.64 | 0 | 0 | 27668.64 | N | 0 | 0 | 0 | 27668.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27668.64 | 0 | 0 | 27668.64 | 0 | 0 | 0 | 0 | 0 | 0 | -27668.64 | 0 | 0 | 27668.64 | 27668.64 | 0 | 0 | 0 | 288 | 0 | 288 | 288 | 288 | 0 | 288 | 288 | HR | 6 | 0 | 6 | 6 | BL | 0 | 0 | 0 | 27668.64
N | M007-07-2000-C | M007 | M007 | 07-2000 | INSTALL WATERSTOP | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 313 | 0 | 313 | HR | 0 | 0 | 0 | 0
N | M007-07-2000-L | M007 | M007 | 07-2000 | INSTALL WATERSTOP | N | L |  | NR | P | 0 | 3491.54 | 3491.54 | 3491.54 | 3491.54 | 100 | 0 | 0 | 0 | 0 | Y | 3491.54 | Y | -3491.54 | 0 | 0 | 0 | 0 | 0 | 3491.54 | Y | -3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3491.54 | 0 | 0 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | -3491.54 | 0 | 0 | 3491.54 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 34 | 0 | 34 | HR | 0 | 313 | 0 | 313 | HR | 0 | 0 | 0 | 0
N | M007-07-5000-L | M007 | M007 | 07-5000 | FURNISH FIRESTOPPING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 18 | 0 | 18 | 18 | BL | 0 | 0 | 0 | 0
N | M007-07-5000-M | M007 | M007 | 07-5000 | FURNISH FIRESTOPPING | N | M |  | NR | A | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | N | 90000 | N | 0 | 0 | 0 | 90000 | 0 | 0 | 90000 | N | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -90000 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | -90000 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 18 | 0 | 0 |  | 0 | 0 | 0 | 0 | BL | 18 | 0 | 18 | 18 | BL | 0 | 0 | 0 | 90000
N | M007-07-5100-L | M007 | M007 | 07-5100 | FURNISH JOINT SEALANT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 18 | 0 | 18 | 18 | BL | 0 | 0 | 0 | 0
N | M007-07-5100-M | M007 | M007 | 07-5100 | FURNISH JOINT SEALANT | N | M |  | NR | A | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | N | 90000 | N | 0 | 0 | 0 | 90000 | 0 | 0 | 90000 | N | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -90000 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | -90000 | 0 | 0 | 90000 | 90000 | 0 | 0 | 0 | 18 | 0 | 0 |  | 0 | 0 | 0 | 0 | BL | 18 | 0 | 18 | 18 | BL | 0 | 0 | 0 | 90000
N | M007-07-6000-L | M007 | M007 | 07-6000 | WATERPROOFING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 140655 | 0 | 140655 | 140655 | SF | 0 | 0 | 0 | 0
N | M007-07-6000-S | M007 | M007 | 07-6000 | WATERPROOFING SUB | N | S |  | NR | A | 1261382.25 | 907406.25 | 907406.25 | 22860.57 | 907406.25 | 2.2693 | 0 | 0 | 0 | 100000 | Y | 1007406.25 | Y | 253976 | 0 | 0 | 1261382.25 | 0 | 0 | 1007406.25 | Y | 253976 | 0 | 0 | 1261382.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1007406.25 | 0 | 0 | 1007406.25 | 0 | 0 | 0 | 0 | 0 | 0 | -1007406.25 | 0 | 0 | 1007406.25 | 1007406.25 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0.58 | 0.42 | 1 | LS | 140655 | 0 | 140655 | 140655 | SF | 907406.25 | 884545.68 | 22860.57 | 100000
N | M007-07-6010-L | M007 | M007 | 07-6010 | WATERPROOFING SUB SUPPORT | N | L |  | NR | P | 0 | 1172.93 | 1172.93 | 1172.93 | 1172.93 | 100 | 0 | 0 | 0 | 0 | N | 1172.93 | N | -1172.93 | 0 | 0 | 0 | 0 | 0 | 1172.93 | N | -1172.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1172.93 | 0 | 0 | 1172.93 | 0 | 0 | 0 | 0 | 0 | 0 | -1172.93 | 0 | 0 | 1172.93 | 1172.93 | 0 | 0 | 0 | 0 | 0 | 11.5 | 11.5 | 0 | 11.5 | 0 | 11.5 | HR | 14065.5 | 0 | 14065.5 | 14065.5 | SF | 0 | 0 | 0 | 0
N | M007-07-6010-S | M007 | M007 | 07-6010 | WATERPROOFING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103857.43 | Y | 103857.43 | Y | -103857.43 | 0 | 0 | 0 | 0 | 0 | 103857.43 | Y | -103857.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -103857.43 | 0 | 0 | 103857.43 | 0 | 0 | 0 | 0 | 0 | 0 | -103857.43 | 0 | 0 | 103857.43 | 103857.43 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 14065.5 | 0 | 14065.5 | 14065.5 | SF | 0 | 0 | 0 | 103857.43
N | M007-07-6020-L | M007 | M007 | 07-6020 | PREP SURFACE FOR WATERPROOFING | N | L |  | NR | P | 0 | 34796.43 | 34796.43 | 34796.43 | 34796.43 | 69.5929 | 0 | 0 | 0 | 15203.57 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 349 | 349 | 0 | 349 | 0 | 349 | HR | 0 | 332 | 0 | 332 | HR | 0 | 0 | 0 | 15203.57
N | M007-07-6100-L | M007 | M007 | 07-6100 | METAL PANELS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 38765 | 0 | 38765 | 38765 | SF | 0 | 0 | 0 | 0
N | M007-07-6100-S | M007 | M007 | 07-6100 | METAL PANELS SUB | N | S |  | NR | P | 3610864.8 | 3350000 | 3350000 | 1331828 | 3350000 | 39.3856 | 0 | 0 | 0 | 31506.41 | Y | 3381506.41 | Y | 229358.39 | 0 | 0 | 3610864.8 | 0 | 0 | 3381506.41 | Y | 229358.39 | 0 | 0 | 3610864.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3381506.41 | 0 | 1331828 | 3381506.41 | 0 | 0 | 0 | 0 | 0 | 0 | -3381506.41 | 0 | 0 | 3381506.41 | 3381506.41 | 0 | 0 | 0 | 38764.98 | 0 | 0 |  | 0 | 8.97 | 0.08 | 9.05 | SF | 38765 | 0 | 38765 | 38765 | SF | 3350000 | 2018172 | 1331828 | 31506.41
N | M007-07-6110-L | M007 | M007 | 07-6110 | METAL PANELS SUB SUPPORT | N | L |  | NR | P | 0 | 8164.29 | 8164.29 | 8164.29 | 8164.29 | 11.9198 | 0 | 0 | 0 | 60329.3 | Y | 68493.59 | Y | -68493.59 | 0 | 0 | 0 | 0 | 0 | 68493.59 | Y | -68493.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -68493.59 | 427.54 | 946.51 | 68493.59 | 0 | 0 | 0 | 0 | 0 | 0 | -68493.59 | 0 | 0 | 68493.59 | 68493.59 | 0 | 0 | 0 | 0 | 0 | 575 | 575 | 0 | 68.5 | 506.5 | 575 | HR | 0 | 359.2 | 594.45 | 953.65 | LS | 0 | 0 | 0 | 60329.3
N | M007-07-6110-S | M007 | M007 | 07-6110 | METAL PANELS SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 359.2 | 594.45 | 953.65 | LS | 0 | 0 | 0 | 0
N | M007-07-6200-L | M007 | M007 | 07-6200 | ROOFING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 21000 | 0 | 21000 | 21000 | SF | 0 | 0 | 0 | 0
N | M007-07-6200-S | M007 | M007 | 07-6200 | ROOFING SUB | N | S |  | NR | A | 1214999.1 | 1135000 | 1135000 | 99066 | 1135000 | 8.7283 | 0 | 0 | 0 | 0 | Y | 1135000 | Y | 79999.1 | 0 | 0 | 1214999.1 | 0 | 0 | 1135000 | Y | 79999.1 | 0 | 0 | 1214999.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1135000 | 0 | 99066 | 1135000 | 0 | 0 | 0 | 0 | 1135000 | 0 | -1135000 | 0 | 0 | 1135000 | 1135000 | 0 | 0 | 0 | 21000 | 0 | 0 |  | 0 | 0.65 | 20999.35 | 21000 | SF | 21000 | 0 | 21000 | 21000 | SF | 1135000 | 1035934 | 99066 | 0
N | M007-07-6210-L | M007 | M007 | 07-6210 | ROOFING SUB SUPPORT | N | L |  | NR | P | 0 | 1171.78 | 1171.78 | 1171.78 | 1171.78 | 11.7178 | 0 | 0 | 0 | 8828.22 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 0 | 1171.78 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 10 | -1 | 9 | HR | 0 | 10 | 0 | 10 | LS | 0 | 0 | 0 | 8828.22
N | M007-07-6210-S | M007 | M007 | 07-6210 | ROOFING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | Y | 70000 | Y | -70000 | 0 | 0 | 0 | 0 | 0 | 70000 | Y | -70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -70000 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | -70000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 10 | 0 | 10 | LS | 0 | 0 | 0 | 70000
N | M007-07-6220-L | M007 | M007 | 07-6220 | PREP ROOF SURFACE FOR WORK | N | L |  | NR | P | 0 | 21135.17 | 21135.17 | 21135.17 | 21135.17 | 105.6758 | 0 | 0 | 0 | -1135.17 | Y | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 20000 | Y | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20000 | 5957.61 | 4190.94 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 198.34 | 198.34 | 0 | 211 | -12.66 | 198.34 | HR | 0 | 3.8 | 2.2 | 6 | EA | 0 | 0 | 0 | -1135.17
N | M007-07-6300-L | M007 | M007 | 07-6300 | SPRAY ON FIREPROOFING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 67690 | 0 | 67690 | 67690 | SF | 0 | 0 | 0 | 0
N | M007-07-6300-S | M007 | M007 | 07-6300 | SPRAY ON FIREPROOFING SUB | N | S |  | NR | A | 338450 | 254755.38 | 254755.38 | 184755.38 | 254755.38 | 72.5227 | 0 | 0 | 0 | 0 | Y | 254755.38 | Y | 83694.62 | 0 | 0 | 338450 | 0 | 0 | 254755.38 | Y | 83694.62 | 0 | 0 | 338450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -254755.38 | 0 | 0 | 254755.38 | 0 | 0 | 0 | 0 | 0 | 0 | -254755.38 | 0 | 0 | 254755.38 | 254755.38 | 0 | 0 | 0 | 67690 | 0 | 0 |  | 0 | 4.28 | 1.72 | 6 | SF | 67690 | 0 | 67690 | 67690 | SF | 254755.38 | 70000 | 184755.38 | 0
N | M007-07-6310-L | M007 | M007 | 07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | N | L |  | NR | P | 0 | 1377.92 | 1377.92 | 1377.92 | 1377.92 | 6.3098 | 0 | 0 | 0 | 20460 | Y | 21837.92 | Y | -21837.92 | 0 | 0 | 0 | 0 | 0 | 21837.92 | Y | -21837.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21837.92 | 0 | 0 | 21837.92 | 0 | 0 | 0 | 0 | 0 | 0 | -21837.92 | 0 | 0 | 21837.92 | 21837.92 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 0 | 9.5 | 170.5 | 180 | HR | 0 | 9.5 | 0 | 9.5 | LS | 0 | 0 | 0 | 20460
N | M007-07-6310-S | M007 | M007 | 07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 9.5 | 0 | 9.5 | LS | 0 | 0 | 0 | 0
N | M007-07-6320-L | M007 | M007 | 07-6320 | Maintain heat for Fireproofers | N | L |  | NR | P | 0 | 9196.97 | 9196.97 | 9196.97 | 9196.97 | 100 | 0 | 0 | 0 | 0 | Y | 9196.97 | Y | -9196.97 | 0 | 0 | 0 | 0 | 0 | 9196.97 | Y | -9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9196.97 | 0 | 0 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | -9196.97 | 0 | 0 | 9196.97 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 91.5 | 91.5 | 0 | 91.5 | 0 | 91.5 | HR | 0 | 75.64 | 0 | 75.64 | HR | 0 | 0 | 0 | 0
N | M007-07-6330-L | M007 | M007 | 07-6330 | FIREPROOFING CLEANUP | N | L |  | NR | P | 0 | 2771.84 | 2771.84 | 2771.84 | 2771.84 | 55.4368 | 0 | 0 | 0 | 2228.16 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 45.1 | 45.1 | 0 | 25 | 20.1 | 45.1 | HR | 0 | 25 | 20 | 45 | HR | 0 | 0 | 0 | 2228.16
N | M007-08-1600-L | M007 | M007 | 08-1600 | ACCESS HATCH | N | L |  | NR | P | 114418.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114418.44 | N | 114418.44 | N | 0 | 0 | 0 | 114418.44 | 0 | 0 | 114418.44 | N | 0 | 0 | 0 | 114418.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -114418.44 | 0 | 0 | 114418.44 | 0 | 0 | 0 | 0 | 0 | 0 | -114418.44 | 0 | 0 | 114418.44 | 114418.44 | 0 | 0 | 0 | 1008 | 0 | 1008 | 1008 | 1008 | 0 | 1008 | 1008 | HR | 36 | 0 | 36 | 36 | EA | 0 | 0 | 0 | 114418.44
N | M007-08-1700-L | M007 | M007 | 08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | N | L |  | NR | P | 19069.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19069.74 | N | 19069.74 | N | 0 | 0 | 0 | 19069.74 | 0 | 0 | 19069.74 | N | 0 | 0 | 0 | 19069.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19069.74 | 0 | 0 | 19069.74 | 0 | 0 | 0 | 0 | 0 | 0 | -19069.74 | 0 | 0 | 19069.74 | 19069.74 | 0 | 0 | 0 | 168 | 0 | 168 | 168 | 168 | 0 | 168 | 168 | HR | 33 | 0 | 33 | 33 | EA | 0 | 0 | 0 | 19069.74
N | M007-08-1800-L | M007 | M007 | 08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | N | L |  | NR | P | 6356.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6356.58 | N | 6356.58 | N | 0 | 0 | 0 | 6356.58 | 0 | 0 | 6356.58 | N | 0 | 0 | 0 | 6356.58 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6356.58 | 0 | 0 | 6356.58 | 0 | 0 | 0 | 0 | 0 | 0 | -6356.58 | 0 | 0 | 6356.58 | 6356.58 | 0 | 0 | 0 | 56 | 0 | 56 | 56 | 56 | 0 | 56 | 56 | HR | 17 | 0 | 17 | 17 | EA | 0 | 0 | 0 | 6356.58
N | M007-08-5000-L | M007 | M007 | 08-5000 | FURNISH HM DOORS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 96 | 32 | 64 | 96 | EA | 0 | 0 | 0 | 0
N | M007-08-5000-M | M007 | M007 | 08-5000 | FURNISH HM DOORS | N | M |  | NR | A | 191266.4 | 131759.13 | 131759.13 | 64204.24 | 131759.13 | 33.568 | 0 | 0 | 0 | 59507.27 | N | 191266.4 | N | 0 | 0 | 0 | 191266.4 | 0 | 0 | 191266.4 | N | 0 | 0 | 0 | 191266.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -191266.4 | 0 | 1615.73 | 191266.4 | 0 | 0 | 0 | 0 | 1759.13 | 0 | -191266.4 | 0 | 0 | 191266.4 | 191266.4 | 0 | 0 | 0 | 96 | 0 | 0 |  | 0 | 0.67 | 3.69 | 4.36 | EA | 96 | 32 | 64 | 96 | EA | 131759.13 | 67554.89 | 64204.24 | 59507.27
N | M007-08-5010-L | M007 | M007 | 08-5010 | HM DOOR SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-08-5010-M | M007 | M007 | 08-5010 | HM DOOR SUPPORT | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 50000
N | M007-08-5100-L | M007 | M007 | 08-5100 | FURNISH ACCESS HATCHES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 36 | 0 | 36 | 36 | EA | 0 | 0 | 0 | 0
N | M007-08-5100-M | M007 | M007 | 08-5100 | FURNISH ACCESS HATCHES | N | M |  | NR | A | 90000 | 99876.64 | 99876.64 | 91781 | 99876.64 | 100 | 0 | 0 | 0 | -8095.64 | Y | 91781 | Y | -1781 | 0 | 0 | 90000 | 0 | 0 | 91781 | Y | -1781 | 0 | 0 | 90000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -91781 | 0 | 0 | 91781 | 0 | 0 | 0 | 0 | 0 | 0 | -91781 | 0 | 0 | 91781 | 91781 | 0 | 0 | 0 | 36 | 0 | 0 |  | 0 | 18 | 0 | 18 | EA | 36 | 0 | 36 | 36 | EA | 99876.64 | 8095.64 | 91781 | -8095.64
N | M007-08-6000-L | M007 | M007 | 08-6000 | OVERHEAD DOORS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
N | M007-08-6000-S | M007 | M007 | 08-6000 | OVERHEAD DOORS SUB | N | S |  | NR | A | 70000 | 22632 | 22632 | 5658 | 22632 | 25 | 0 | 0 | 0 | 0 | Y | 22632 | Y | 47368 | 0 | 0 | 70000 | 0 | 0 | 22632 | Y | 47368 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22632 | 0 | 0 | 22632 | 0 | 0 | 0 | 0 | 0 | 0 | -22632 | 0 | 0 | 22632 | 22632 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0.25 | 1.75 | 2 | EA | 2 | 0 | 2 | 2 | EA | 22632 | 16974 | 5658 | 0
N | M007-08-6010-L | M007 | M007 | 08-6010 | OVERHEAD DOORS SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-08-6010-S | M007 | M007 | 08-6010 | OVERHEAD DOORS SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 5000
N | M007-08-6100-L | M007 | M007 | 08-6100 | GLAZING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
N | M007-08-6100-S | M007 | M007 | 08-6100 | GLAZING SUB | N | S |  | NR | A | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | N | 28000 | N | 0 | 0 | 0 | 28000 | 0 | 0 | 28000 | N | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -28000 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | -28000 | 0 | 0 | 28000 | 28000 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 28000
N | M007-08-6200-L | M007 | M007 | 08-6200 | LOUVERS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-08-6200-S | M007 | M007 | 08-6200 | LOUVERS SUB | N | S |  | NR | A | 503455.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 503455.03 | 0 | 0 | 503455.03 | 0 | 0 | 0 | Y | 503455.03 | 0 | 0 | 503455.03 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-09-6000-L | M007 | M007 | 09-6000 | STUCCO SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 5060 | 0 | 5060 | 5060 | SF | 0 | 0 | 0 | 0
N | M007-09-6000-S | M007 | M007 | 09-6000 | STUCCO SUB | N | S |  | NR | A | 328900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 328900 | 0 | 0 | 328900 | 0 | 0 | 0 | Y | 328900 | 0 | 0 | 328900 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5060 | 0 | 0 |  | 0 | 0 | 5060 | 5060 | SF | 5060 | 0 | 5060 | 5060 | SF | 0 | 0 | 0 | 0
N | M007-09-6100-L | M007 | M007 | 09-6100 | TILE SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 246 | 0 | 246 | 246 | SF | 0 | 0 | 0 | 0
N | M007-09-6100-S | M007 | M007 | 09-6100 | TILE SUB | N | S |  | NR | A | 14760 | 23820 | 23820 | 0 | 23820 | 0 | 0 | 0 | 0 | 10380 | Y | 34200 | Y | -19440 | 0 | 0 | 14760 | 0 | 0 | 34200 | Y | -19440 | 0 | 0 | 14760 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -34200 | 0 | 0 | 34200 | 0 | 0 | 0 | 0 | 11910 | 0 | -34200 | 0 | 0 | 34200 | 34200 | 0 | 0 | 0 | 246 | 0 | 0 |  | 0 | 0 | 246 | 246 | SF | 246 | 0 | 246 | 246 | SF | 23820 | 23820 | 0 | 10380
N | M007-09-6110-L | M007 | M007 | 09-6110 | TILING SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-09-6110-S | M007 | M007 | 09-6110 | TILING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 5000 | Y | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 5000
N | M007-09-6200-L | M007 | M007 | 09-6200 | VCT FLOORING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 173 | 0 | 173 | 173 | SF | 0 | 0 | 0 | 0
N | M007-09-6200-S | M007 | M007 | 09-6200 | VCT FLOORING SUB | N | S |  | NR | A | 82742.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 82742.44 | 0 | 0 | 82742.44 | 0 | 0 | 0 | Y | 82742.44 | 0 | 0 | 82742.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 |  | 0 | 0 | 173 | 173 | SF | 173 | 0 | 173 | 173 | SF | 0 | 0 | 0 | 0
N | M007-09-6300-L | M007 | M007 | 09-6300 | PAINT SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-09-6300-S | M007 | M007 | 09-6300 | PAINT SUB | N | S |  | NR | A | 660816.22 | 330000 | 330000 | 0 | 330000 | 0 | 0 | 0 | 0 | 203755 | Y | 533755 | Y | 127061.22 | 0 | 0 | 660816.22 | 0 | 0 | 533755 | Y | 127061.22 | 0 | 0 | 660816.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -533755 | 0 | 0 | 533755 | 0 | 0 | 0 | 0 | 0 | 0 | -533755 | 0 | 0 | 533755 | 533755 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 330000 | 330000 | 0 | 203755
N | M007-09-6310-L | M007 | M007 | 09-6310 | PAINTING SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-09-6310-S | M007 | M007 | 09-6310 | PAINTING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | Y | 40000 | Y | -40000 | 0 | 0 | 0 | 0 | 0 | 40000 | Y | -40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | -40000 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 40000
N | M007-10-1000-L | M007 | M007 | 10-1000 | FIRE EXTINGUISHERS NEW BLDGS | N | L |  | NR | P | 1836.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836.95 | N | 1836.95 | N | 0 | 0 | 0 | 1836.95 | 0 | 0 | 1836.95 | N | 0 | 0 | 0 | 1836.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1836.95 | 0 | 0 | 1836.95 | 0 | 0 | 0 | 0 | 0 | 0 | -1836.95 | 0 | 0 | 1836.95 | 1836.95 | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 16 | 0 | 16 | 16 | HR | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 1836.95
N | M007-10-1100-L | M007 | M007 | 10-1100 | TOILET ACCESSORIES NEW BLDGS | N | L |  | NR | P | 11021.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11021.7 | N | 11021.7 | N | 0 | 0 | 0 | 11021.7 | 0 | 0 | 11021.7 | N | 0 | 0 | 0 | 11021.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11021.7 | 0 | 0 | 11021.7 | 0 | 0 | 0 | 0 | 0 | 0 | -11021.7 | 0 | 0 | 11021.7 | 11021.7 | 0 | 0 | 0 | 96 | 0 | 96 | 96 | 96 | 0 | 96 | 96 | HR | 15 | 0 | 15 | 15 | EA | 0 | 0 | 0 | 11021.7
N | M007-10-1200-L | M007 | M007 | 10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | N | L |  | NR | P | 289147.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289147.86 | N | 289147.86 | N | 0 | 0 | 0 | 289147.86 | 0 | 0 | 289147.86 | N | 0 | 0 | 0 | 289147.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -289147.86 | 0 | 0 | 289147.86 | 0 | 0 | 0 | 0 | 0 | 0 | -289147.86 | 0 | 0 | 289147.86 | 289147.86 | 0 | 0 | 0 | 2480 | 0 | 2480 | 2480 | 2480 | 0 | 2480 | 2480 | HR | 930 | 0 | 930 | 930 | LF | 0 | 0 | 0 | 289147.86
N | M007-10-1300-L | M007 | M007 | 10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | N | L |  | NR | P | 22248.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22248.03 | N | 22248.03 | N | 0 | 0 | 0 | 22248.03 | 0 | 0 | 22248.03 | N | 0 | 0 | 0 | 22248.03 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22248.03 | 0 | 0 | 22248.03 | 0 | 0 | 0 | 0 | 0 | 0 | -22248.03 | 0 | 0 | 22248.03 | 22248.03 | 0 | 0 | 0 | 196 | 0 | 196 | 196 | 196 | 0 | 196 | 196 | HR | 14 | 0 | 14 | 14 | EA | 0 | 0 | 0 | 22248.03
N | M007-10-1400-L | M007 | M007 | 10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | N | L |  | NR | P | 50000.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000.29 | N | 50000.29 | N | 0 | 0 | 0 | 50000.29 | 0 | 0 | 50000.29 | N | 0 | 0 | 0 | 50000.29 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000.29 | 0 | 0 | 50000.29 | 0 | 0 | 0 | 0 | 0 | 0 | -50000.29 | 0 | 0 | 50000.29 | 50000.29 | 0 | 0 | 0 | 440.49 | 0 | 440.49 | 440.49 | 440.49 | 0 | 440.49 | 440.49 | HR | 387 | 0 | 387 | 387 | LF | 0 | 0 | 0 | 50000.29
N | M007-10-1500-L | M007 | M007 | 10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | N | L |  | NR | P | 19069.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19069.74 | N | 19069.74 | N | 0 | 0 | 0 | 19069.74 | 0 | 0 | 19069.74 | N | 0 | 0 | 0 | 19069.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -19069.74 | 0 | 0 | 19069.74 | 0 | 0 | 0 | 0 | 0 | 0 | -19069.74 | 0 | 0 | 19069.74 | 19069.74 | 0 | 0 | 0 | 168 | 0 | 168 | 168 | 168 | 0 | 168 | 168 | HR | 105 | 0 | 105 | 105 | LF | 0 | 0 | 0 | 19069.74
N | M007-10-5000-L | M007 | M007 | 10-5000 | FURNISH TOILET ACCESSORIES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 15 | 0 | 15 | 15 | EA | 0 | 0 | 0 | 0
N | M007-10-5000-M | M007 | M007 | 10-5000 | FURNISH TOILET ACCESSORIES | N | M |  | NR | A | 811.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 811.05 | N | 811.05 | N | 0 | 0 | 0 | 811.05 | 0 | 0 | 811.05 | N | 0 | 0 | 0 | 811.05 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -811.05 | 0 | 0 | 811.05 | 0 | 0 | 0 | 0 | 0 | 0 | -811.05 | 0 | 0 | 811.05 | 811.05 | 0 | 0 | 0 | 15 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 15 | 0 | 15 | 15 | EA | 0 | 0 | 0 | 811.05
N | M007-10-5100-L | M007 | M007 | 10-5100 | FURNISH FIRE EXTINGUISHERS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 0
N | M007-10-5100-M | M007 | M007 | 10-5100 | FURNISH FIRE EXTINGUISHERS | N | M |  | NR | A | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2450 | N | 2450 | N | 0 | 0 | 0 | 2450 | 0 | 0 | 2450 | N | 0 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2450 | 0 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 0 | -2450 | 0 | 0 | 2450 | 2450 | 0 | 0 | 0 | 7 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 2450
N | M007-10-5200-L | M007 | M007 | 10-5200 | FURNISH AQUA FLOOD BARRIERS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 930 | 0 | 930 | 930 | LF | 0 | 0 | 0 | 0
N | M007-10-5200-M | M007 | M007 | 10-5200 | FURNISH AQUA FLOOD BARRIERS | N | M |  | NR | A | 479954.4 | 1532090 | 1532090 | 763362.2 | 1532090 | 45.3647 | 0 | 0 | 0 | 150634.63 | Y | 1682724.63 | Y | -1202770.23 | 0 | 0 | 479954.4 | 0 | 0 | 1682724.63 | Y | -1202770.23 | 0 | 0 | 479954.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1682724.63 | 0 | 142050 | 1682724.63 | 0 | 0 | 0 | 0 | 0 | 0 | -1682724.63 | 0 | 0 | 1682724.63 | 1682724.63 | 0 | 0 | 0 | 930 | 0 | 0 |  | 0 | 52.05 | 101.95 | 154 | LF | 930 | 0 | 930 | 930 | LF | 1532090 | 768727.8 | 763362.2 | 150634.63
N | M007-10-5300-L | M007 | M007 | 10-5300 | FURNISH 8.08 FLOOD DOORS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 30 | 0 | 30 | 30 | EA | 0 | 0 | 0 | 0
N | M007-10-5300-M | M007 | M007 | 10-5300 | FURNISH 8.08 FLOOD DOORS | N | M |  | NR | A | 385685.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 385685.7 | 0 | 0 | 385685.7 | 0 | 0 | 0 | Y | 385685.7 | 0 | 0 | 385685.7 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 30 | 0 | 30 | 30 | EA | 0 | 0 | 0 | 0
N | M007-10-5400-L | M007 | M007 | 10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-10-5400-M | M007 | M007 | 10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | N | M |  | NR | A | 817084.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 817084.53 | 0 | 0 | 817084.53 | 0 | 0 | 0 | Y | 817084.53 | 0 | 0 | 817084.53 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-11-1000-L | M007 | M007 | 11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | N | L |  | NR | P | 35505.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35505.12 | N | 35505.12 | N | 0 | 0 | 0 | 35505.12 | 0 | 0 | 35505.12 | N | 0 | 0 | 0 | 35505.12 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -35505.12 | 0 | 0 | 35505.12 | 0 | 0 | 0 | 0 | 0 | 0 | -35505.12 | 0 | 0 | 35505.12 | 35505.12 | 0 | 0 | 0 | 336 | 0 | 336 | 336 | 336 | 0 | 336 | 336 | HR | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 35505.12
N | M007-11-6000-L | M007 | M007 | 11-6000 | PLAY AREA ITEMS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 0
N | M007-11-6000-M | M007 | M007 | 11-6000 | PLAY AREA ITEMS SUB | N | M |  | NR | U | 0 | 224018 | 224018 | 224018 | 224018 | 100 | 0 | 0 | 0 | 0 | N | 224018 | N | -224018 | 0 | 0 | 0 | 0 | 0 | 224018 | N | -224018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -224018 | 0 | 0 | 224018 | 0 | 0 | 0 | 0 | 0 | 0 | -224018 | 0 | 0 | 224018 | 224018 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7 | 0 | 7 | NA | 7 | 0 | 7 | 7 | EA | 224018 | 0 | 224018 | 0
N | M007-11-6000-S | M007 | M007 | 11-6000 | PLAY AREA ITEMS SUB | N | S |  | NR | A | 446718.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222700.49 | Y | 222700.49 | Y | 224018 | 0 | 0 | 446718.49 | 0 | 0 | 222700.49 | Y | 224018 | 0 | 0 | 446718.49 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -222700.49 | 0 | 0 | 222700.49 | 0 | 0 | 0 | 0 | 0 | 0 | -222700.49 | 0 | 0 | 222700.49 | 222700.49 | 0 | 0 | 0 | 7 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 7 | 0 | 7 | 7 | EA | 0 | 0 | 0 | 222700.49
N | M007-14-6000-L | M007 | M007 | 14-6000 | ELEVATOR SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-14-6000-S | M007 | M007 | 14-6000 | ELEVATOR SUB | N | S |  | NR | A | 540000 | 34687.58 | 34687.58 | 31860 | 34687.58 | 3.0995 | 0 | 0 | 0 | 993215.92 | Y | 1027903.5 | Y | -487903.5 | 0 | 0 | 540000 | 0 | 0 | 1027903.5 | Y | -487903.5 | 0 | 0 | 540000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1027903.5 | 0 | 0 | 1027903.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1027903.5 | 0 | 0 | 1027903.5 | 1027903.5 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 1 | 0 | 1 | LS | 1 | 0 | 1 | 1 | LS | 34687.58 | 2827.58 | 31860 | 993215.92
N | M007-14-6010-L | M007 | M007 | 14-6010 | ELEVATOR JUNCTION BOXES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 36 | 0 | 36 | 36 | EA | 0 | 0 | 0 | 0
N | M007-14-6010-S | M007 | M007 | 14-6010 | ELEVATOR JUNCTION BOXES | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 36 | 0 | 36 | 36 | EA | 0 | 0 | 0 | 250000
N | M007-22-5000-C | M007 | M007 | 22-5000 | Purchase Yard Pumps | N | C |  | NR | U | 0 | 90656 | 90656 | 0 | 90656 | 0 | 0 | 0 | 0 | -90656 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 16 | 16 | NA | 16 | 0 | 16 | 16 | EA | 90656 | 90656 | 0 | -90656
N | M007-22-5000-L | M007 | M007 | 22-5000 | Purchase Yard Pumps | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 16 | 0 | 16 | 16 | EA | 0 | 0 | 0 | 0
N | M007-22-5000-M | M007 | M007 | 22-5000 | Purchase Yard Pumps | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99876.64 | Y | 99876.64 | Y | -99876.64 | 0 | 0 | 0 | 0 | 0 | 99876.64 | Y | -99876.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -99876.64 | 0 | 0 | 99876.64 | 0 | 0 | 0 | 0 | 0 | 0 | -99876.64 | 0 | 0 | 99876.64 | 99876.64 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 16 | 0 | 16 | 16 | EA | 0 | 0 | 0 | 99876.64
N | M007-22-6000-L | M007 | M007 | 22-6000 | PLUMBING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-22-6000-S | M007 | M007 | 22-6000 | PLUMBING SUB | N | S |  | NR | A | 15094999.93 | 13099982.4 | 13099982.4 | 6910021.12 | 13099982.4 | 52.7483 | 0 | 0 | 0 | 17.6 | Y | 13100000 | Y | 1994999.93 | 0 | 0 | 15094999.93 | 0 | 0 | 13100000 | Y | 1994999.93 | 0 | 0 | 15094999.93 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13100000 | 1043761.78 | 1267473.71 | 13100000 | 0 | 0 | 0 | 0 | 0 | 0 | -13100000 | 0 | 0 | 13100000 | 13100000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 13479.23 | 15618.44 | 29097.67 | LS | 1 | 0 | 1 | 1 | LS | 13099982.4 | 6189961.28 | 6910021.12 | 17.6
N | M007-22-6010-C | M007 | M007 | 22-6010 | PLUMBING BOND | N | C |  | NR | U | 0 | 125426 | 125426 | 125426 | 125426 | 100 | 0 | 0 | 0 | 0 | Y | 125426 | Y | -125426 | 0 | 0 | 0 | 0 | 0 | 125426 | Y | -125426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -125426 | 0 | 0 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 | -125426 | 0 | 0 | 125426 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
N | M007-22-6010-L | M007 | M007 | 22-6010 | PLUMBING BOND | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 1 | 0 | 1 | LS | 0 | 0 | 0 | 0
N | M007-22-6020-L | M007 | M007 | 22-6020 | PIPE INSULATION | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 0
N | M007-22-6020-S | M007 | M007 | 22-6020 | PIPE INSULATION | N | S |  | NR | A | 0 | 400000 | 400000 | 33100 | 400000 | 6.62 | 0 | 0 | 0 | 100000 | Y | 500000 | Y | -500000 | 0 | 0 | 0 | 0 | 0 | 500000 | Y | -500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500000 | 0 | 30120 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.46 | -1.46 | 0 | NA | 0 | 0 | 0 | 0 | LS | 400000 | 366900 | 33100 | 100000
N | M007-22-6025-L | M007 | M007 | 22-6025 | PLUMBING INSULATION REMOVAL | N | L |  | NR | P | 0 | 8405.69 | 8405.69 | 8405.69 | 8405.69 | 33.6228 | 0 | 0 | 0 | 16594.31 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 84 | 166 | 250 | HR | 0 | 670 | 1330 | 2000 | LF | 0 | 0 | 0 | 16594.31
N | M007-22-6030-L | M007 | M007 | 22-6030 | YARD PUMP SUPPLY | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-22-6030-M | M007 | M007 | 22-6030 | YARD PUMP SUPPLY | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-22-6030-S | M007 | M007 | 22-6030 | YARD PUMP SUPPLY | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-22-6040-LAB | M007 | M007 | 22-6040 | YARD PUMP INSTALL | N | LAB |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209344 | Y | 209344 | Y | -209344 | 0 | 0 | 0 | 0 | 0 | 209344 | Y | -209344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -209344 | 0 | 0 | 209344 | 0 | 0 | 0 | 0 | 0 | 0 | -209344 | 0 | 0 | 209344 | 209344 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2093.44 | 2093.44 | NA | 16 | 0 | 16 | 16 | EA | 0 | 0 | 0 | 209344
N | M007-22-6050-L | M007 | M007 | 22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 21 | 0 | 21 | 21 | EA | 0 | 0 | 0 | 0
N | M007-22-6050-M | M007 | M007 | 22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | N | M |  | NR | U | 0 | 44723.67 | 44723.67 | 41078 | 44723.67 | 91.2844 | 0 | 0 | 0 | 276.33 | Y | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 45000 | Y | -45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45000 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | -45000 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | -1 | 0 | NA | 21 | 0 | 21 | 21 | EA | 44723.67 | 3645.67 | 41078 | 276.33
N | M007-22-6050-S | M007 | M007 | 22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 21 | 0 | 21 | 21 | EA | 0 | 0 | 0 | 0
N | M007-22-6060-L | M007 | M007 | 22-6060 | PLUMBING SUB SUPPORT | N | L |  | NR | P | 0 | 698.78 | 698.78 | 698.78 | 698.78 | 100 | 0 | 0 | 0 | 0 | N | 698.78 | N | -698.78 | 0 | 0 | 0 | 0 | 0 | 698.78 | N | -698.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -698.78 | 698.78 | 0 | 0 | -698.78 | 0 | 0 | 0 | 0 | 0 | -698.78 | 0 | 0 | 698.78 | 698.78 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | HR | 0 | 6 | 0 | 6 | NA | 0 | 0 | 0 | 0
N | M007-22-6060-S | M007 | M007 | 22-6060 | PLUMBING SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 6 | 0 | 6 | NA | 0 | 0 | 0 | 0
N | M007-22-6070-L | M007 | M007 | 22-6070 | PLUMBING SCAFFOLD | N | L |  | NR | P | 0 | 1257.95 | 1257.95 | 1257.95 | 1257.95 | 100 | 0 | 0 | 0 | 0 | Y | 1257.95 | Y | -1257.95 | 0 | 0 | 0 | 0 | 0 | 1257.95 | Y | -1257.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1257.95 | 0 | 1257.95 | 1257.95 | 0 | 0 | 0 | 0 | 0 | 0 | -1257.95 | 0 | 0 | 1257.95 | 1257.95 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 11 | 0 | 11 | HR | 0 | 11 | 0 | 11 | NA | 0 | 0 | 0 | 0
N | M007-23-6000-L | M007 | M007 | 23-6000 | HVAC SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-23-6000-S | M007 | M007 | 23-6000 | HVAC SUB | N | S |  | NR | A | 22636999.82 | 22500000 | 22500000 | 14513950.31 | 22500000 | 60.2239 | 0 | 0 | 0 | 1600000 | Y | 24100000 | Y | -1463000.18 | 0 | 0 | 22636999.82 | 0 | 0 | 24100000 | Y | -1463000.18 | 0 | 0 | 22636999.82 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -24100000 | 0 | 1562696.75 | 24100000 | 0 | 0 | 0 | 0 | 0 | 0 | -24100000 | 0 | 0 | 24100000 | 24100000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 76306.59 | 35398.41 | 111705 | LS | 1 | 0 | 1 | 1 | LS | 22500000 | 7986049.69 | 14513950.31 | 1600000
N | M007-23-6010-L | M007 | M007 | 23-6010 | HVAC SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-23-6010-S | M007 | M007 | 23-6010 | HVAC SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 200000 | Y | -200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 200000
N | M007-23-6020-L | M007 | M007 | 23-6020 | MECHANICAL LOUVERS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-23-6020-M | M007 | M007 | 23-6020 | MECHANICAL LOUVERS | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-26-6000-L | M007 | M007 | 26-6000 | ELECTRICAL SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-26-6000-S | M007 | M007 | 26-6000 | ELECTRICAL SUB | N | S |  | NR | A | 48559999.54 | 50075000 | 50075000 | 17975171.65 | 50075000 | 35.8146 | 0 | 0 | 2486 | 111995.05 | Y | 50186995.05 | Y | -1626995.51 | 2486 | 2486 | 48562485.54 | 0 | 2486 | 50189481.05 | Y | -1626995.51 | 0 | 2486 | 48559999.54 | 0 | 2486 | 2486 | 0 | 0 | N | 2486 | 0 | -50189481.05 | 2896720 | 2211175 | 50186995.05 | 0 | 0 | 0 | 0 | 0 | 0 | -50189481.05 | 0 | 0 | 50186995.05 | 50186995.05 | 0 | 0 | 2486 | 1 | 0 | 0 |  | 1 | 481706.22 | 1009417.03 | 1491123.25 | LS | 1 | 0 | 1 | 1 | LS | 50075000 | 32099828.35 | 17975171.65 | 114481.05
N | M007-26-6010-C | M007 | M007 | 26-6010 | TEMP ELECTRIC | N | C |  | NR | U | 0 | 2449.46 | 2449.46 | 2449.46 | 2449.46 | 100 | 0 | 0 | 0 | 0 | N | 2449.46 | N | -2449.46 | 0 | 0 | 0 | 0 | 0 | 2449.46 | N | -2449.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2449.46 | 2449.46 | 0 | 0 | -2449.46 | 0 | 0 | 2449.46 | 0 | 0 | -2449.46 | 0 | 0 | 2449.46 | 2449.46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 | 1 | NA | 18 | 0 | 18 | 18 | EA | 2449.46 | 0 | 2449.46 | 0
N | M007-26-6010-L | M007 | M007 | 26-6010 | TEMP ELECTRIC | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 18 | 0 | 18 | 18 | EA | 0 | 0 | 0 | 0
N | M007-26-6010-S | M007 | M007 | 26-6010 | TEMP ELECTRIC | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128004.95 | Y | 128004.95 | Y | -128004.95 | 0 | 0 | 0 | 0 | 0 | 128004.95 | Y | -128004.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -128004.95 | 0 | 0 | 128004.95 | 0 | 0 | 0 | 0 | 0 | 0 | -128004.95 | 0 | 0 | 128004.95 | 128004.95 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 18 | 0 | 18 | 18 | EA | 0 | 0 | 0 | 128004.95
N | M007-26-6020-L | M007 | M007 | 26-6020 | ELECTRICAL SUB SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-26-6020-S | M007 | M007 | 26-6020 | ELECTRICAL SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-26-6030-L | M007 | M007 | 26-6030 | EQUIPMENT INSTALLATION SUPPORT | N | L |  | NR | P | 0 | 20938.11 | 20938.11 | 20938.11 | 20938.11 | 101.9571 | 0 | 0 | 0 | -401.91 | Y | 20536.2 | Y | -20536.2 | 0 | 0 | 0 | 0 | 0 | 20536.2 | Y | -20536.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -20536.2 | 5892.11 | 2323.72 | 20536.2 | 0 | 0 | 0 | 0 | 0 | 0 | -20536.2 | 0 | 0 | 20536.2 | 20536.2 | 0 | 0 | 0 | 0 | 0 | 160.21 | 160.21 | 0 | 168.5 | -8.29 | 160.21 | HR | 0 | 150.54 | 9.46 | 160 | HR | 0 | 0 | 0 | -401.91
N | M007-31-1000-L | M007 | M007 | 31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | N | L |  | NR | P | 58380 | 114105.2 | 114105.2 | 114105.2 | 114105.2 | 74.4111 | 0 | 0 | 0 | 39239.15 | Y | 153344.35 | Y | -94964.35 | 0 | 0 | 58380 | 0 | 0 | 153344.35 | Y | -94964.35 | 0 | 0 | 58380 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -153344.35 | 10158.31 | 22700.25 | 153344.35 | 0 | 0 | 0 | 0 | 0 | 0 | -153344.35 | 0 | 0 | 153344.35 | 153344.35 | 0 | 0 | 0 | 533.6 | 0 | 1411.1 | 1411.1 | 533.6 | 1034.5 | 376.6 | 1411.1 | HR | 3335 | 3380 | 3358 | 6738 | CY | 0 | 0 | 0 | 39239.15
N | M007-31-1100-L | M007 | M007 | 31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | N | L |  | NR | P | 54203.86 | 51790.98 | 51790.98 | 51790.98 | 51790.98 | 63.1438 | 0 | 0 | 0 | 30229.68 | Y | 82020.66 | Y | -27816.8 | 0 | 0 | 54203.86 | 0 | 0 | 82020.66 | Y | -27816.8 | 0 | 0 | 54203.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -82020.66 | 2487.58 | 0 | 82020.66 | 0 | 0 | 0 | 0 | 0 | 0 | -82020.66 | 0 | 0 | 82020.66 | 82020.66 | 0 | 0 | 0 | 566.66 | 0 | 780.27 | 780.27 | 566.66 | 456.5 | 323.77 | 780.27 | HR | 2125 | 1421 | 3026.3 | 4447.3 | CY | 0 | 0 | 0 | 30229.68
N | M007-31-1200-L | M007 | M007 | 31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | N | L |  | NR | P | 4107.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4107.44 | N | 4107.44 | N | 0 | 0 | 0 | 4107.44 | 0 | 0 | 4107.44 | N | 0 | 0 | 0 | 4107.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4107.44 | 0 | 0 | 4107.44 | 0 | 0 | 0 | 0 | 0 | 0 | -4107.44 | 0 | 0 | 4107.44 | 4107.44 | 0 | 0 | 0 | 42.94 | 0 | 42.94 | 42.94 | 42.94 | 0 | 42.94 | 42.94 | HR | 161 | 0 | 161 | 161 | CY | 0 | 0 | 0 | 4107.44
N | M007-31-1300-L | M007 | M007 | 31-1300 | EXCAVATION NEW BLDGS | N | L |  | NR | P | 110807.92 | 205909.86 | 205909.86 | 205909.86 | 205909.86 | 100 | 0 | 0 | 0 | 0 | Y | 205909.86 | Y | -95101.94 | 0 | 0 | 110807.92 | 0 | 0 | 205909.86 | Y | -95101.94 | 0 | 0 | 110807.92 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -205909.86 | 0 | 0 | 205909.86 | 0 | 0 | 0 | 0 | 0 | 0 | -205909.86 | 0 | 0 | 205909.86 | 205909.86 | 0 | 0 | 0 | 1012.8 | 0 | 1841 | 1841 | 1012.8 | 1841 | 0 | 1841 | HR | 6330 | 7989.55 | 3 | 7992.55 | CY | 0 | 0 | 0 | 0
N | M007-31-1400-L | M007 | M007 | 31-1400 | BACKFILL NEW BLDGS | N | L |  | NR | P | 113077.62 | 138674.5 | 138674.5 | 138674.5 | 138674.5 | 92.4497 | 0 | 0 | 0 | 11325.5 | Y | 150000 | Y | -36922.38 | 0 | 0 | 113077.62 | 0 | 0 | 150000 | Y | -36922.38 | 0 | 0 | 113077.62 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 4564.77 | 6088.92 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 1182.14 | 0 | 1381.55 | 1381.55 | 1182.14 | 1259.5 | 122.05 | 1381.55 | HR | 4433 | 3064.25 | 383.75 | 3448 | CY | 0 | 0 | 0 | 11325.5
N | M007-31-1500-L | M007 | M007 | 31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | N | L |  | NR | P | 7933.64 | 23506.32 | 23506.32 | 23506.32 | 23506.32 | 94.0253 | 0 | 0 | 0 | 1493.68 | Y | 25000 | Y | -17066.36 | 0 | 0 | 7933.64 | 0 | 0 | 25000 | Y | -17066.36 | 0 | 0 | 7933.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 82.94 | 0 | 222.98 | 222.98 | 82.94 | 218.5 | 4.48 | 222.98 | HR | 311 | 303 | 0 | 303 | CY | 0 | 0 | 0 | 1493.68
N | M007-31-1600-L | M007 | M007 | 31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | N | L |  | NR | P | 87903.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 87903.75 | 0 | 0 | 87903.75 | 0 | 0 | 0 | Y | 87903.75 | 0 | 0 | 87903.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | HR | 3 | 0 | 0 | 0 | MO | 0 | 0 | 0 | 0
N | M007-31-1700-L | M007 | M007 | 31-1700 | DEWATER NEW BLDGS | N | L |  | NR | P | 205108.75 | 140469.48 | 140469.48 | 140469.48 | 140469.48 | 95.9019 | 0 | 0 | 0 | 6002.6 | Y | 146472.08 | Y | 58636.67 | 0 | 0 | 205108.75 | 0 | 0 | 146472.08 | Y | 58636.67 | 0 | 0 | 205108.75 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -146472.08 | 0 | 0 | 146472.08 | 0 | 0 | 0 | 0 | 0 | 0 | -146472.08 | 0 | 0 | 146472.08 | 146472.08 | 0 | 0 | 0 | 1540 | 0 | 1032.05 | 1032.05 | 1540 | 962.5 | 69.55 | 1032.05 | HR | 1200 | 1066.55 | 0 | 1066.55 | HR | 0 | 0 | 0 | 6002.6
N | M007-31-1800-L | M007 | M007 | 31-1800 | INSTALL H PILES | N | L |  | NR | P | 104668.74 | 26802.94 | 26802.94 | 26802.94 | 26802.94 | 100 | 0 | 0 | 0 | 0 | Y | 26802.94 | Y | 77865.8 | 0 | 0 | 104668.74 | 0 | 0 | 26802.94 | Y | 77865.8 | 0 | 0 | 104668.74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26802.94 | 0 | 0 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 0 | -26802.94 | 0 | 0 | 26802.94 | 26802.94 | 0 | 0 | 0 | 878 | 0 | 223 | 223 | 878 | 223 | 0 | 223 | HR | 120 | 280 | 0 | 280 | LF | 0 | 0 | 0 | 0
N | M007-31-1810-C | M007 | M007 | 31-1810 | SOE MATERIAL | N | C |  | NR | U | 0 | 483998.19 | 483998.19 | 439637.81 | 483998.19 | 89.3103 | 0 | 0 | 0 | 8260.56 | Y | 492258.75 | Y | -492258.75 | 0 | 0 | 0 | 0 | 0 | 492258.75 | Y | -492258.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -492258.75 | 0 | 0 | 492258.75 | 0 | 0 | 0 | 0 | 0 | 0 | -492258.75 | 0 | 0 | 492258.75 | 492258.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 446488.33 | 7648.67 | 454137 | NA | 1 | 0 | 1 | 1 | LS | 483998.19 | 44360.38 | 439637.81 | 8260.56
N | M007-31-1810-L | M007 | M007 | 31-1810 | SOE MATERIAL | N | L |  | NR | P | 0 | 1339.44 | 1339.44 | 1339.44 | 1339.44 | 100 | 0 | 0 | 0 | 0 | Y | 1339.44 | Y | -1339.44 | 0 | 0 | 0 | 0 | 0 | 1339.44 | Y | -1339.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1339.44 | 0 | 0 | 1339.44 | 0 | 0 | 0 | 0 | 0 | 0 | -1339.44 | 0 | 0 | 1339.44 | 1339.44 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-1810-M | M007 | M007 | 31-1810 | SOE MATERIAL | N | M |  | NR | U | 0 | 4600 | 4600 | 4600 | 4600 | 100 | 0 | 0 | 0 | 0 | N | 4600 | N | -4600 | 0 | 0 | 0 | 0 | 0 | 4600 | N | -4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4600 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | -4600 | 0 | 0 | 4600 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | 0 | 100 | NA | 1 | 0 | 1 | 1 | LS | 4600 | 0 | 4600 | 0
N | M007-31-1820-L | M007 | M007 | 31-1820 | INSTALL SHEETING | N | L |  | NR | P | 0 | 207132.01 | 207132.01 | 207132.01 | 207132.01 | 98.1956 | 0 | 0 | 0 | 3806.14 | Y | 210938.15 | Y | -210938.15 | 0 | 0 | 0 | 0 | 0 | 210938.15 | Y | -210938.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -210938.15 | 0 | 0 | 210938.15 | 0 | 0 | 0 | 0 | 0 | 0 | -210938.15 | 0 | 0 | 210938.15 | 210938.15 | 0 | 0 | 0 | 0 | 0 | 1738.42 | 1738.42 | 0 | 1711 | 27.42 | 1738.42 | HR | 0 | 8681.99 | 0 | 8681.99 | SF | 0 | 0 | 0 | 3806.14
N | M007-31-1820-S | M007 | M007 | 31-1820 | INSTALL SHEETING | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 8681.99 | 0 | 8681.99 | SF | 0 | 0 | 0 | 0
N | M007-31-1830-L | M007 | M007 | 31-1830 | INSTALL LAGGING | N | L |  | NR | P | 0 | 53855.12 | 53855.12 | 53855.12 | 53855.12 | 100 | 0 | 0 | 0 | 0 | Y | 53855.12 | Y | -53855.12 | 0 | 0 | 0 | 0 | 0 | 53855.12 | Y | -53855.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -53855.12 | 0 | 0 | 53855.12 | 0 | 0 | 0 | 0 | 0 | 0 | -53855.12 | 0 | 0 | 53855.12 | 53855.12 | 0 | 0 | 0 | 0 | 0 | 465 | 465 | 0 | 465 | 0 | 465 | HR | 0 | 8318.5 | 0 | 8318.5 | SF | 0 | 0 | 0 | 0
N | M007-31-1830-O | M007 | M007 | 31-1830 | INSTALL LAGGING | N | O |  | NR | U | 0 | 1771.2 | 1771.2 | 1771.2 | 1771.2 | 100 | 0 | 0 | 0 | 0 | N | 1771.2 | N | -1771.2 | 0 | 0 | 0 | 0 | 0 | 1771.2 | N | -1771.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1771.2 | 0 | 0 | 1771.2 | 0 | 0 | 0 | 0 | 0 | 0 | -1771.2 | 0 | 0 | 1771.2 | 1771.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 8318.5 | 0 | 8318.5 | SF | 0 | 0 | 0 | 0
N | M007-31-1840-L | M007 | M007 | 31-1840 | MUD SLAB | N | L |  | NR | P | 0 | 55578.77 | 55578.77 | 55578.77 | 55578.77 | 87.1383 | 0 | 0 | 0 | 8203.47 | Y | 63782.24 | Y | -63782.24 | 0 | 0 | 0 | 0 | 0 | 63782.24 | Y | -63782.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -63782.24 | 0 | 0 | 63782.24 | 0 | 0 | 0 | 0 | 0 | 0 | -63782.24 | 0 | 0 | 63782.24 | 63782.24 | 0 | 0 | 0 | 0 | 0 | 569.92 | 569.92 | 0 | 495 | 74.92 | 569.92 | HR | 120 | 863 | 247 | 1110 | CY | 0 | 0 | 0 | 8203.47
N | M007-31-1850-L | M007 | M007 | 31-1850 | SOE Sub | N | L |  | NR | P | 0 | 133053.32 | 133053.32 | 133053.32 | 133053.32 | 100 | 0 | 0 | 0 | 0 | Y | 133053.32 | Y | -133053.32 | 0 | 0 | 0 | 0 | 0 | 133053.32 | Y | -133053.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -133053.32 | 0 | 0 | 133053.32 | 0 | 0 | 0 | 0 | 0 | 0 | -133053.32 | 0 | 0 | 133053.32 | 133053.32 | 0 | 0 | 0 | 0 | 0 | 988.5 | 988.5 | 0 | 988.5 | 0 | 988.5 | HR | 0 | 836 | 0 | 836 | HR | 0 | 0 | 0 | 0
N | M007-31-1850-S | M007 | M007 | 31-1850 | SOE Sub | N | S |  | NR | A | 0 | 269285.61 | 269285.61 | 269285.61 | 269285.61 | 100 | 0 | 0 | 0 | 0 | N | 269285.61 | N | -269285.61 | 0 | 0 | 0 | 0 | 0 | 269285.61 | N | -269285.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -269285.61 | 0 | 0 | 269285.61 | 0 | 0 | 0 | 0 | 0 | 0 | -269285.61 | 0 | 0 | 269285.61 | 269285.61 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 6 | 2 | 8 | NA | 0 | 836 | 0 | 836 | HR | 269285.61 | -180000 | 449285.61 | 0
N | M007-31-1860-L | M007 | M007 | 31-1860 | SOE Sub Support | N | L |  | NR | P | 0 | 15201.85 | 15201.85 | 15201.85 | 15201.85 | 100 | 0 | 0 | 0 | 0 | Y | 15201.85 | Y | -15201.85 | 0 | 0 | 0 | 0 | 0 | 15201.85 | Y | -15201.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15201.85 | 0 | 0 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 0 | -15201.85 | 0 | 0 | 15201.85 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 143 | 143 | 0 | 143 | 0 | 143 | HR | 0 | 11.91 | 0.09 | 12 | SH | 0 | 0 | 0 | 0
N | M007-31-1900-L | M007 | M007 | 31-1900 | TREE PROTECTION | N | L |  | NR | P | 19131 | 42328.59 | 42328.59 | 42328.59 | 42328.59 | 84.6572 | 0 | 0 | 0 | 7671.41 | Y | 50000 | Y | -30869 | 0 | 0 | 19131 | 0 | 0 | 50000 | Y | -30869 | 0 | 0 | 19131 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 200 | 0 | 450.15 | 450.15 | 200 | 387.5 | 62.65 | 450.15 | HR | 135 | 135 | 0 | 135 | EA | 0 | 0 | 0 | 7671.41
N | M007-31-2000-L | M007 | M007 | 31-2000 | TEST PIT SUPPORT | N | L |  | NR | P | 46459.22 | 83241.53 | 83241.53 | 83241.53 | 83241.53 | 100 | 0 | 0 | 0 | 0 | Y | 83241.53 | Y | -36782.31 | 0 | 0 | 46459.22 | 0 | 0 | 83241.53 | Y | -36782.31 | 0 | 0 | 46459.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -83241.53 | 0 | 0 | 83241.53 | 0 | 0 | 0 | 0 | 0 | 0 | -83241.53 | 0 | 0 | 83241.53 | 83241.53 | 0 | 0 | 0 | 488.89 | 0 | 792.5 | 792.5 | 488.89 | 792.5 | 0 | 792.5 | HR | 400 | 1620.62 | 29.38 | 1650 | CY | 0 | 0 | 0 | 0
N | M007-31-2010-L | M007 | M007 | 31-2010 | HAND EXCAVATION SUPPORT | N | L |  | NR | P | 0 | 1978.47 | 1978.47 | 1978.47 | 1978.47 | 100 | 0 | 0 | 0 | 0 | Y | 1978.47 | Y | -1978.47 | 0 | 0 | 0 | 0 | 0 | 1978.47 | Y | -1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1978.47 | 0 | 0 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | -1978.47 | 0 | 0 | 1978.47 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 18 | 0 | 18 | HR | 800 | 5.87 | 0 | 5.87 | CY | 0 | 0 | 0 | 0
N | M007-31-2100-L | M007 | M007 | 31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | N | L |  | NR | P | 13862.87 | 13325.08 | 13325.08 | 13325.08 | 13325.08 | 96.1206 | 0 | 0 | 0 | 537.79 | Y | 13862.87 | Y | 0 | 0 | 0 | 13862.87 | 0 | 0 | 13862.87 | Y | 0 | 0 | 0 | 13862.87 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -13862.87 | 0 | 10039.2 | 13862.87 | 0 | 0 | 0 | 0 | 0 | 0 | -13862.87 | 0 | 0 | 13862.87 | 13862.87 | 0 | 0 | 0 | 131.19 | 0 | 105.47 | 105.47 | 131.19 | 112.5 | -7.03 | 105.47 | HR | 410 | 195 | 215 | 410 | CY | 0 | 0 | 0 | 537.79
N | M007-31-2200-L | M007 | M007 | 31-2200 | BACKFILL UTILITIES | N | L |  | NR | P | 383288.4 | 205276.94 | 205276.94 | 205276.94 | 205276.94 | 53.5568 | 0 | 0 | 0 | 178011.46 | Y | 383288.4 | Y | 0 | 0 | 0 | 383288.4 | 0 | 0 | 383288.4 | Y | 0 | 0 | 0 | 383288.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -383288.4 | 18791.8 | 11539.4 | 383288.4 | 0 | 0 | 0 | 0 | 0 | 0 | -383288.4 | 0 | 0 | 383288.4 | 383288.4 | 0 | 0 | 0 | 3696 | 0 | 3484.4 | 3484.4 | 3696 | 1768 | 1716.4 | 3484.4 | HR | 13200 | 6545.73 | 6654.27 | 13200 | CY | 0 | 0 | 0 | 178011.46
N | M007-31-2300-L | M007 | M007 | 31-2300 | EXCAVATION FOR PAVEMENTS | N | L |  | NR | P | 10328.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10328.22 | N | 10328.22 | N | 0 | 0 | 0 | 10328.22 | 0 | 0 | 10328.22 | N | 0 | 0 | 0 | 10328.22 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10328.22 | 0 | 0 | 10328.22 | 0 | 0 | 0 | 0 | 0 | 0 | -10328.22 | 0 | 0 | 10328.22 | 10328.22 | 0 | 0 | 0 | 94.4 | 0 | 94.4 | 94.4 | 94.4 | 0 | 94.4 | 94.4 | HR | 590 | 0 | 590 | 590 | CY | 0 | 0 | 0 | 10328.22
N | M007-31-2400-L | M007 | M007 | 31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | N | L |  | NR | P | 7141.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7141.61 | N | 7141.61 | N | 0 | 0 | 0 | 7141.61 | 0 | 0 | 7141.61 | N | 0 | 0 | 0 | 7141.61 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7141.61 | 0 | 0 | 7141.61 | 0 | 0 | 0 | 0 | 0 | 0 | -7141.61 | 0 | 0 | 7141.61 | 7141.61 | 0 | 0 | 0 | 74.66 | 0 | 74.66 | 74.66 | 74.66 | 0 | 74.66 | 74.66 | HR | 280 | 0 | 280 | 280 | CY | 0 | 0 | 0 | 7141.61
N | M007-31-2500-L | M007 | M007 | 31-2500 | DENSE GRADED STONE BASE | N | L |  | NR | P | 65042.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65042.88 | N | 65042.88 | N | 0 | 0 | 0 | 65042.88 | 0 | 0 | 65042.88 | N | 0 | 0 | 0 | 65042.88 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -65042.88 | 0 | 0 | 65042.88 | 0 | 0 | 0 | 0 | 0 | 0 | -65042.88 | 0 | 0 | 65042.88 | 65042.88 | 0 | 0 | 0 | 627.2 | 0 | 627.2 | 627.2 | 627.2 | 0 | 627.2 | 627.2 | HR | 1680 | 0 | 1680 | 1680 | CY | 0 | 0 | 0 | 65042.88
N | M007-31-2600-L | M007 | M007 | 31-2600 | SITE FURNISHINGS | N | L |  | NR | P | 38534.4 | 1006.96 | 1006.96 | 1006.96 | 1006.96 | 2.5641 | 0 | 0 | 0 | 38264.48 | N | 39271.44 | N | -737.04 | 0 | 0 | 38534.4 | 0 | 0 | 39271.44 | N | -737.04 | 0 | 0 | 38534.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -39271.44 | 1006.96 | 0 | 38534.4 | -737.04 | 0 | 0 | 0 | 0 | 0 | -39271.44 | 0 | 0 | 39271.44 | 39271.44 | 0 | 0 | 0 | 384 | 0 | 351 | 351 | 384 | 9 | 342 | 351 | HR | 117 | 3 | 114 | 117 | EA | 0 | 0 | 0 | 38264.48
N | M007-31-2700-L | M007 | M007 | 31-2700 | BOLLARDS | N | L |  | NR | P | 4816.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4816.8 | N | 4816.8 | N | 0 | 0 | 0 | 4816.8 | 0 | 0 | 4816.8 | N | 0 | 0 | 0 | 4816.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4816.8 | 0 | 0 | 4816.8 | 0 | 0 | 0 | 0 | 0 | 0 | -4816.8 | 0 | 0 | 4816.8 | 4816.8 | 0 | 0 | 0 | 48 | 0 | 48 | 48 | 48 | 0 | 48 | 48 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 4816.8
N | M007-31-2800-L | M007 | M007 | 31-2800 | DRINKING FOUNTAIN | N | L |  | NR | P | 14450.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | Y | 30000 | Y | -15549.6 | 0 | 0 | 14450.4 | 0 | 0 | 30000 | Y | -15549.6 | 0 | 0 | 14450.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 144 | 0 | 298.95 | 298.95 | 144 | 0 | 298.95 | 298.95 | HR | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 30000
N | M007-31-2900-L | M007 | M007 | 31-2900 | LANDSCAPE BOULDERS | N | L |  | NR | P | 9888.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9888.96 | N | 9888.96 | N | 0 | 0 | 0 | 9888.96 | 0 | 0 | 9888.96 | N | 0 | 0 | 0 | 9888.96 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9888.96 | 0 | 0 | 9888.96 | 0 | 0 | 0 | 0 | 0 | 0 | -9888.96 | 0 | 0 | 9888.96 | 9888.96 | 0 | 0 | 0 | 96 | 0 | 96 | 96 | 96 | 0 | 96 | 96 | HR | 148 | 0 | 148 | 148 | EA | 0 | 0 | 0 | 9888.96
N | M007-31-3000-L | M007 | M007 | 31-3000 | BASKETBALL BACKSTOP | N | L |  | NR | P | 3296.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3296.32 | N | 3296.32 | N | 0 | 0 | 0 | 3296.32 | 0 | 0 | 3296.32 | N | 0 | 0 | 0 | 3296.32 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3296.32 | 0 | 0 | 3296.32 | 0 | 0 | 0 | 0 | 0 | 0 | -3296.32 | 0 | 0 | 3296.32 | 3296.32 | 0 | 0 | 0 | 32 | 0 | 32 | 32 | 32 | 0 | 32 | 32 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 3296.32
N | M007-31-4000-S | M007 | M007 | 31-4000 | VAC TRUCKING SUB | N | S |  | NR | A | 0 | 114830 | 114830 | 96213.1 | 114830 | 74.0101 | 0 | 0 | 0 | 15170 | Y | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 130000 | Y | -130000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -130000 | 0 | 5568.6 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 | -130000 | 0 | 0 | 130000 | 130000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 335.89 | -335.89 | 0 | NA | 30 | 0 | 30 | 30 | DY | 120275 | 18616.9 | 101658.1 | 15170
N | M007-31-5000-L | M007 | M007 | 31-5000 | FURNISH GRAVEL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 637.2 | 0 | 637.2 | 637.2 | CY | 0 | 0 | 0 | 0
N | M007-31-5000-M | M007 | M007 | 31-5000 | FURNISH GRAVEL | N | M |  | NR | P | 12744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12744 | N | 12744 | N | 0 | 0 | 0 | 12744 | 0 | 0 | 12744 | N | 0 | 0 | 0 | 12744 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12744 | 0 | 0 | 12744 | 0 | 0 | 0 | 0 | 0 | 0 | -12744 | 0 | 0 | 12744 | 12744 | 0 | 0 | 0 | 637.2 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 637.2 | 0 | 637.2 | 637.2 | CY | 0 | 0 | 0 | 12744
N | M007-31-5100-L | M007 | M007 | 31-5100 | FURNISH CLEAN FILL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8681 | 0 | 8681 | 8681 | CY | 0 | 0 | 0 | 0
N | M007-31-5100-M | M007 | M007 | 31-5100 | FURNISH CLEAN FILL | N | M |  | NR | P | 173620 | 5039.95 | 5039.95 | 5039.95 | 5039.95 | 2.821 | 0 | 0 | 0 | 173620 | N | 178659.95 | N | -5039.95 | 0 | 0 | 173620 | 0 | 0 | 178659.95 | N | -5039.95 | 0 | 0 | 173620 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -178659.95 | 5039.95 | 0 | 173620 | -5039.95 | 0 | 0 | 5039.95 | 0 | 0 | -178659.95 | 0 | 0 | 178659.95 | 178659.95 | 0 | 0 | 0 | 8681 | 0 | 0 |  | 0 | 144.66 | 0 | 144.66 | CY | 8681 | 0 | 8681 | 8681 | CY | 5039.95 | 0 | 5039.95 | 173620
N | M007-31-6000-C | M007 | M007 | 31-6000 | DISPOSAL & TRUCKING SUB | N | C |  | NR | U | 0 | 1625344.1 | 1625344.1 | 1353651.33 | 1625344.1 | 89.1717 | 0 | 0 | 0 | -107316.84 | Y | 1518027.26 | Y | -1518027.26 | 0 | 0 | 0 | 0 | 0 | 1518027.26 | Y | -1518027.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1518027.26 | 0 | 73385.48 | 1518027.26 | 0 | 0 | 0 | 0 | -11537.73 | 0 | -1518027.26 | 0 | 0 | 1518027.26 | 1518027.26 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 22283.97 | -3116.41 | 19167.56 | NA | 1 | 0 | 1 | 1 | LS | 1625344.1 | 271692.77 | 1353651.33 | -107316.84
N | M007-31-6000-L | M007 | M007 | 31-6000 | DISPOSAL & TRUCKING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6000-S | M007 | M007 | 31-6000 | DISPOSAL & TRUCKING SUB | N | S |  | NR | A | 1072337.11 | 107361.92 | 107361.92 | 20996 | 107361.92 | 19.0183 | 0 | 0 | 0 | 3037.08 | Y | 110399 | Y | 961938.11 | 0 | 0 | 1072337.11 | 0 | 0 | 110399 | Y | 961938.11 | 0 | 0 | 1072337.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -110399 | 0 | 0 | 110399 | 0 | 0 | 0 | 0 | 0 | 0 | -110399 | 0 | 0 | 110399 | 110399 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 140 | -139 | 1 | LS | 1 | 0 | 1 | 1 | LS | 107361.92 | 86365.92 | 20996 | 3037.08
N | M007-31-6100-L | M007 | M007 | 31-6100 | DEWATERING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6100-S | M007 | M007 | 31-6100 | DEWATERING SUB | N | S |  | NR | A | 2746110 | 38820 | 38820 | 38820 | 38820 | 100 | 0 | 0 | 0 | 0 | Y | 38820 | Y | 2707290 | 0 | 0 | 2746110 | 0 | 0 | 38820 | Y | 2707290 | 0 | 0 | 2746110 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -38820 | 0 | 0 | 38820 | 0 | 0 | 0 | 0 | 0 | 0 | -38820 | 0 | 0 | 38820 | 38820 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 2 | -1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 38820 | 0 | 38820 | 0
N | M007-31-6110-L | M007 | M007 | 31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 16 | 16 | UM | 0 | 0 | 0 | 0
N | M007-31-6110-M | M007 | M007 | 31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | N | M |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 16 | 16 | UM | 0 | 0 | 0 | 0
N | M007-31-6120-L | M007 | M007 | 31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 48 | 48 | HR | 0 | 0 | 16 | 16 | DY | 0 | 0 | 0 | 0
N | M007-31-6130-L | M007 | M007 | 31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-31-6140-L | M007 | M007 | 31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439.02 | 439.02 | 0 | 0 | 439.02 | 439.02 | HR | 0 | 0 | 180 | 180 | DY | 0 | 0 | 0 | 0
N | M007-31-6150-E | M007 | M007 | 31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | N | E |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 60 | 60 | DY | 0 | 0 | 0 | 0
N | M007-31-6150-L | M007 | M007 | 31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 60 | 60 | DY | 0 | 0 | 0 | 0
N | M007-31-6160-C | M007 | M007 | 31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 400 | 0 | 400 | 400 | CY | 0 | 0 | 0 | 0
N | M007-31-6160-L | M007 | M007 | 31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 400 | 0 | 400 | 400 | CY | 0 | 0 | 0 | 0
N | M007-31-6170-L | M007 | M007 | 31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 30 | 0 | 30 | 30 | DY | 0 | 0 | 0 | 0
N | M007-31-6170-S | M007 | M007 | 31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 30 | 0 | 30 | 30 | DY | 0 | 0 | 0 | 0
N | M007-31-6180-C | M007 | M007 | 31-6180 | WATER TREATMENT | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6180-L | M007 | M007 | 31-6180 | WATER TREATMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6180-S | M007 | M007 | 31-6180 | WATER TREATMENT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6190-C | M007 | M007 | 31-6190 | ELECTRIC SERVICE | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6190-L | M007 | M007 | 31-6190 | ELECTRIC SERVICE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6190-S | M007 | M007 | 31-6190 | ELECTRIC SERVICE | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6200-L | M007 | M007 | 31-6200 | DUMPSTERS FOR DEWATERING | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-31-6210-C | M007 | M007 | 31-6210 | DEWATERING DISCHARGE | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6210-L | M007 | M007 | 31-6210 | DEWATERING DISCHARGE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-6210-S | M007 | M007 | 31-6210 | DEWATERING DISCHARGE | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-7000-C | M007 | M007 | 31-7000 | LUMBER - TREE PROTECTION | N | C |  | NR | A | 4355.2 | 21930.72 | 21930.72 | 21930.72 | 21930.72 | 99.173 | 0 | 0 | 0 | 182.89 | Y | 22113.61 | Y | -17758.41 | 0 | 0 | 4355.2 | 0 | 0 | 22113.61 | Y | -17758.41 | 0 | 0 | 4355.2 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -22113.61 | 0 | 0 | 22113.61 | 0 | 0 | 0 | 0 | 0 | 0 | -22113.61 | 0 | 0 | 22113.61 | 22113.61 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0 | 2949 | -240 | 2709 | MB | 4 | 9.34 | 0 | 9.34 | MB | 21680.23 | -250.49 | 21930.72 | 182.89
N | M007-31-7000-L | M007 | M007 | 31-7000 | LUMBER - TREE PROTECTION | N | L |  | NR | P | 0 | 994.29 | 994.29 | 994.29 | 994.29 | 100 | 0 | 0 | 0 | 0 | N | 994.29 | N | -994.29 | 0 | 0 | 0 | 0 | 0 | 994.29 | N | -994.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -994.29 | 0 | 0 | 994.29 | 0 | 0 | 0 | 0 | 0 | 0 | -994.29 | 0 | 0 | 994.29 | 994.29 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 4 | 0 | 4 | HR | 4 | 9.34 | 0 | 9.34 | MB | 0 | 0 | 0 | 0
N | M007-31-7100-C | M007 | M007 | 31-7100 | DEWATERING PUMPS | N | C |  | NR | A | 130656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 130656 | 0 | 0 | 130656 | 0 | 0 | 0 | Y | 130656 | 0 | 0 | 130656 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0 | 0 | 10 | 10 | MO | 10 | 0 | 10 | 10 | MO | 0 | 0 | 0 | 0
N | M007-31-7100-L | M007 | M007 | 31-7100 | DEWATERING PUMPS | N | L |  | NR | P | 0 | 14.07 | 14.07 | 14.07 | 14.07 | 100 | 0 | 0 | 0 | 0 | N | 14.07 | N | -14.07 | 0 | 0 | 0 | 0 | 0 | 14.07 | N | -14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14.07 | 0 | 0 | 14.07 | 0 | 0 | 0 | 0 | 0 | 0 | -14.07 | 0 | 0 | 14.07 | 14.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 10 | 0 | 10 | 10 | MO | 0 | 0 | 0 | 0
N | M007-31-7200-C | M007 | M007 | 31-7200 | SOLDIER PILE & LAGGING BLDGS | N | C |  | NR | A | 63524.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 63524.95 | 0 | 0 | 63524.95 | 0 | 0 | 0 | Y | 63524.95 | 0 | 0 | 63524.95 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-7200-L | M007 | M007 | 31-7200 | SOLDIER PILE & LAGGING BLDGS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-7300-C | M007 | M007 | 31-7300 | TRENCH BOX - UTILITY TRENCHES | N | C |  | NR | A | 610816.8 | 199402.56 | 199402.56 | 140269.87 | 199402.56 | 79.5804 | 0 | 0 | 0 | -23140.73 | Y | 176261.83 | Y | 434554.97 | 0 | 0 | 610816.8 | 0 | 0 | 176261.83 | Y | 434554.97 | 0 | 0 | 610816.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -176261.83 | 2231.93 | 10876.59 | 176261.83 | 0 | 0 | 0 | 0 | 0 | 0 | -176261.83 | 0 | 0 | 176261.83 | 176261.83 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 1257 | 373 | 1630 | LS | 1 | 0.1 | 0.9 | 1 | LS | 199402.56 | 59132.69 | 140269.87 | -23140.73
N | M007-31-7300-L | M007 | M007 | 31-7300 | TRENCH BOX - UTILITY TRENCHES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.1 | 0.9 | 1 | LS | 0 | 0 | 0 | 0
N | M007-31-7400-C | M007 | M007 | 31-7400 | PLATES - UTILITY TRENCHES | N | C |  | NR | A | 81660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 81660 | 0 | 0 | 81660 | 0 | 0 | 0 | Y | 81660 | 0 | 0 | 81660 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 3000 | 0 | 3000 | 3000 | SF | 0 | 0 | 0 | 0
N | M007-31-7400-L | M007 | M007 | 31-7400 | PLATES - UTILITY TRENCHES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3000 | 0 | 3000 | 3000 | SF | 0 | 0 | 0 | 0
N | M007-31-7500-C | M007 | M007 | 31-7500 | LUMBER - UTILITY TRENCHES | N | C |  | NR | A | 11636.55 | 21915.27 | 21915.27 | 16396.43 | 21915.27 | 74.8174 | 0 | 0 | 0 | 0 | N | 21915.27 | N | -10278.72 | 0 | 0 | 11636.55 | 0 | 0 | 21915.27 | N | -10278.72 | 0 | 0 | 11636.55 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21915.27 | 0 | 0 | 21915.27 | 0 | 0 | 0 | 0 | 0 | 0 | -21915.27 | 0 | 0 | 21915.27 | 21915.27 | 0 | 0 | 0 | 11.25 | 0 | 0 |  | 0 | 599 | 341 | 940 | MB | 11.25 | 0 | 11.25 | 11.25 | MB | 21915.27 | 5518.84 | 16396.43 | 0
N | M007-31-7500-L | M007 | M007 | 31-7500 | LUMBER - UTILITY TRENCHES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 11.25 | 0 | 11.25 | 11.25 | MB | 0 | 0 | 0 | 0
N | M007-32-5000-L | M007 | M007 | 32-5000 | FURNISH BOLLARDS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 0
N | M007-32-5000-M | M007 | M007 | 32-5000 | FURNISH BOLLARDS | N | M |  | NR | A | 7600 | 10010 | 10010 | 10010 | 10010 | 100 | 0 | 0 | 0 | 0 | Y | 10010 | Y | -2410 | 0 | 0 | 7600 | 0 | 0 | 10010 | Y | -2410 | 0 | 0 | 7600 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10010 | 0 | 0 | 10010 | 0 | 0 | 0 | 0 | 0 | 0 | -10010 | 0 | 0 | 10010 | 10010 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 11 | 0 | 11 | EA | 8 | 0 | 8 | 8 | EA | 10010 | 0 | 10010 | 0
N | M007-32-5100-L | M007 | M007 | 32-5100 | FURNISH SUBBASE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2268 | 0 | 2268 | 2268 | CY | 0 | 0 | 0 | 0
N | M007-32-5100-M | M007 | M007 | 32-5100 | FURNISH SUBBASE | N | M |  | NR | A | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56700 | N | 56700 | N | 0 | 0 | 0 | 56700 | 0 | 0 | 56700 | N | 0 | 0 | 0 | 56700 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56700 | 0 | 0 | 56700 | 0 | 0 | 0 | 0 | 0 | 0 | -56700 | 0 | 0 | 56700 | 56700 | 0 | 0 | 0 | 2268 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 2268 | 0 | 2268 | 2268 | CY | 0 | 0 | 0 | 56700
N | M007-32-5200-L | M007 | M007 | 32-5200 | FURNISH BENCHES & TABLES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 106 | 0 | 106 | 106 | EA | 0 | 0 | 0 | 0
N | M007-32-5200-M | M007 | M007 | 32-5200 | FURNISH BENCHES & TABLES | N | M |  | NR | A | 103800 | 380865 | 380865 | 190392.5 | 380865 | 48.4459 | 0 | 0 | 0 | 12135 | Y | 393000 | Y | -289200 | 0 | 0 | 103800 | 0 | 0 | 393000 | Y | -289200 | 0 | 0 | 103800 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -393000 | 0 | 0 | 393000 | 0 | 0 | 0 | 0 | 0 | 0 | -393000 | 0 | 0 | 393000 | 393000 | 0 | 0 | 0 | 106 | 0 | 0 |  | 0 | 0.5 | 105.5 | 106 | EA | 106 | 0 | 106 | 106 | EA | 380865 | 190472.5 | 190392.5 | 12135
N | M007-32-5300-L | M007 | M007 | 32-5300 | FURNISH PING PONG TABLE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3 | 0 | 3 | 3 | EA | 0 | 0 | 0 | 0
N | M007-32-5300-M | M007 | M007 | 32-5300 | FURNISH PING PONG TABLE | N | M |  | NR | A | 32700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32700 | N | 32700 | N | 0 | 0 | 0 | 32700 | 0 | 0 | 32700 | N | 0 | 0 | 0 | 32700 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32700 | 0 | 0 | 32700 | 0 | 0 | 0 | 0 | 0 | 0 | -32700 | 0 | 0 | 32700 | 32700 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 3 | 0 | 3 | 3 | EA | 0 | 0 | 0 | 32700
N | M007-32-5400-L | M007 | M007 | 32-5400 | FURNISH BIKE RACK | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 0
N | M007-32-5400-M | M007 | M007 | 32-5400 | FURNISH BIKE RACK | N | M |  | NR | A | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | N | 2400 | N | 0 | 0 | 0 | 2400 | 0 | 0 | 2400 | N | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2400 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | -2400 | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 2400
N | M007-32-5500-L | M007 | M007 | 32-5500 | FURNISH DRINKING FOUNTAIN | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 0
N | M007-32-5500-M | M007 | M007 | 32-5500 | FURNISH DRINKING FOUNTAIN | N | M |  | NR | A | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | N | 9000 | N | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | N | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | -9000 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 9000
N | M007-32-5600-L | M007 | M007 | 32-5600 | FURNISH SHOWER EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 0
N | M007-32-5600-M | M007 | M007 | 32-5600 | FURNISH SHOWER EQUIPMENT | N | M |  | NR | A | 26188.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26188.02 | N | 26188.02 | N | 0 | 0 | 0 | 26188.02 | 0 | 0 | 26188.02 | N | 0 | 0 | 0 | 26188.02 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -26188.02 | 0 | 0 | 26188.02 | 0 | 0 | 0 | 0 | 0 | 0 | -26188.02 | 0 | 0 | 26188.02 | 26188.02 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 26188.02
N | M007-32-5700-L | M007 | M007 | 32-5700 | FURNISH LANDSCAPE BOULDERS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 148 | 0 | 148 | 148 | EA | 0 | 0 | 0 | 0
N | M007-32-5700-M | M007 | M007 | 32-5700 | FURNISH LANDSCAPE BOULDERS | N | M |  | NR | A | 239316 | 221092.5 | 221092.5 | 191092.5 | 221092.5 | 79.8494 | 0 | 0 | 0 | 18223.5 | N | 239316 | N | 0 | 0 | 0 | 239316 | 0 | 0 | 239316 | N | 0 | 0 | 0 | 239316 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -239316 | 0 | 0 | 239316 | 0 | 0 | 0 | 0 | 0 | 0 | -239316 | 0 | 0 | 239316 | 239316 | 0 | 0 | 0 | 148 | 0 | 0 |  | 0 | 149 | 33.93 | 182.93 | EA | 148 | 0 | 148 | 148 | EA | 221092.5 | 30000 | 191092.5 | 18223.5
N | M007-32-5800-L | M007 | M007 | 32-5800 | FURNISH BASKETBALL BOARD AND POST | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
N | M007-32-5800-M | M007 | M007 | 32-5800 | FURNISH BASKETBALL BOARD AND POST | N | M |  | NR | A | 5340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5340 | N | 5340 | N | 0 | 0 | 0 | 5340 | 0 | 0 | 5340 | N | 0 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5340 | 0 | 0 | 5340 | 0 | 0 | 0 | 0 | 0 | 0 | -5340 | 0 | 0 | 5340 | 5340 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 5340
N | M007-32-6000-C | M007 | M007 | 32-6000 | SAWCUTTING | N | C |  | NR | U | 0 | 17664.75 | 17664.75 | 17664.75 | 17664.75 | 100 | 0 | 0 | 0 | 0 | N | 17664.75 | N | -17664.75 | 0 | 0 | 0 | 0 | 0 | 17664.75 | N | -17664.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -17664.75 | 0 | 0 | 17664.75 | 0 | 0 | 0 | 0 | 0 | 0 | -17664.75 | 0 | 0 | 17664.75 | 17664.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 43 | 0 | 43 | NA | 1 | 122 | 0 | 122 | EA | 14173.86 | 0 | 14173.86 | 0
N | M007-32-6000-L | M007 | M007 | 32-6000 | SAWCUTTING | N | L |  | NR | P | 0 | 113946.43 | 113946.43 | 113946.43 | 113946.43 | 94.9554 | 0 | 0 | 0 | 6053.57 | Y | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120000 | 0 | 10291.75 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | -120000 | 0 | 0 | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 1011 | 1011 | 0 | 1110.5 | -99.5 | 1011 | HR | 1 | 122 | 0 | 122 | EA | 0 | 0 | 0 | 6053.57
N | M007-32-6000-S | M007 | M007 | 32-6000 | SAWCUTTING | N | S |  | NR | A | 64500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 64500 | 0 | 0 | 64500 | 0 | 0 | 0 | Y | 64500 | 0 | 0 | 64500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 122 | 0 | 122 | EA | 0 | 0 | 0 | 0
N | M007-32-6100-L | M007 | M007 | 32-6100 | ASPHALT SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-32-6100-S | M007 | M007 | 32-6100 | ASPHALT SUB | N | S |  | NR | A | 413300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210269.79 | Y | 210269.79 | Y | 203030.21 | 0 | 0 | 413300 | 0 | 0 | 210269.79 | Y | 203030.21 | 0 | 0 | 413300 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -210269.79 | 0 | 0 | 210269.79 | 0 | 0 | 0 | 0 | 0 | 0 | -210269.79 | 0 | 0 | 210269.79 | 210269.79 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 210269.79
N | M007-32-6200-L | M007 | M007 | 32-6200 | FLATWORK SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-32-6200-S | M007 | M007 | 32-6200 | FLATWORK SUB | N | S |  | NR | A | 5330750 | 2940000 | 2940000 | 0 | 2940000 | 0 | 0 | 0 | 0 | 0 | Y | 2940000 | Y | 2390750 | 0 | 0 | 5330750 | 0 | 0 | 2940000 | Y | 2390750 | 0 | 0 | 5330750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2940000 | 0 | 0 | 2940000 | 0 | 0 | 0 | 0 | 0 | 0 | -2940000 | 0 | 0 | 2940000 | 2940000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 31.79 | 31.79 | LS | 1 | 0 | 1 | 1 | LS | 2940000 | 2940000 | 0 | 0
N | M007-32-6210-L | M007 | M007 | 32-6210 | FLATWORK SUB SUPPORT | N | L |  | NR | P | 0 | 746.88 | 746.88 | 746.88 | 746.88 | 100 | 0 | 0 | 0 | 0 | N | 746.88 | N | -746.88 | 0 | 0 | 0 | 0 | 0 | 746.88 | N | -746.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -746.88 | 0 | 746.88 | 746.88 | 0 | 0 | 0 | 0 | 0 | 0 | -746.88 | 0 | 0 | 746.88 | 746.88 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 6 | 0 | 6 | HR | 0 | 6 | -6 | 0 | LS | 0 | 0 | 0 | 0
N | M007-32-6210-S | M007 | M007 | 32-6210 | FLATWORK SUB SUPPORT | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184287 | Y | 184287 | Y | -184287 | 0 | 0 | 0 | 0 | 0 | 184287 | Y | -184287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -184287 | 0 | 0 | 184287 | 0 | 0 | 0 | 0 | 0 | 0 | -184287 | 0 | 0 | 184287 | 184287 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 6 | -6 | 0 | LS | 0 | 0 | 0 | 184287
N | M007-32-6220-L | M007 | M007 | 32-6220 | JMC EQUIP BACKCHARGE | N | L |  | NR | P | 0 | 6698.28 | 6698.28 | 6698.28 | 6698.28 | 66.9828 | 0 | 0 | 0 | 3301.72 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 1746.35 | 2322.21 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 76.05 | 76.05 | 0 | 53.5 | 22.55 | 76.05 | HR | 0 | 47.4 | 0 | 47.4 | NA | 0 | 0 | 0 | 3301.72
N | M007-32-6300-L | M007 | M007 | 32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 10500 | 0 | 10500 | 10500 | LF | 0 | 0 | 0 | 0
N | M007-32-6300-S | M007 | M007 | 32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | N | S |  | NR | A | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10500 | 0 | 0 | 10500 | 0 | 0 | 0 | Y | 10500 | 0 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 0 |  | 0 | 0 | 10500 | 10500 | LF | 10500 | 0 | 10500 | 10500 | LF | 0 | 0 | 0 | 0
N | M007-32-6400-L | M007 | M007 | 32-6400 | COURT SURFACES SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8500 | 0 | 8500 | 8500 | SF | 0 | 0 | 0 | 0
N | M007-32-6400-S | M007 | M007 | 32-6400 | COURT SURFACES SUB | N | S |  | NR | A | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425000 | N | 425000 | N | 0 | 0 | 0 | 425000 | 0 | 0 | 425000 | N | 0 | 0 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -425000 | 0 | 0 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | -425000 | 0 | 0 | 425000 | 425000 | 0 | 0 | 0 | 8500 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 8500 | 0 | 8500 | 8500 | SF | 0 | 0 | 0 | 425000
N | M007-32-6500-L | M007 | M007 | 32-6500 | FENCING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-32-6500-S | M007 | M007 | 32-6500 | FENCING SUB | N | S |  | NR | A | 752598.1 | 1036387.5 | 1036387.5 | 757678.8 | 1036387.5 | 57.4586 | 0 | 0 | 0 | 282265 | Y | 1318652.5 | Y | -566054.4 | 0 | 0 | 752598.1 | 0 | 0 | 1318652.5 | Y | -566054.4 | 0 | 0 | 752598.1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1318652.5 | 0 | 0 | 1318652.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1318652.5 | 0 | 0 | 1318652.5 | 1318652.5 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 5877.12 | 3226.58 | 9103.7 | LS | 1 | 0 | 1 | 1 | LS | 1036387.5 | 278708.7 | 757678.8 | 282265
N | M007-32-6510-C | M007 | M007 | 32-6510 | FENCE MESH INSTALL | N | C |  | NR | U | 0 | 5852.38 | 5852.38 | 4801.73 | 5852.38 | 43.2526 | 0 | 0 | 0 | 5249.23 | Y | 11101.61 | Y | -11101.61 | 0 | 0 | 0 | 0 | 0 | 11101.61 | Y | -11101.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -11101.61 | 0 | 0 | 11101.61 | 0 | 0 | 0 | 0 | 0 | 0 | -11101.61 | 0 | 0 | 11101.61 | 11101.61 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2274 | -1306.61 | 967.39 | NA | 12750 | 14344.82 | 655.18 | 15000 | LF | 5852.38 | 1050.65 | 4801.73 | 5249.23
N | M007-32-6510-L | M007 | M007 | 32-6510 | FENCE MESH INSTALL | N | L |  | NR | P | 0 | 84533.52 | 84533.52 | 84533.52 | 84533.52 | 95.6321 | 0 | 0 | 0 | 3860.98 | Y | 88394.5 | Y | -88394.5 | 0 | 0 | 0 | 0 | 0 | 88394.5 | Y | -88394.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -88394.5 | 0 | 0 | 88394.5 | 0 | 0 | 0 | 0 | 0 | 0 | -88394.5 | 0 | 0 | 88394.5 | 88394.5 | 0 | 0 | 0 | 0 | 0 | 871.57 | 871.57 | 0 | 833.5 | 38.07 | 871.57 | HR | 12750 | 14344.82 | 655.18 | 15000 | LF | 0 | 0 | 0 | 3860.98
N | M007-32-6510-S | M007 | M007 | 32-6510 | FENCE MESH INSTALL | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 12750 | 14344.82 | 655.18 | 15000 | LF | 0 | 0 | 0 | 0
N | M007-32-6520-C | M007 | M007 | 32-6520 | FENCE INSTALL SELF PERFORM | N | C |  | NR | U | 0 | 64667.59 | 64667.59 | 44656.75 | 64667.59 | 111.6419 | 0 | 0 | 0 | -24667.59 | Y | 40000 | Y | -40000 | 0 | 0 | 0 | 0 | 0 | 40000 | Y | -40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -40000 | 9594 | 0 | 40000 | 0 | 0 | 0 | 10445.48 | 10445.48 | 0 | -40000 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2094 | -702.39 | 1391.61 | NA | 400 | 5705.65 | 894.35 | 6600 | LF | 64667.59 | 20010.84 | 44656.75 | -24667.59
N | M007-32-6520-L | M007 | M007 | 32-6520 | FENCE INSTALL SELF PERFORM | N | L |  | NR | P | 0 | 193193.23 | 193193.23 | 193193.23 | 193193.23 | 101.4322 | 0 | 0 | 0 | -2727.93 | Y | 190465.3 | Y | -190465.3 | 0 | 0 | 0 | 0 | 0 | 190465.3 | Y | -190465.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -190465.3 | 2581.62 | 16859.53 | 190465.3 | 0 | 0 | 0 | 0 | 0 | 0 | -190465.3 | 0 | 0 | 190465.3 | 190465.3 | 0 | 0 | 0 | 0 | 0 | 1834.93 | 1834.93 | 0 | 1857.5 | -22.57 | 1834.93 | HR | 400 | 5705.65 | 894.35 | 6600 | LF | 0 | 0 | 0 | -2727.93
N | M007-32-6600-L | M007 | M007 | 32-6600 | LANDSCAPING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-32-6600-S | M007 | M007 | 32-6600 | LANDSCAPING SUB | N | S |  | NR | A | 768340 | 638633.25 | 638633.25 | 31172.29 | 638633.25 | 4.9073 | 0 | 0 | 0 | -3407.71 | Y | 635225.54 | Y | 133114.46 | 0 | 0 | 768340 | 0 | 0 | 635225.54 | Y | 133114.46 | 0 | 0 | 768340 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -635225.54 | 0 | 0 | 635225.54 | 0 | 0 | 0 | 0 | 0 | 0 | -635225.54 | 0 | 0 | 635225.54 | 635225.54 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 6692.2 | 35863.87 | 42556.07 | LS | 1 | 0 | 1 | 1 | LS | 638633.25 | 607460.96 | 31172.29 | -3407.71
N | M007-32-6610-L | M007 | M007 | 32-6610 | CLEAR AND GRUB | N | L |  | NR | P | 0 | 74762.26 | 74762.26 | 74762.26 | 74762.26 | 86.0612 | 0 | 0 | 0 | 12108.76 | Y | 86871.02 | Y | -86871.02 | 0 | 0 | 0 | 0 | 0 | 86871.02 | Y | -86871.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -86871.02 | 7360.06 | 0 | 86871.02 | 0 | 0 | 0 | 0 | 0 | 0 | -86871.02 | 0 | 0 | 86871.02 | 86871.02 | 0 | 0 | 0 | 0 | 0 | 793 | 793 | 0 | 652 | 141 | 793 | HR | 137053 | 111191.99 | 25861.01 | 137053 | SF | 0 | 0 | 0 | 12108.76
N | M007-32-6610-S | M007 | M007 | 32-6610 | CLEAR AND GRUB | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 137053 | 111191.99 | 25861.01 | 137053 | SF | 0 | 0 | 0 | 0
N | M007-32-6620-L | M007 | M007 | 32-6620 | SELF PERFORM TREE REMOVAL | N | L |  | NR | P | 0 | 23436.18 | 23436.18 | 23436.18 | 23436.18 | 93.7447 | 0 | 0 | 0 | 1563.82 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 228.5 | 228.5 | 0 | 228.5 | 0 | 228.5 | HR | 23 | 57 | 0 | 57 | EA | 0 | 0 | 0 | 1563.82
N | M007-32-6630-L | M007 | M007 | 32-6630 | LANDSCAPING SUB SUPPORT | N | L |  | NR | P | 0 | 21223.48 | 21223.48 | 21223.48 | 21223.48 | 42.447 | 0 | 0 | 0 | 28776.52 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 489.56 | 489.56 | 0 | 215.5 | 274.06 | 489.56 | HR | 500 | 215.5 | 274.06 | 489.56 | HR | 0 | 0 | 0 | 28776.52
N | M007-32-6700-L | M007 | M007 | 32-6700 | Arbor Consultant | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0
N | M007-32-6700-S | M007 | M007 | 32-6700 | Arbor Consultant | N | S |  | NR | A | 0 | 1134.2 | 1134.2 | 960 | 1134.2 | 84.6412 | 0 | 0 | 0 | 0 | Y | 1134.2 | Y | -1134.2 | 0 | 0 | 0 | 0 | 0 | 1134.2 | Y | -1134.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1134.2 | 0 | 0 | 1134.2 | 0 | 0 | 0 | 0 | 0 | 0 | -1134.2 | 0 | 0 | 1134.2 | 1134.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 12 | -12 | 0 | NA | 0 | 0 | 0 | 0 | HR | 1134.2 | 174.2 | 960 | 0
N | M007-33-1000-L | M007 | M007 | 33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | N | L |  | NR | P | 51626.6 | 35633.47 | 35633.47 | 35633.47 | 35633.47 | 69.0215 | 0 | 0 | 0 | 15993.13 | Y | 51626.6 | Y | 0 | 0 | 0 | 51626.6 | 0 | 0 | 51626.6 | Y | 0 | 0 | 0 | 51626.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -51626.6 | 2992.01 | 1889.61 | 51626.6 | 0 | 0 | 0 | 0 | 0 | 0 | -51626.6 | 0 | 0 | 51626.6 | 51626.6 | 0 | 0 | 0 | 480 | 0 | 428.02 | 428.02 | 480 | 309.5 | 118.52 | 428.02 | HR | 5 | 3.23 | 1.77 | 5 | LO | 0 | 0 | 0 | 15993.13
N | M007-33-1100-L | M007 | M007 | 33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | N | L |  | NR | P | 56789.26 | 11965.19 | 11965.19 | 11965.19 | 11965.19 | 21.0695 | 0 | 0 | 0 | 44824.07 | Y | 56789.26 | Y | 0 | 0 | 0 | 56789.26 | 0 | 0 | 56789.26 | Y | 0 | 0 | 0 | 56789.26 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -56789.26 | 3222.2 | 1028.37 | 56789.26 | 0 | 0 | 0 | 0 | 0 | 0 | -56789.26 | 0 | 0 | 56789.26 | 56789.26 | 0 | 0 | 0 | 528 | 0 | 527.97 | 527.97 | 528 | 105 | 422.97 | 527.97 | HR | 3300 | 558.13 | 2741.87 | 3300 | LF | 0 | 0 | 0 | 44824.07
N | M007-33-1200-L | M007 | M007 | 33-1200 | WATER | N | L |  | NR | P | 144140.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 144140.25 | 0 | 0 | 144140.25 | 0 | 0 | 0 | Y | 144140.25 | 0 | 0 | 144140.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1362.82 | 0 | 0 | 0 | 1362.82 | 0 | 0 | 0 | HR | 3042 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1200-S | M007 | M007 | 33-1200 | WATER | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3042 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1300-L | M007 | M007 | 33-1300 | WELDING OF WATER PIPE | N | L |  | NR | P | 344423.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 344423.46 | 0 | 0 | 344423.46 | 0 | 0 | 0 | Y | 344423.46 | 0 | 0 | 344423.46 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3169.36 | 0 | 1735.36 | 1735.36 | 3169.36 | 0 | 1735.36 | 1735.36 | HR | 700 | 0 | 383.28 | 383.28 | LF | 0 | 0 | 0 | 0
N | M007-33-1310-L | M007 | M007 | 33-1310 | WATER PIPE FIT UP | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 36 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-1400-L | M007 | M007 | 33-1400 | INSTALL JOJNT INSULATORS | N | L |  | NR | P | 42383.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 42383.38 | 0 | 0 | 42383.38 | 0 | 0 | 0 | Y | 42383.38 | 0 | 0 | 42383.38 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446 | 0 | 0 | 0 | 446 | 0 | 0 | 0 | HR | 223 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-1500-L | M007 | M007 | 33-1500 | PRESSURE & AIR TEST | N | L |  | NR | P | 18445.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 18445.76 | 0 | 0 | 18445.76 | 0 | 0 | 0 | Y | 18445.76 | 0 | 0 | 18445.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | HR | 16 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-1600-L | M007 | M007 | 33-1600 | FIX 10% FAILURE PIPE | N | L |  | NR | P | 34442.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 34442.76 | 0 | 0 | 34442.76 | 0 | 0 | 0 | Y | 34442.76 | 0 | 0 | 34442.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.94 | 0 | 0 | 0 | 316.94 | 0 | 0 | 0 | HR | 70 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1700-L | M007 | M007 | 33-1700 | PRESSURE & AIR RE-TEST | N | L |  | NR | P | 2305.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2305.72 | 0 | 0 | 2305.72 | 0 | 0 | 0 | Y | 2305.72 | 0 | 0 | 2305.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 25 | 25 | 24 | 0 | 25 | 25 | HR | 2 | 0 | 2 | 2 | EA | 0 | 0 | 0 | 0
N | M007-33-1800-L | M007 | M007 | 33-1800 | CONDENSATE & STEAM PIPE | N | L |  | NR | P | 184511.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 184511.25 | 0 | 0 | 184511.25 | 0 | 0 | 0 | Y | 184511.25 | 0 | 0 | 184511.25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744.52 | 0 | 0 | 0 | 1744.52 | 0 | 0 | 0 | HR | 3894 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1800-S | M007 | M007 | 33-1800 | CONDENSATE & STEAM PIPE | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 3894 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1900-L | M007 | M007 | 33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | N | L |  | NR | P | 518604.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 518604.27 | 0 | 0 | 518604.27 | 0 | 0 | 0 | Y | 518604.27 | 0 | 0 | 518604.27 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4772.16 | 0 | 0 | 0 | 4772.16 | 0 | 0 | 0 | HR | 1054 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-1910-L | M007 | M007 | 33-1910 | STEAM AND CONDENSATE PIPE FIT UP | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 24 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-2000-L | M007 | M007 | 33-2000 | INSTALL JOJNT INSULATORS | N | L |  | NR | P | 38582.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 38582.18 | 0 | 0 | 38582.18 | 0 | 0 | 0 | Y | 38582.18 | 0 | 0 | 38582.18 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406 | 0 | 0 | 0 | 406 | 0 | 0 | 0 | HR | 203 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-2100-L | M007 | M007 | 33-2100 | PRESSURE & AIR TEST | N | L |  | NR | P | 16140.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 16140.04 | 0 | 0 | 16140.04 | 0 | 0 | 0 | Y | 16140.04 | 0 | 0 | 16140.04 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | HR | 14 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-2200-L | M007 | M007 | 33-2200 | FIX 10% FAILURE PIPE | N | L |  | NR | P | 51883.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 51883.67 | 0 | 0 | 51883.67 | 0 | 0 | 0 | Y | 51883.67 | 0 | 0 | 51883.67 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477.43 | 0 | 0 | 0 | 477.43 | 0 | 0 | 0 | HR | 105 | 0 | 0 | 0 | LF | 0 | 0 | 0 | 0
N | M007-33-2210-L | M007 | M007 | 33-2210 | EXCAVATE UTILITIES | N | L |  | NR | P | 0 | 1849.67 | 1849.67 | 1849.67 | 1849.67 | 100 | 0 | 0 | 0 | 0 | Y | 1849.67 | Y | -1849.67 | 0 | 0 | 0 | 0 | 0 | 1849.67 | Y | -1849.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1849.67 | 0 | 0 | 1849.67 | 0 | 0 | 0 | 0 | 0 | 0 | -1849.67 | 0 | 0 | 1849.67 | 1849.67 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 16 | 0 | 16 | HR | 0 | 25 | 8490 | 8515 | CY | 0 | 0 | 0 | 0
N | M007-33-2300-L | M007 | M007 | 33-2300 | PRESSURE & AIR RE-TEST | N | L |  | NR | P | 2305.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 2305.72 | 0 | 0 | 2305.72 | 0 | 0 | 0 | Y | 2305.72 | 0 | 0 | 2305.72 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | HR | 2 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-2400-L | M007 | M007 | 33-2400 | DEWATER UTILITIES | N | L |  | NR | P | 234410 | 52421.1 | 52421.1 | 52421.1 | 52421.1 | 74.8873 | 0 | 0 | 0 | 17578.9 | Y | 70000 | Y | 164410 | 0 | 0 | 234410 | 0 | 0 | 70000 | Y | 164410 | 0 | 0 | 234410 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -70000 | 1556.67 | 652.16 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | -70000 | 0 | 0 | 70000 | 70000 | 0 | 0 | 0 | 1760 | 0 | 430.77 | 430.77 | 1760 | 323 | 107.77 | 430.77 | HR | 8 | 1.34 | 1.74 | 3.08 | MO | 0 | 0 | 0 | 17578.9
N | M007-33-2500-L | M007 | M007 | 33-2500 | DUCTILE IRON PIPE SEWERS | N | L |  | NR | P | 276988.13 | 84276.23 | 84276.23 | 84276.23 | 84276.23 | 24.9178 | 0 | 0 | 0 | 253941.18 | Y | 338217.41 | Y | -61229.28 | 0 | 0 | 276988.13 | 0 | 0 | 338217.41 | Y | -61229.28 | 0 | 0 | 276988.13 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -338217.41 | 46241.04 | 21925.98 | 338217.41 | 0 | 0 | 0 | 0 | 0 | 0 | -338217.41 | 0 | 0 | 338217.41 | 338217.41 | 0 | 0 | 0 | 2431.36 | 0 | 2839.52 | 2839.52 | 2431.36 | 706 | 2133.52 | 2839.52 | HR | 3799 | 1120 | 3511 | 4631 | LF | 0 | 0 | 0 | 253941.18
N | M007-33-2510-L | M007 | M007 | 33-2510 | SEWER LINE WORK | N | L |  | NR | P | 0 | 54528.11 | 54528.11 | 54528.11 | 54528.11 | 36.3521 | 0 | 0 | 0 | 95471.89 | Y | 150000 | Y | -150000 | 0 | 0 | 0 | 0 | 0 | 150000 | Y | -150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 38738.86 | 15789.25 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 1153.85 | 1153.85 | 0 | 458 | 695.85 | 1153.85 | HR | 0 | 30 | 170 | 200 | NA | 0 | 0 | 0 | 95471.89
N | M007-33-2600-L | M007 | M007 | 33-2600 | CATCH BASIN CONNECTIONS | N | L |  | NR | P | 313516.44 | 64154.74 | 64154.74 | 64154.74 | 64154.74 | 20.463 | 0 | 0 | 0 | 249361.7 | Y | 313516.44 | Y | 0 | 0 | 0 | 313516.44 | 0 | 0 | 313516.44 | Y | 0 | 0 | 0 | 313516.44 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -313516.44 | 27344.1 | 17556.26 | 313516.44 | 0 | 0 | 0 | 0 | 0 | 0 | -313516.44 | 0 | 0 | 313516.44 | 313516.44 | 0 | 0 | 0 | 2752 | 0 | 2847.26 | 2847.26 | 2752 | 525.5 | 2321.76 | 2847.26 | HR | 86 | 35.7 | 58.3 | 94 | EA | 0 | 0 | 0 | 249361.7
N | M007-33-2700-L | M007 | M007 | 33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | N | L |  | NR | P | 7291.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7291.08 | N | 7291.08 | N | 0 | 0 | 0 | 7291.08 | 0 | 0 | 7291.08 | N | 0 | 0 | 0 | 7291.08 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -7291.08 | 0 | 0 | 7291.08 | 0 | 0 | 0 | 0 | 0 | 0 | -7291.08 | 0 | 0 | 7291.08 | 7291.08 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 64 | 0 | 64 | 64 | HR | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 7291.08
N | M007-33-2800-L | M007 | M007 | 33-2800 | DRAINAGE MANHOLES | N | L |  | NR | P | 21873.24 | 552.53 | 552.53 | 552.53 | 552.53 | 2.5261 | 0 | 0 | 0 | 21320.71 | Y | 21873.24 | Y | 0 | 0 | 0 | 21873.24 | 0 | 0 | 21873.24 | Y | 0 | 0 | 0 | 21873.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21873.24 | 0 | 0 | 21873.24 | 0 | 0 | 0 | 0 | 0 | 0 | -21873.24 | 0 | 0 | 21873.24 | 21873.24 | 0 | 0 | 0 | 192 | 0 | 192 | 192 | 192 | 5 | 187 | 192 | HR | 3 | 0.3 | 2.7 | 3 | EA | 0 | 0 | 0 | 21320.71
N | M007-33-2900-L | M007 | M007 | 33-2900 | REMOVE AREA DRAINS | N | L |  | NR | P | 32809.86 | 7686.92 | 7686.92 | 7686.92 | 7686.92 | 23.4287 | 0 | 0 | 0 | 25122.94 | Y | 32809.86 | Y | 0 | 0 | 0 | 32809.86 | 0 | 0 | 32809.86 | Y | 0 | 0 | 0 | 32809.86 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32809.86 | 2877.32 | 2635.01 | 32809.86 | 0 | 0 | 0 | 0 | 0 | 0 | -32809.86 | 0 | 0 | 32809.86 | 32809.86 | 0 | 0 | 0 | 288 | 0 | 253.01 | 253.01 | 288 | 64 | 189.01 | 253.01 | HR | 18 | 7.5 | 10.5 | 18 | EA | 0 | 0 | 0 | 25122.94
N | M007-33-3000-L | M007 | M007 | 33-3000 | ELECTRICAL MANHOLES | N | L |  | NR | P | 21873.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 21873.24 | 0 | 0 | 21873.24 | 0 | 0 | 0 | Y | 21873.24 | 0 | 0 | 21873.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | 192 | 0 | 0 | 0 | HR | 6 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-3100-L | M007 | M007 | 33-3100 | UTILITY TRENCHES | N | L |  | NR | P | 373303.29 | 613716.23 | 613716.23 | 613716.23 | 613716.23 | 85.4948 | 0 | 0 | 0 | 104124.59 | Y | 717840.82 | Y | -344537.53 | 0 | 0 | 373303.29 | 0 | 0 | 717840.82 | Y | -344537.53 | 0 | 0 | 373303.29 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -717840.82 | 8170.91 | 17234.48 | 717840.82 | 0 | 0 | 0 | 0 | 0 | 0 | -717840.82 | 0 | 0 | 717840.82 | 717840.82 | 0 | 0 | 0 | 3276.8 | 0 | 6348.82 | 6348.82 | 3276.8 | 5426.5 | 922.32 | 6348.82 | HR | 6400 | 17687.1 | 7766.9 | 25454 | CY | 0 | 0 | 0 | 104124.59
N | M007-33-3200-L | M007 | M007 | 33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | N | L |  | NR | P | 51165.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 51165.3 | 0 | 0 | 51165.3 | 0 | 0 | 0 | Y | 51165.3 | 0 | 0 | 51165.3 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | HR | 15 | 0 | 0 | 0 | EA | 0 | 0 | 0 | 0
N | M007-33-3300-L | M007 | M007 | 33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | N | L |  | NR | P | 299824.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 299824.8 | 0 | 0 | 299824.8 | 0 | 0 | 0 | Y | 299824.8 | 0 | 0 | 299824.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112 | 0 | 2112 | 2112 | 2112 | 0 | 2112 | 2112 | HR | 12 | 0 | 12 | 12 | MO | 0 | 0 | 0 | 0
N | M007-33-5000-L | M007 | M007 | 33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | N | L |  | NR | P | 0 | 2270.77 | 2270.77 | 2270.77 | 2270.77 | 100 | 0 | 0 | 0 | 0 | Y | 2270.77 | Y | -2270.77 | 0 | 0 | 0 | 0 | 0 | 2270.77 | Y | -2270.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2270.77 | 0 | 0 | 2270.77 | 0 | 0 | 0 | 0 | 0 | 0 | -2270.77 | 0 | 0 | 2270.77 | 2270.77 | 0 | 0 | 0 | 0 | 0 | 19.5 | 19.5 | 0 | 19.5 | 0 | 19.5 | HR | 7796 | 0 | 7796 | 7796 | LF | 0 | 0 | 0 | 0
N | M007-33-5000-M | M007 | M007 | 33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | N | M |  | NR | P | 865851.11 | 912686.19 | 912686.19 | 715147.84 | 912686.19 | 81.3238 | 0 | 0 | 0 | -33303.38 | Y | 879382.81 | Y | -13531.7 | 0 | 0 | 865851.11 | 0 | 0 | 879382.81 | Y | -13531.7 | 0 | 0 | 865851.11 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -879382.81 | 0 | 206478.83 | 879382.81 | 0 | 0 | 0 | 0 | 0 | 0 | -879382.81 | 0 | 0 | 879382.81 | 879382.81 | 0 | 0 | 0 | 7796 | 0 | 0 |  | 0 | 322.44 | -321.86 | 0.58 | LF | 7796 | 0 | 7796 | 7796 | LF | 912686.19 | 197538.35 | 715147.84 | -33303.38
N | M007-33-5100-L | M007 | M007 | 33-5100 | FURNISH 2 COPPER WATER PIPE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 675 | 0 | 675 | 675 | LF | 0 | 0 | 0 | 0
N | M007-33-5100-M | M007 | M007 | 33-5100 | FURNISH 2 COPPER WATER PIPE | N | M |  | NR | P | 115654.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115654.5 | N | 115654.5 | N | 0 | 0 | 0 | 115654.5 | 0 | 0 | 115654.5 | N | 0 | 0 | 0 | 115654.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -115654.5 | 0 | 0 | 115654.5 | 0 | 0 | 0 | 0 | 0 | 0 | -115654.5 | 0 | 0 | 115654.5 | 115654.5 | 0 | 0 | 0 | 675 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 675 | 0 | 675 | 675 | LF | 0 | 0 | 0 | 115654.5
N | M007-33-5200-L | M007 | M007 | 33-5200 | FURNISH DIP DRAINAGE PIPE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 3799 | 0 | 3799 | 3799 | LF | 0 | 0 | 0 | 0
N | M007-33-5200-M | M007 | M007 | 33-5200 | FURNISH DIP DRAINAGE PIPE | N | M |  | NR | P | 185823 | 266742.96 | 266742.96 | 239914.17 | 266742.96 | 100 | 0 | 0 | 0 | -26828.79 | Y | 239914.17 | Y | -54091.17 | 0 | 0 | 185823 | 0 | 0 | 239914.17 | Y | -54091.17 | 0 | 0 | 185823 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -239914.17 | 0 | 203434.08 | 239914.17 | 0 | 0 | 0 | 26828.79 | 44599.85 | 0 | -239914.17 | 0 | 0 | 239914.17 | 239914.17 | 0 | 0 | 0 | 3799 | 0 | 0 |  | 0 | 4548 | -3567.78 | 980.22 | LF | 3799 | 0 | 3799 | 3799 | LF | 266742.96 | 26828.79 | 239914.17 | -26828.79
N | M007-33-5300-L | M007 | M007 | 33-5300 | FURNISH PRECAST AREA DRAINS & MHS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 89 | 0 | 89 | 89 | EA | 0 | 0 | 0 | 0
N | M007-33-5300-M | M007 | M007 | 33-5300 | FURNISH PRECAST AREA DRAINS & MHS | N | M |  | NR | P | 109200 | 63789.68 | 63789.68 | 38930.81 | 63789.68 | 30.8935 | 0 | 0 | 0 | 62226.32 | Y | 126016 | Y | -16816 | 0 | 0 | 109200 | 0 | 0 | 126016 | Y | -16816 | 0 | 0 | 109200 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -126016 | 0 | 23711.81 | 126016 | 0 | 0 | 0 | 0 | 17717.1 | 0 | -126016 | 0 | 0 | 126016 | 126016 | 0 | 0 | 0 | 89 | 0 | 0 |  | 0 | 109.5 | -109.5 | 0 | EA | 89 | 0 | 89 | 89 | EA | 63789.68 | 24858.87 | 38930.81 | 62226.32
N | M007-33-5400-L | M007 | M007 | 33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 0
N | M007-33-5400-M | M007 | M007 | 33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | N | M |  | NR | P | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 5100 | 0 | 0 | 5100 | 0 | 0 | 0 | Y | 5100 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 6 | 0 | 6 | 6 | EA | 0 | 0 | 0 | 0
N | M007-33-5500-L | M007 | M007 | 33-5500 | FURNISH DETENTION TANK | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
N | M007-33-5500-M | M007 | M007 | 33-5500 | FURNISH DETENTION TANK | N | M |  | NR | P | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | Y | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
N | M007-33-5600-C | M007 | M007 | 33-5600 | CHLORINATION | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 100000
N | M007-33-6000-L | M007 | M007 | 33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | N | L |  | NR | P | 0 | 20750.65 | 20750.65 | 20750.65 | 20750.65 | 83.0026 | 0 | 0 | 0 | 4249.35 | Y | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 25000 | Y | -25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | -25000 | 0 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 214.98 | 214.98 | 0 | 182 | 32.98 | 214.98 | HR | 0 | 7300.5 | 699.5 | 8000 | LF | 0 | 0 | 0 | 4249.35
N | M007-33-6010-L | M007 | M007 | 33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | N | L |  | NR | P | 0 | 95857.57 | 95857.57 | 95857.57 | 95857.57 | 95.8576 | 0 | 0 | 0 | 4142.43 | Y | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 100000 | Y | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -100000 | 1297.52 | 197.01 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 793.84 | 793.84 | 0 | 756 | 37.84 | 793.84 | HR | 0 | 6104 | 1896 | 8000 | LF | 0 | 0 | 0 | 4142.43
N | M007-33-7000-C | M007 | M007 | 33-7000 | WELDING MATERIALS | N | C |  | NR | P | 32664 | 11377.07 | 11377.07 | 10729.44 | 11377.07 | 32.8479 | 0 | 0 | 0 | 21286.93 | Y | 32664 | Y | 0 | 0 | 0 | 32664 | 0 | 0 | 32664 | Y | 0 | 0 | 0 | 32664 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -32664 | 0 | 163 | 32664 | 0 | 0 | 0 | 0 | 0 | 0 | -32664 | 0 | 0 | 32664 | 32664 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 705 | 83.04 | 788.04 | LS | 1 | 0.29 | 0.71 | 1 | LS | 11214.07 | 647.63 | 10566.44 | 21286.93
N | M007-33-7000-L | M007 | M007 | 33-7000 | WELDING MATERIALS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.29 | 0.71 | 1 | LS | 0 | 0 | 0 | 0
N | M007-33-9000-C | M007 | M007 | 33-9000 | GAS LINE DAMAGE | N | C |  | NR | U | 0 | 86333.67 | 86333.67 | 81465.37 | 86333.67 | 30.0413 | 0 | 0 | 0 | 184843.98 | Y | 271177.65 | Y | -271177.65 | 0 | 0 | 0 | 0 | 0 | 271177.65 | Y | -271177.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -271177.65 | 0 | 9611.28 | 271177.65 | 0 | 0 | 0 | 0 | 0 | 0 | -271177.65 | 0 | 0 | 271177.65 | 271177.65 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | -1 | 0 | NA | 0 | 14 | 0 | 14 | HR | 59722.39 | 4868.3 | 54854.09 | 184843.98
N | M007-33-9000-L | M007 | M007 | 33-9000 | GAS LINE DAMAGE | N | L |  | NR | P | 0 | 1607.9 | 1607.9 | 1607.9 | 1607.9 | 100 | 0 | 0 | 0 | 0 | Y | 1607.9 | Y | -1607.9 | 0 | 0 | 0 | 0 | 0 | 1607.9 | Y | -1607.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1607.9 | 0 | 0 | 1607.9 | 0 | 0 | 0 | 0 | 0 | 0 | -1607.9 | 0 | 0 | 1607.9 | 1607.9 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 14 | 0 | 14 | HR | 0 | 14 | 0 | 14 | HR | 0 | 0 | 0 | 0
N | M007-33-9000-S | M007 | M007 | 33-9000 | GAS LINE DAMAGE | N | S |  | NR | A | 0 | 27214.45 | 27214.45 | 0 | 27214.45 | 0 | 0 | 0 | 0 | 0 | N | 27214.45 | N | -27214.45 | 0 | 0 | 0 | 0 | 0 | 27214.45 | N | -27214.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -27214.45 | 0 | 0 | 27214.45 | 0 | 0 | 0 | 0 | 27214.45 | 0 | -27214.45 | 0 | 0 | 27214.45 | 27214.45 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 122 | 122 | NA | 0 | 14 | 0 | 14 | HR | 27214.45 | 27214.45 | 0 | 0
N | M007-97-6000-L | M007 | M007 | 97-6000 | Bulk ACM removal, hose wire insulation | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 0
N | M007-97-6000-S | M007 | M007 | 97-6000 | Bulk ACM removal, hose wire insulation | N | S |  | NR | P | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | N | 25 | N | 0 | 0 | 0 | 25 | 0 | 0 | 25 | N | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | -25 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 25
N | M007-97-6100-L | M007 | M007 | 97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 0
N | M007-97-6100-S | M007 | M007 | 97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | N | S |  | NR | P | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | N | 74 | N | 0 | 0 | 0 | 74 | 0 | 0 | 74 | N | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -74 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | -74 | 0 | 0 | 74 | 74 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 74
N | M007-97-6200-L | M007 | M007 | 97-6200 | Bulk ACM removal, pipe insulation and assoc jack | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 0
N | M007-97-6200-S | M007 | M007 | 97-6200 | Bulk ACM removal, pipe insulation and assoc jack | N | S |  | NR | P | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | N | 42 | N | 0 | 0 | 0 | 42 | 0 | 0 | 42 | N | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -42 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | -42 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 42
N | M007-97-6300-L | M007 | M007 | 97-6300 | Bulk ACM removal, pipe insulation and braided wire | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 0
N | M007-97-6300-S | M007 | M007 | 97-6300 | Bulk ACM removal, pipe insulation and braided wire | N | S |  | NR | P | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | N | 42 | N | 0 | 0 | 0 | 42 | 0 | 0 | 42 | N | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -42 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | -42 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LF | 1 | 0 | 1 | 1 | LF | 0 | 0 | 0 | 42
N | M007-97-6400-L | M007 | M007 | 97-6400 | Bulk ACM removal, ACM Contamined Debris | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 0
N | M007-97-6400-S | M007 | M007 | 97-6400 | Bulk ACM removal, ACM Contamined Debris | N | S |  | NR | P | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | N | 25 | N | 0 | 0 | 0 | 25 | 0 | 0 | 25 | N | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | -25 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 25
N | M007-97-6500-L | M007 | M007 | 97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 0
N | M007-97-6500-S | M007 | M007 | 97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | N | S |  | NR | P | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | N | 30 | N | 0 | 0 | 0 | 30 | 0 | 0 | 30 | N | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | -30 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 30
N | M007-97-6600-L | M007 | M007 | 97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 0
N | M007-97-6600-S | M007 | M007 | 97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | N | S |  | NR | P | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | N | 400 | N | 0 | 0 | 0 | 400 | 0 | 0 | 400 | N | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -400 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | -400 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 400
N | M007-97-6700-L | M007 | M007 | 97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 0
N | M007-97-6700-S | M007 | M007 | 97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | N | S |  | NR | P | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | N | 750 | N | 0 | 0 | 0 | 750 | 0 | 0 | 750 | N | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -750 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | -750 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 750
N | M007-97-6800-L | M007 | M007 | 97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 0
N | M007-97-6800-S | M007 | M007 | 97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | N | S |  | NR | P | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | N | 85 | N | 0 | 0 | 0 | 85 | 0 | 0 | 85 | N | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -85 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | -85 | 0 | 0 | 85 | 85 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | SF | 1 | 0 | 1 | 1 | SF | 0 | 0 | 0 | 85
N | M007-97-7000-L | M007 | M007 | 97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 0
N | M007-97-7000-S | M007 | M007 | 97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | N | S |  | NR | P | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | N | 60 | N | 0 | 0 | 0 | 60 | 0 | 0 | 60 | N | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | -60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | CY | 1 | 0 | 1 | 1 | CY | 0 | 0 | 0 | 60
N | M007-98-1000-L | M007 | M007 | 98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-98-1000-S | M007 | M007 | 98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | N | S |  | NR | P | 51926.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51926.66 | Y | 51926.66 | Y | -0.06 | 0 | 0 | 51926.6 | 0 | 0 | 51926.66 | Y | -0.06 | 0 | 0 | 51926.6 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -51926.66 | 0 | 0 | 51926.66 | 0 | 0 | 0 | 0 | 0 | 0 | -51926.66 | 0 | 0 | 51926.66 | 51926.66 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 51926.66
N | M007-98-1100-L | M007 | M007 | 98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-98-1100-S | M007 | M007 | 98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | N | S |  | NR | P | 141408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141408 | N | 141408 | N | 0 | 0 | 0 | 141408 | 0 | 0 | 141408 | N | 0 | 0 | 0 | 141408 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -141408 | 0 | 0 | 141408 | 0 | 0 | 0 | 0 | 0 | 0 | -141408 | 0 | 0 | 141408 | 141408 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 141408
N | M007-99-1000-C | M007 | M007 | 99-1000 | Supervision | N | C |  | NR | U | 0 | 119722.7 | 119722.7 | 117834.39 | 119722.7 | 98.1953 | 0 | 0 | 0 | 277.3 | Y | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 120000 | Y | -120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -120000 | 615.36 | 30311.58 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | -120000 | 0 | 0 | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 221 | -97.07 | 123.93 | NA | 37 | 22 | 15 | 37 | MO | 19083.31 | 1888.31 | 17195 | 277.3
N | M007-99-1000-L | M007 | M007 | 99-1000 | Supervision | N | L |  | NR | P | 4757500 | 4464867.5 | 4464867.5 | 4464867.5 | 4464867.5 | 65.2949 | 0 | 0 | 0 | 2373132.5 | Y | 6838000 | Y | -2080500 | 0 | 0 | 4757500 | 0 | 0 | 6838000 | Y | -2080500 | 0 | 0 | 4757500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6838000 | 162024.13 | 214448.78 | 6838000 | 0 | 0 | 0 | 0 | 0 | 0 | -6838000 | 0 | 0 | 6838000 | 6838000 | 0 | 0 | 0 | 37 | 0 | 0 |  | 67964.29 | 55616.63 | 34117.42 | 89734.05 | MO | 37 | 22 | 15 | 37 | MO | 0 | 0 | 0 | 2373132.5
N | M007-99-1010-C | M007 | M007 | 99-1010 | CLAIMS CONSULTANT | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-99-1020-C | M007 | M007 | 99-1020 | LEGAL COSTS | N | C |  | NR | U | 0 | 5030 | 5030 | 5030 | 5030 | 10.06 | 0 | 0 | 0 | 44970 | Y | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 50000 | Y | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | LS | 0 | 0 | 0 | 44970
N | M007-99-1100-L | M007 | M007 | 99-1100 | TEAMSTER | N | L |  | NR | P | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000 | Y | 315000 | Y | 0 | 0 | 0 | 315000 | 0 | 0 | 315000 | Y | 0 | 0 | 0 | 315000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -315000 | 0 | 0 | 315000 | 0 | 0 | 0 | 0 | 0 | 0 | -315000 | 0 | 0 | 315000 | 315000 | 0 | 0 | 0 | 18 | 0 | 0 |  | 0 | 0 | 3150 | 3150 | MO | 18 | 0 | 18 | 18 | MO | 0 | 0 | 0 | 315000
N | M007-99-1200-L | M007 | M007 | 99-1200 | OPER ENG MASTER MECH | N | L |  | NR | P | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000 | Y | 600000 | Y | 0 | 0 | 0 | 600000 | 0 | 0 | 600000 | Y | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -600000 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | -600000 | 0 | 0 | 600000 | 600000 | 0 | 0 | 0 | 24 | 0 | 0 |  | 0 | 0 | 6000 | 6000 | MO | 24 | 0 | 24 | 24 | MO | 0 | 0 | 0 | 600000
N | M007-99-1300-L | M007 | M007 | 99-1300 | OPER ENG MECH | N | L |  | NR | P | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480000 | Y | 480000 | Y | 0 | 0 | 0 | 480000 | 0 | 0 | 480000 | Y | 0 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -480000 | 0 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 0 | -480000 | 0 | 0 | 480000 | 480000 | 0 | 0 | 0 | 24 | 0 | 0 |  | 0 | 0 | 4800 | 4800 | MO | 24 | 0 | 24 | 24 | MO | 0 | 0 | 0 | 480000
N | M007-99-2000-C | M007 | M007 | 99-2000 | SURVEY SUB | N | C |  | NR | P | 0 | 21300 | 21300 | 21300 | 21300 | 100 | 0 | 0 | 0 | 0 | Y | 21300 | Y | -21300 | 0 | 0 | 0 | 0 | 0 | 21300 | Y | -21300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21300 | 0 | 0 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 | -21300 | 0 | 0 | 21300 | 21300 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17 | -0.53 | 16.47 | NA | 9 | 0 | 9 | 9 | EA | 21300 | 0 | 21300 | 0
N | M007-99-2000-L | M007 | M007 | 99-2000 | SURVEY SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9 | 0 | 9 | 9 | EA | 0 | 0 | 0 | 0
N | M007-99-2000-S | M007 | M007 | 99-2000 | SURVEY SUB | N | S |  | NR | P | 379500 | 433738.25 | 433738.25 | 386282.75 | 433738.25 | 77.2566 | 0 | 0 | 0 | 66261.75 | Y | 500000 | Y | -120500 | 0 | 0 | 379500 | 0 | 0 | 500000 | Y | -120500 | 0 | 0 | 379500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500000 | 9612 | 36799.75 | 500000 | 0 | 0 | 0 | 0 | 100000 | 0 | -500000 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 150 | 0 | 0 |  | 0 | 2262.53 | 889.33 | 3151.86 | SH | 9 | 0 | 9 | 9 | EA | 433738.25 | 47455.5 | 386282.75 | 66261.75
N | M007-99-3000-L | M007 | M007 | 99-3000 | SECURITY SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-3000-S | M007 | M007 | 99-3000 | SECURITY SUB | N | S |  | NR | P | 648295.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 648295.5 | Y | 648295.5 | Y | 0 | 0 | 0 | 648295.5 | 0 | 0 | 648295.5 | Y | 0 | 0 | 0 | 648295.5 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -648295.5 | 0 | 0 | 648295.5 | 0 | 0 | 0 | 0 | 0 | 0 | -648295.5 | 0 | 0 | 648295.5 | 648295.5 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 648295.5
N | M007-99-3100-C | M007 | M007 | 99-3100 | CONTAINERS - 30 CY | N | C |  | NR | P | 35168.24 | 745579.51 | 745579.51 | 593998.18 | 745579.51 | 74.2498 | 0 | 0 | 0 | 54420.49 | Y | 800000 | Y | -764831.76 | 0 | 0 | 35168.24 | 0 | 0 | 800000 | Y | -764831.76 | 0 | 0 | 35168.24 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -800000 | -1905.42 | 12246.42 | 800000 | 0 | 0 | 0 | 0 | -46346 | 0 | -800000 | 0 | 0 | 800000 | 800000 | 0 | 0 | 0 | 34 | 0 | 0 |  | 0 | 10591.35 | 865.22 | 11456.57 | EA | 34 | 80 | 320 | 400 | EA | 780474.19 | 151581.33 | 628892.86 | 54420.49
N | M007-99-3100-L | M007 | M007 | 99-3100 | CONTAINERS - 30 CY | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 34 | 80 | 320 | 400 | EA | 0 | 0 | 0 | 0
N | M007-99-4000-C | M007 | M007 | 99-4000 | YARD W/ TEMP ELECT | N | C |  | NR | P | 370000 | 69470.49 | 69470.49 | 69470.49 | 69470.49 | 84.4952 | 0 | 0 | 0 | 12747.81 | Y | 82218.3 | Y | 287781.7 | 0 | 0 | 370000 | 0 | 0 | 82218.3 | Y | 287781.7 | 0 | 0 | 370000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -82218.3 | 6496.7 | 0 | 82218.3 | 0 | 0 | 0 | 0 | 0 | 0 | -82218.3 | 0 | 0 | 82218.3 | 82218.3 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 908.02 | -890.75 | 17.27 | MO | 37 | 74.02 | 0 | 74.02 | HR | 48473.34 | -3623.45 | 52096.79 | 12747.81
N | M007-99-4000-L | M007 | M007 | 99-4000 | YARD W/ TEMP ELECT | N | L |  | NR | P | 0 | 41060.83 | 41060.83 | 41060.83 | 41060.83 | 73.565 | 0 | 0 | 0 | 14754.87 | Y | 55815.7 | Y | -55815.7 | 0 | 0 | 0 | 0 | 0 | 55815.7 | Y | -55815.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -55815.7 | 693.93 | 0 | 55815.7 | 0 | 0 | 0 | 0 | 0 | 0 | -55815.7 | 0 | 0 | 55815.7 | 55815.7 | 0 | 0 | 0 | 0 | 0 | 535.04 | 535.04 | 0 | 382 | 153.04 | 535.04 | HR | 37 | 74.02 | 0 | 74.02 | HR | 0 | 0 | 0 | 14754.87
N | M007-99-4050-C | M007 | M007 | 99-4050 | COMPUTER/SOFTWARE | N | C |  | NR | P | 43552 | 78313.79 | 78313.79 | 78313.79 | 78313.79 | 97.8922 | 0 | 0 | 0 | 1686.21 | Y | 80000 | Y | -36448 | 0 | 0 | 43552 | 0 | 0 | 80000 | Y | -36448 | 0 | 0 | 43552 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -80000 | 466 | 477.95 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | -80000 | 0 | 0 | 80000 | 80000 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 5 | 0.2 | 5.2 | EA | 8 | 0 | 8 | 8 | EA | 1227.82 | 0 | 1227.82 | 1686.21
N | M007-99-4050-L | M007 | M007 | 99-4050 | COMPUTER/SOFTWARE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 0 | 8 | 8 | EA | 0 | 0 | 0 | 0
N | M007-99-4100-C | M007 | M007 | 99-4100 | STATIONWORK DESK | N | C |  | NR | P | 8710.4 | 6193.68 | 6193.68 | 6193.68 | 6193.68 | 71.1067 | 0 | 0 | 0 | 2516.72 | Y | 8710.4 | Y | 0 | 0 | 0 | 8710.4 | 0 | 0 | 8710.4 | Y | 0 | 0 | 0 | 8710.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -8710.4 | 0 | 0 | 8710.4 | 0 | 0 | 0 | 0 | 0 | 0 | -8710.4 | 0 | 0 | 8710.4 | 8710.4 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 32 | -32 | 0 | EA | 8 | 7 | 1 | 8 | EA | 6193.68 | 0 | 6193.68 | 2516.72
N | M007-99-4100-L | M007 | M007 | 99-4100 | STATIONWORK DESK | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 7 | 1 | 8 | EA | 0 | 0 | 0 | 0
N | M007-99-4150-C | M007 | M007 | 99-4150 | IT SUPPORT | N | C |  | NR | P | 10071.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 10071.4 | 0 | 0 | 10071.4 | 0 | 0 | 0 | Y | 10071.4 | 0 | 0 | 10071.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 37 | 15 | 22 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4150-L | M007 | M007 | 99-4150 | IT SUPPORT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 15 | 22 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4200-C | M007 | M007 | 99-4200 | PHONE EQUIPMENT | N | C |  | NR | P | 3048.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 3048.64 | 0 | 0 | 3048.64 | 0 | 0 | 0 | Y | 3048.64 | 0 | 0 | 3048.64 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 0 | 0 | 0 | EA | 8 | 7 | 1 | 8 | EA | 0 | 0 | 0 | 0
N | M007-99-4200-L | M007 | M007 | 99-4200 | PHONE EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 8 | 7 | 1 | 8 | EA | 0 | 0 | 0 | 0
N | M007-99-4250-C | M007 | M007 | 99-4250 | PHONE SYSTEM | N | C |  | NR | P | 7376.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 7376.62 | 0 | 0 | 7376.62 | 0 | 0 | 0 | Y | 7376.62 | 0 | 0 | 7376.62 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 |  | 0 | 0 | 0 | 0 | UM | 271 | 50.65 | 220.35 | 271 | UM | 0 | 0 | 0 | 0
N | M007-99-4250-L | M007 | M007 | 99-4250 | PHONE SYSTEM | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 271 | 50.65 | 220.35 | 271 | UM | 0 | 0 | 0 | 0
N | M007-99-4300-C | M007 | M007 | 99-4300 | PRINTERS/PLOTTER | N | C |  | NR | P | 60428.4 | 36547 | 36547 | 36547 | 36547 | 60.4798 | 0 | 0 | 0 | 23881.4 | Y | 60428.4 | Y | 0 | 0 | 0 | 60428.4 | 0 | 0 | 60428.4 | Y | 0 | 0 | 0 | 60428.4 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -60428.4 | 728.58 | 1068.56 | 60428.4 | 0 | 0 | 0 | 0 | 0 | 0 | -60428.4 | 0 | 0 | 60428.4 | 60428.4 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 |  | 0 | 0 | MO | 37 | 22 | 15 | 37 | MO | 0 | 0 | 0 | 23881.4
N | M007-99-4300-L | M007 | M007 | 99-4300 | PRINTERS/PLOTTER | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 22 | 15 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4350-C | M007 | M007 | 99-4350 | SUPPLIES | N | C |  | NR | P | 29506.48 | 49556.73 | 49556.73 | 49556.72 | 49556.73 | 99.1134 | 0 | 0 | 0 | 443.27 | Y | 50000 | Y | -20493.52 | 0 | 0 | 29506.48 | 0 | 0 | 50000 | Y | -20493.52 | 0 | 0 | 29506.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -50000 | 121.92 | 3845.52 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 271 | 0 | 0 |  | 0 | 2 | -2 | 0 | UM | 271 | 14.65 | 256.35 | 271 | UM | 76.81 | 0.01 | 76.8 | 443.27
N | M007-99-4350-L | M007 | M007 | 99-4350 | SUPPLIES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 271 | 14.65 | 256.35 | 271 | UM | 0 | 0 | 0 | 0
N | M007-99-4400-C | M007 | M007 | 99-4400 | TELEPHONE | N | C |  | NR | P | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | Y | 18500 | Y | 0 | 0 | 0 | 18500 | 0 | 0 | 18500 | Y | 0 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18500 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | -18500 | 0 | 0 | 18500 | 18500 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 18500
N | M007-99-4400-L | M007 | M007 | 99-4400 | TELEPHONE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4450-C | M007 | M007 | 99-4450 | CELL PHONES | N | C |  | NR | P | 29506.48 | 18135.92 | 18135.92 | 18135.92 | 18135.92 | 61.4642 | 0 | 0 | 0 | 11370.56 | Y | 29506.48 | Y | 0 | 0 | 0 | 29506.48 | 0 | 0 | 29506.48 | Y | 0 | 0 | 0 | 29506.48 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -29506.48 | 0 | 609.17 | 29506.48 | 0 | 0 | 0 | 0 | 0 | 0 | -29506.48 | 0 | 0 | 29506.48 | 29506.48 | 0 | 0 | 0 | 271 | 0 | 0 |  | 0 |  | 0 | 0 | UM | 271 | 14.65 | 256.35 | 271 | UM | 0 | 0 | 0 | 11370.56
N | M007-99-4450-L | M007 | M007 | 99-4450 | CELL PHONES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 271 | 14.65 | 256.35 | 271 | UM | 0 | 0 | 0 | 0
N | M007-99-4500-C | M007 | M007 | 99-4500 | ELECTRIC | N | C |  | NR | P | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18500 | Y | 18500 | Y | 0 | 0 | 0 | 18500 | 0 | 0 | 18500 | Y | 0 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -18500 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | -18500 | 0 | 0 | 18500 | 18500 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 18500
N | M007-99-4500-L | M007 | M007 | 99-4500 | ELECTRIC | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 8 | 29 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4550-C | M007 | M007 | 99-4550 | SANITATION | N | C |  | NR | P | 18500 | 182119.57 | 182119.57 | 123800.51 | 182119.57 | 88.4289 | 0 | 0 | 0 | -42119.57 | Y | 140000 | Y | -121500 | 0 | 0 | 18500 | 0 | 0 | 140000 | Y | -121500 | 0 | 0 | 18500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -140000 | 23823.99 | 17406.09 | 140000 | 0 | 0 | 0 | 37562.11 | -47060.39 | 0 | -140000 | 0 | 0 | 140000 | 140000 | 0 | 0 | 0 | 37 | 0 | 0 |  | 37 | 851.67 | -600.83 | 250.84 | MO | 37 | 22 | 15 | 37 | MO | 182119.57 | 58319.06 | 123800.51 | -42119.57
N | M007-99-4550-L | M007 | M007 | 99-4550 | SANITATION | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 22 | 15 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-4560-L | M007 | M007 | 99-4560 | SITE MAINTENANCE | N | L |  | NR | P | 0 | 693857.23 | 693857.23 | 693857.23 | 693857.23 | 85.2125 | 0 | 0 | 0 | 120409.5 | Y | 814266.73 | Y | -814266.73 | 0 | 0 | 0 | 0 | 0 | 814266.73 | Y | -814266.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -814266.73 | 37678.65 | 41889.41 | 814266.73 | 0 | 0 | 0 | 0 | 0 | 0 | -814266.73 | 0 | 0 | 814266.73 | 814266.73 | 0 | 0 | 0 | 0 | 0 | 7646.47 | 7646.47 | 0 | 6617.5 | 1028.97 | 7646.47 | HR | 0 | 5706.5 | 2019.5 | 7726 | HR | 0 | 0 | 0 | 120409.5
N | M007-99-4560-M | M007 | M007 | 99-4560 | SITE MAINTENANCE | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 5706.5 | 2019.5 | 7726 | HR | 0 | 0 | 0 | 0
N | M007-99-4560-S | M007 | M007 | 99-4560 | SITE MAINTENANCE | N | S |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 5706.5 | 2019.5 | 7726 | HR | 0 | 0 | 0 | 0
N | M007-99-4570-C | M007 | M007 | 99-4570 | BASEMENT MAINTENANCE | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 960 | 960 | HR | 0 | 0 | 0 | 0
N | M007-99-4570-LAB | M007 | M007 | 99-4570 | BASEMENT MAINTENANCE | N | LAB |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 960 | 960 | HR | 0 | 0 | 0 | 0
N | M007-99-4570-M | M007 | M007 | 99-4570 | BASEMENT MAINTENANCE | N | M |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 960 | 960 | HR | 0 | 0 | 0 | 0
N | M007-99-4600-C | M007 | M007 | 99-4600 | VEHICLES | N | C |  | NR | P | 270000 | 49196.88 | 49196.88 | 44498.72 | 49196.88 | 22.2494 | 0 | 0 | 0 | 150803.12 | Y | 200000 | Y | 70000 | 0 | 0 | 270000 | 0 | 0 | 200000 | Y | 70000 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -200000 | 522.6 | 1775.26 | 200000 | 0 | 0 | 0 | 0 | 935.24 | 0 | -200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 180 | 0 | 0 |  | 0 | 300 | 505.62 | 805.62 | MO | 180 | 22 | 158 | 180 | MO | 44661.93 | 4698.16 | 39963.77 | 150803.12
N | M007-99-4600-D | M007 | M007 | 99-4600 | VEHICLES | N | D |  | NR | A | 0 | 14108.22 | 14108.22 | 14108.22 | 14108.22 | 100 | 0 | 0 | 0 | 0 | N | 14108.22 | N | -14108.22 | 0 | 0 | 0 | 0 | 0 | 14108.22 | N | -14108.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -14108.22 | 0 | 1998.78 | 14108.22 | 0 | 0 | 0 | 0 | 0 | 0 | -14108.22 | 0 | 0 | 14108.22 | 14108.22 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 180 | 22 | 158 | 180 | MO | 0 | 0 | 0 | 0
N | M007-99-4600-L | M007 | M007 | 99-4600 | VEHICLES | N | L |  | NR | P | 0 | 745.96 | 745.96 | 745.96 | 745.96 | 25.9757 | 0 | 0 | 0 | 2125.8 | Y | 2871.76 | Y | -2871.76 | 0 | 0 | 0 | 0 | 0 | 2871.76 | Y | -2871.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -2871.76 | 0 | 0 | 2871.76 | 0 | 0 | 0 | 0 | 0 | 0 | -2871.76 | 0 | 0 | 2871.76 | 2871.76 | 0 | 0 | 0 | 0 | 0 | 27.33 | 27.33 | 0 | 3 | 24.33 | 27.33 | HR | 180 | 22 | 158 | 180 | MO | 0 | 0 | 0 | 2125.8
N | M007-99-4650-C | M007 | M007 | 99-4650 | FUEL | N | C |  | NR | P | 270000 | 147920.65 | 147920.65 | 97954.2 | 147920.65 | 54.419 | 0 | 0 | 0 | 32079.35 | Y | 180000 | Y | 90000 | 0 | 0 | 270000 | 0 | 0 | 180000 | Y | 90000 | 0 | 0 | 270000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -180000 | 3296.67 | 5013.63 | 180000 | 0 | 0 | 0 | 37.37 | -48954.57 | 0 | -180000 | 0 | 0 | 180000 | 180000 | 0 | 0 | 0 | 180 | 0 | 0 |  | 0 | 81169.59 | -14033.6 | 67135.99 | MO | 180 | 22 | 158 | 180 | MO | 144611.48 | 49966.45 | 94645.03 | 32079.35
N | M007-99-4650-L | M007 | M007 | 99-4650 | FUEL | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 180 | 22 | 158 | 180 | MO | 0 | 0 | 0 | 0
N | M007-99-4700-C | M007 | M007 | 99-4700 | PETTY CASH | N | C |  | NR | P | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111000 | N | 111000 | N | 0 | 0 | 0 | 111000 | 0 | 0 | 111000 | N | 0 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -111000 | 0 | 0 | 111000 | 0 | 0 | 0 | 0 | 0 | 0 | -111000 | 0 | 0 | 111000 | 111000 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 0 | 0 | 0 | MO | 37 | 0 | 37 | 37 | MO | 0 | 0 | 0 | 111000
N | M007-99-4700-L | M007 | M007 | 99-4700 | PETTY CASH | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 0 | 37 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-5000-C | M007 | M007 | 99-5000 | OFFICE RENT | N | C |  | NR | P | 335256.76 | 408271.7 | 408271.7 | 400138.74 | 408271.7 | 71.326 | 0 | 0 | 0 | 152728.3 | Y | 561000 | Y | -225743.24 | 0 | 0 | 335256.76 | 0 | 0 | 561000 | Y | -225743.24 | 0 | 0 | 335256.76 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -561000 | 0 | 12777.77 | 561000 | 0 | 0 | 0 | 0 | 0 | 0 | -561000 | 0 | 0 | 561000 | 561000 | 0 | 0 | 0 | 222 | 0 | 0 |  | 0 | 0 | 0 | 0 | UM | 222 | 22 | 200 | 222 | UM | 8132.96 | 8132.96 | 0 | 152728.3
N | M007-99-5000-L | M007 | M007 | 99-5000 | OFFICE RENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 222 | 22 | 200 | 222 | UM | 0 | 0 | 0 | 0
N | M007-99-5100-C | M007 | M007 | 99-5100 | NYCHA OFFICE FURNITURE | N | C |  | NR | P | 65328 | 34537.26 | 34537.26 | 33257.26 | 34537.26 | 67.3519 | 0 | 0 | 0 | 14841.13 | Y | 49378.39 | Y | 15949.61 | 0 | 0 | 65328 | 0 | 0 | 49378.39 | Y | 15949.61 | 0 | 0 | 65328 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -49378.39 | 0 | 0 | 49378.39 | 0 | 0 | 0 | 0 | 0 | 0 | -49378.39 | 0 | 0 | 49378.39 | 49378.39 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 146 | 62.74 | 208.74 | LS | 1 | 0.72 | 0.28 | 1 | LS | 32283.38 | 1280 | 31003.38 | 14841.13
N | M007-99-5100-L | M007 | M007 | 99-5100 | NYCHA OFFICE FURNITURE | N | L |  | NR | P | 0 | 5621.61 | 5621.61 | 5621.61 | 5621.61 | 100 | 0 | 0 | 0 | 0 | Y | 5621.61 | Y | -5621.61 | 0 | 0 | 0 | 0 | 0 | 5621.61 | Y | -5621.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -5621.61 | 0 | 0 | 5621.61 | 0 | 0 | 0 | 0 | 0 | 0 | -5621.61 | 0 | 0 | 5621.61 | 5621.61 | 0 | 0 | 0 | 0 | 0 | 65.5 | 65.5 | 0 | 65.5 | 0 | 65.5 | HR | 1 | 0.72 | 0.28 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-6000-C | M007 | M007 | 99-6000 | SMALL TOOLS | N | C |  | NR | P | 376000 | 673694.99 | 673694.99 | 512539.68 | 673694.99 | 80.0843 | 0 | 0 | 0 | -33694.99 | Y | 640000 | Y | -264000 | 0 | 0 | 376000 | 0 | 0 | 640000 | Y | -264000 | 0 | 0 | 376000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -640000 | 11016.42 | 14552.09 | 640000 | 0 | 0 | 0 | 18839.25 | 18956.57 | 0 | -640000 | 0 | 0 | 640000 | 640000 | 0 | 0 | 0 | 37 | 0 | 0 |  | 0 | 65736.47 | -1919.4 | 63817.07 | LS | 37 | 22 | 15 | 37 | MO | 675637.26 | 161155.31 | 514481.95 | -33694.99
N | M007-99-6000-L | M007 | M007 | 99-6000 | SMALL TOOLS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 37 | 22 | 15 | 37 | MO | 0 | 0 | 0 | 0
N | M007-99-7000-L | M007 | M007 | 99-7000 | LABOR ESCAL | N | L |  | NR | P | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | Y | 1000000 | Y | 0 | 0 | 0 | 1000000 | 0 | 0 | 1000000 | Y | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | -1000000 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 10000 | 0 | 10000 | 10000 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 1000000
N | M007-99-7100-L | M007 | M007 | 99-7100 | PREMIUM COST | N | L |  | NR | P | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | Y | 500000 | Y | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 | Y | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | -500000 | 0 | 0 | 500000 | 500000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 5000 | 0 | 5000 | 5000 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 500000
N | M007-99-7200-C | M007 | M007 | 99-7200 | HOLIDAY PAY | N | C |  | NR | U | 0 | 432.56 | 432.56 | 432.56 | 432.56 | 100 | 0 | 0 | 0 | 0 | Y | 432.56 | Y | -432.56 | 0 | 0 | 0 | 0 | 0 | 432.56 | Y | -432.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -432.56 | 0 | 0 | 432.56 | 0 | 0 | 0 | 0 | 0 | 0 | -432.56 | 0 | 0 | 432.56 | 432.56 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0.91 | 0.09 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-7200-L | M007 | M007 | 99-7200 | HOLIDAY PAY | N | L |  | NR | P | 150000 | 158126.8 | 158126.8 | 158126.8 | 158126.8 | 83.2246 | 0 | 0 | 0 | 31873.2 | Y | 190000 | Y | -40000 | 0 | 0 | 150000 | 0 | 0 | 190000 | Y | -40000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -190000 | 25689.14 | 0 | 190000 | 0 | 0 | 0 | 0 | 0 | 0 | -190000 | 0 | 0 | 190000 | 190000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1500 | 1389 | 264.98 | 1653.98 | LS | 1 | 0.91 | 0.09 | 1 | LS | 0 | 0 | 0 | 31873.2
N | M007-99-7210-L | M007 | M007 | 99-7210 | PAID TIME OFF | N | L |  | NR | P | 0 | 10436.48 | 10436.48 | 10436.48 | 10436.48 | 104.3648 | 0 | 0 | 0 | -436.48 | Y | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 10000 | Y | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -10000 | 1004.56 | 5509.19 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 81.58 | 81.58 | 0 | 88 | -6.42 | 81.58 | HR | 0 | 152 | 0 | 152 | NA | 0 | 0 | 0 | -436.48
N | M007-99-7300-C | M007 | M007 | 99-7300 | LOST TIME | N | C |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 1 | 0.26 | 0.74 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-7300-L | M007 | M007 | 99-7300 | LOST TIME | N | L |  | NR | P | 150000 | 39042.88 | 39042.88 | 39042.88 | 39042.88 | 26.0286 | 0 | 0 | 0 | 110957.12 | Y | 150000 | Y | 0 | 0 | 0 | 150000 | 0 | 0 | 150000 | Y | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | -150000 | 0 | 0 | 150000 | 150000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1500 | 313 | 1187 | 1500 | LS | 1 | 0.26 | 0.74 | 1 | LS | 0 | 0 | 0 | 110957.12
N | M007-99-7400-C | M007 | M007 | 99-7400 | PERMITS | N | C |  | NR | P | 10000 | 13348.7 | 13348.7 | 11023.7 | 13348.7 | 73.4913 | 0 | 0 | 0 | 1651.3 | Y | 15000 | Y | -5000 | 0 | 0 | 10000 | 0 | 0 | 15000 | Y | -5000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | -15000 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 2 | 0.84 | 2.84 | LS | 1 | 0.79 | 0.21 | 1 | LS | 3025 | 2325 | 700 | 1651.3
N | M007-99-7400-L | M007 | M007 | 99-7400 | PERMITS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.79 | 0.21 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-7500-L | M007 | M007 | 99-7500 | ENGINEERING SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.86 | 0.14 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-7500-S | M007 | M007 | 99-7500 | ENGINEERING SUB | N | S |  | NR | P | 125000 | 178984.95 | 178984.95 | 163369.93 | 178984.95 | 89.1028 | 0 | 0 | 0 | 4365.05 | Y | 183350 | Y | -58350 | 0 | 0 | 125000 | 0 | 0 | 183350 | Y | -58350 | 0 | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -183350 | 0 | 0 | 183350 | 0 | 0 | 0 | 7489.6 | 0 | 0 | -183350 | 0 | 0 | 183350 | 183350 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 13.47 | -5.3 | 8.17 | LS | 1 | 0.86 | 0.14 | 1 | LS | 178984.95 | 15615.02 | 163369.93 | 4365.05
N | M007-99-7510-C | M007 | M007 | 99-7510 | CADD SERVICES | N | C |  | NR | U | 0 | 11018.53 | 11018.53 | 9360.83 | 11018.53 | 74.2923 | 0 | 0 | 0 | 1581.47 | Y | 12600 | Y | -12600 | 0 | 0 | 0 | 0 | 0 | 12600 | Y | -12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -12600 | 335.65 | 335.65 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | -12600 | 0 | 0 | 12600 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 28 | -25 | 3 | NA | 9 | 0 | 9 | 9 | EA | 4657.7 | 1657.7 | 3000 | 1581.47
N | M007-99-7510-L | M007 | M007 | 99-7510 | CADD SERVICES | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 9 | 0 | 9 | 9 | EA | 0 | 0 | 0 | 0
N | M007-99-7600-L | M007 | M007 | 99-7600 | SECTION 3 ADMINISTRATOR SUB | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-7600-S | M007 | M007 | 99-7600 | SECTION 3 ADMINISTRATOR SUB | N | S |  | NR | P | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | Y | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-8000-C | M007 | M007 | 99-8000 | EQUIPMENT | N | C |  | NR | U | 0 | 83845.77 | 83845.77 | 75282.28 | 83845.77 | 94.2896 | 0 | 0 | 0 | -4004.18 | Y | 79841.59 | Y | -79841.59 | 0 | 0 | 0 | 0 | 0 | 79841.59 | Y | -79841.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -79841.59 | 0 | 0 | 79841.59 | 0 | 0 | 0 | 0 | 0 | 0 | -79841.59 | 0 | 0 | 79841.59 | 79841.59 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 205 | 323.95 | 528.95 | NA | 1 | 0.38 | 0.62 | 1 | LS | 44779.02 | 8563.49 | 36215.53 | -4004.18
N | M007-99-8000-D | M007 | M007 | 99-8000 | EQUIPMENT | N | D |  | NR | A | 0 | 21120.45 | 21120.45 | 21120.45 | 21120.45 | 100 | 0 | 0 | 0 | 0 | N | 21120.45 | N | -21120.45 | 0 | 0 | 0 | 0 | 0 | 21120.45 | N | -21120.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -21120.45 | 0 | 1408.03 | 21120.45 | 0 | 0 | 0 | 0 | 0 | 0 | -21120.45 | 0 | 0 | 21120.45 | 21120.45 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0.38 | 0.62 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-8000-E | M007 | M007 | 99-8000 | EQUIPMENT | N | E |  | NR | P | 1554967.8 | 993196.96 | 993196.96 | 804564.94 | 993196.96 | 55.0257 | 0 | 0 | 0 | 468965.28 | Y | 1462162.24 | Y | 92805.56 | 0 | 0 | 1554967.8 | 0 | 0 | 1462162.24 | Y | 92805.56 | 0 | 0 | 1554967.8 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1462162.24 | 43502.65 | 0 | 1462162.24 | 0 | 0 | 0 | 67063.23 | -30432.83 | 0 | -1462162.24 | 0 | 0 | 1462162.24 | 1462162.24 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 6308.93 | 2698.57 | 9007.5 | LS | 1 | 0.38 | 0.62 | 1 | LS | 994382.83 | 188632.02 | 805750.81 | 468965.28
N | M007-99-8000-L | M007 | M007 | 99-8000 | EQUIPMENT | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.38 | 0.62 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-8050-L | M007 | M007 | 99-8050 | AID TO SUBS | N | L |  | NR | P | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | 250000 | Y | 0 | 0 | 0 | 250000 | 0 | 0 | 250000 | Y | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 2500 | 2500 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 250000
N | M007-99-8100-C | M007 | M007 | 99-8100 | PROJECT SIGNS | N | C |  | NR | P | 2500 | 2854.71 | 2854.71 | 2854.7 | 2854.71 | 71.3675 | 0 | 0 | 0 | 1145.29 | Y | 4000 | Y | -1500 | 0 | 0 | 2500 | 0 | 0 | 4000 | Y | -1500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | -4000 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 6 | -1.8 | 4.2 | EA | 1 | 0 | 1 | 1 | EA | 2854.71 | 0.01 | 2854.7 | 1145.29
N | M007-99-8100-L | M007 | M007 | 99-8100 | PROJECT SIGNS | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0 | 1 | 1 | EA | 0 | 0 | 0 | 0
N | M007-99-8200-C | M007 | M007 | 99-8200 | PUNCH LIST | N | C |  | NR | P | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | Y | 250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 | 0 | 1 | 1 | LS | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-8200-L | M007 | M007 | 99-8200 | PUNCH LIST | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 250000 | Y | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -250000 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | -250000 | 0 | 0 | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 2500 | 2500 | HR | 1 | 0 | 1 | 1 | LS | 0 | 0 | 0 | 250000
N | M007-99-9000-C | M007 | M007 | 99-9000 | BOND | N | C |  | NR | P | 1174680.06 | 948765.41 | 948765.41 | 948765.41 | 948765.41 | 81.0811 | 0 | 0 | 0 | 221378.59 | Y | 1170144 | Y | 4536.06 | 0 | 0 | 1174680.06 | 0 | 0 | 1170144 | Y | 4536.06 | 0 | 0 | 1174680.06 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -1170144 | 189753.33 | 0 | 1170144 | 0 | 0 | 0 | 0 | 0 | 0 | -1170144 | 0 | 0 | 1170144 | 1170144 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 |  | 0.83 | 0.83 | LS | 1 | 0.48 | 0.52 | 1 | LS | 0 | 0 | 0 | 221378.59
N | M007-99-9000-L | M007 | M007 | 99-9000 | BOND | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.48 | 0.52 | 1 | LS | 0 | 0 | 0 | 0
N | M007-99-9100-C | M007 | M007 | 99-9100 | INSURANCE | N | C |  | NR | P | 3248000 | 45247 | 45247 | 45247 | 45247 | 100 | 0 | 0 | 0 | 0 | Y | 45247 | Y | 3202753 | 0 | 0 | 3248000 | 0 | 0 | 45247 | Y | 3202753 | 0 | 0 | 3248000 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -45247 | 0 | 0 | 45247 | 0 | 0 | 0 | 0 | 0 | 0 | -45247 | 0 | 0 | 45247 | 45247 | 0 | 0 | 0 | 1 | 0 | 0 |  | 1 |  | 0.8 | 0.8 | LS | 1 | 0.2 | 0.8 | 1 | LS | 0 | 0 | 0 | 0
Y | M007-99-9100-INS | M007 | M007 | 99-9100 | INSURANCE | N | INS |  | NR | A | 0 | 1449527 | 1449527 | 1449527 | 1449527 | 45.2588 | 0 | 0 | 0 | 1753226 | Y | 3202753 | Y | -3202753 | 0 | 0 | 0 | 0 | 0 | 3202753 | Y | -3202753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -3202753 | 0 | 293366 | 3202753 | 0 | 0 | 0 | 0 | 0 | 0 | -3202753 | 0 | 0 | 3202753 | 3202753 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 1 | 0.2 | 0.8 | 1 | LS | 0 | 0 | 0 | 1753226
N | M007-99-9100-L | M007 | M007 | 99-9100 | INSURANCE | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 1 | 0.2 | 0.8 | 1 | LS | 0 | 0 | 0 | 0
Y | M007-99-9999-A | M007 | M007 | 99-9999 | Accruals | N | A |  | NR | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | -12180729.69 | -1310023.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-99-9999-L | M007 | M007 | 99-9999 | Accruals | N | L |  | NR | P | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-99-9999-O | M007 | M007 | 99-9999 | Accruals | N | O |  | NR | U | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-99-NY0001-C | M007 | M007 | 99-NY0001 | Supervision- Do Not Use | N | C |  | NR | U | 0 | 6200 | 6200 | 6200 | 6200 | 100 | 0 | 0 | 0 | 0 | N | 6200 | N | -6200 | 0 | 0 | 0 | 0 | 0 | 6200 | N | -6200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -6200 | 0 | 0 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | -6200 | 0 | 0 | 6200 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | NA | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0
N | M007-99-NY0001-L | M007 | M007 | 99-NY0001 | Supervision- Do Not Use | N | L |  | NR | P | 0 | 16208.12 | 16208.12 | 16208.12 | 16208.12 | 100 | 0 | 0 | 0 | 0 | N | 16208.12 | N | -16208.12 | 0 | 0 | 0 | 0 | 0 | 16208.12 | N | -16208.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 | -16208.12 | 0 | 0 | 16208.12 | 0 | 0 | 0 | 0 | 0 | 0 | -16208.12 | 0 | 0 | 16208.12 | 16208.12 | 0 | 0 | 0 | 0 | 0 | 248 | 248 | 0 | 248 | 0 | 248 | HR | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0